## Historical Jira Data
Jira ID | Summary | Status | Story Points | Assigned Sprint | Assigned Sprint Start date | Assigned Sprint End date | Assignee | Priority | Issue id | Issue Type | Project key | Project name | Project type | Project lead | Project lead id | Project description | Resolution | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Description | Environment | Watchers | Watchers.1 | Watchers.2 | Watchers.3 | Watchers.4 | Watchers.5 | Watchers Id | Watchers Id.1 | Watchers Id.2 | Watchers Id.3 | Watchers Id.4 | Watchers Id.5 | Log Work | Log Work.1 | Log Work.2 | Log Work.3 | Log Work.4 | Log Work.5 | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Î£ Original Estimate | Î£ Remaining Estimate | Î£ Time Spent | Security Level | Inward issue link (Baseline) | Inward issue link (Baseline).1 | Inward issue link (Baseline).2 | Outward issue link (Baseline) | Inward issue link (Blocks) | Inward issue link (Blocks).1 | Outward issue link (Blocks) | Inward issue link (Cloners) | Outward issue link (Cloners) | Inward issue link (Work item split) | Outward issue link (Work item split) | Attachment | Attachment.1 | Attachment.2 | Attachment.3 | Attachment.4 | Attachment.5 | Attachment.6 | Attachment.7 | Attachment.8 | Custom field ( Eppix) | Custom field (% Complete) | Custom field (% Complete).1 | Custom field (1st Body Text Top) | Custom field (2nd Body Text Bottom) | Custom field (ADF Required) | Custom field (ARB reference) | Custom field (ARIX Rating) | Custom field (ARIX Rating(migrated)) | Custom field (ARIX-3) | Custom field (ARMS Group) | Custom field (ASR Reference) | Custom field (AUC Number) | Custom field (AVA Reference Number) | Custom field (Acceptance Criteria) | Custom field (Access Status) | Custom field (Action Due Date) | Custom field (Actual Benefit) | Custom field (Actual Business Hours) | Custom field (Actual Completion Date) | Custom field (Actual Completion Date).1 | Custom field (Actual Cost) | Custom field (Actual Demand Completion Date) | Custom field (Actual Disrupted Effort) | Custom field (Actual Disrupted Effort Description) | Custom field (Actual DoR Date) | Custom field (Actual Effort) | Custom field (Actual Engineering End Date) | Custom field (Actual Engineering Start Date) | Custom field (Actual Hours Savings) | Custom field (Actual Receipt Date) | Custom field (Actual Receipt Value) | Custom field (Actual Release Ready Date) | Custom field (Actual Result) | Custom field (Actual Revenue Rollover (ZAR)) | Custom field (Actual Start Date) | Custom field (Affected Area) | Custom field (Affected services) | Custom field (Ageing) | Custom field (Agreed Action) | Custom field (Annual planning?) | Custom field (App ID) | Custom field (Application) | Custom field (Application (UAM)) | Custom field (Application Category) | Custom field (Application Delegate) | Custom field (Application Owner) | Custom field (Application Owner).1 | Custom field (Application Owner).2 | Custom field (Application Owner/Delegate (if not on JIRA)) | Custom field (Application Support Person) | Custom field (Application form Updated) | Custom field (Approvals) | Custom field (Approved in the CAB (yes/no)) | Custom field (Architect) | Custom field (Architect).1 | Custom field (Architect).2 | Custom field (Architect x) | Custom field (Are the following level items readily available: Level 1: UX Information including USP, Positioning, Research, Competitor analysis & Insights.) | Custom field (Are the following level items readily available: Level 2: Scenario planning & Journey mapping) | Custom field (Are the following level items readily available: Level 3: Wireframing?) | Custom field (Are the following level items readily available: Level 4: Detailed design) | Custom field (Are the following level items readily available: Level 5: Testing data or customer insights) | Custom field (Area Originator) | Custom field (Asset ID) | Custom field (Assigned To) | Custom field (Assigned team ) | Custom field (Assigned team ).1 | Custom field (Assignee (Product Owner)) | Custom field (Atlassian project) | Custom field (Atlassian project status) | Custom field (Auto provisioned) | Custom field (BCA) | Custom field (BCA).1 | Custom field (BCA).2 | Custom field (BCA Due Date) | Custom field (BRS Quarter) | Custom field (BU Cost Centre) | Custom field (BU Epic) | Custom field (BYOD enabled) | Custom field (Backout plan) | Custom field (Band) | Custom field (Baseline end date) | Custom field (Baseline start date) | Custom field (Benefit) | Custom field (Benefit Comments ) | Custom field (Benefit Description) | Custom field (Benefit Description ) | Custom field (Benefit Description ).1 | Custom field (Benefit Description (Deprecated)) | Custom field (Benefit Justification) | Custom field (Benefit Justification).1 | Custom field (Benefit Quantification) | Custom field (Benefit Quantification).1 | Custom field (Benefit Realisable in FY+1 (Deprecated)) | Custom field (Benefit Realisation Period) | Custom field (Benefit Type) | Custom field (Benefit Type).1 | Custom field (Benefit ZAR Value (Full-Year)) | Custom field (Benefit type) | Custom field (Benefits) | Custom field (Biz Unit) | Custom field (Blocked By) | Custom field (Blocked Reason) | Custom field (Budget) | Custom field (Budget).1 | Custom field (Budget).2 | Custom field (Budget Category) | Custom field (Budget Category and Sub Category) | Custom field (Budget Line Type) | Custom field (Budget Type) | Custom field (Budget/WBS No.) | Custom field (Build) | Custom field (Build Start Date) | Custom field (Bulk Migration IT Notification) | Custom field (Bulk Migration eff date) | Custom field (Business Analyst) | Custom field (Business Analyst).1 | Custom field (Business AnalystX) | Custom field (Business Area) | Custom field (Business AreaX) | Custom field (Business Criticality) | Custom field (Business Department Requesting) | Custom field (Business Impact) | Custom field (Business Impact).1 | Custom field (Business Impact (migrated)) | Custom field (Business Objective) | Custom field (Business Objective).1 | Custom field (Business Owner) | Custom field (Business Partners) | Custom field (Business Portfolio) | Custom field (Business Portfolio).1 | Custom field (Business Theme or EPIC) | Custom field (Business Unit) | Custom field (Business Unit).1 | Custom field (Business Unit).2 | Custom field (Business Unit).3 | Custom field (Business Unit).4 | Custom field (Business Unit).5 | Custom field (Business Unit).6 | Custom field (Business Unit).7 | Custom field (Business Unit).8 | Custom field (Business Unit).9 | Custom field (Business Unit and Portfolio) | Custom field (Business User) | Custom field (Business User (UAT)) | Custom field (Business User (migrated)) | Custom field (Business Value Picker) | Custom field (Business severity) | Custom field (Buttons) | Custom field (By transitioning issues into the Cycle Time KPI Activated workflow status, you acknowledge and agree to be bound by the Vodacom Assurance Workflow Terms of Use?) | Custom field (CI CMDB) | Custom field (CMDB App/Server name) | Custom field (COPS Team/Areas) | Custom field (CSO Reason) | Custom field (CTSM Ticket) | Custom field (CVM Campaign) | Custom field (CX Testing) | Custom field (CX, P&S Governance and Customer Care Briefing) | Custom field (Cadence) | Custom field (Call Disposition Code ) | Custom field (Call Volume Baseline (Monthly Average)) | Custom field (Call Volume Reduction YTD) | Custom field (Can take expansion model) | Custom field (Cancelled Date) | Custom field (Cancelled Reason) | Custom field (Candidate Type) | Custom field (Capability Stream) | Custom field (Capacity Requirements (People Days)) | Custom field (Catalogued) | Custom field (Category) | Custom field (Category).1 | Custom field (Category).2 | Custom field (Category).3 | Custom field (Category (Fibre)) | Custom field (Category X) | Custom field (Change Approved) | Custom field (Change Approvers) | Custom field (Change Impact) | Custom field (Change Implemented?) | Custom field (Change Implementer) | Custom field (Change Implementers) | Custom field (Change Reason (migrated)) | Custom field (Change Request) | Custom field (Change Rollback Plan) | Custom field (Change Urgency) | Custom field (Change completion date) | Custom field (Change reason) | Custom field (Change risk) | Custom field (Change start date) | Custom field (Checklist Content YAML) | Custom field (Checklist Progress) | Custom field (Checklist Progress).1 | Custom field (Checklist Progress %) | Custom field (Checklist Text) | Custom field (Checklist Text (view-only)) | Custom field (Checklist YAML) | Custom field (Clasification) | Custom field (Class) | Custom field (Classification) | Custom field (Classification).1 | Custom field (Cluster) | Custom field (Comm's to Sales) | Custom field (Comm's to Sales).1 | Custom field (Comments) | Custom field (Comments).1 | Custom field (Comments).2 | Custom field (Commercial Grooming ) | Custom field (Commercials) | Custom field (Commitment) | Custom field (Commitment Status) | Custom field (Communication of Launch Status) | Custom field (Company) | Custom field (Completed Date) | Custom field (Component Artifact) | Custom field (Concept Slide) | Custom field (Concept Slide).1 | Custom field (Confidence) | Custom field (Confidence Level) | Custom field (Config Type) | Custom field (Confluence link page) | Custom field (Contact Number) | Custom field (Contact: Legal/Compliance/Risk) | Custom field (Contact: Marketing) | Custom field (Contact: SCM) | Custom field (Contact: Sales & Distribution) | Custom field (Contract Amount) | Custom field (Contract number) | Custom field (Control/Domain) | Custom field (Cookies List Visible) | Custom field (Cookies Statement Visible) | Custom field (Cost) | Custom field (Cost).1 | Custom field (Cost).2 | Custom field (Cost Centre) | Custom field (Cost Type / Element) | Custom field (Created ) | Custom field (Created date) | Custom field (Critical Incidents) | Custom field (Criticality) | Custom field (Criticality Rating) | Custom field (Criticality Rating).1 | Custom field (Criticality Rating).2 | Custom field (Criticality Rating).3 | Custom field (Currency Symbol) | Custom field (Current Perception) | Custom field (Current Server) | Custom field (Customer Facing) | Custom field (Customer Facing?) | Custom field (Customer Journey) | Custom field (Customer Journey Code) | Custom field (Customer Life Cycle) | Custom field (Customer Wish Date) | Custom field (Cyber Security Baseline) | Custom field (Cyber Security Query) | Custom field (CyberSecurity Prioritisation) | Custom field (DAC / Invoice Number) | Custom field (DIDS Microservice) | Custom field (DIDS ODI Target) | Custom field (DIDS VROM) | Custom field (DOD) | Custom field (DOD).1 | Custom field (DOR) | Custom field (Dashboard Link) | Custom field (Data Classification) | Custom field (Data Privacy) | Custom field (Data Storage) | Custom field (Data Storage).1 | Custom field (Date) | Custom field (Date).1 | Custom field (Date).2 | Custom field (Date).3 | Custom field (Date).4 | Custom field (Date).5 | Custom field (Date Disputed) | Custom field (Date Handed over to Business ) | Custom field (Date Movement Tracker) | Custom field (Date Required) | Custom field (Date SR Logged) | Custom field (Date Submitted) | Custom field (Dated Sized) | Custom field (Days to FIX) | Custom field (Dealsheet Creation) | Custom field (Defect Type) | Custom field (Definition of Done) | Custom field (Delay in Days) | Custom field (Delivered Value Score) | Custom field (Delivery Month) | Custom field (Delivery Quarter) | Custom field (Delivery Quarter X) | Custom field (Delivery progress) | Custom field (Delivery status) | Custom field (Demand Process Completion Required By) | Custom field (Demand Type) | Custom field (Demo Sales) | Custom field (Department) | Custom field (Department).1 | Custom field (Department).2 | Custom field (Department).3 | Custom field (Department).4 | Custom field (Department).5 | Custom field (Dependencies) | Custom field (Dependencies).1 | Custom field (Dependencies).2 | Custom field (Deployment Start) | Custom field (Deprioritized Reason ) | Custom field (Deprioritized Reason ).1 | Custom field (Design Link) | Custom field (Design Partners) | Custom field (Designation) | Custom field (Designs ready) | Custom field (Dev/Config/Promo/Extension/Add-On Deals/AO) | Custom field (Development) | Custom field (Development Quarter X) | Custom field (Did you send out the comms?) | Custom field (Did you try and answer your business question from a Qlik Sense App?) | Custom field (Discount Value) | Custom field (Dispute Amount) | Custom field (Dispute Status) | Custom field (Disputed Amount) | Custom field (Disruptor) | Custom field (Division) | Custom field (Division & Department) | Custom field (Division and Department) | Custom field (Do not Want) | Custom field (Do you have access to Qlik Sense?) | Custom field (Do you require subscriber level information? ie. MSISDN) | Custom field (DoC Target Date) | Custom field (DoR Required By) | Custom field (Does the change have Implementation Plan?) | Custom field (Does the change have QA/UAT Test Results?) | Custom field (Does this requirement need ANY of the User Experience (UX) levels or gates to be initiated (this includes UX desktop research, defining UX strategy, creating journeys, scenario planning, wireframing, detailed design)?) | Custom field (Domain Specific) | Custom field (Don't Want) | Custom field (Done Quarter) | Custom field (Downtime) | Custom field (Due Date) | Custom field (Due Date).1 | Custom field (Due date) | Custom field (Due date).1 | Custom field (EHOD) | Custom field (EHOD).1 | Custom field (EHOD).2 | Custom field (EHOD).3 | Custom field (EHoD) | Custom field (ENS ANTs System ) | Custom field (Effective Date) | Custom field (Effort) | Custom field (Effort).1 | Custom field (Effort Est) | Custom field (Effort Scale) | Custom field (Effort Sized) | Custom field (Email) | Custom field (Email).1 | Custom field (Email).2 | Custom field (Employee Name) | Custom field (End Date) | Custom field (End Date).1 | Custom field (End Date ) | Custom field (End Time) | Custom field (End date) | Custom field (End of sale) | Custom field (Engineering Actual Effort Spent (Days)) | Custom field (Engineering CRQ #) | Custom field (Engineering Delivery Month) | Custom field (Engineering Delivery Quarter) | Custom field (Engineering Delivery RAG Status) | Custom field (Engineering Delivery Status Update) | Custom field (Engineering Effort Estimate (Days)) | Custom field (Engineering Impediment Description) | Custom field (Engineering Program Manager) | Custom field (Engineering T-Shirt Size) | Custom field (Engineering Testing URL's) | Custom field (Environment) | Custom field (Environments) | Custom field (Epic) | Custom field (Epic Color) | Custom field (Epic Link) | Custom field (Epic Name) | Custom field (Epic Status) | Custom field (Equipment / Solution / Services) | Custom field (Escalated by) | Custom field (Estimated Effort (days)) | Custom field (Estimated End Date) | Custom field (Estimated timeline) | Custom field (Executive Status) | Custom field (Existing) | Custom field (Expected Business Value) | Custom field (Expected Due date) | Custom field (Expected Result) | Custom field (External Architect / Tech Lead) | Custom field (External Business analyst) | Custom field (External Project Manager) | Custom field (External issue ID) | Custom field (External issue ID).1 | Custom field (External issue ID).2 | Custom field (External issue ID).3 | Custom field (External issue ID).4 | Custom field (External issue ID).5 | Custom field (External issue ID).6 | Custom field (External issue ID).7 | Custom field (External issue ID).8 | Custom field (External issue ID).9 | Custom field (External issue ID).10 | Custom field (External issue ID).11 | Custom field (FAQ's) | Custom field (FSP Link) | Custom field (FTTX Support Owner) | Custom field (FTTX Support SR Number) | Custom field (FTTx Target Month) | Custom field (Failed Reason) | Custom field (Feature) | Custom field (Feature Count) | Custom field (Feature Name) | Custom field (Feature Priority) | Custom field (Feature Size) | Custom field (Feature Size).1 | Custom field (Feature Type ) | Custom field (Feedback) | Custom field (Feedback Due Date) | Custom field (Feedback Received) | Custom field (Field Restricted) | Custom field (Finance Rep) | Custom field (Financial (P&L and BS) â‚¬) | Custom field (Financial Year) | Custom field (Financial Year).1 | Custom field (Fix version committed) | Custom field (Fixed Business Unit) | Custom field (Fixed Comms (CX, Customer Care, Sales & Ops Support)) | Custom field (Focus Areas) | Custom field (For whom (End Users) is it required?) | Custom field (Forecast Value) | Custom field (GPOP Risk Assessment) | Custom field (Go Live date) | Custom field (Go To Market) | Custom field (Go To Market Plan) | Custom field (Go live Date) | Custom field (Go-Live) | Custom field (Go-Live Date) | Custom field (Goal Impact) | Custom field (Goal impact) | Custom field (Goals) | Custom field (Group Assigned To) | Custom field (Group Assigned To).1 | Custom field (Group Assigned To).2 | Custom field (HLD Required) | Custom field (HRBP) | Custom field (Handover to OPS) | Custom field (High Priority Indicator) | Custom field (Hours) | Custom field (Hours Spent) | Custom field (IDR Status) | Custom field (IP phone type) | Custom field (IT FSP Ticket Link) | Custom field (IT Status (Product PI Planning/Analysis/Design/Dev)) | Custom field (Icap Efforts) | Custom field (Idea archived) | Custom field (Idea archived on) | Custom field (If Critical or Urgent) | Custom field (If less than 1 day, mention hours) | Custom field (Image Included) | Custom field (Impact) | Custom field (Impact Size) | Custom field (Impact if not Approved) | Custom field (Impact on Data Security Standards/Regulations?) | Custom field (Impact score) | Custom field (Impact vs. effort) | Custom field (Impacted Area) | Custom field (Impacted Area).1 | Custom field (Impacted System) | Custom field (Impacted Systems) | Custom field (Impacted Systems).1 | Custom field (Impediment Description) | Custom field (Implementation Group) | Custom field (Implementation plan) | Custom field (Importance) | Custom field (In-Year Q1 % Planned Benefit) | Custom field (In-Year Q1 Actual Benefit (ZAR)) | Custom field (In-Year Q2 % Planned Benefit) | Custom field (In-Year Q2 Actual Benefit (ZAR)) | Custom field (In-Year Q3 % Planned Benefit) | Custom field (In-Year Q3 Actual Benefit (ZAR)) | Custom field (In-Year Q4 % Planned Benefit) | Custom field (In-Year Q4 Actual Benefit (ZAR)) | Custom field (Incident Number) | Custom field (Incident Priority) | Custom field (Information Criticality) | Custom field (Initial Questionnaire) | Custom field (Initial Wish Date) | Custom field (Initiative) | Custom field (Initiative).1 | Custom field (Initiative).2 | Custom field (Initiative (PI)) | Custom field (Initiative Key) | Custom field (Initiative Name) | Custom field (Initiative Name).1 | Custom field (Initiative Preference) | Custom field (Initiative Product Owner) | Custom field (Initiative Resources) | Custom field (Initiative Type) | Custom field (Initiative Type).1 | Custom field (InitiativeXXX) | Custom field (Insights) | Custom field (Insights impact) | Custom field (Internal Team Notes) | Custom field (Investigation reason (migrated)) | Custom field (Issue) | Custom field (Issue ) | Custom field (Issue Category) | Custom field (Issue Category).1 | Custom field (Issue Type(Demo)) | Custom field (Issue color) | Custom field (Items Done) | Custom field (Items Done Percentage) | Custom field (Items Remaining) | Custom field (JIRA Ticket Number) | Custom field (JO Ref:) | Custom field (Jira Product Development: URL) | Custom field (Joint Impl with 3rd party) | Custom field (Journey ) | Custom field (Journey or Process ) | Custom field (Journey/Design/Review before DEV) | Custom field (KANO) | Custom field (Kano) | Custom field (Key Recommendations) | Custom field (Key Results) | Custom field (Key Results).1 | Custom field (Key Stakeholder Of Initiative / Feature) | Custom field (Key Stakeholder/s) | Custom field (L3/L4 Number) | Custom field (LOB Program) | Custom field (Last Comment) | Custom field (Last Date Change) | Custom field (Last Deployment date) | Custom field (Last Deployment date ) | Custom field (Latest Comment) | Custom field (Latest Comment).1 | Custom field (Latest Update) | Custom field (Latest Update).1 | Custom field (Latest Update).2 | Custom field (Latest Update).3 | Custom field (Latest Updates) | Custom field (Latest Updates).1 | Custom field (Likelihood of Occurrence) | Custom field (Likelihood of Occurrence).1 | Custom field (Likelihood of Occurrence).2 | Custom field (Line Manager) | Custom field (Line Of Business (LOB)) | Custom field (Line of Business) | Custom field (Line of Business).1 | Custom field (Line of Business).2 | Custom field (Linked Issues) | Custom field (Linked items) | Custom field (Location) | Custom field (Location).1 | Custom field (Location).2 | Custom field (Locked forms) | Custom field (Lodgement Date) | Custom field (Lodgement Required) | Custom field (Lodgement ¦ Regulatory) | Custom field (MAB Initiative Template) | Custom field (ME) | Custom field (ME).1 | Custom field (ME).2 | Custom field (MP Classification) | Custom field (MP Development Method) | Custom field (MP Release Date) | Custom field (MSISDN) | Custom field (Main Benefitting Area) | Custom field (Maintenance Type) | Custom field (Major incident) | Custom field (Man Day Estimate) | Custom field (ManDays) | Custom field (Management Update) | Custom field (Managing Executive) | Custom field (Mandatory Items Done) | Custom field (Mandatory Items Done Percentage) | Custom field (Mandatory Items Remaining) | Custom field (Market ) | Custom field (Material Code) | Custom field (Members) | Custom field (Memo) | Custom field (Memo).1 | Custom field (Memo).2 | Custom field (Merchant Classification) | Custom field (Merchant Commercial Lead) | Custom field (Merchant Name) | Custom field (Merchant Tech Lead) | Custom field (Merchant Tier) | Custom field (Merchant backend) | Custom field (Message) | Custom field (Milestone Name) | Custom field (MoSCoW) | Custom field (MoSCow) | Custom field (Mobile Application) | Custom field (Monitoring Scripts) | Custom field (Month) | Custom field (Month).1 | Custom field (Month).2 | Custom field (Monthly Anticipated Benefits - Hours) | Custom field (Monthly Anticipated Benefits - Hours ) | Custom field (Monthly Anticipated Benefits Financial) | Custom field (Monthly Anticipated Benefits Financial).1 | Custom field (Monthly Discount Value) | Custom field (Motivation For Given Date) | Custom field (Moved From) | Custom field (Moved To) | Custom field (Movement Date) | Custom field (Movement reason) | Custom field (Mover) | Custom field (NI-MPV2) | Custom field (Name and surname) | Custom field (Name of Your Project) | Custom field (New Application/Project) | Custom field (New Application?) | Custom field (New Feature Title) | Custom field (New or Existing) | Custom field (New required received date) | Custom field (Ni Dependent) | Custom field (Notes) | Custom field (Notes).1 | Custom field (Num Value) | Custom field (Number of Cookies) | Custom field (Number of DS/RT) | Custom field (Numeric Value) | Custom field (OLA) | Custom field (Objective) | Custom field (Occurrence Date & Time) | Custom field (Occurrence URL) | Custom field (On Hold Reason) | Custom field (On Hold Status Change) | Custom field (OneTrust ID) | Custom field (Online Business Analyst) | Custom field (Online Project Manager) | Custom field (Opcos) | Custom field (Open forms) | Custom field (Operational-Customers) | Custom field (Operational-Employees) | Custom field (Operational-Systems and Operations) | Custom field (Ops Call Reference) | Custom field (Ops Manual to be updated) | Custom field (Ops Requirement) | Custom field (Order Device) | Custom field (Organization) | Custom field (Output Test Field) | Custom field (Overall Percentage) | Custom field (Overall Risk) | Custom field (P&L Driver) | Custom field (P-Value) | Custom field (PBI) | Custom field (PCC) | Custom field (PI) | Custom field (PI Backlog Refinement Date) | Custom field (PI Grooming) | Custom field (PI Item?) | Custom field (PI Prioritization) | Custom field (PI Priority) | Custom field (PI Priority (ASOC)) | Custom field (PI Project Manager) | Custom field (PI Status) | Custom field (PII Onboarded?) | Custom field (PIR Due Date) | Custom field (PM Requirement) | Custom field (PO Priority) | Custom field (PO Requester) | Custom field (Parent ID) | Custom field (Parent Issue ACQ Number) | Custom field (Payment Period (migrated)) | Custom field (Payment Terms) | Custom field (Pending reason) | Custom field (Phase ) | Custom field (Phone Number) | Custom field (Plan Quarter) | Custom field (Plan of Action) | Custom field (PlanX Quarter) | Custom field (Planned Delivery Month) | Custom field (Planned Duration in Workdays) | Custom field (Planned End) | Custom field (Planned Receipt Date) | Custom field (Planned SIT Date) | Custom field (Planned end date) | Custom field (Planned start date) | Custom field (Planned value score) | Custom field (Planning Quarter X) | Custom field (Po Number (migrated)) | Custom field (Policy/Process) | Custom field (Port Count) | Custom field (Position) | Custom field (Post Change Notes) | Custom field (Post Deployment Test) | Custom field (Postcondition(s)) | Custom field (Postproduction Verification ) | Custom field (Precondition(s)) | Custom field (Preview Link) | Custom field (Pricing) | Custom field (Pricing ) | Custom field (Priority) | Custom field (Priority).1 | Custom field (Priority).2 | Custom field (Priority).3 | Custom field (Priority (migrated)) | Custom field (Priority Ranking) | Custom field (Priority Ranking XXX) | Custom field (Privacy Impact Assessment) | Custom field (Privacy Statement Visible) | Custom field (Problem Statement) | Custom field (Problem Statement ) | Custom field (Problem Statement ).1 | Custom field (Problem System) | Custom field (Prod A Approver - Dev) | Custom field (Prod A Approver - Product Owner) | Custom field (Prod Date) | Custom field (Product ID Forum) | Custom field (Product Owner) | Custom field (Product Owner).1 | Custom field (Product OwnerX) | Custom field (Product Quarterly Roadmap) | Custom field (Product Roadmap) | Custom field (Product area) | Custom field (Product or Service Description) | Custom field (Producy Category) | Custom field (Program) | Custom field (Program Manager) | Custom field (Program ManagerX) | Custom field (Program Priority) | Custom field (Program X) | Custom field (Programme Category) | Custom field (Progress Indicator) | Custom field (Progress Percent) | Custom field (Project) | Custom field (Project Business Analyst) | Custom field (Project Design Analyst) | Custom field (Project Developer) | Custom field (Project Development Type?) | Custom field (Project Development Type?).1 | Custom field (Project Due Date) | Custom field (Project Lead) | Custom field (Project Lead).1 | Custom field (Project Manager x) | Custom field (Project OPS Representative) | Custom field (Project PMO Project Manager) | Custom field (Project Plan) | Custom field (Project Product Owner) | Custom field (Project Project Manager) | Custom field (Project Revised date) | Custom field (Project Start Date) | Custom field (Project Status) | Custom field (Project Tech Lead) | Custom field (Project Test Analyst) | Custom field (Project Type) | Custom field (Project overview key) | Custom field (Project overview status) | Custom field (Project start) | Custom field (Project target) | Custom field (Projected Hour Savings) | Custom field (Proposed (Solution)) | Custom field (Proposed Benefit ) | Custom field (Proposed Solution) | Custom field (Proposed Solution).1 | Custom field (Proposed Solution ) | Custom field (Public description) | Custom field (Purchase Order Issue Date) | Custom field (Purchase Order Request Reference) | Custom field (Purchase Order Value) | Custom field (Purpose) | Custom field (Q-value) | Custom field (QA Approver - Test Analyst) | Custom field (Qoute Ref-number) | Custom field (Quadrant) | Custom field (Quarter Targeted) | Custom field (RAG) | Custom field (RAG).1 | Custom field (RAG Reason) | Custom field (RAG Status) | Custom field (RCA) | Custom field (RCA).1 | Custom field (RCA ) | Custom field (RCA Core Theme) | Custom field (RCA Resolution) | Custom field (RCA Sub Theme) | Custom field (RCA Sub-Themes) | Custom field (RPA Budget) | Custom field (RPAprocess) | Custom field (RQ End DateTime) | Custom field (RQ Start DateTime) | Custom field (RTE) | Custom field (RTE X) | Custom field (Radwin Services) | Custom field (Rag Reason x) | Custom field (Rag Reason xx) | Custom field (Rank) | Custom field (Reason) | Custom field (Reason For Pending) | Custom field (Reason for Carry-over) | Custom field (Reason for Descope) | Custom field (Reason for Vacancy) | Custom field (Receipt Number) | Custom field (Receipt Request Reference Number) | Custom field (Receipt Status) | Custom field (Receipt Value) | Custom field (Recommended resolution) | Custom field (Recreation Steps) | Custom field (Reduction Target %) | Custom field (Reference) | Custom field (Regulatory Requirement Description) | Custom field (Reject Button Visible) | Custom field (Related Feature) | Custom field (Release Date) | Custom field (Release Date).1 | Custom field (Release Notes) | Custom field (Release Ready Approver - Design Analyst ) | Custom field (Release Ready Approver - OPS Representative ) | Custom field (Release Ready Approver - Product Owner ) | Custom field (Release Slot) | Custom field (Remedy CRQ) | Custom field (Replacement model) | Custom field (Reporter (migrated)) | Custom field (Reporting) | Custom field (Reporting Tool) | Custom field (Reprioritised Date) | Custom field (Reprioritised Reason) | Custom field (Reputational-Brand) | Custom field (Reputational-Health and Safety) | Custom field (Reputational-Stakeholders) | Custom field (ReqID) | Custom field (Request Category) | Custom field (Request Classification) | Custom field (Request Identification) | Custom field (Request Type) | Custom field (Request for Architecture Detail) | Custom field (Request language) | Custom field (Request participants) | Custom field (Requested By) | Custom field (Requested By BU) | Custom field (Requested group) | Custom field (Requestor) | Custom field (Requirement Approver - Design Analyst ) | Custom field (Requirement Approver - OPS Representative ) | Custom field (Requirement Approver - Product Owner ) | Custom field (Requisition number) | Custom field (Resolution) | Custom field (Resolution ) | Custom field (Resolution Category) | Custom field (Resolution Description) | Custom field (Resolution Description).1 | Custom field (Resolution Duration) | Custom field (Resource Rate) | Custom field (Responders) | Custom field (Responsible Group) | Custom field (Responsible Partner) | Custom field (Responsible Partner).1 | Custom field (Responsible Person) | Custom field (Restricted Field) | Custom field (Review Type) | Custom field (Reviewed) | Custom field (Reviewer) | Custom field (Reviewer).1 | Custom field (Reviewer).2 | Custom field (Revised Customer Wish Date) | Custom field (Risk) | Custom field (Risk Assessment type) | Custom field (Risk Category) | Custom field (Risk Dependancies) | Custom field (Risk Impact Ranking) | Custom field (Risk Impact Ranking).1 | Custom field (Risk Impact Ranking).2 | Custom field (Risk Level) | Custom field (Risk Level).1 | Custom field (Risk Mitigation) | Custom field (Risk Priority) | Custom field (Risk Rating) | Custom field (Risk Rating).1 | Custom field (Risk Rating).2 | Custom field (Risk Reduction) | Custom field (Risk Strategy) | Custom field (Risk Strategy).1 | Custom field (Risk Type) | Custom field (Risk Type).1 | Custom field (Risks) | Custom field (Risks).1 | Custom field (Risks).2 | Custom field (Roadmap) | Custom field (Roadmap Epic Type) | Custom field (Role) | Custom field (Role Description) | Custom field (Role Description).1 | Custom field (RoleX) | Custom field (Rollover Quarter) | Custom field (Root Cause (migrated)) | Custom field (Root Cause 2) | Custom field (Root Cause Analysis) | Custom field (Root Cause Category) | Custom field (Root Cause Description) | Custom field (Root Cause Description).1 | Custom field (Root Cause Description).2 | Custom field (Root Cause TART) | Custom field (Rules) | Custom field (SD QA Resource) | Custom field (SLA) | Custom field (SOX System) | Custom field (SOX System).1 | Custom field (SPDA Acknowledgement) | Custom field (SPDA Completed. If Yes, please add reference number.) | Custom field (SPDA Completed?) | Custom field (SPDA's) | Custom field (SPOC) | Custom field (SPOC).1 | Custom field (SR Area ) | Custom field (SR Description) | Custom field (SR Fault Type ) | Custom field (SR Reduction YTD) | Custom field (SR Ref Number) | Custom field (SR Reference ) | Custom field (SR Subject) | Custom field (SR Volume Baseline (Monthly Average)) | Custom field (SRS logged with same issue) | Custom field (SWE Classification) | Custom field (Sample Sales Order) | Custom field (Satelite Site) | Satisfaction rating | Custom field (Satisfaction date) | Custom field (Savings Type) | Custom field (Schedule) | Custom field (Scheduling) | Custom field (Scope of Work) | Custom field (Scope of Work ID / Quote Number) | Custom field (Scrum Master) | Custom field (Scrum Master).1 | Custom field (Scrum Master x) | Custom field (Select Source Department) | Custom field (Select Team) | Custom field (Sensitive Data) | Custom field (Sensitive Data involved in the Solution?) | Custom field (Sensitive Data?) | Custom field (Sentiment) | Custom field (Server Coordinator) | Custom field (Service) | Custom field (Services) | Custom field (Severity) | Custom field (Shopping Cart) | Custom field (Short description) | Custom field (Siebel) | Custom field (Siebel Contact) | Custom field (Siebel MDs) | Custom field (Signature Program) | Custom field (Site Link) | Custom field (Site URL) | Custom field (Size) | Custom field (Size (migrated 2)) | Custom field (Size (migrated)) | Custom field (Sized By ) | Custom field (Sizing) | Custom field (Solution Description) | Custom field (Source) | Custom field (Source).1 | Custom field (Source).2 | Custom field (Source).3 | Custom field (Source Of Change Request) | Custom field (Source of Demand) | Custom field (Spec ready) | Custom field (Specify any architectural / system considerations) | Custom field (Spend Category) | Custom field (Splash End Date) | Custom field (Splash Priority) | Custom field (Splash Start) | Custom field (Sponsor) | Custom field (Sponsor).1 | Custom field (Sponsor).2 | Unnamed: 1045 | Unnamed: 1046 | Unnamed: 1047 | Sprint | Sprint.1 | Sprint.2 | Sprint.3 | Sprint.4 | Sprint.5 | Sprint.6 | Sprint.7 | Sprint.8 | Custom field (Sprint (Migration mapping)) | Custom field (Stakeholder Category) | Custom field (Stakeholder Category).1 | Custom field (Stakeholder Type) | Custom field (Stakeholder Type).1 | Custom field (Stakeholders) | Custom field (Start Date) | Custom field (Start Date (migrated 2)) | Custom field (Start Date (migrated)) | Custom field (Start Quarter) | Custom field (Start Time) | Custom field (Start date) | Custom field (Start date).1 | Custom field (State Of Feature) | Custom field (Status Update) | Custom field (Status and Mitigation) | Custom field (Storage Coordinator) | Custom field (Story Points) | Custom field (Story Points).1 | Unnamed: 1076 | Custom field (Story Size) | Custom field (Story Type) | Custom field (Story point estimate) | Custom field (Story points) | Custom field (Strategic Theme) | Custom field (Stream) | Custom field (Sub Class) | Custom field (Sub Project) | Custom field (Submitted forms) | Custom field (Support Partners) | Custom field (Swarm Team) | Custom field (System Analyst) | Custom field (System Name) | Custom field (T's & C's) | Custom field (T-Shirt) | Custom field (Talent Acquisition Partner) | Custom field (Target Date) | Custom field (Target Date: Analysis) | Custom field (Target Date: Release) | Custom field (Target Launch Month) | Custom field (Target Market (VC/Non-VC)) | Custom field (Target Market Description) | Custom field (Target Prod Date) | Custom field (Target Quarter) | Custom field (Target end) | Custom field (Target month) | Custom field (Target start) | Custom field (Targeted Benefit ) | Custom field (Targeted Month) | Custom field (Targeted benefit ) | Custom field (Task Category) | Custom field (Task End Date) | Custom field (Task Owner) | Custom field (Task Owner).1 | Custom field (Task Percentage) | Custom field (Task Revised Date) | Custom field (Task Start Date) | Custom field (Task progress) | Custom field (Team) | Custom field (Team).1 | Custom field (Teams) | Custom field (Tech Business Unit) | Custom field (Tech Groomed) | Custom field (Tech Groomed).1 | Custom field (Tech Panel) | Custom field (Technical Architect) | Custom field (Technical BA) | Custom field (Template) | Custom field (Terms & Conditions) | Custom field (Test Analyst) | Custom field (Test Cases Blocked) | Custom field (Test Data) | Custom field (Test Results) | Custom field (Test Type) | Custom field (Test plan) | Custom field (Testing Done?) | Custom field (Testing Type) | Custom field (Testing URL(s)) | Custom field (Text Value) | Custom field (Theme) | Custom field (Ticket Lifespan) | Custom field (Ticket Reference) | Custom field (Ticket Type) | Custom field (Ticket reference) | Custom field (Time Criticality) | Custom field (Time In Status (Bug Fix)) | Custom field (Time In Status (Pending)) | Custom field (Time Of Change) | Custom field (Time Tracking) | Custom field (Time in IN PROGRESS Category) | Custom field (Time in Status) | Custom field (Time in Status (Blocked)) | Custom field (Time in TO DO Category) | Custom field (Time in status (Open)) | Custom field (Time to approve normal change) | Custom field (Time to close after resolution) | Custom field (Time to done) | Custom field (Time to first response) | Custom field (Time to resolution) | Custom field (Time to review normal change) | Custom field (To be considered:) | Custom field (Total Duration) | Custom field (Total Eppix Events) | Custom field (Total Items) | Custom field (Total Mandatory Items) | Custom field (Total PCC Events) | Custom field (Total Sections) | Custom field (Total Siebel Events) | Custom field (Total Tabs) | Custom field (Total forms) | Custom field (Trade Bulletin) | Custom field (Training) | Custom field (Training Partners) | Custom field (Transition Timestamp) | Custom field (Ts&Cs Legal Approved & Online Updated) | Custom field (Type) | Custom field (Type X) | Custom field (Type of Problem) | Custom field (Type of system) | Custom field (UAT Approver - OPS Representative) | Custom field (UAT Approver - Product Owner) | Custom field (UAT Approver - Tech Lead) | Custom field (UAT Approver - Test Analyst) | Custom field (UAT Testing) | Custom field (URL) | Custom field (URL).1 | Custom field (URL to SPDA) | Custom field (URS Received) | Custom field (UX Design Required) | Custom field (Unit) | Custom field (Update Bitstream Portals) | Custom field (Updates/Comments) | Custom field (Urgency) | Custom field (User) | Custom field (User Stories Acceptance (DOR "Definition of Ready")) | Custom field (User Story) | Custom field (User-Business Value) | Custom field (VFS Compliance) | Custom field (VFS Portfolio) | Custom field (VPC Fees) | Custom field (VPS Number) | Custom field (VPS number) | Custom field (VROM) | Custom field (Value Score) | Custom field (Vendor) | Custom field (Vendor (migrated)) | Custom field (Video enabled) | Custom field (VodaPay Commercial Lead) | Custom field (VodaPay Project Manager) | Custom field (VodaPay Tech Lead) | Custom field (Vodacom Group Name) | Custom field (Vulnerability) | Custom field (WBS number) | Custom field (Want) | Custom field (Want).1 | Custom field (Was the change tested after implementation?) | Custom field (Was the change tested?) | Custom field (Web Application) | Custom field (Website) | Custom field (Weight) | Custom field (What is being done?) | Custom field (What is the Problem Statement ?) | Custom field (What is the envisioned Definition of Done?) | Custom field (What is the objective/intention?) | Custom field (What outcomes are required?) | Custom field (What prevented you from not being able to answer your business question by using Qlik Sense?) | Custom field (What type of data does it process?) | Custom field (Which App did you use?) | Custom field (Who is the Partner/s building the capability?) | Custom field (Who is the sponsor of this initiative?) | Custom field (Who is their UX/UI lead or company? (please provide Name, Surname and contact details)) | Custom field (Why is it required?) | Custom field (Wish Date) | Custom field (Work Around) | Custom field (Work category) | Custom field (Workaround) | Custom field (Workstream Owner ) | Custom field (Year) | Custom field (Yes / No Question) | Custom field (You are responsible for (and have sufficient authority to take) all actions that are performed on or through this status transition.) | Custom field (You understand the implications associated with these actions?) | Custom field ([CHART] Date of First Response) | Custom field ([CHART] Time in Status) | Custom field (accountable_business_area) | Custom field (accountable_name_role) | Custom field (data_processing_activity) | Custom field (description) | Custom field (https://www.figma.com/design/1ndT1QkLMJ63rOvy9IzehN/VodaStore-MVP--2024-?node-id=3275-13398&t=rSKIfSNAWc8O4PMW-1) | Custom field (purpose_of_data_sharing) | Custom field (recipients_of_data_sharing) | Custom field (requesting_business_area) | Custom field (requestor_email) | Custom field (requestor_name_surname) | Custom field (requestor_role) | Custom field (uuid) | Comment | Comment.1 | Comment.2 | Comment.3 | Comment.4 | Comment.5 | Comment.6 | Comment.7 | Comment.8 | Comment.9 | Comment.10 | Comment.11 | Comment.12 | Comment.13 | Comment.14 | Comment.15 | Comment.16 | Comment.17 | Comment.18 | Comment.19 | Comment.20 | Comment.21 | Comment.22 | Comment.23 | Comment.24 | Comment.25 | Comment.26 | Parent | Parent key | Parent summary | Status Category | Status Category Changed
AM20-311 | Cynet ¦¦ Server Installation | To Do |  | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1887432 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-06 13:12 | 2026-01-06 13:12 | 2026-01-07 08:19 |  |  | 0 | As Product owner I want to install Cynet agent on Linux/Windows EC2 instance so that threat detechtion and response coverage is enabled Acceptance Criteria. *Linux*: * Installation package hosted/accessible securely (S3 with KMS, repo, or Cynet direct download). * SSM document / automation executes successfully on a pilot group and then on all in-scope instances. * Agent registers to correct Cynet tenant and shows â€œonline/healthyâ€ in console within defined SLA (e.g., 15 minutes). * Installation is idempotent (re-run does not break existing installation). * Logging captured: instance ID, hostname, timestamp, status, version, and failure reason if any. *Windows*: * Silent install works (msi/exe unattended flags), including token/tenant configuration. * Service is running after installation and agent appears healthy in console. * Windows Event Logs / install logs are retained for troubleshooting. * | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@19d1d99d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0q0i3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2026-01-06 13:12
AM20-310 | Security Hardening Audit and Analysis for FLYSAA Backend | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Sumit Nikam | Medium | 1886488 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-05 10:11 | 2026-01-08 08:29 | 2026-01-08 08:41 |  |  | 0 | As an Internal Auditor, I want to review EKS control plane security configurations across all production accounts, IAM authentication and Kubernetes RBAC mappings, Audit Node & Worker Security Controls, Audit Network Security & Traffic Controls, Audit Pod & Workload Security Posture, Audit Secrets Management & Data Protection So that gaps against AWS and Kubernetes security benchmarks are identified, Acceptance Criteria * EKS cluster version documented per account * API endpoint exposure (public/private) recorded * Allowed CIDR ranges captured * Control plane logging status verified * Secrets encryption (KMS / default) documented * Evidence stored (CLI output / console screenshots) * Gaps mapped to CIS EKS benchmark controls * IAM users vs roles usage documented * aws-auth ConfigMap reviewed * Cluster-admin bindings identified * Namespace vs cluster scoped access recorded * IRSA adoption status captured * Evidence collected (RBAC YAML, IAM role list) * High-risk access clearly flagged * Node type (Managed / Self-managed / Fargate) documented * AMI patching and update mechanism recorded * Node IAM role permissions reviewed * IMDS version (v1/v2) verified * SSH access presence documented * Evidence retained (Launch Template / ASG config) * NetworkPolicy enforcement status recorded * Default deny posture verified * Ingress exposure documented (public/private) * WAF & TLS configuration reviewed * Egress paths documented * Evidence retained (manifests, ALB config) * Pod Security Standards status documented * Privileged pods identified * Containers running as root recorded * Linux capabilities usage reviewed * Secrets usage method documented * Evidence retained (pod specs, namespace labels) * Image registries used documented * Image scanning availability verified * CVE handling process reviewed * Image tagging strategy recorded * Admission control presence documented * Evidence captured (CI logs, ECR settings) * Secret storage mechanisms documented * Encryption at rest/in transit verified * Secrets rotation capability reviewed * Backup and restore process recorded * Evidence retained (KMS config, secret manifests) * Control plane & workload logs documented * Log centralization status verified * Runtime threat detection presence reviewed * Alerting and escalation paths documented * SIEM integration status captured * Evidence retained (CloudWatch, GuardDuty) * GitOps vs manual change model documented * Policy enforcement tooling identified * Change approval records reviewed * Ownership & RACI clarity assessed * CIS / ISO alignment documented * Findings categorized (High / Medium / Low) * Risk statement defined for each gap * Affected accounts listed * Evidence referenced * Recommendations documented separately * Executive summary prepared |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [11 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@26af9eed | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0px2z: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-08 06:30 | [13 empty] | 08/Jan/26 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Initial discovery has been started post discussion. Working on Kyverno issue first in-order to have necessary violations report. | [29 empty] | In Progress | 2026-01-08 08:28
AM20-309 | Central EKS management Account Setup | To Do | 0 | None( Backlog) |  |  |  | Medium | 1886264 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-04 09:03 | 2026-01-05 08:27 | 2026-01-05 08:27 |  |  | 0 | As a Cloud platform, I want to establish a central EKS management account so that all EKS cluster across child accounts can be governed and managed from a single control plane Acceptance Criteria: Central AWS account is designated as EKS management Account IAM roles created to allow cross account EKS access Trust relationships established between * Central account * All child application account # SCP prevent direct EKS admin access from the child account # Network connectivity (TGW/VPC peering) validated # Design approved by AWS architecture, Security expert | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@b37afdb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [126 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [200 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001s | [57 empty] | Online Dev | [109 empty] | Business | [200 empty] | YES | YES | [44 empty] | To Do | 2026-01-04 09:03
AM20-308 | Front End (SMS notification)- Business Level Improvements | To Do | 4 | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1885790 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-12-30 08:45 | 2026-01-08 11:54 | 2026-01-06 08:25 |  |  | 0 | As Product Owner I would like to take business input and configure the SMS accordingly so that informative SMS notification reached out to operation and support group. *Acceptance Criteria*: * SMS notification configured successfully as Business input |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@55581f2c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptv7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-08 09:34 | [13 empty] | 08/Jan/26 11:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reached out to Hoosen and Javier to enquire their availability for resuming the discussions, awaiting their response. | [29 empty] | To Do | 2025-12-30 08:45
AM20-307 | Centralized Cluster Creation Strategy | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Sanjot Fotedar | Medium | 1885775 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-12-30 07:58 | 2026-01-07 19:23 | 2026-01-08 08:38 |  |  | 0 | As A platform Owner I want to create a detailed design document for centralized management of EKS cluster across multiple AWS child accounts from a central account so that the solution is secure, scalable, compliant and operationally ready before implementation Acceptance Criteria: *Architecture and Account structure* - * Parent, central management and child application accounts * hub and spoke model connectivity model * shared vs isolation responsibilities *EKS management Strategy* - * Centralized model * Namespace isolation strategy * Cluster ownership and lifecycle boundaries *IAM and Security design* - * Cross account IAM roles and trust relationship * K8s RBAC mapping * Least privileges access model * SCP usage and guardrails *Network and Connectivity design* - * VPC architecture per account * Connectivity via TGW /VPC peering * Control plane and data plane traffic flow * DNS resolution strategy *Governance and Policy Enforcement* - * Kubernetes admission controls (Kyverno) * naming, tagging and quota standards * Policy exception handling process *Observability and Logging* - * Centralized logging and metrics flow * Alerting and escalation paths *Security and Compliance* - * EKS security monitoring * Image scanning approach * Compliance reporting and audit readiness *Operation model* - * RACI matrix (L1/L2/L3) * Incident and change management process * upgrade and patching strategy * Backup and DR approach |  | Sanjot Fotedar | [5 empty] | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [5 empty] | ;07/Jan/26 7:23 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;7200 | [5 empty] | 115200 | 108000 | 7200 | 0.06 | 115200 | 108000 | 7200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43715548 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptve: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-07 17:24 | [13 empty] | 07/Jan/26 7:23 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Started work on this. Currently evaluating the framework for assessing multi-tenancy readiness of existing eks cluster. Identifying key focus areas for hardening -Â namespace isolation, RBAC scope, network segmentation, resource governance, policy enforcement. | [29 empty] | In Progress | 2026-01-07 19:21
AM20-306 | Budget management - AWS Cost Control on application | In Progress | 6 | Sprint 22 | 2026-01-05 | 2026-01-16 | Diksha Koul | Medium | 1885694 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-12-29 10:47 | 2026-01-08 12:16 | 2026-01-08 08:32 |  |  | 0 | As Product Owner, I would like to address frequent spikes on budget of AWS accounts so that we can manage cost within the forecasted cost. Acceptance Criteria: * Identify the root cost of cost spiked in EKS cluster, Audit account, SAA_Airnavx and CMS backend(Prod) * resolve the root cause to reduce the associated cost |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [5 empty] | ;08/Jan/26 7:38 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | [5 empty] | 86400 | 57600 | 28800 | 0.33 | 86400 | 57600 | 28800 | [12 empty] | 08/Jan/26 10:57 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-085716.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197716 | 08/Jan/26 11:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-093536.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197744 | 08/Jan/26 12:15 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-101131.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197769 | 08/Jan/26 12:15 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-101412.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197770 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3731daff | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptcb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-06 11:56 | [13 empty] | 06/Jan/26 1:55 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started working on the root cause and cost spike for AirnavX | 08/Jan/26 7:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have checked the costing spike for all accounts its showing that EC2 instances are consuming more cost. Now checking the cloud watch logs for them. | 08/Jan/26 10:57 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I checked in the *AirnavX Account* there are snapshots which has been created for all EC2 instances including the DR instance and also the backup is enabled. Attaching the screenshot below: !image-20260108-085716.png¦width=641,alt="image-20260108-085716.png"! This is also one reason that the costing is spiking. For *Audit Account* also i checked that the SNS and Cloudwatch is consuming lot of cost spike due to which the budget costing is spiked. Attaching the screenshot: !image-20260108-093536.png¦width=613,alt="image-20260108-093536.png"! For *CMS_Backend_Prod* the t3.xlarge instances that is EKS nodes is cost consuming as you can see below Attached Screenshot below showing nodes spike for 4 months. !image-20260108-101131.png¦width=496,alt="image-20260108-101131.png"! Also, below screenshot showing instance type size for EC2 and EKS nodes and there costing for 4 months. !image-20260108-101412.png¦width=583,alt="image-20260108-101412.png"! | [27 empty] | In Progress | 2026-01-06 12:51
AM20-305 | Adding description for CloudWatch notifications sent to ServiceNow for AWS Lambda | Done |  | Sprint 21 | 2025-12-22 | 2026-01-02 | Shreyash Talwekar | Medium | 1883878 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2025-12-17 10:16 | 2026-01-02 08:22 |  |  |  | 0 | Update alarm payloads configured for Lambda functions alarms to sent the description alongwith other previous details to ServiceNow. |  | Faisal Sayed | Shreyash Talwekar |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cac3dfe | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pm6j: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-02 05:41 | [13 empty] | 02/Jan/26 7:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Lambda Function for Alarm Handling* *Overview:* This Lambda function is triggered whenever a CloudWatch alarm transitions to the {{ALARM}} state. *Functionality:* * Retrieves detailed metrics for the Lambda function that breached the configured threshold and triggered the alarm. * Constructs a payload containing the relevant metric details. * Publishes the payload to an Amazon SNS topic, which has ServiceNow configured as a subscriber for incident management. *Recent Enhancement:* A human-readable description has been added to the payload to improve clarity and facilitate better understanding in ServiceNow. This enhancement is now implemented and operational. | [26 empty] | 1881266 | AM20-302 | Convert Alarms description into simple user understandable format | Done | 2026-01-02 08:22
AM20-304 | Adding description for CloudWatch notifications sent to ServiceNow for AWS infrastructure resources | Done |  | Sprint 21 | 2025-12-22 | 2026-01-02 | Shreyash Talwekar | Medium | 1883876 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2025-12-17 10:13 | 2026-01-02 08:22 | 2025-12-18 08:18 |  |  | 0 | Update the lambda functions to sent description of CloudWatch alarms in the payload to be sent ServiceNow. |  | Diksha Koul | Shreyash Talwekar |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  |  | ;18/Dec/25 8:28 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;14400 | [5 empty] | 14400 | 0 | 14400 | 1 | 14400 | 0 | 14400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@449d7c5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pm6b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-18 06:31 | [13 empty] | 18/Dec/25 8:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have updated the reason and Description for all prod, dev & qa lambda functions and also tested that as well. | [26 empty] | 1881266 | AM20-302 | Convert Alarms description into simple user understandable format | Done | 2026-01-02 08:22
AM20-303 | Route53 ¦¦ Alert Configuration | In Progress | 6 | Sprint 22 | 2026-01-05 | 2026-01-16 | Satya Varanasi | Medium | 1881343 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-12-11 10:55 | 2026-01-08 08:27 | 2026-01-08 08:39 |  |  | 0 | As a cloud infra platform team I want to implement automated alerting for Route53 DNS health, record changes and DNS health, record changes and DNS failover so that application teams and support teams can proactively detect outages, unauthorized changes and DNS failures across all AWS accounts. Acceptance Criteria: # Route 53 Health Check Alerts * Health checks must be created for all critical endpoints (HTTP, 1. HTTPS, TCP, or CloudWatch metric-based). * Â A CloudWatch alarm must automatically trigger if the health check status = Unhealthy. * Â Alarm must send a notification to an SNS topic configured for the environment (Dev/Pre-Prod/Prod). * Â Health check status must be visible on the central monitoring dashboard. # DNS Failover Alarms * Â Failover configurations (Primary/Secondary records) must be validated after deployment. * Â A CloudWatch alarm must trigger when Route 53 performs an automated failover action. Â Notification must include: * Â hosted zone name * Â record name * Â failover type (PRIMARY â†’ SECONDARY) * Â timestamp Â Application team must receive ServiceNow notification immediately. Â All failover events must be recorded in audit logs (CloudTrail). # Hosted Zone Change & Record Modification Alerts Â CloudTrail must be enabled for all Route 53 API events: * Â CreateHostedZone * Â ChangeResourceRecordSets * Â DeleteHostedZone 4.Â An EventBridge rule must detect record or zone changes and send alerts to SNS. Alert must contain: * user/role who made the change * old value vs new value * timestamp * AWS account ID # Unauthorized changes must automatically raise a ticket in ServiceNow/JIRA (if integrated). * All record changes must be stored for audit (S3/CloudTrail). * DNS Query Volume / Anomaly Alerts * Â CloudWatch metric "DNS Queries" must be monitored for abnormal spikes or drops. * Â CloudWatch Anomaly Detection must be configured with proper thresholds. * Â Alerts must trigger when query volume deviates beyond normal traffic window. * Â Notification must reach platform + application teams. * Â Alerts must indicate possible DDoS, misconfiguration, or routing issue.Â * DNS Latency or Resolver Issue Alerts * Â Route 53 Resolver metric "ResolverQueryError" or "DNS Resolution Failure" must be monitored. * Â Alerts must trigger when error rate exceeds threshold (ex: >5% errors for 5 mins). * Â Alerts must include resolver IP, VPC ID, region. * Â Incident must be auto-created in monitoring tool.Â # Alert Routing & Escalation * Â Alerts from all child accounts must centralize into a single parent-account SNS topic using cross-account permissions. * Â Separate channels must exist for PROD vs NON-PROD. * Â Severity mapping must follow organizational incident guidelines (SEV-1, SEV-2, SEV-3) # Â A centralized CloudWatch dashboard must show: * Â health check status * Â failover events * Â DNS query traffic * Â record change logs * Â Dashboard must be accessible from parent account to all authorized users. * Â Dashboard updated in near real-time (<1 min delay).Â # Security & Governance * Â IAM policies must restrict record modification to authorized roles. * Â All Route 53 API calls must be captured via CloudTrail. * Â Patchable misconfigurations (e.g., TTL mismatch, missing health checks) must be flagged automatically. * Â Alerts must comply with compliance policies (PCI, CIS benchmarks if applicable). # Integration Requirements * Â SNS must integrate with: * Â ServiceNowÂ * Alert payload must follow a standard message template. 10. Testing & Validation * Test failover must generate an alert. * Test manual record change must generate an audit alert. * Test endpoint failure must trigger "Unhealthy" alarm. |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2e5b4dfc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptvd: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-07 14:38 | [13 empty] | 07/Jan/26 4:38 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working on it. | [29 empty] | In Progress | 2026-01-08 08:27
AM20-302 | Convert Alarms description into simple user understandable format | Done | 4 | Sprint 21 | 2025-12-22 | 2026-01-02 | Yashwant Thakur | Medium | 1881266 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-12-11 10:22 | 2026-01-02 11:04 | 2026-01-04 09:12 | 2026-01-02 11:04 |  | 0 | As Product owner I like to convert alarm description into simple understandable language so that user or resolver group are able to understand what is causing the error for flysaa backend , Front end and airnavx. Acceptance Criteria: alarm description send to Service Now via SNS and Lamda function must be user understable and successfully cascaded to ServiceNow using API. |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;02/Jan/26 9:49 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 72000 | 28800 | 43200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@18246054 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pcib: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2026-01-02 07:49 | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Jan/26 9:48 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Description was added for infrastructure , Lambda function and Flysaa Frontend account alerts. Example payload of frontend account alert: {"Name": "FlySaaCms_ALB_HTTPCode_Target_4XX_Count","IP Address": "NA","Fully Qualified Domain Name": "[api.flysaa.com¦http://api.flysaa.com]","Company": "VFSA","Hostname": "app/FlySaaCmsWebALB/968b1f7492941705","Department": "App DevOps Team","Operating System": "Amazon Linux","DNS Domain": "[api-frontdev-flysaa.com¦http://api-frontdev-flysaa.com]","Disk Space (GB)": "NA","RAM (MB)": "NA","CPU Count": "2","CPU core count": "2","Alarm Time": "2026-01-01 19:42:30 UTC","Account ID": "261365109009","Environment": "prod","Cluster Name": "NA","MetricName": "HTTPCode_Target_4XX_Count","Current State": "ALARM","Reason": "Threshold Crossed: 3 out of the last 3 datapoints [6534.0 (01/01/26 19:35:00), 6206.0 (01/01/26 19:30:00), 3164.0 (01/01/26 19:25:00)] were greater than or equal to the threshold (3000.0) (minimum 3 datapoints for OK -> ALARM transition).","Severity": "Warning","Description": "Error Count for http request exceeded threshold for metric: HTTPCode_Target_4XX_Count ,Loadbalancer affected: app/FlySaaCmsWebALB/968b1f7492941705"} | 02/Jan/26 11:04 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2026-01-02 11:04
AM20-301 | Patching ¦¦ RHEL Server Patching | In Progress | 6 | Sprint 21 | 2025-12-22 | 2026-01-02 | Faisal Sayed | Medium | 1881212 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-12-11 09:47 | 2026-01-08 08:43 | 2026-01-08 08:33 |  |  | 0 | AS Product Owner I would like to implement Patching solution for RHEL servers so that it can fulfil security compliance and always work on latest updates. Acceptance Criteria: Patch Discovery & Inventory * System must automatically retrieve the latest RHEL patch repositories based on the subscribed BYOL entitlements (Red Hat Satellite, RHSM, or custom repo). * Server must appear in the patch inventory list with accurate OS version, kernel version, and patch level. * Â Unsupported or expired RHEL entitlements must be flagged automatically before patching.Â # Pre-Patching Compliance & Health Checks * Â Server must pass pre-patch health checks (CPU < 80%, memory < 85%, disk free > 20%, no critical services in failed state). * Â Server must have successful backup or AMI snapshot created before patching. * Â If using Red Hat Satellite / RHSM, subscription-manager must show a valid entitlement. * Â Application owner approval collected via ServiceNow/JIRA (if part of process). * CMDB / tagging validation must confirm correct environment (DEV/TEST/PROD) and workload ownership.Â # Patch Deployment * Patch manager must install only approved RHEL patches according to patch baseline (Security, Bugfix, Enhancement as applicable). * Â Kernel updates must follow defined policy (auto-apply or optional). * Â Patching must complete within approved maintenance window. * Â Packages must be updated using the approved repo path (Satellite, RHSM, or yum custom repo). * Â No unexpected package removal or dependency conflict during patching.Â # Reboot Handling (if required) * Â If patches require reboot, system must reboot automatically per schedule. * Â Post-reboot health check must verify: * Â Server is reachable over SSH * Â Application services are running * Â Kernel version reflects newly installed patches * Â Any reboot failure must trigger automatic alert via CloudWatch â†’ SNS â†’ Support. # Post-Patching Verification * Â yum history or dnf history must reflect successful patch installation. * Â rpm -qa matches required patch baseline versions. * Â Satellite / Red Hat Insights (if used) must report server as fully patched. # Logging, Reporting & Audit * Â Patch job must store logs in CloudWatch Logs or S3 for audit retention. * Â Patch status (success/failure) must update the central patch dashboard. * Â Failed patch servers must be automatically added to re-run queue or manual review queue. * Â All patch cycles must meet compliance % target (ex. 95% of PROD servers patched monthly).Â # BYOL (Own License) Specific Criteria * Â Server must maintain valid RHEL subscription mapping via Satellite or RHSM. * Â No unauthorized access to public Red Hat repos (BYOL compliance). * Â Evidence of license compliance must be available for audit. * Â License renewal reminders must be triggered 30/60/90 days before expiration. # Security & Compliance Requirements * Only approved users/roles (via IAM + SSM) can initiate patching. * Patching must not break CIS/NIST compliance checks. * Servers must be scanned by Inspector/Qualys/Trivy post-patch for vulnerabilities. * Â Critical & High CVEs must be remediated within SLA (ex: 7 days for PROD). # Rollback & Failure Handling * Â If patching fails, automatic rollback (AMI snapshot or Satellite snapshot) must be available. * Â Failed servers must generate an incident with detailed error context. * Â Application owners must be notified in case of partial or full failure. |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@d90afb5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pc9f: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 22 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-02 06:02 | [13 empty] | 02/Jan/26 8:02 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status:* Blocked *Reason:* Required configuration details for RHEL BYOL license usage in the security account are not yet documented by Aravind. These steps are essential for creating a BYOL AMI and launching the patch repository instance for RHEL. We approached AWS Support for guidance previously, and Aravind has agreed to assist once available. Until the documentation and required steps are provided, this story remains *blocked due to dependency on Aravindâ€™s input*. | [29 empty] | In Progress | 2026-01-08 08:43
AM20-300 | Voager connectivity | Done | 2 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1872880 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-12-01 12:03 | 2025-12-12 11:20 | 2025-12-14 19:04 | 2025-12-12 11:20 |  | 0 | Static Routes need to be setup. Advertise Subnets DX. Establish Routing |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;04/Dec/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [12 empty] | 02/Dec/25 5:02 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251202-150140.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1191675 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a461fc5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0oflf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-02 15:02 | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Dec/25 5:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Static routes has been implemented. Notified customer to submit CSOC for routing implementation.(CHR0031699) !image-20251202-150140.png¦width=612,alt="image-20251202-150140.png"! | 02/Dec/25 5:10 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Routing has been implemented and connectivity has been implemented. | 04/Dec/25 8:19 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Customer validated connectivity and working fine, hence resolving this story. | 12/Dec/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-12-12 11:20
AM20-299 | Ingesting 500 of lines of inbound and outbound rules from excel to Terraform code for enablement | Done | 6 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1869689 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-28 12:53 | 2025-12-12 14:51 | 2025-12-14 17:51 | 2025-12-12 14:51 |  | 0 |  |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bae0685 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ocbn: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-05 06:26 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Dec/25 8:26 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script deployment. Currently we are adding the inbound and outbound rule with excel only. | 12/Dec/25 2:51 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approving provided we see workable solution during demo | [28 empty] | Done | 2025-12-12 14:51
AM20-298 | RDS default config changes in Dev environment | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Pankaj Pathak | Medium | 1869424 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-11-28 11:12 | 2026-01-02 08:31 | 2026-01-02 08:18 |  |  | 0 | h2. Summary Changes are needed for the RDS default configuration. This includes modifying the default port for MySQL and changing the default database user. h2. Context The current setup uses the default MySQL port and user. Adjustments are required for improved security and monitoring. h2. Acceptance criteria * Change the default port for MySQL RDS from 3306 to a different port. * Change the default database user from 'admin' to a different username. * Enable enhanced monitoring for the production instance. h2. Other information N/A |  | Aravind Raj | Pankaj Pathak |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb |  |  |  |  | ;11/Dec/25 3:56 PM;0bd64ee0-8d59-462f-ab15-54fcd1a1fb2b;28800 | [6 empty] | 43200 | 28800 |  |  | 43200 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2aacc09d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obsr: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-05 13:32 | [13 empty] | 05/Dec/25 3:31 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Awaiting application team to confirm feasibility post updating port number. | 11/Dec/25 12:41 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;This subtask has dependency over application team availability to transition the port change on RDS instance. | 11/Dec/25 3:26 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;RDS Database port has been updated and shared with [~accountid:712020:5d317226-2402-463f-bda5-c2cac5f43c13] . However default superuser name â€œAdminâ€ is immutable and canâ€™t be updated. It can only be changed during instance creation. | 12/Dec/25 10:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;I could see the custom RDS port changes made only to dev environment, so switching back to in progress state. Upon completing preprod and prod this US can be marked as closed. | 02/Jan/26 8:27 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;This has been discussed with Project Owner and agreed and understood that this change is only feasible on Dev environment because it require downtime and changes around firewall and other important network components. On Dev RDS we updated port details and â€œadminâ€ user canâ€™t be changed as it is immutable. | [22 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2026-01-02 08:31
AM20-297 | EKS public sharing | To Do |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Sumit Nikam | Medium | 1869422 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-11-28 11:12 | 2026-01-08 08:37 | 2026-01-08 08:37 |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3ef27d1f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obsj: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [41 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | To Do | 2025-11-28 11:12
AM20-296 | SSM Documents and cloudtrail - pipeline cleanup | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Aravind Raj | Medium | 1869416 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-11-28 11:12 | 2025-12-12 10:26 | 2025-12-11 08:16 |  |  | 0 |  |  | Aravind Raj | Faisal Sayed |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb |  |  |  |  | ;11/Dec/25 5:41 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [6 empty] | 0 | 28800 |  |  | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@148fb93 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obs3: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-11 14:59 | [13 empty] | 11/Dec/25 4:58 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;---- h3. *Account: Backend-Prod* *Control:* {{SSM.7 â€“ SSM documents should have the block public sharing setting enabled}} *Status:* *Remediated* *Action Taken:* * Disabled public access for all Systems Manager (SSM) documents to enforce the *Block Public Sharing* setting. ---- h3. *Account: Backend-PreProd* *Control:* {{CloudTrail.2 â€“ CloudTrail should have encryption at rest enabled}} *Status:* *Suppressed* *Justification:* The presence of {{"Values": []}} (empty array) in the event selector configuration is conclusive evidence of the following sequence: # *Pipeline Creation:* An AWS CodePipeline with an S3 source was initially created. This action automatically provisioned a dedicated CloudTrail trail to capture S3 object-level events for event-driven triggers. # *Pipeline Deletion:* The pipeline was subsequently deleted. # *Orphaned Resources:* During deletion, the pipeline removed the S3 bucket ARN from the CloudTrail event selectors, resulting in an empty {{Values}} array. However, the CloudTrail trail itself and its placeholder bucket were not removed, leaving orphaned resources in the account. # *EventBridge Rules Cleanup:* The absence of EventBridge rules ({{aws events list-rules}} returned empty) confirms that these rules were cleaned up as part of the pipeline deletion process. # *Orphaned CloudTrail trail*: {{codepipeline-source-trail}} with empty event selectors (not logging anything) # *Orphaned placeholder bucket*: {{codepipeline-cloudtrail-placeholder-bucket-af-south-1}} ---- h3. *Account: Backend-Dev* *Status:* *No Action Required* | 12/Dec/25 10:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed the status is in passed state hence marking for PO approval. | 12/Dec/25 10:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;marking to done. | [24 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2025-12-12 10:26
AM20-295 | Cloud watch and secrets manager | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Shreyash Talwekar | Medium | 1869414 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-11-28 11:11 | 2025-12-13 14:33 | 2025-12-12 08:25 |  |  | 0 | Remediate or provide justification comments for failed security controls. |  | Aravind Raj | Shreyash Talwekar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [29 empty] | 10/Dec/25 12:10 PM;17cb9418-1850-4923-932b-7098ec51b6bb;CloudWatch.15 2025-12-10T15_37_22+05_30.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194024 | 10/Dec/25 12:10 PM;17cb9418-1850-4923-932b-7098ec51b6bb;CloudWatch.17 2025-12-10T15_33_10+05_30.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194025 | 10/Dec/25 12:17 PM;17cb9418-1850-4923-932b-7098ec51b6bb;SecretsManager.1 2025-12-10T15_41_47+05_30.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194029 | 10/Dec/25 12:17 PM;17cb9418-1850-4923-932b-7098ec51b6bb;SecretsManager.4 2025-12-10T15_45_31+05_30.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194028 | 12/Dec/25 10:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251212-083216.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194759 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@275f2c9e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obrv: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-10 10:10 | [13 empty] | 10/Dec/25 12:10 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Backend Prod [^CloudWatch.17 2025-12-10T15_33_10+05_30.csv] [^CloudWatch.15 2025-12-10T15_37_22+05_30.csv] I have provided comment for CloudWatch 17 and Cloudwatch 15 Security Control. The actions specified in those cannot be enabled because As per decided implementation approach, we are using Lambda to send notifications hence alarm actions are not needed. ¦As per decided implementation approach, we are using Lambda to send notifications hence alarm actions are not needed¦ | 10/Dec/25 12:11 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Backend Prod: We have updated log group retention period for log group with no retention period prior. This is for CloudWatch 16 rule, but the rule is showing failed because the rule expects retention period to be more than 365 days but it will cause increase in CloudWatch costs. | 10/Dec/25 12:17 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;[^SecretsManager.1 2025-12-10T15_41_47+05_30.csv] [^SecretsManager.4 2025-12-10T15_45_31+05_30.csv] Backend Prod Automatic rotation cannot be enabled because we store application specific confidential parameters used by deployment, auto rotate will change value in secret and that will cause issue in running application since incorrect parameter value will be fetched from AWS secret manager. | 10/Dec/25 12:53 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Backend Preprod: CloudWatch 17 and CloudWatch 15 rules cannot be enforced due to same reason as Prod environment. | 12/Dec/25 10:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;upon the requirement control state can be suppressed, so mark the control status to suppressed. cloudwatch15 and cloudwatch17 !image-20251212-083216.png¦width=435,alt="image-20251212-083216.png"! | 12/Dec/25 2:38 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Updated security controls to suppress for CloudWatch 15 and CloudWatch 17. | [21 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2025-12-13 14:33
AM20-294 | S3, KMS Failed Controls | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Aravind Raj | Medium | 1869412 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-11-28 11:11 | 2025-12-12 10:35 | 2025-12-11 08:18 |  |  | 0 | With a different compliances and standard framework will remediate the failed controls for S3 and KMS |  | Aravind Raj | Sanjot Fotedar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 |  |  |  |  | ;08/Dec/25 7:28 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18000 | ;11/Dec/25 8:25 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;39720 |  |  |  |  | 57600 | 0 | 57720 | 1 | 57600 | 0 | 57720 | [12 empty] | 10/Dec/25 10:36 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;Assessment_sheet_s3KMS.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1193964 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b7df5b0 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obrn: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-08 17:27 | [13 empty] | 08/Dec/25 7:27 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Have started working with fixing Failed Compliance s3 and KMS resources. | 10/Dec/25 10:36 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Compliance gaps identified and resolved failed controllers for S3 and KMS in backend accounts by implementing required configurations. Excel sheet is attached for fixed controllers.[^Assessment_sheet_s3KMS.xlsx] | 12/Dec/25 10:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed all controls are in passed state hence closing. | [24 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2025-12-12 10:35
AM20-293 | Security compliance actionpoint | To Do | 0 | None( Backlog) |  |  | Aravind Raj | Medium | 1868968 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-28 08:52 | 2025-12-14 17:39 | 2025-12-12 08:19 |  |  | 0 | As Product owner for Cloud Platform I would like to ensure that we are compliant with 98% from Infra Security perspective | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ee9de6f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001v | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-28 08:52
AM20-292 | CloudWatch Metrics configuration in all AWS account | To Do | 0 | None( Backlog) |  |  | Faisal Sayed | Medium | 1868810 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-28 08:08 | 2025-12-01 12:03 | 2026-01-06 08:22 |  |  | 0 | As Cloud Product Owner I wish to configure below metrices in Cloudwatch for all the AWS accounts so that we can monitor the memory and Disk availability for each applications residing over the AWS accounts. * Memory Available MBytes * LogicalDisk % Free Space * LogicalDisk Free Megabytes Acceptance Criteria * CloudWatch dashboard must consist of all the above mentioned metrics for all application so that we can view the memory and disk available space * Only specific IAM role must give permission to the CloudWatch agent to collect metrics from server * The above metrics view is restricted with relevant IAM role * The dashboard must be configured in centralized audit account ¦ ¦ | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@32f363c4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0002 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-28 08:08
AM20-291 | Review Memory dashboard and alarm of all application hosted in AWS and configure the right dashboard for memory utilization | Done | 4 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1866169 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-27 10:58 | 2025-12-12 11:19 | 2025-12-14 17:51 | 2025-12-12 11:19 |  | 0 | As product Manager I want to correct the current memory related dashboard for all applications in alignment with TM1 application which is already corrected by Aravind |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;03/Dec/25 7:29 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;21600 | ;07/Dec/25 1:47 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;09/Dec/25 12:42 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;25320 |  |  |  | 57600 | 0 | 57720 | 1 | 57600 | 0 | 57720 | [12 empty] | 09/Dec/25 12:52 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251209-105119.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1193693 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@14947356 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7xb: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 |  | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | [65 empty] | YES | YES | 2025-12-03 05:28 | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | [12 empty] | 03/Dec/25 7:28 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Started working on 2 Account and will complete the remaining oneâ€™s by today. | 07/Dec/25 1:49 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have updated the Memory Committed Bytes for all the Windows servers for all the accounts. Need to review it with faisal. And then will move this story to PO approval. | 09/Dec/25 12:43 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Completed the activity and updated the Memory Committed Bytes Name and Threshold value for all accounts. | 09/Dec/25 12:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251209-105119.png¦width=641,alt="image-20251209-105119.png"! Evidence has been attached from one of the account for which the Memory Committed bytes has been updated. | 12/Dec/25 11:19 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-12-12 11:19
AM20-290 | Handover of Patching solution | Done | 4 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1866136 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-27 10:49 | 2025-12-12 11:19 | 2025-12-14 17:52 | 2025-12-12 11:19 |  | 0 | As product owner I want Diksha to take handover along with Satya from Faisal so that she can support customer |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [5 empty] | ;09/Dec/25 12:43 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;10/Dec/25 3:38 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 09/Dec/25 12:55 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251209-105350.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1193694 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@58f0f8fd | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7xd: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-09 10:45 | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 09/Dec/25 12:45 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started the Hands on for patching first worked on pre-requisites and AWS cli and cloud watch agent installation on the Sandbox EC2 instance. The Session has been recorded as well. | 09/Dec/25 12:55 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251209-105350.png¦width=641,alt="image-20251209-105350.png"! This server is created as a Test Patching server for the Windows patching activity. As of now this has been kept in stopped state later after the patching will get done we will delete the server moving further. The below pointers has been completed. * *Provisioned Test Environment* ** Deployed a test EC2 instance in the designated sandbox environment. * *Network Configuration* ** Configured VPC endpoints to enable *private connectivity for AWS Systems Manager (SSM)*, ensuring secure management without requiring a public IP. * *Identity and Access Management (IAM)* ** Created IAM roles, policies, and instance profiles for EC2 to support required permissions. ** Implemented a *cross-account IAM role* for Lambda in the security account, enabling patching operations in the sandbox environment. ** Updated trust relationships to align with cross-account access requirements. * *Instance Setup and Agent Installation* ** Downloaded and installed *AWS CLI*, *CloudWatch Agent*, and *SSM Agent* on the EC2 instance. ** Deployed a custom compliance reporting script within the instance. * *Automation and Management* ** Authored and deployed a *custom SSM document* to support patching and compliance workflows. | 10/Dec/25 3:37 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Below pending points are also covered today and the handover of the patching is completed. * *S3 Bucket Configuration* ** Set up an Amazon S3 bucket with the required folder structure. ** Apply appropriate *IAM permissions* and *bucket policies* to ensure secure access. ** Configure *S3 event notifications* to trigger downstream processes as needed. * *Lambda Automation for Patching* ** Develop and deploy a Lambda function to *automate patching activities* within the sandbox account. ** Ensure the Lambda function uses the *cross-account IAM role* created today, granting it the necessary permissions to execute patching tasks in the sandbox environment. ** Validate the Lambda execution policy and trust relationship for compliance and least-privilege access. | 10/Dec/25 3:38 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[Recap: Patch Implementation - Internal Tuesday, December 9 ¦ Meeting ¦ Microsoft Teams¦https://teams.microsoft.com/l/meetingrecap?driveId=b%21d5bfbASx8UyuyN5zJPY_C1jj3vg4dqxGo4vsecE4YZu3kE97HxTiSrSKd-pI-KUx&driveItemId=016NKAQFNQOEZURWCDERFYBPVICI6NDJX2&sitePath=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQCwcTNI2EMkS4C-qBI80ab6Af6L1MuuoLAsP4web0CEjFk&fileUrl=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQCwcTNI2EMkS4C-qBI80ab6Af6L1MuuoLAsP4web0CEjFk&iCalUid=040000008200E00074C5B7101A82E00800000000A47F206EE268DC01000000000000000010000000321233C36A404C46934C1B5B72B7F07A&threadId=19%3Ameeting_ZjBlZDVhMjMtNDI4ZC00NjQ5LThiMzgtM2FiMDhhNTIyZDg2%40thread.v2&organizerId=8f4c76ce-ca6e-44bd-bbde-0eb6186f9df7&tenantId=68283f3b-8487-4c86-adb3-a5228f18b893&callId=76b0f585-b89d-412b-b23f-2527a464dab5&threadType=Meeting&meetingType=Scheduled&subType=RecapSharingLink_RecapChiclet] [Recap: Patch Implementation - Internal Wednesday, December 10 ¦ Meeting ¦ Microsoft Teams¦https://teams.microsoft.com/l/meetingrecap?driveId=b%21d5bfbASx8UyuyN5zJPY_C1jj3vg4dqxGo4vsecE4YZu3kE97HxTiSrSKd-pI-KUx&driveItemId=016NKAQFKGUFQPO2BR7VC3OZIJ4T4BALUJ&sitePath=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQBGoWD3aDH9RbdlCeT4EC6JAf1ANE41qecWYg-ZpI8nWPs&fileUrl=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQBGoWD3aDH9RbdlCeT4EC6JAf1ANE41qecWYg-ZpI8nWPs&iCalUid=040000008200E00074C5B7101A82E00800000000F3F48BFDF868DC01000000000000000010000000D320B3E36531F44C8156C61B7DCD0871&threadId=19%3Ameeting_YTQ3OGI1ODMtM2JjMy00YTkzLTlhNjQtYWUwMGY4OTFlZDAz%40thread.v2&organizerId=8f4c76ce-ca6e-44bd-bbde-0eb6186f9df7&tenantId=68283f3b-8487-4c86-adb3-a5228f18b893&callId=3fb32e76-7aa1-40f8-a245-6ac6fdac8f6c&threadType=Meeting&meetingType=Scheduled&subType=RecapSharingLink_RecapChiclet] Both recording links has been attached above. | [26 empty] | Done | 2025-12-12 11:19
AM20-289 | CMS Frontend SMS PROD implementation | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865997 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-27 10:08 | 2025-12-12 14:50 | 2025-12-14 17:52 | 2025-12-12 14:50 |  | 0 | As a cloud platform application owner I want to perform a detailed assessment for enable SMS notification in the CMS frontend application hosted in AWS Acceptance Criteria Dedicated SNS topic created successfully for CMS frontend specific Subscribe long code to SNS topic successfully Complete Configuration of CloudWatch alarms for application error through custom metrics CloudWatch Alarms are created successfully AWS Lamda function is created with all the required error details in compliant with ServiceNow format including Severity Validation of Setup is completed successfully post implementation |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Worked on understanding the alarm list and discussing their priorities.;03/Dec/25 12:11 PM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on adding support for sms notification for critical alerts like ALB getting 400, 500 errors;09/Dec/25 8:00 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Re-deployed sms notification infrastructure on preprod env to mimic instance down scenario.;09/Dec/25 8:01 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on testing number of liferay instances running metric and updating lambda to make sure sms notification indicates which node is not working.;09/Dec/25 8:02 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on replicating logic for similar alarms.;09/Dec/25 8:04 AM;17cb9418-1850-4923-932b-7098ec51b6bb;14400 |  | 115200 | 7200 | 108000 | 0.93 | 115200 | 7200 | 108000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4211dfc7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7x7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-03 10:14 | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 03/Dec/25 12:13 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Discussed with Hoosen regarding the list of alarms to enable SMS notification for and priorities to be assigned to them. Started working on configuring P1 alerts. | 09/Dec/25 8:08 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Status till now: # Worked on configuring sms notifications for critical alerts like ALB, number of liferay running and CPU utilization of instances ,RDS , alarms for metrics like procstat_num_fds, procstat_num_threads. # Replicated sms implementation on saa frontend preprod to test alarms involving stopping instances, alarms are sending correct info regarding which instances are down. # Working on adding sms support for metrics like homepage availability, fabric availability etc. | 10/Dec/25 8:19 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created and tested few alarms for monitoring metric like HomePage availability , Fabric Availability etc in prod. | 12/Dec/25 2:31 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created and Tested alarms in Prod and Preprod. | 12/Dec/25 2:50 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-12-12 14:50
AM20-288 | Documentation ¦¦ Centralized CICD Design Creation | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865918 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-27 09:50 | 2025-12-12 14:49 | 2026-01-06 13:11 | 2025-12-12 14:49 |  | 0 | As Product Owner I would like to create a design for centralized CICD pipeline so that Terraform code can be deployed automatically and systematically as per standards Acceptance Criteria: * *Automated Deployment:* The solution must automatically deploy Terraform code to specified target AWS accounts upon successful pipeline execution. * *Multi-Account Support:* The solution must be capable of deploying to and managing resources across multiple distinct AWS accounts. * *Centralized Control:* All deployments and pipeline configurations must be managed from a central location within the CI/CD solution. * *Version Control Integration:* The solution must integrate with a chosen version control system (e.g., Git) to trigger pipelines on code changes and manage Terraform code versions. * *Terraform State Management:* The solution must securely and reliably manage Terraform state files, ideally using a remote backend to prevent state corruption and enable collaboration. # Security and Compliance: * *Secure Credential Management:* The solution must securely store and manage AWS credentials required for deployments, utilizing mechanisms like IAM roles and secrets management services. * *Least Privilege Access:* The solution must enforce the principle of least privilege, granting only necessary permissions to deploy resources in target AWS accounts. * *Auditing and Logging:* The solution must provide comprehensive logging of all deployment activities, including who initiated the deployment, what changes were applied, and the outcome. * *Compliance Checks:* The solution should support integration with tools for static code analysis, security scanning (e.g., Trivy, SonarQube), and compliance policy enforcement on Terraform code. # Reliability and Scalability: * *Idempotency:* Terraform deployments executed by the CI/CD solution must be idempotent, meaning running the same configuration multiple times yields the same result without unintended side effects. * *Error Handling and Rollback:* The solution must provide robust error handling and, where possible, support automated rollback mechanisms in case of deployment failures. * *Scalability:* The solution must be able to scale to handle an increasing number of AWS accounts, Terraform modules, and deployment frequency. # Usability and Maintainability: * *Clear Pipeline Visualization:* The solution should offer a clear and intuitive visualization of the CI/CD pipeline stages and their status. * *Parameterization and Templating:* The solution should support parameterization and templating of Terraform configurations to enable reusability and reduce duplication across accounts. * *Notifications:* The solution should provide configurable notifications via SNS to email on pipeline status changes, successes, and failures. * *Documentation:* Comprehensive documentation for setting up, configuring, and using the centralized CI/CD solution must be available. |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [11 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 12/Dec/25 2:35 PM;17cb9418-1850-4923-932b-7098ec51b6bb;AWS Multi-Account CICD Documentation.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194851 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@23ca158b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7pn: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_367685610_*¦*_10041_*:*_1_*:*_945188680_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_367685610_*¦*_10041_*:*_1_*:*_945188680_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_367685610_*¦*_10041_*:*_1_*:*_945188680_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_367685610_*¦*_10041_*:*_1_*:*_945188680_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-12 12:36 | 3_*:*_1_*:*_367685610_*¦*_10041_*:*_1_*:*_945188680_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 12/Dec/25 2:35 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;[^AWS Multi-Account CICD Documentation.docx] Attaching proposed approach document. | [29 empty] | Done | 2025-12-12 14:49
AM20-287 | Route53 ¦¦ Post Cutover validation and Support for Airchef | Done | 0 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865870 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-27 09:37 | 2025-12-12 11:18 | 2025-12-14 18:50 | 2025-12-12 11:18 |  | 0 | As Product owner I wish to validate the behaviour of Airchef so that we can assure that the Airchef is working as expected and change caused by AWS does not create any issues. Acceptance Criteria: Airchef BAU is working as expected and the traffic is directed via AWS route53 |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@50f9cacc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7nf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-04 06:32 | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 04/Dec/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Original [airchefs.co.za¦http://airchefs.co.za] migration completed still on-prem to VDC cutover need to be implemented. | 05/Dec/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;On prem to VDC cutover has been completed and tested by SITA team, According to Hoosen Tlou <[hoosentlou@flysaa.com¦mailto:hoosentlou@flysaa.com]> current Airchefs servers are shutdown and decommissioned. Notified to team don't go for decom but Denise notified to go for decom. | 12/Dec/25 11:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-12-12 11:18
AM20-286 | Route53 cutover for FlySAA.com | Done | 2 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865867 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-27 09:36 | 2025-12-12 11:18 | 2025-12-14 18:49 | 2025-12-12 11:18 |  | 0 | As product Ownwer I like to perform cutover for Route53 for [FlySAA.com¦http://FlySAA.com] Acceptance Criteria: The [flysaa.com¦http://flysaa.com] application must be highly available and resilient to single-region outages (e.g., 99.99% uptime). *Route 53 Implementation:* Configure *Failover Routing* policies. A primary record is associated with an active endpoint. A secondary, passive record is configured as a backup. Route 53 health checks automatically switch traffic to the secondary region if the primary endpoint is deemed unhealthy. |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;04/Dec/25 8:30 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;43200 | [5 empty] | 28800 | 0 | 43200 | 1.5 | 28800 | 0 | 43200 | [12 empty] | 04/Dec/25 8:30 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251204-063001.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1192161 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@769d9d3b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7mz: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-02 16:21 | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Dec/25 6:20 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Latest zone file has been imported under public hosted zone route53 AWS.. Earlier 313 after upload 318 records has-been created. | 04/Dec/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;DNS pointer has been modified to route53. C:\Users\VaranasiS>nslookup -query=NS [flysaa.com¦http://flysaa.com] Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: [flysaa.com¦http://flysaa.com] nameserver = [ns-1419.awsdns-49.org¦http://ns-1419.awsdns-49.org] [flysaa.com¦http://flysaa.com] nameserver = [ns-308.awsdns-38.com¦http://ns-308.awsdns-38.com] [flysaa.com¦http://flysaa.com] nameserver = [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] [flysaa.com¦http://flysaa.com] nameserver = [ns-1777.awsdns-30.co.uk¦http://ns-1777.awsdns-30.co.uk] [ns-1419.awsdns-49.org¦http://ns-1419.awsdns-49.org] internet address = 205.251.197.139 [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] internet address = 205.251.194.93 [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] AAAA IPv6 address = 2600:9000:5302:5d00::1 [ns-1777.awsdns-30.co.uk¦http://ns-1777.awsdns-30.co.uk] internet address = 205.251.198.241 C:\Users\VaranasiS> | 04/Dec/25 8:23 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Customer requested to add new alias zone for ALB. ¦[flysaa.com¦http://flysaa.com]¦A¦Simple¦-¦Yes¦[flysaa-cms-alb-402247724.af-south-1.elb.amazonaws.com¦http://flysaa-cms-alb-402247724.af-south-1.elb.amazonaws.com].¦ ¦ Zone has been created and validated after DNS cutover and same working fine. !image-20251204-063001.png¦width=591,alt="image-20251204-063001.png"! | 05/Dec/25 8:29 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SAA SSL DNS has been modified according to request. the change requested under â€œCHG0068431/ CHR0031920â€ has been successfully implemented. Below you will find the latest and updated record for your reference. Â Â C:\Users\VaranasiS>nslookup [upwards.flysaa.com¦http://upwards.flysaa.com] Server:Â UnKnown Address:Â 2401:4900:50:9::7d5 Â Non-authoritative answer: Name:Â Â Â [upwards.flysaa.com¦http://upwards.flysaa.com] Address:Â [102.130.96.4¦https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2F102.130.96.4%2F&data=05%7C02%7Csatyasairam.varanasi%40vodafone.com%7C3d58714d9d324c04956d08de33430e8a%7C68283f3b84874c86adb3a5228f18b893%7C0%7C0%7C639004560572522291%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=w7K%2F%2Fjsk9kHTi00XQSJKC3mq2iHGjbBvw1316zlJjyk%3D&reserved=0] Â Â C:\Users\VaranasiS> Â | 12/Dec/25 11:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-12-12 11:18
AM20-285 | MQ - Parser trigger based on incoming message | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1863569 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-26 14:10 | 2025-12-12 14:49 | 2025-12-14 17:52 | 2025-12-12 14:49 |  | 0 | As Product Owner I like to ensure that each relevant incoming message triggers the respective parser and process the message successfully |  | Sanjot Fotedar | [5 empty] | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [5 empty] | ;11/Dec/25 4:51 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;86400 | ;12/Dec/25 1:19 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;28800 |  |  |  |  | 115200 | 0 | 115200 | 1 | 115200 | 0 | 115200 | [12 empty] | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111735.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194825 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111750.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194828 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111758.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194830 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111812.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194831 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111822.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194826 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111832.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194829 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111843.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194827 | [11 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4937ec21 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o64z: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_104373748_*¦*_10041_*:*_1_*:*_1274929064_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_104373748_*¦*_10041_*:*_1_*:*_1274929064_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_104373748_*¦*_10041_*:*_1_*:*_1274929064_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_104373748_*¦*_10041_*:*_1_*:*_1274929064_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-11 14:53 | 3_*:*_1_*:*_104373748_*¦*_10041_*:*_1_*:*_1274929064_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 11/Dec/25 4:53 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Working on lambda integration setup to trigger as soon as message arrives to specific queue in AWS Active MQ broker. | 12/Dec/25 1:18 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;* Integrated AWS lambda with Active MQ so that any message on queue automatically triggers processing * Added secure integration with aws secrets manager for fetching MQ broker credentials * Implemented java 17 lambda to decode base64 messages, run ParserLogic, and generate outputs. * added logging to track message received, parsed output, and any errors. * End-to end flow: Message arrives in MQ â†’ Lambda Triggers â†’ Credentials fetched securely â†’ Message Decoded â†’ Parsed â†’ Logged successfully. !image-20251212-111735.png¦width=455,alt="image-20251212-111735.png"! !image-20251212-111750.png¦width=455,alt="image-20251212-111750.png"! !image-20251212-111758.png¦width=455,alt="image-20251212-111758.png"! !image-20251212-111812.png¦width=455,alt="image-20251212-111812.png"! !image-20251212-111822.png¦width=455,alt="image-20251212-111822.png"! !image-20251212-111832.png¦width=455,alt="image-20251212-111832.png"! !image-20251212-111843.png¦width=455,alt="image-20251212-111843.png"! | [28 empty] | Done | 2025-12-12 14:49
AM20-284 | MQ POC -SbrSplit Parser Testing | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1863568 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-26 14:10 | 2026-01-02 11:05 | 2026-01-04 09:12 | 2026-01-02 11:05 |  | 0 | I need to test SbrSplit MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [5 empty] | ;17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;18000 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;23/Dec/25 8:26 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18120 | 115200 | 0 | 115320 | 1 | 115200 | 0 | 115320 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2372d0ee | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o64r: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 21 | [97 empty] | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-09 06:22 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 09/Dec/25 8:21 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Testing has been started. Few errors were identified during execution of jar files. Being checked further. | 11/Dec/25 8:17 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Still working on error fixes | 17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Errors have been fixed and initial testing has been completed. | [27 empty] | Done | 2026-01-02 11:05
AM20-283 | Patching New Requirement ¦¦ Cache Drive for Patching | Done | 5 | Sprint 21 | 2025-12-22 | 2026-01-02 | Yashwant Thakur | Medium | 1863471 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-26 13:35 | 2026-01-02 11:27 | 2025-12-18 08:19 | 2026-01-02 11:27 |  | 0 | As Cloud Product manager I would like to use Cache drive for the EC2 servers where Storage is low to proceed with Patching so that we can successfully patch servers without any issue. Acceptance Criteria: * Before Patching is initiated Lamda function first assess if the given EC2 server has sufficient storage available. If the Storage is insufficient then it must attach cache drive to the server and reboot flow must be initiated * Post reboot the storage must be attached successfully * If the Storage is sufficient on the given EC2 instance then the patching should be progressed without any issue |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@66bf1276 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001r | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2026-01-02 06:08 | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Jan/26 8:08 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Update* The *AWS Systems Manager (SSM) document* has been modified to optimize patch installation by leveraging a temporary attached volume. h3. *Technical Details* * The SSM document now: ** Utilizes an *attached temporary volume* mounted with drive letter {{T:}}. ** Downloads and installs patches onto this temporary volume during execution. * Post-installation: ** The system does *not maintain any dependency* on the temporary volume. ** The temporary volume is *manually deleted* after installation is complete (deletion is *not automated* within the document). | [29 empty] | Done | 2026-01-02 11:27
AM20-282 | Patching New Requirement ¦¦ Automatic reboots post Patching | Done | 6 | Sprint 21 | 2025-12-22 | 2026-01-02 | Yashwant Thakur | Medium | 1863370 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-26 12:57 | 2026-01-02 11:27 | 2026-01-04 09:12 | 2026-01-02 11:27 |  | 0 | As a cloud platform product owner I would like Patching workflow to automatically trigger the controlled reboot once the patching is completed so that the servers come back online and running with the updated Patch applied without any manual intervention Acceptance Criteria: * Reboot trigger - AN EC2 instance with patching enabled when the patching task for that instance completed successfully system must trigger a reboot workflow * Given that instance tagged with *Reboot=Yes* when the patching completes then the instance must be rebooted and given the instance tagged with *Reboot=No* when the patching completes then the instance reboot is skipped * If the reboot fails, it should try minimum of 3 times and if the reboot is failed than an alert is sent to ServiceNow via SNS so that the incidents can be recorded * Agonistic Reboot workflow - Given the EC2 is linux or windows , post reboot it should be able to run the automatic commands successfully * Given that the reboot is performed when the EC2 returns online then both the system status and instance status must reach *Status = OK* within the defined timeout of 5-10 mins. |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [5 empty] | ;17/Dec/25 8:21 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 17/Dec/25 8:43 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251217-064315.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1195352 | 17/Dec/25 8:44 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251217-064400.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1195353 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@706d20f8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001i | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_1380898735_*¦*_10041_*:*_1_*:*_1797880683_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1380898735_*¦*_10041_*:*_1_*:*_1797880683_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1380898735_*¦*_10041_*:*_1_*:*_1797880683_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1380898735_*¦*_10041_*:*_1_*:*_1797880683_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-17 06:35 | 3_*:*_1_*:*_1380898735_*¦*_10041_*:*_1_*:*_1797880683_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 17/Dec/25 8:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Summary â€“ CloudWatch Logs â†’ EC2 Restart Automation (Postâ€‘Patch)* Implemented an endâ€‘toâ€‘end serverless workflow that monitors SSM patch logs and automatically restarts EC2 instances tagged for restart once compliance is detected. *Outcome* * âœ… Realâ€‘time detection of *FINAL_STATUS: COMPLIANT* in the latest SSM patch log stream * âœ… Automatic reboot/start of EC2 instances with {{Restart=True}} tag, based on instance state * âœ… Robust logging, error handling, and leastâ€‘privilege access *Architecture (Highâ€‘Level)* SSM Patch â†’ CloudWatch Logs â†’ Subscription Filter â†’ Lambda â†’ EC2 Actions * Monitors *latest* log stream only to prevent duplicate actions * Latency typically < 3 minutes from compliance log to instance action *Key Logic & Actions* * Validate source log group and most recent stream * Detect compliance message * Discover instances via tag {{Restart=True}} ** Running â†’ {{reboot}} ** Stopped â†’ {{start}} ** Other states â†’ skip (logged with reason) *Security & Permissions (Summary)* * Lambda execution role: minimal permissions for CloudWatch Logs (write/describe) and EC2 (describe/reboot/start) * CloudWatch Logs â†’ Lambda invoke permission scoped to the specific log group *Testing & Validation* * Simulated compliance events via CloudShell. * Verified: subscription trigger, Lambda execution, latestâ€‘stream check, instance discovery/actions, error handling, and logging. | 17/Dec/25 8:43 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251217-064315.png¦width=486,alt="image-20251217-064315.png"! | 17/Dec/25 8:44 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251217-064400.png¦width=486,alt="image-20251217-064400.png"! | 02/Jan/26 7:56 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *1. Overview* The configuration enables automated EC2 instance reboot post-installation compliance by leveraging AWS services such as CloudWatch Logs, Lambda, and EC2 tagging. h3. *2. Trigger Condition* * An *EC2 instance* is tagged with a specific key-value pair (e.g., {{restart=true}}). * This tag acts as the primary condition for initiating the workflow. h3. *3. Log Monitoring* * A *CloudWatch Logs subscription filter* is configured to monitor log streams. * It searches for the phrase *â€œfinal status: compliantâ€* in the latest log entries. * This ensures the reboot only occurs after successful compliance verification. h3. *4. Lambda Invocation* * Upon detecting the compliance status in the logs, the subscription filter triggers an *AWS Lambda function*. * The Lambda function: ** Processes the payload from CloudWatch. ** Validates the EC2 instance tags. ** Confirms the restart condition. h3. *5. EC2 Reboot Action* * After validation, the Lambda function initiates a *reboot operation* on the targeted EC2 instance. * This guarantees the restart happens *post-installation and compliance checks*. h3. *6. Key AWS Components* * *Amazon EC2*: Target instance for reboot. * *CloudWatch Logs*: Monitors log streams for compliance status. * *Subscription Filter*: Detects specific log patterns. * *AWS Lambda*: Handles logic and initiates reboot. | [26 empty] | Done | 2026-01-02 11:27
AM20-281 | Create Fortinet Firewall Implementation SOW and client Proposal Document. | Done | 0 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1850377 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-20 14:32 | 2025-11-28 14:00 | 2025-11-21 10:34 | 2025-11-28 14:00 |  | 0 | As Product owner I would like to create SOW for Fortinet firewall implementation so that Stakeholders can review and take a call whether to implement it. Acceptance Criteria: The SOW document should consist of below topic. * Complete SOW Structure * Deployment Phases * Proposed Architecture * License and Billing * Key Deliverables * RACI * Assumptions and Risks |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [29 empty] | 21/Nov/25 8:15 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;SAA-FortiGateFirewall_Implementation.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187538 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7e936038 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0nmmb: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_43219_*¦*_10041_*:*_1_*:*_63823497_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_43219_*¦*_10041_*:*_1_*:*_63823497_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_43219_*¦*_10041_*:*_1_*:*_63823497_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_43219_*¦*_10041_*:*_1_*:*_63823497_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-21 06:17 | 3_*:*_1_*:*_43219_*¦*_10041_*:*_1_*:*_63823497_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 21/Nov/25 8:16 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Attaching document on Sankalpâ€™s behalf because his Jira is not working. Moving this to review | 28/Nov/25 2:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-11-28 14:00
AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | In Progress | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Aravind Raj | Medium | 1843633 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-17 14:14 | 2026-01-04 09:03 | 2026-01-08 14:26 |  |  | 0 | With a different compliances and standard framework will remediate the failed controls. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;28/Nov/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 144000 | 43200 | 201720 | [12 empty] | 28/Nov/25 5:29 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Backend-ProdFailedControls.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190855 | 28/Nov/25 5:26 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Security Checklist - Hub Standards.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190854 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@44750d99 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n9p7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-21 06:04 | [13 empty] | 21/Nov/25 8:04 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working with backend Dev environment. | 25/Nov/25 7:44 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on backend preprod for failed controls to remediate. | 27/Nov/25 8:18 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have remediated failed controls from all the three account, just waiting for security score to update, FlySAA_CMS_Backend_DevQA FlySAA_CMS_Backend_PreProd FlySAA_CMS_Backend_Prod | 27/Nov/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Upon score update, will pull the failed controls after remediation and will ask concern person to work on that. | 28/Nov/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;In standup call have given walkthrough to team to work on individual to get the failed controls remediated. | 28/Nov/25 11:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have created a sub task for team to work on respective controls remediation. | 28/Nov/25 5:28 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Attached Controls checklist for your reference, im still waiting for the failed controls to update the latest status, after the status update will be attaching sheet for dev and preprod account. | 28/Nov/25 5:29 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;[^Backend-ProdFailedControls.csv] Attaching backend prod failed controls | [22 empty] | In Progress | 2025-11-21 08:03
AM20-279 | MQ POC ¦¦ MQ Parser Execution - Lambda integration testing & Message body validation | Done | 8 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1842282 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-17 08:36 | 2025-11-28 07:36 |  | 2025-11-28 07:36 |  | 0 | As Application product owner I would like to perform Lamda integration test with MQ parser and validate the messages output |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Nov/25 5:05 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;7200 | ;21/Nov/25 9:21 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;43200 | ;25/Nov/25 4:07 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;64800 |  |  |  | 115200 | 0 | 115200 | 1 | 115200 | 0 | 115200 | [12 empty] | 25/Nov/25 4:07 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251125-140722.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189321 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124739.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189722 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124758.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189723 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124816.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189725 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124826.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189726 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124840.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189721 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124850.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189724 | [11 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@21c31db9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5mz: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 15:05 | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 5:05 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Exploring feasible approaches for Lambda integration with MQ parser, since direct MQ - Lambda integration is not possible. | 21/Nov/25 8:27 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;we have configured lambda and tested workfow funtionality by pushing message to s3 bucket from SQS. Now we go with checking feasibility with pegasys application usecase | 25/Nov/25 4:07 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Another approach, we tried to integrate MQ queue â€œPEGASYS.OUT.UATâ€ directly to Lambda !image-20251125-140722.png¦width=459,alt="image-20251125-140722.png"! | 26/Nov/25 2:49 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Â We tried integrating both S3 and MQ with Lambda directly. Whenever message reaches to MQ queue, it should trigger lambda which doesnâ€™t happen. However we tested then by integrating s3 event type â€œPutâ€, as soon as any object is uploaded to s3 bucket, it triggers Lambda Â !image-20251126-124739.png¦width=443,alt="image-20251126-124739.png"! Â !image-20251126-124758.png¦width=443,alt="image-20251126-124758.png"! Â !image-20251126-124840.png¦width=443,alt="image-20251126-124840.png"! !image-20251126-124850.png¦width=443,alt="image-20251126-124850.png"! !image-20251126-124816.png¦width=443,alt="image-20251126-124816.png"! !image-20251126-124826.png¦width=443,alt="image-20251126-124826.png"! As next step in next sprint , we will raise support ticket with AWS to get more clarity on this approach of direct integration of lambda and MQ | 28/Nov/25 7:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-28 07:36
AM20-278 | Add-On ¦¦ WAF Rule creation for Voyager | To Do | 4 | None( Backlog) |  |  | Aravind Raj | Medium | 1842274 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-17 08:33 | 2025-11-18 13:54 |  |  |  | 0 | [20 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@37603ed1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5m3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-17 08:33
AM20-277 | RDS Upgrade in Flysaa backend Dev environment | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1842266 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-17 08:32 | 2025-11-27 09:18 | 2025-11-26 08:48 | 2025-11-27 09:18 |  | 0 | h2. User story * When the RDS instance is upgraded, I want to ensure compatibility with MySQL 8.4 so that our application runs smoothly without issues. h2. Context The development RDS instance will be upgraded from MySQL version 5.7 to 8.4. This upgrade may affect the functionality and performance of the application. h2. Acceptance criteria * The RDS instance must be successfully upgraded to MySQL 8.4. * All application features should function correctly after the upgrade. * Performance benchmarks should be met post-upgrade. h2. Other information N/A |  | Pankaj Pathak | Yashwant Thakur |  |  |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7e1de089 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5lf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [65 empty] | YES | YES | 2025-11-20 06:25 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [12 empty] | 20/Nov/25 8:24 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;The upgrade from MySQL version 5.7.44 to 8.0.42 was successful. The DB instance is running smoothly. We asked the application team (Donald and Gavin) to confirm everything is functioning well on their end. We are awaiting their response to close this story. | 25/Nov/25 2:00 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Ticket moved to In review. As we have completed internal review. | 27/Nov/25 9:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Post upgrade, Business confirmed that BAU is working as expected hence approving | [27 empty] | Done | 2025-11-27 09:18
AM20-276 | Assessment on CMS Frontend SMS implementation | Done | 8 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Highest | 1842250 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-17 08:30 | 2025-11-28 14:00 | 2025-11-28 11:16 | 2025-11-28 14:00 |  | 0 | As a cloud platform application owner I want to perform a detailed assessment for enable SMS notification in the CMS frontend application hosted in AWS so that I can determine best approach, integration method, cost impact, security requirement and technical feasibility before implementation Acceptance Criteria: All use cases for SMS notification are documented SLA, frequency and criticality of SMS delivered and captured User flow diagrams for each SMS scenario prepared Assessment must identify How front will invoke API Required IAM permission documented for access for SMS publishing Consideration for rate limiting and Compliance requirements Risk, Assumption and dependencies |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Understanding alarm implementation and getting AWS frontend access from Leigh.;28/Nov/25 10:33 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on implementing SMS notification on frontend dev account;28/Nov/25 10:33 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | SMS implementation is working, worked on debugging minor issues and updating timeout of Lambda function to enable sending SMS to multiple numbers.;28/Nov/25 10:34 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 |  |  |  | 115200 | 28800 | 86400 | 0.75 | 115200 | 28800 | 86400 | [12 empty] | 28/Nov/25 1:49 PM;17cb9418-1850-4923-932b-7098ec51b6bb;SMS_frontend_alerts.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190540 | 28/Nov/25 10:36 AM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251128-083619.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190436 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67436dd5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5jf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-25 08:56 | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 25/Nov/25 10:56 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created a Whitepage access request to enable access for frontend AWS accounts, reached out to Leigh with ticket details. | 26/Nov/25 8:54 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Access request is approved, awaiting access enabling from Leigh. | 27/Nov/25 8:21 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Got the access from Leigh, worked on provisioning AWS resources (Lambda , eventbridge rule , dynamodb table) for alert implementation, need to get number from Hoosen for sending sms. | 28/Nov/25 10:36 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Hoosen confirmed he got SMS for sample alarm in frontend dev . !image-20251128-083619.png¦width=281,alt="image-20251128-083619.png"! | 28/Nov/25 1:49 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;[^SMS_frontend_alerts.docx] Please find attached document for SMS implementation. | 28/Nov/25 2:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-28 14:00
AM20-275 | Guardy duty and Guardrail implementation on Pegasys account | To Do | 0 | None( Backlog) |  |  |  | Medium | 1835991 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-13 19:35 | 2025-11-18 09:56 |  |  |  | 0 | [57 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@69378c41 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g000i | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-13 19:35
AM20-274 | Terraform code to automate the Route 53 cutover | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Satya Varanasi | Medium | 1835056 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-11-13 10:54 | 2025-11-25 09:23 | 2025-11-25 08:21 |  |  | 0 | [airchefs.co.za¦http://airchefs.co.za] need to be setup on network account. |  | Harsh Chandra | Sanket Kale |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:91948faf-1676-4820-bf6b-d50a7992943e | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@279e63c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxgj: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 07:08 | [13 empty] | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | 25/Nov/25 8:17 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Validated with the internal team and assign it to Satyasairam for the review | [25 empty] | 1834911 | AM20-267 | Route53 cutover for Airchef | Done | 2025-11-25 09:23
AM20-273 | Servicenow Payload severity updates for Lambda alarms | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Shreyash Talwekar | Medium | 1835024 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-11-13 10:48 | 2025-11-24 08:42 |  |  |  | 0 | Enhance the existing Lambda function that triggers when Lambda alarms enter an alarm state. Currently, the function gathers alarm-related metrics, collects function details, and sends an approved payload to ServiceNow. However, severity information from the alarm is not included in the payload. This story addresses that gap by updating the Lambda function to capture and transmit the correct severity level from the alarm to ServiceNow. *Acceptance Criteria:* * Lambda function must include severity details from the alarm in the payload. * Payload sent to ServiceNow should accurately reflect the alarm severity. |  | Faisal Sayed | Harsh Chandra | Shreyash Talwekar |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  | ;20/Nov/25 8:33 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;14400 | [6 empty] | 0 | 14400 |  |  | 0 | 14400 | [12 empty] | 21/Nov/25 7:04 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251121-050425.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187511 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@560f4ab3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxar: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 05:33 | [13 empty] | 20/Nov/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Requirements have been gathered. Lambda function code will be reconfigured to incorporate changes, followed by payload testing. Ticket will be updated upon successful completion of testing. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Lambda function has been updated per requirements to capture severity. A test event was executed to validate behavior and output; results are attached. Test outcome is successful, and the implementation is complete. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251121-050425.png¦width=555,alt="image-20251121-050425.png"! | 24/Nov/25 8:42 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reviewed output, LGTM. | [23 empty] | 1832856 | AM20-264 | Update ServiceNow Payloads with severity | Done | 2025-11-24 08:41
AM20-272 | Servicenow Payload severity updates for Infra alarms | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Aravind Raj | Medium | 1835021 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-11-13 10:47 | 2025-11-19 14:02 | 2025-11-21 10:34 |  |  | 0 | Modify Lambda function to allow a parameter severity to the service now workload. |  | Aravind Raj | Harsh Chandra | Shreyash Talwekar |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  | ;19/Nov/25 2:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 19/Nov/25 1:50 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251119-115035.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186444 | 19/Nov/25 1:50 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251119-115039.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186445 | 19/Nov/25 1:51 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251119-115135.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186450 | 19/Nov/25 2:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251119-120126.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186469 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@501b8627 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxab: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-19 11:51 | [13 empty] | 19/Nov/25 1:50 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have updated the lambda function to allow the severity parameter and have verified the payload getting via an email. | 19/Nov/25 1:50 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Production payload !image-20251119-115039.png¦width=423,alt="image-20251119-115039.png"! | 19/Nov/25 1:51 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Dev Payload !image-20251119-115135.png¦width=423,alt="image-20251119-115135.png"! | 19/Nov/25 2:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;QA payload !image-20251119-120126.png¦width=423,alt="image-20251119-120126.png"! | [23 empty] | 1832856 | AM20-264 | Update ServiceNow Payloads with severity | Done | 2025-11-19 14:02
AM20-271 | Terraform code for route 53 implementation | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Satya Varanasi | Medium | 1835009 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-11-13 10:44 | 2025-11-27 10:24 | 2025-11-27 08:28 |  |  | 0 | [airchefs.co.za¦http://airchefs.co.za] hosted zone need to setup via Terraform. |  | Harsh Chandra | Sanket Kale | Satya Varanasi |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ca1ef33 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mx8b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-25 06:19 | [13 empty] | 25/Nov/25 8:19 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Hosted zone setup is completed on Network account and also validated with internal team. Updated the status as in review and reassign it to Satyasairam. | 27/Nov/25 10:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration done currently all pointing to [airchefs.co.za¦http://airchefs.co.za] is pointing to AWS. | [25 empty] | 1832849 | AM20-262 | Route53 implementation using terraform - Phase 1 | Done | 2025-11-27 10:24
AM20-270 | Airnavx budget update | Done | 2 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834954 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-13 10:16 | 2025-11-27 09:17 | 2025-11-21 08:29 | 2025-11-27 09:17 |  | 0 | I would like to update budget of airnavx as per the revised LLD since the configuration of EC2 were change and budget should reflect the cost accordingly |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;20/Nov/25 8:19 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;36600 | [5 empty] | 28800 | 0 | 36600 | 1.27 | 28800 | 0 | 36600 | [12 empty] | 19/Nov/25 8:44 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251119-064353.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186120 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5ed5a68d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mwyr: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:49 | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:49 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will check the updated LLD document and will update the new pricing as per the updated one. | 19/Nov/25 8:44 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the Updated LLD v1.4 and updated the pricing in the management payers account as per the new LLD. !image-20251119-064353.png¦width=629,alt="image-20251119-064353.png"! same has been implemented in the budget account. | 27/Nov/25 9:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:17
AM20-269 | CloudWatch log analysis for Cost optimization | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834933 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-13 10:12 | 2025-11-28 13:59 | 2025-11-28 13:47 | 2025-11-28 13:59 |  | 0 | As Product owner I like to analyse the Cloudwatch logs and eliminate any duplicate logs to ensure that cost is being charged fairly and take action to reduce the current cost, which is very high at this point of time |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Worked on analysis CloudWatch cost spent on backend dev account to see the detailed spend and identify the sectors with most spent. ;18/Nov/25 8:19 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on identifying cloudwatch components contributing majorly to the CloudWatch costs.;19/Nov/25 8:21 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | ;24/Nov/25 4:49 PM;17cb9418-1850-4923-932b-7098ec51b6bb;7200 | Worked on identifying ingestion in log group to control putLogevents cost;24/Nov/25 4:50 PM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on disabling enhanced monitoring , this will disable scraping pod level metrics to save cost on ObservationUsage.;24/Nov/25 4:51 PM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 |  | 86400 | 0 | 93600 | 1.08 | 86400 | 0 | 93600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cb03268 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mww3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:20 | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:20 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Worked on analysis CloudWatch cost spent on backend dev account to see the detailed spend and identify the sectors with most spent. | 19/Nov/25 8:30 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Enabled CloudTrail to monitor CloudWatch Data Events so that we can track which API is getting used and interacting with CloudWatch. | 24/Nov/25 4:49 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Worked on creating dashboard to identify log ingestion in each log group , updated fluent bit config to send logs only for flysaa backend amadeus and fabric microservices only to CloudWatch, also disabled sending logs to these log groups: # /aws/containerinsights/<eks-dev-cluster>/dataplane # /aws/containerinsights/<eks-dev-cluster>/host # /flysaa/dev/eks Disabled enhanced monitoring for eks cluster to save on ObservationUsage costs. | 28/Nov/25 1:59 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-28 13:59
AM20-268 | Tagging Compliance implementation | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834929 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-13 10:10 | 2025-11-28 11:38 | 2025-11-27 08:26 | 2025-11-28 11:38 |  | 0 | As product owner I would like to setup tagging compliance in centralized Cloudwatch dashboard so that I know how many workloads are not been tagged and take corrective actions accordingly |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;20/Nov/25 8:27 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;21/Nov/25 7:56 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;25/Nov/25 10:41 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;26/Nov/25 3:33 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;27/Nov/25 4:17 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;7200 |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 27/Nov/25 4:17 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251127-141419.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190266 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fa2be84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mwv7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:50 | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:50 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Satya sir is checking with leigh regarding the tag policy enable part after updating the tag policy will start working on the Tag compliance part. | 19/Nov/25 1:33 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have Enabled the Tag Compliance policy for all account. Waiting for security score. | 21/Nov/25 7:55 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Security score is visible for all accounts now next step is we are disabling the ID on with we donâ€™t require this tag compliance policy for all accounts. | 23/Nov/25 2:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have disabled the Tag Compliance policy for all the non required resource IDâ€™s for all 17 mandatory accounts. 746669190453â€ƒâ€ƒFlySAA_CMS_Backend_DevQA 216989128782Â Â Â Â Â Â Â FlySAA_CMS_Backend_PreProd 396608788916â€ƒâ€ƒFlySAA_CMS_Backend_Prod 209479274829â€ƒâ€ƒSAA TM1 345594574792â€ƒâ€ƒSAA AirnavxÂ 536697265099â€ƒâ€ƒSAA_NEXIOAV_PROD 650251698621â€ƒâ€ƒSAA_PROS_PROD 307946680641â€ƒâ€ƒSAA_Informatica_DEV 536697248966â€ƒâ€ƒSAA_Informatica_PROD 195973603339â€ƒâ€ƒvod001_001_payer9 300204747992â€ƒâ€ƒSAA-AuditÂ 730335236533â€ƒâ€ƒAWS_SAA_Security 080284287007â€ƒâ€ƒSAA-LogArchive 339712943527â€ƒâ€ƒAWS_SAA_Network 585768167545Â Â Â Â Â Â Â SharedVPCDevQA() 253490777663Â Â Â Â Â Â Â SharedVPCPreProd() 820242899278Â Â Â Â Â Â Â SharedVPCProd() | 25/Nov/25 10:40 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;For the Untagged one IDâ€™s we are remediating the failed ones as much as we can for all 17 accounts before getting the centralized dashboard enabled for Tag compliance. | 26/Nov/25 9:04 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Tag compliance security score is 95% for all 17 Accounts and to make it 100% we need to Tag IAM Roles for all Accounts and Each account contains more than 60 IAM Roles which is not possible for a Single person to tag them. I need team support to tag those IAM roles as its a manual work no automation will help as they are the existing resources not the new ones. | 26/Nov/25 3:32 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*UPDATE :* With the Help of lambda function we were able to tag all the IAM roles for all 17 accounts. Except the oneâ€™s which are not handled by our team and we are not authorized to tag them. | 27/Nov/25 4:17 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251127-141419.png¦width=629,alt="image-20251127-141419.png"! Tags has been implemented for all resources and in the security account under Security Hub we can see all the tagged resources and the information. | 28/Nov/25 11:38 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. Saw the data presented in review call. satisfied with results | [21 empty] | Done | 2025-11-28 11:38
AM20-267 | Route53 cutover for Airchef | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834911 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-13 10:00 | 2025-11-28 14:01 | 2025-11-28 10:20 | 2025-11-28 14:01 |  | 0 | As product Onwer I like to perform cutover for Route53 for airchef |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;28/Nov/25 10:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 28/Nov/25 10:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ CHG0068339 for Airchef Route 53 cutover .msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190434 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@c54e709 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mws3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_268391979_*¦*_10041_*:*_2_*:*_1029530025_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_2_*:*_268391979_*¦*_10041_*:*_2_*:*_1029530025_*¦*_13940_*:*_1_*:*_0 | 3_*:*_2_*:*_268391979_*¦*_10041_*:*_2_*:*_1029530025_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_268391979_*¦*_10041_*:*_2_*:*_1029530025_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-25 06:03 | 3_*:*_2_*:*_268391979_*¦*_10041_*:*_2_*:*_1029530025_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 25/Nov/25 8:03 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;[airchefs.co.za¦http://airchefs.co.za] hosted zone has been configured, zone file has been imported. for test point of view i have tried to reach new route53 resolvers from my local laptop and the same able to reach. Share NS resolvers to network team towards adding main domain account. NS resolvers: [ns-1087.awsdns-07.org¦http://ns-1087.awsdns-07.org] [ns-918.awsdns-50.net¦http://ns-918.awsdns-50.net] [ns-1948.awsdns-51.co.uk¦http://ns-1948.awsdns-51.co.uk] [ns-496.awsdns-62.com¦http://ns-496.awsdns-62.com] C:\Users\VaranasiS>nslookup Default Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 {quote}{quote} C:\Users\VaranasiS>nslookup [ns-1087.awsdns-07.org¦http://ns-1087.awsdns-07.org] Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: Name: [ns-1087.awsdns-07.org¦http://ns-1087.awsdns-07.org] Addresses: 2600:9000:5304:3f00::1 205.251.196.63 C:\Users\VaranasiS>nslookup [ns-918.awsdns-50.net¦http://ns-918.awsdns-50.net]. Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: Name: [ns-918.awsdns-50.net¦http://ns-918.awsdns-50.net] Addresses: 2600:9000:5303:9600::1 205.251.195.150 C:\Users\VaranasiS>nslookup [ns-1948.awsdns-51.co.uk¦http://ns-1948.awsdns-51.co.uk]. Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: Name: [ns-1948.awsdns-51.co.uk¦http://ns-1948.awsdns-51.co.uk] Addresses: 2600:9000:5307:9c00::1 205.251.199.156 C:\Users\VaranasiS>nslookup [ns-496.awsdns-62.com¦http://ns-496.awsdns-62.com] Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: Name: [ns-496.awsdns-62.com¦http://ns-496.awsdns-62.com] Addresses: 2600:9000:5301:f000::1 205.251.193.240, | 25/Nov/25 9:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change plan has been shared to customer, customer under process of scheduling the change. | 27/Nov/25 10:28 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;CHG0068339 for [Airchefs.co.za¦http://Airchefs.co.za] is pointing to AWS Route 53 and working fine. | 28/Nov/25 10:34 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change implemented and working smoothly since 36 hours. hence i am closing this story.[^RE_ CHG0068339 for Airchef Route 53 cutover .msg] | 28/Nov/25 2:01 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Implementation done for airchef | [25 empty] | Done | 2025-11-28 14:01
AM20-266 | AMOS Follow-up Assessment | Blocked | 4 | None( Backlog) |  |  | Sumit Nikam | Medium | 1833693 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-12 10:56 | 2025-11-28 11:40 | 2025-11-28 11:14 |  |  | 0 | As Product owner I would like to reinitiate assessment for AMOS application so that we can finalize approach to modernize it |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7ed8f0ed | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0009 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-24 06:09 | [13 empty] | 24/Nov/25 8:09 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Still awaiting approval from SAA\Tumelo for migration to AWS. Moving this to blocked state since the assessment canâ€™t be resumed until then. | [29 empty] | To Do | 2025-11-12 10:56
AM20-265 | CMS Backend RDS instance (Pre-prod/Prod) analysis | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1833687 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-12 10:53 | 2025-11-27 09:21 |  | 2025-11-27 09:21 |  | 0 | As Product owner I like to analyse RDS for rightsizing based on utlization to reduce cost |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Nov/25 5:10 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;21600 | ;25/Nov/25 4:08 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;64800 |  |  |  |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 18/Nov/25 5:09 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251118-150648.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1185982 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6460780 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo2n: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 15:10 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 5:09 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;RDS cost analysis is started. Today, we have reduced backup retention period of preprod rds to 7 days from 35 days. Also, storage limit threshold for dev rds is updated to 200 GiB from 110GiB because it was generating alerts â€œ*_Storage size 100 GiB is approaching the maximum storage threshold 110 GiB. Increase the maximum storage threshold_*â€ !image-20251118-150648.png¦width=459,alt="image-20251118-150648.png"! Next we will monitor cpu, memory consumption across three environments | 25/Nov/25 4:15 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;h3. Next Steps for CMS Backend RDS Cost Optimization With discussion with Pankaj, we have identified the following points as next steps for CMS Backend RDS cost optimization: * Turn off non-prod RDS instances when not in use or during off-business hours and turn them back on when required. * Further reduce backup retention period for non-prod RDS instances (currently 7 days) to explore additional cost savings. These actions will be implemented post confirmation from FlySAA team. | 27/Nov/25 9:21 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:21
AM20-264 | Update ServiceNow Payloads with severity | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832856 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-11 14:52 | 2025-11-27 09:16 | 2025-11-25 08:24 | 2025-11-27 09:16 |  | 0 | As Product owner I would like to send severity to ServiceNow as well in the payload so that alerts can be classified based on Critical, High, Medium, Low and the incident can be generated accordingly. Acceptance Criteria: Lamda function to be updated with Severity SNS should be able to send mandatory parameters along with severity to ServiceNow successfully |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 115200 | 57600 | 72000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ed98b6b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo2j: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-19 10:36 | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 19/Nov/25 12:35 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Discussed with Aravind regarding adding severity to payload and tested execution for infra alarms in dev env. | 24/Nov/25 4:42 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Alarms payloads are now configured with severity field, working on updating list of alarms to be sent to ServiceNow. | 27/Nov/25 9:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:16
AM20-263 | Pegasys LLD Creation | To Do | 0 | None( Backlog) |  |  |  | Medium | 1832851 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-11 14:48 | 2025-11-17 08:22 |  |  |  | 0 |  |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@ab71d36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g002 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-11 14:48
AM20-262 | Route53 implementation using terraform - Phase 1 | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832849 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-11 14:46 | 2025-11-28 14:01 | 2025-11-28 10:20 | 2025-11-28 14:01 |  | 0 | As product owner I would like to implement Route53 got both airchef and [Flysaa.com¦http://Flysaa.com] |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;28/Nov/25 10:30 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 28/Nov/25 10:29 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251128-082851.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190433 | 28/Nov/25 10:29 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251128-082914.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190431 | 28/Nov/25 10:29 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251128-082937.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190432 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@709e087b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo0z: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_612662868_*¦*_10041_*:*_1_*:*_840707031_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_612662868_*¦*_10041_*:*_1_*:*_840707031_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_612662868_*¦*_10041_*:*_1_*:*_840707031_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_612662868_*¦*_10041_*:*_1_*:*_840707031_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-21 06:19 | 3_*:*_1_*:*_612662868_*¦*_10041_*:*_1_*:*_840707031_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 21/Nov/25 8:19 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code has been modified and implemented on network account. Zone file also imported. | 28/Nov/25 10:29 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Latest zone file imported, changed TTL values to 300 sec for quick propagation. Saket gave demo on the same. Hence sharing this story Yashwant Thakur. for closer. !image-20251128-082851.png¦width=612,alt="image-20251128-082851.png"! !image-20251128-082914.png¦width=597,alt="image-20251128-082914.png"! !image-20251128-082937.png¦width=597,alt="image-20251128-082937.png"! | 28/Nov/25 2:01 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-28 14:01
AM20-261 | MQ Modernization POC ¦¦ Parser testing based on sample pegasys parser | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832848 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-11-11 14:45 | 2025-11-28 12:00 | 2025-11-28 11:15 | 2025-11-28 12:00 |  | 0 | As DevOps Engineer, I need to test few existing MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6bedb0f1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo0r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:26 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:26 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;CPP to Java: Parser to be re-written with line to line conversion to retain logic. | 20/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Java Parser Covering Following High-level Algorithm- # Input * Receive a raw text message body (rawMessage) from AmazonMQ PEGASYS.OUT.UAT. # Pre-check * If rawMessage is null or empty â†’ return ParseResult with error = true (this is defensive; in normal operation this should not happen). # stripId() â€“ remove ID block if present 3.1. Let msg = rawMessage. 3.2. If msg contains "\nM42": * Call stripId(msg): * Find index of " /ID ". * From there, find "ACARS\r\n". * Return: msg_before_ID + msg_from_ACARS_onwards. 3.3. Else: keep msg unchanged. . # Construct buff and newbuff 4.1. buff = msg (the stripped or original message). 4.2. Append control chars: * CR = 13, NL = 10, ETX = 3. * newbuff = buff + CR + NL + ETX. # Split into lines & find .JNB 5.1. Split newbuff by '\n' into lines[]. 5.2. Search for first line where lines[i].startsWith(".JNB"). 5.3. If found, set counter = i + 1 (line after .JNB). 5.4. If not found or counter >= lines.length: * Default: create OutboundMessage(qMng, newbuff) â†’ MNG only. * Return this as ParseResult with error = false. # Extract relevant lines safely * line0 = lines[counter] (or "" if out of range). * line1 = lines[counter + 1] * line2 = lines[counter + 2] * line3 = lines[counter + 3] Using helpers: * safeLine(lines, index) â€“ returns "" if index out of range. # Extract tokens (T1, T2, etc.) safely Using safeSub(s, begin, endExclusive) to avoid index errors. 7.1. T1 = line0[0..3) â†’ message type (MVT, DIV, ASM, SSM, CGO, etc.). 7.2. T2 = line1[1..5) â†’ secondary code (CIRQ, CICX, etc.). 7.3. line1_0_2 = line1[0..2) â†’ used to check "SA". 7.4. line2_0_2 = line2[0..2) â†’ used to check "ED". 7.5. line3_0_3 = line3[0..3) â†’ used to check "TIM". # Prepare result container * outputs = new ArrayList<OutboundMessage>(); # Rule 1 (SSM/CGO â†’ ICARGO) * If T1 is "SSM" or "CGO": * outputs.add(new OutboundMessage(qIcargo, buff)); 10. Rule 2 (CIRQ/CICX â†’ SIP) * If T2 is "CIRQ" or "CICX": * Add OutboundMessage(qSip, buff) to outputs. * Return ParseResult(outputs, false, null) immediately 11. Rule 3 (MVT / DIV / ASM) 11.1. If T1 in { "MVT", "DIV", "ASM" }: 11.1.1 ASM + TIM * If T1 == "ASM" and line3_0_3 == "TIM": * Add OutboundMessage(qCimp, buff) (CIMP). * Add OutboundMessage(qIcargo, buff) (ICARGO). * Then continue. 11.1.2 MVT-specific * If T1 == "MVT": * If line1_0_2 == "SA" (SA flight): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG with CR/LF/ETX). * Add OutboundMessage(qIcargo, buff) (ICARGO). * If line2_0_2 == "ED": * Add OutboundMessage(qCimp, buff) (CIMP). * Add another OutboundMessage(qIcargo, buff) (ICARGO again â€“ same as C++ double-write). * Else (non-SA): * Add OutboundMessage(qMng, newbuff) (MNG only). 11.1.3 DIV/ASM (fallback) * Else (T1 is DIV or ASM without TIM rule): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG). 12. Rule 4 (other message types) * Else (T1 is not MVT, DIV, ASM, and not CIRQ/CICX): * Add OutboundMessage(qMng, newbuff) (MNG only). 13. Return final result * return new ParseResult(outputs, false, null); | 24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Additional parser related to Pegasys called SbrSplit has been shared by Sampi. Analysis has been started for the same. | 28/Nov/25 11:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SbrSplit parser - CPP has been converted into java based code. Repo structure has also been transformed to adopt microservice alike design. [https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git¦https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git] Parser to be tested in next sprint. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [25 empty] | Done | 2025-11-28 12:00
AM20-259 | IAM roles need to created based on LLD. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Satya Varanasi | Medium | 1832050 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Satya Varanasi | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Satya Varanasi | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 2025-11-11 08:53 | 2025-11-14 08:10 |  |  |  | 0 | IAM roles need to be created. Â·Â Â Â Â Â Â Â IAM-based access with predefined roles: oÂ Â *DNSAdmin*Â â€“ Full Route 53 management. oÂ Â *DNSOperator*Â â€“ Modify records, no zone deletions. oÂ Â *DNSViewer*Â â€“ Read-only access. |  | Faisal Sayed | Satya Varanasi |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 |  |  |  |  | ;12/Nov/25 10:19 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fec0f31 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mkiz: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:41 | [13 empty] | 12/Nov/25 6:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Update* * Permission policies for *DNS Admin*, *DNS Operator*, and *DNS Viewer* have been configured. * These will be implemented in the *Management Account (ID: 195973603339)* after approval from *Staya Sir*. h3. *Next Steps* * Schedule a call with *Staya Sir* to review and obtain approval for policy implementation. * Post-approval, apply the policies in the Management Account and validate access controls. | 12/Nov/25 10:19 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Call has been scheduled and IAM roles have been successfully created. Moving the item to *Staya Sirâ€™s review bucket* and updating the status to *In Review*. | 14/Nov/25 8:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Roles has been created according to LLD on main account. | [24 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-14 08:10
AM20-258 | (Airchef)Terraform Implementation for Creation of Route 53 Hosted Zones & Records. | In Progress |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Sanket Kale | Medium | 1827709 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2025-11-05 12:15 | 2025-11-20 09:07 |  |  |  | 0 | *Acceptance Criteria:* * *Deploy Public Hosted Zone* Use Terraform to provision a *Route 53 public hosted zone* for the domain [*airchef.co.za*¦http://airchef.co.za]. * *Manage DNS Records via Terraform* Implement Terraform configurations to create and manage various DNS record types (A, CNAME, MX, TXT, etc.) within the hosted zone. |  | Faisal Sayed | Sanket Kale | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [20 empty] | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28df5c12 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1vn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-07 05:56 | [13 empty] | 07/Nov/25 7:56 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Code review completed from my side its working. Created and deployed the base and component modules. | 10/Nov/25 9:07 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and tested on Sandbox environment | 14/Nov/25 4:01 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code deployment done sandbox and same tested. | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | In Progress | 2025-11-20 08:59
AM20-257 | (Airchef)Terraform code generation for Route 53 Hosted Zone Creation & Record Migration. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Faisal Sayed | Medium | 1827706 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2025-11-05 12:13 | 2025-11-12 10:17 |  |  |  | 0 | Hosted Zone Creation Develop infrastructure-as-code to provision a Route 53 hosted zone for the specified domain. The configuration should support tagging, environment-specific naming, and be reusable across deployments. DNS Record Management Implement a declarative script to define and manage DNS records within the hosted zone. This should include support for common record types (A, CNAME, MX, TXT) with configurable TTLs and values. |  | Faisal Sayed | Sanket Kale |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e |  |  |  |  | ;12/Nov/25 10:17 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 |  |  |  |  | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@53b50383 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1v7: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:56 | [13 empty] | 07/Nov/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status: Blocked* Awaiting SAA approval for the updated DNS records associated with the {{airchef}} domain. Terraform provisioning is currently on hold until the DNS configuration is finalized. | 12/Nov/25 6:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status Update:* * Task moved from *Blocked* to *In Progress*. * Terraform code for Route 53 provisioning has been developed and handed over to *Sanket*. * *Next Action:* Sanket to review and execute the code in the *sandbox account* for validation. | 12/Nov/25 6:55 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform code has been successfully reviewed and tested in the sandbox environment, and all validations are positive. Â | 12/Nov/25 10:16 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Code has been reviewed, tested successfully, and validated. Moving the sub-story to *Done*. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-12 10:12
AM20-256 | (Airchef)Route 53 Migration & Security Creation. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Satya Varanasi | Medium | 1827698 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2025-11-05 12:10 | 2025-11-14 16:02 |  |  |  | 0 | h3. 1. *Record Migration & Cutover* * All DNS records migrated from the current provider to Route 53 without data loss. * Validation of record accuracy (A, AAAA, CNAME, MX, TXT, SRV, etc.) against the source. * Successful cutover: traffic resolves correctly via Route 53 after TTL expiry. * Rollback plan documented and tested in case of failure. h3. 2. *IAM Roles & Access Control* * IAM roles created with least privilege for Route 53 access. * Granular policies defined (e.g., read-only vs. admin). * Access logging enabled for auditing DNS changes. * Periodic review of IAM roles and policies for compliance. |  | Faisal Sayed | Sanket Kale | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 |  |  |  | ;12/Nov/25 10:24 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;10800 | ;13/Nov/25 9:44 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;7200 | ;13/Nov/25 5:03 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;14400 |  |  |  | 57600 | 25200 | 32400 | 0.56 | 57600 | 25200 | 32400 |  |  |  |  | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@732c0e00 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1tv: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-14 14:03 | [13 empty] | 10/Nov/25 7:09 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status: Blocked* Awaiting SAA approval for the updated DNS records associated with the airchef domain. Terraform provisioning is currently on hold until the DNS configuration is finalized. | 12/Nov/25 7:12 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* * Terraform-deployed Route 53 hosted zone and DNS records have been tested successfully in the *sandbox account* using IAM roles created for the test. * Access validation is complete and confirmed. * *Local DNS testing* will be tested today. * Post successful DNS validation, the sub-story will move to *Review*, and upon approval, transition to *Done*. | 13/Nov/25 4:59 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Update:* After creating the hosted zone and importing DNS records, local testing returned positive results. To validate further, the following steps were performed: h4. *Environment Setup* * *Launched 2 EC2 Instances* ({{t4g.micro}} in {{af-south-1}}): ** *Instance A:* DNS Client ** *Instance B:* DNS Forwarder ({{IP: 10.43.1.6}}) h4. *Security Group Configuration* * *SSH Access:* Port 22 * *DNS Communication:* Ports 53 (UDP/TCP) between instances * *ICMP:* Enabled for connectivity testing h4. *DNS Forwarder Configuration (Instance B)* * Installed *dnsmasq* as DNS caching/forwarding service * Configured forwarding to Route 53 nameservers: ** {{ns-1367.awsdns-42.org}} ** {{ns-74.awsdns-09.com}} ** {{ns-886.awsdns-46.net}} ** {{ns-1772.awsdns-29.co.uk}} * Enabled DNS caching (1000 entries) * Enabled query logging h4. *DNS Client Configuration (Instance A)* * Installed *bind-utils* ({{dig}}, {{nslookup}}) * Configured to query via Instance B h4. *Custom DNS Resolution Path* {noformat}Internet â†’ Instance A â†’ Instance B (dnsmasq) â†’ Route 53 â†’ Response{noformat} | 13/Nov/25 5:02 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status Transition:* Iâ€™m moving this item to the â€œ*In Review*â€ status under *Satya Sirâ€™s* bucket. Once itâ€™s approved, Iâ€™ll transition it to the â€œ*Pending PO Approval*â€ status in *Yashwantâ€™s bucket*. | 14/Nov/25 4:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Tested on sand box and working fine. | [22 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-14 16:02
AM20-255 | Create Hosted Zone via Terraform | Done | 8 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824841 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-31 15:16 | 2025-11-15 14:39 |  | 2025-11-15 14:39 |  | 0 | As a Cloud Platform Engineer I want a Terraform module that creates a Route 53 Hosted Zone (Public or Private) so that teams can provision DNS consistently across accounts and environments. *Scope* * Supports Public and Private hosted zones. * For Private zones: supports single and cross-account VPC associations. * Optional DNSSEC for Public zones (toggle). * Standardized tags, outputs, and README. *Acceptance Criteria (Functional)* # *Zone Type & Creation* Â Given zone_type âˆˆ {public, private} When I run terraform apply Then an AWS Route 53 hosted zone is created with the provided name ([Airchef.co.za¦https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2Fcorp.example.com%2F&data=05%7C02%7Cyashwant.thakur02%40vodafone.com%7Ce00faab9b43b48d8658008de187b13e5%7C68283f3b84874c86adb3a5228f18b893%7C0%7C0%7C638975114066746666%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=c7zVCLwqZ0TyO4ZgLXI7nmQwcYQASdX%2Bd%2BoDRecN0Gw%3D&reserved=0] and [flysaa.com¦http://flysaa.com] ) in the Network account/workspace. # *Public Hosted Zone Outputs* Â Given a Public zone When apply completes Then module outputs include: zone_id, zone_arn, name_servers (list), soa_record (string), and zone_name.Â # *Private Hosted Zone VPC Associations* (Same Account) Given zone_type = private and a list of VPC IDs in the same account When apply completes Then the zone is associated with all listed VPCs and associated_vpc_ids are output.Â # *Private Hosted Zone Cross-Account Associations* Given zone_type = private, a target zone account, and VPCs in other accounts When apply completes Then: VPC association authorization is created in the zoneâ€™s account. Zone associations are established from each workload account (using provider aliases). Associations are idempotent and re-applies do not error.Â # *DNSSEC (Optional, Public Only)* Â Given enable_dnssec = true and a valid KMS key alias/ARN When apply completes Then DNSSEC signing is enabled for the zone, and outputs include dnssec_status and ds_record (for registrar).Â # *Tagging Standard* Â Given tags map When resources are created Then all supported resources include tags: Environment, Owner, CostCenter, ManagedBy = terraform.Â # *Naming & Validation* Â Given invalid domain names (trailing dot, uppercase, spaces) When plan runs Then validation fails with a clear error message before creating resources. |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@c68852a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lps3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 19:11 | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 31/Oct/25 3:21 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Hi [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] , Please review this user story, I created this based on your LLD instruction. Please check if acceptance criteria needs alteration and make changes | 10/Nov/25 9:11 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and deployed on Sandbox environment | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-15 14:39
AM20-254 | Import & Manage DNS Records via Terraform | Done | 8 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824829 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-31 15:09 | 2025-11-15 14:39 |  | 2025-11-15 14:39 |  | 0 | As a Cloud Platform Engineer I want Terraform code that models existing Route 53 records (and creates new ones) using aws_route53_record so that all DNS changes are version-controlled, peer-reviewed, and reproducible. *In Scope* * Â Public & private hosted zones (given zone_id) * Â Record types: A/AAAA, CNAME, TXT, MX, SRV, NS (delegations), PTR, and Alias (ALB/NLB/CloudFront/S3) * Â Routing policies: Simple, Weighted, Latency, Failover, Multi-Value * Â Health checks (referenced by record) * Â Import of existing records into state (terraform import) with code generation scaffolding * Â Bulk records via for_each maps Acceptance Criteria: # *Module Interface* Given a module input records (map of objects) and zone_id When I apply the module Then it renders one aws_route53_record per map item with correct name, type, ttl/alias, routing policy, and (optional) health check. # *Create New Records* Â Given a new item in records ( [Airchefs.co.za¦http://Airchefs.co.za] â†’ A â†’ ALB alias) *OR* ([flysaa.com¦http://flysaa.com] â†’ A â†’ ALB alias) When I run terraform apply Then the record is created and resolves via dig/nslookup with the expected value and TTL. # *Import Existing Records (Single)* Â Given an existing record set in the hosted zone Â When I run terraform import 'module.dns.aws_route53_record.this["[api.¦https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2Fapi.dev.example.com%2F&data=05%7C02%7Cyashwant.thakur02%40vodafone.com%7C17d1c2e405554efe772908de187c51d4%7C68283f3b84874c86adb3a5228f18b893%7C0%7C0%7C638975119406199329%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=oRvm%2FU%2BWpaEnyS1rnSXR%2FX7cSrnvEtIDK2FabJQqYiY%3D&reserved=0][Airchefs.co.za¦http://Airchefs.co.za] â†’ A â†’ ALB alias)¦A¦simple"]' '<zone_id>_<fqdn>_<type>' *OR* Â When I run terraform import 'module.dns.aws_route53_record.this["[flysaa.com¦http://flysaa.com] â†’ A â†’ ALB alias)¦A¦simple"]' '<zone_id>_<fqdn>_<type>' Â Then the resource is tracked in state and a subsequent plan is a no-op (no drift), provided the HCL matches.Â # *Import Existing Records (Bulk)* Â Given a CSV/JSON export of Route 53 record sets Â When I use the supplied mapping template to populate records and run the generated terraform import commands Â Then all imported records show as no changes on plan.Â # *Routing Policies* Â Weighted: Given two records with the same name/type and different set_identifier & weight When applied Then both weighted records are present and traffic splits per weight. Â Latency/Failover/Multi-Value: Similar acceptance via identifiers/actions; health checks wired for Failover and Multi-Value.Â # *TXT & Special Cases* Â Given a TXT record requiring quotes/escaping (SPF/Google site-verification) Â When applied Â Then the exact string appears in DNS (including spaces/quotes) and validation passes.Â # *Alias Targets* Â Given alias to ALB/NLB/CloudFront/S3 Website Â When applied Â Then target name and zone_id are set correctly and record resolves (no TTL required).Â # *Private Zones* Â Given zone_id for a private hosted zone Â When I create/import records Â Then theyâ€™re only resolvable from associated VPCs.Â # *Guardrails* Â Given prevent_destroy = true at module level (lifecycle) Â When a record is removed from input Â Then destroy is blocked with a clear message unless allow_destroy=true. |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4668ef43 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lps7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_343117453_*¦*_10041_*:*_1_*:*_885693461_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_343117453_*¦*_10041_*:*_1_*:*_885693461_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_343117453_*¦*_10041_*:*_1_*:*_885693461_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_343117453_*¦*_10041_*:*_1_*:*_885693461_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 19:11 | 10060_*:*_1_*:*_343117453_*¦*_10041_*:*_1_*:*_885693461_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 31/Oct/25 3:20 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Hi [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] , Please review this user story, I created this based on your LLD instruction. Please check if acceptance criteria needs alteration and make changes | 10/Nov/25 9:11 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and deployed on Sandbox environment | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-15 14:39
AM20-253 | SMS Alerting implementation- Opt in/Opt out | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-10-31 12:11 | 2025-11-15 14:38 |  | 2025-11-15 14:38 |  | 0 | As a cloud product owner I want application and platform alerts to be delivered via SMS from a dedicated long code so that on call engineers and stakeholders receive time critical notifications Acceptance criteria: *Long code configured and verified* - given the approved long code when I set SNS and SMS preferences then the long code is used as the origination identity for the supported countries and unsupported routes use the configured Sender ID feedback *E2E SMS on P1/P2* - Given the cloudWatch alarm changes to ALARM with severity ðŸ˜›1 when the alarm event is routed via EventBridge to the SNS topic than all active on-call receipients for the app+env recieve an SMS within 60s and message body includes app, env, alarm name, severity, runbook link and ACK instruction ¦¦*Severity*¦¦*objective signals*¦¦*examples*¦¦ ¦P1 - Critical, user impact¦harsh outage, data loss, security incdences¦API 5xx>10% 5m in production, RDS storage<5% 10m. certificate expiry < 3days, guard duty, unauthrized access¦ ¦P2 - Degradation,Urgent¦performance, throughput, redundancy lost,¦EKS node group<N healthy, ALB healthy, RDS IOPS deviation, CPU utilization, disk innode,¦ ¦P3 - Action soon¦Capacity/Ops issues, repeated flaps¦log patterns,¦ ¦P4 - Informational¦chnages , warnings, failures without user impact¦Daily back ok, lamda changes, deloyment success¦ *Delivery logging and metrics* - Given SMS messages are sent when carriers return delivery statuses then statuses are captured in CloudWatch logs and S3 and dashboards show sends, successes, failures, per country breakdown *Retry and escalations ( in the event of SMS failure)* - Given a send gets a transient failure when the system retries with backoff( up to 3 times in 5 minutes) then on persistent failure an escalation SMS is triggered to secondary contacts and a ticket is created in ServiceNow with failure details *Deduplication and storm control* - Given multiple identical alarms fire within 5 minutes when routing occurs then recipients receive at most one SMS per unique alarm/signature per 5 minute window and a summary SMS is sent after 15 minutes if >5 deduped alerts occurred. *Opt-out/Opt-in* - Given a recipient replied STOP when routing future SMS to that number then messages are surpassed and audit shows timestamp and actor and START re-enables *Cost Guardrails* - Given a monthly SMS budget when SNS spend reaches 80% then P2 alert is sent to Ops and at 100% sends are rate limited to P1 only until an override flag is set *Cross account publish* - Given alarms originate in child accounts when Event Bridge forwards to central account Then publishing to the central SNS topic succeeds via resources based and IAM roles |  | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Working on exploring the ways to implement cost guardrail for lambda. Exploring enabling cloudwatch metric to track the money spent on SMS sent through the account.;10/Nov/25 8:37 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on understanding how cost is shown in billing in case of SMS sent through SNS or SMS sent using End User Messaging.;11/Nov/25 3:39 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on updating lambda to get cross account cost metric to implement 80% cost guardrail to send notification only in case of P1 and P2 alarms when 80% threshold is breached.;11/Nov/25 3:40 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). Trying the opt-out mechanism for SA number(carrier blocking was cited as one of the issues behind blocking) and parallely raised a request to understand the issue.;13/Nov/25 8:04 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Deployed changes on production cluster.;14/Nov/25 8:18 AM;17cb9418-1850-4923-932b-7098ec51b6bb;14400 |  | 57600 | 0 | 129600 | 2.25 | 57600 | 0 | 129600 | [10 empty] | AM20-176 | [19 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3955b400 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h707: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:34 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Working on implementing cost guardrails to restrict sms sending to only P1 and P2 messages when 80% limit is utilised. | 11/Nov/25 8:25 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Will be testing using cost explorer API to fetch billing cost of SNS during Lambda execution. As per AWS docs, if we are using SNS for sending SMS then the metrics wonâ€™t get reflected on CloudWatch metrics. For opt-in/opt-out as per docs, user can send the STOP message to stop getting message. Need to try this part on our end. | 12/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Updated lambda to fetch amount spent on SMS sent using cost explorer API, currently able to fetch cross account. Working on updating Lambda to avoid duplication using DynamoDB. Testing in progress. | 13/Nov/25 8:02 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Able to fetch cost of sending SMS using API, able to avoid deduplication of alarms with the help of DynamoDB table. Currently Working on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). | 14/Nov/25 8:19 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed changes on production account. | 15/Nov/25 2:38 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-15 14:38
AM20-252 | Connectivity via Lamda and registering the account under patching management | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824389 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-31 10:13 | 2025-11-14 11:12 |  | 2025-11-14 11:12 |  | 0 | Connectivity via Lamda for Patching and Register Informatica Dev & Prod environment and AirNavx Prod via security account so that Patching activites can be carried out in these accounts |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Nov/25 2:43 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5dd220d9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_419736642_*¦*_10041_*:*_1_*:*_115097831_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_419736642_*¦*_10041_*:*_1_*:*_115097831_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_419736642_*¦*_10041_*:*_1_*:*_115097831_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_419736642_*¦*_10041_*:*_1_*:*_115097831_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-01 16:21 | 3_*:*_1_*:*_419736642_*¦*_10041_*:*_1_*:*_115097831_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 01/Nov/25 6:20 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Infra level pre-requisites has been completed for the accounts to be registered under Patching Solution. IAM Roles. IAM Policies. Instance Profiles. Instance Tagging. Lambda Functions. S3 Permission Policies. S3 Folder Structure. And inter-instance level requisites like AWS CLI installation compliance reporting scripts is achieved for the migrated instances. | 14/Nov/25 11:12 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-11-14 11:12
AM20-251 | Extend Codepipeline modules for bitbucket and custom stages - POC over sandbox | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1824325 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-31 09:46 | 2026-01-06 08:25 | 2026-01-08 08:39 |  |  | 0 | *Description:* Enhance existing CodePipeline Terraform modules to support Bitbucket as a source and allow configurable custom stages for improved flexibility and reuse. *Acceptance Criteria:* * Bitbucket source integration added and configurable via variables. * Custom pipeline stages supported through module inputs. * Existing Bitbucket pipelines remain unaffected. * Validation done for both GitHub and Bitbucket pipelines. | [19 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6747613f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptvb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | In Progress | 2026-01-06 08:25
AM20-250 | Cabin Crew App discovery | Done | 6 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1823348 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-30 10:30 | 2025-11-14 11:10 |  | 2025-11-14 11:10 |  | 0 | As Product and Application Architect I would like to analyse the Cabin crew application so that I can suggest the best possible way to modernize and migrate to AWS. Acceptance Criteria: * Application Overview and business context is captured ( Business criticality, use case, compliance and security needs, Pain point) * Current Architecture assessment ( Front end stack, Backend, integration, dabtabase, storage and compute requirements and assess modernize angles * Security and Governance - IAM and RBAC model, secret and configuration storage, certificate management, logging and audit requirements * Performance and Capacity utilization - CPU, memory and disk usage, scalability needs, Latency and throughput requirements are gathered * Dependency and integration landscape captured * Cost and Licensing requirements clarified (current cost of application, licenses etc.) * Modernization readiness documented * Modernization strategy proposed successfully * Operational readiness documented |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:19 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | [5 empty] | 86400 | 64800 | 21600 | 0.25 | 86400 | 64800 | 21600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@36e1c984 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ljtn: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 12:35 | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 2:35 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Cabin Crew is still under discussion and more clarity is expected by Dec-25(Project in pipeline) | 14/Nov/25 8:18 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;We have gathered all the information we could but since SAA is still working to understand business scope, we will close this story with current progress and have separate assessment story in future once we have complete information. | 14/Nov/25 11:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-14 11:10
AM20-249 | Miscellaneous Cluster discovery | Done | 6 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1823345 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-30 10:29 | 2025-11-14 11:13 |  | 2025-11-14 11:13 |  | 0 | As Product and Application Architect I would like to analyse the Cabin crew application so that I can suggest the best possible way to modernize and migrate to AWS. Acceptance Criteria: * Application Overview and business context is captured ( Business criticality, use case, compliance and security needs, Pain point) * Current Architecture assessment ( Front end stack, Backend, integration, dabtabase, storage and compute requirements and assess modernize angles * Security and Governance - IAM and RBAC model, secret and configuration storage, certificate management, logging and audit requirements * Performance and Capacity utilization - CPU, memory and disk usage, scalability needs, Latency and throughput requirements are gathered * Dependency and integration landscape captured * Cost and Licensing requirements clarified (current cost of application, licenses etc.) * Modernization readiness documented * Modernization strategy proposed successfully * Operational readiness documented |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Had workshop with Gayaz and Donald to understand the requirements.;14/Nov/25 8:14 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | Analyzed requirements further.;14/Nov/25 8:15 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Prepared SOW draft;14/Nov/25 8:15 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | Amended SOW as per inputs from internal review and shared with Gayaz.;14/Nov/25 8:16 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 |  |  | 86400 | 7200 | 79200 | 0.91 | 86400 | 7200 | 79200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@27e6cfb4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ljt7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 12:29 | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 2:29 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;# New version of Lounge Tracker application has been under development which consists of a Frontend and a backend microservice component. The backend component will be connecting with 3rd party interfaces like (Discovery Bank, DragonPass etc.) for validations. The ask is to deploy a 'Miscellaneous' cluster which would be capable of hosting diverse set of application microservices with ease. # Focus needs to be on reliability, scalability, and security along with ease of use for this new cluster. # Following two additional projects are in pipeline and business discussions are underway: ## Middleware (Java based microservice which will act as a layer between Amadeus. More clarity is expected by Dec-25) ## Cabin Crew (Project in pipeline) # Â Separate workshops and solutioning will be done for this once business alignment is completed and requirements are finalized. # *Action* â€“ VOIS to share the updated scope of work document for the miscellaneous cluster and related deployments for Gayazâ€™s sign off. | 10/Nov/25 8:16 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Draft SOW document has been prepared. To be reviewed internally. | 13/Nov/25 8:14 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SOW document has been reviewed internally and shared with Gayaz and Vodacom both. | 14/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Followed up with Donald to confirm if there is any new update regarding requirements. There is none. We have already shared an SOW based on current understanding. Activity is completed for now. | 14/Nov/25 11:13 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-14 11:13
AM20-248 | Migration of FLYSAA DNS Zones to AWS Route53 | To Do | 6 | None( Backlog) |  |  | Satya Varanasi | Medium | 1822276 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-29 10:50 | 2025-11-14 15:44 |  |  |  | 0 | As a cloud infrastructure Architect I want to migrate existing DNS zones from FLYSAA to AWS Route 53 so thar DNS management can be centralized with AWS, ensuring stability, availability and integration with other AWS services Acceptance Criteria: DNS Zone Discovery and Assessment * Existing FLYSAA DNS zones are inventoried and validated for record types (A, AAAA, CNAME, MA,TXT, SRV, NS, SOA, PTR etc.) * Dependencies on on-prem or third party systems are identified * Zone delegation hierarchy and authoritative name servers are documented * TTL Values and routing policies (simple, Weighted, latency, failover etc.) are reviewed for compatibility with Route53 Route 53 hosted Zone creation * Corresponding public/private hosted zones are created in Route 53 with identical zone names * Correct VPC associations are configured for private zones in the appropriate AWS accounts (dev, pre-prod and prod) * Hosted zones are tagged appropriately * Record Migration and Validation Record Migration and Validation * All DNS record from FLYSAA are migrated to Route 53 with matching values * Route 53 health checks and routing policies are configured as per existing logic * Random sample validation (at least 10%) of DNS resolution from client endpoints confirm accuracy * Validations confirm parity between source and target DNS records Cutover and Delegations * NS records in parent zones are updated to point to Route53 name servers * Change propagation and DNS TTL impact are communicated and managed * Post-cutover validation confirms DNS resolutions is working correctly from internal and external networks * A rollback plan is documented and tested before cutover Security, Audit and logging * Route53 DNS query logging is enabled to CloudWatch or S3 * Access to hosted zones is restricted using IAM roles and policies * GuardDuty and config rules validate DNS configuration integrity * Audit report is generated post migration with DNS record counts and comparison results Monitoring and Alerting * CloudWatch alarms are configured for health checks and DNS failure * SNS topics notify the platform operations team on failure or health check degradation * Dashboards display query metrics and latency per hosted zone Document * Update DNS architecture diagram reflects Route53 integration * SOPs for future DNS change requests are published in the knowledge base * Migration validation report is approved by the business |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [11 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5a13873 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g004 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-10-29 10:50
AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 10 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1822269 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-29 10:50 | 2025-11-16 07:22 |  | 2025-11-16 07:22 |  | 0 | As a cloud infrastructure Architect I want to migrate existing DNS zones from Airchef to AWS Route 53 so thar DNS management can be centralized with AWS, ensuring stability, availability and integration with other AWS services Acceptance Criteria: DNS Zone Discovery and Assessment * Existing Airchef DNS zones are inventorized and validated for record types (A, AAAA, CNAME, MA,TXT, SRV, NS, SOA, PTR etc.) * Dependencies on on-prem or third party systems are identified * Zone delegation hierarchy and authoritative name servers are documented * TTL Values and routing policies (simple, Weighted, latency, failover etc.) are reviewed for compatibility with Route53 Route 53 hosted Zone creation * Corresponding public/private hosted zones are created in Route 53 with identical zone names * Correct VPC associations are configured for private zones in the appropriate AWS accounts (dev, pre-prod and prod) * Hosted zones are tagged appropriately * Record Migration and Validation Record Migration and Validation * All DNS record from Airchef are migrated to Route 53 with matching values * Route 53 health checks and routing policies are configured as per existing logic * Random sample validation (at least 10%) of DNS resolution from client endpoints confirm accuracy * Validations confirm parity between source and target DNS records Cutover and Delegations * NS records in parent zones are updated to point to Route53 name servers * Change propagation and DNS TTL impact are communicated and managed * Post-cutover validation confirms DNS resolutions is working correctly from internal and external networks * A rollback plan is documented and tested before cutover Security, Audit and logging * Route53 DNS query logging is enabled to CloudWatch or S3 * Access to hosted zones is restricted using IAM roles and policies * GuardDuty and config rules validate DNS configuration integrity * Audit report is generated post migration with DNS record counts and comparison results Monitoring and Alerting * CloudWatch alarms are configured for health checks and DNS failure * SNS topics notify the platform operations team on failure or health check degradation * Dashboards display query metrics and latency per hosted zone Document * Update DNS architecture diagram reflects Route53 integration * SOPs for future DNS change requests are published in the knowledge base * Migration validation report is approved by the business |  | Faisal Sayed | Harsh Chandra | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [9 empty] | 144000 | 144000 |  | 0 | 288000 | 169200 | 118800 |  | AM20-256 | AM20-257 | AM20-258 | [26 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1dcc83d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lf57: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_791182150_*¦*_10041_*:*_1_*:*_610041350_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_791182150_*¦*_10041_*:*_1_*:*_610041350_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_791182150_*¦*_10041_*:*_1_*:*_610041350_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_791182150_*¦*_10041_*:*_1_*:*_610041350_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-03 14:25 | 3_*:*_1_*:*_791182150_*¦*_10041_*:*_1_*:*_610041350_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 03/Nov/25 4:24 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Need certain details from [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] in order to design terraform code. *Current Environment Information:* * List of existing DNS zones in Airchef (zone names and domains) * Current DNS record inventory (types, values, TTLs for each zone) * Existing routing policies and health check configurations in Airchef * Current authoritative name servers and delegation hierarchy * Any dependencies on on-premises or third-party systems *AWS Environment Details:* * Target AWS accounts (dev, pre-prod, prod) and their account IDs * Existing IAM roles/policies that should have DNS management access *Migration Specifics:* * Which zones are public vs private hosted zones * Preferred TTL values if different from current settings * Health check endpoints and criteria for monitoring * Rollback timeline requirements and maintenance windows * Sample domains/records you'd like me to prioritize for the 10% validation *Monitoring and Security:* * Dashboard metric preferences. | 05/Nov/25 3:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Initial DOC has been reviewed and communicated requirements to Sanket and Faisal. According to requirement we need to go with Public Domain. Currently initial code ready and now we are waiting for LLD review accordingly we will move further. Mean while we are creating IAM role for DNS management and support. | 11/Nov/25 8:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;IAM roles need to be created according to LLD. Â·Â Â Â Â Â Â Â IAM-based access with predefined roles: oÂ Â *DNSAdmin*Â â€“ Full Route 53 management. oÂ Â *DNSOperator*Â â€“ Modify records, no zone deletions. oÂ Â *DNSViewer*Â â€“ Read-only access. | 14/Nov/25 4:04 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code executed and tested on sand box and demo has been given. Hence i am closing the this story. | 16/Nov/25 7:21 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Closing this as demo was provided. | [25 empty] | Done | 2025-11-16 07:22
AM20-246 | Tag Validations for AirNavX | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820186 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-28 09:01 | 2025-11-14 10:58 |  | 2025-11-14 10:58 |  | 0 | As a Cloud governance engineer I want to validate that all resources and workloads related to newly migrated applications have the correct mandatory tags applied so that we can ensure accurate cost allocation, compliance reporting and automation alignment across all AirNavX account Acceptance Criteria: * Tags for all applicable application resource type ( EC2, EBS, RDS, S3 lamda, ALB/NLB, Cloudwatch log groups) are successfully captured. * If there are any tags not available then manually updated successfully * Validations runs across all migrated resources and as per agreed format |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:33 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;246000 | [5 empty] | 28800 | 0 | 246000 | 8.54 | 28800 | 0 | 246000 | [12 empty] | 13/Nov/25 9:26 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-072628.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182486 | 13/Nov/25 12:08 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-100724.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182794 | 13/Nov/25 12:08 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-100827.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182795 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ffcb69e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l62j: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-06 06:25 | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 06/Nov/25 8:25 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will Start checking all the tags are in place for AirnavX environment and will update them. | 06/Nov/25 9:35 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;AirnavX code build & code piplines & s3 proper taggings are missing. | 12/Nov/25 2:23 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Followed up with satyabrata he is occupied with some tasks and will connect with me tomorrow for this US. | 13/Nov/25 9:26 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251113-072628.png¦width=631,alt="image-20251113-072628.png"! S3 tagging has been updated by AWS CLI command. Now checking for code build and pipline. | 13/Nov/25 12:08 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251113-100724.png¦width=714,alt="image-20251113-100724.png"! Evidence for code pipline and code build updated tags. !image-20251113-100827.png¦width=695,alt="image-20251113-100827.png"! | 14/Nov/25 10:58 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-14 10:58
AM20-245 | Tag Validations for Informatica | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820185 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-28 09:00 | 2025-11-14 08:34 |  | 2025-11-12 08:22 |  | 0 | As a Cloud governance engineer I want to validate that all resources and workloads related to newly migrated applications have the correct mandatory tags applied so that we can ensure accurate cost allocation, compliance reporting and automation alignment across all Informatica account Acceptance Criteria: * Tags for all applicable application resource type ( EC2, EBS, RDS, S3 lamda, ALB/NLB, Cloudwatch log groups) are successfully captured. * If there are any tags not available then manually updated successfully * Validations runs across all migrated resources and as per agreed format |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:34 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;209400 | [5 empty] | 28800 | 0 | 209400 | 7.27 | 28800 | 0 | 209400 | [12 empty] | 07/Nov/25 9:09 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251107-070856.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1179412 | 07/Nov/25 9:09 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251107-070933.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1179416 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@196a21d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l62b: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 11:53 | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 1:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started verifying the tags are being applied on all resources for both Informatica Dev and Prod environment. | 05/Nov/25 4:19 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have updated all mandatory tags for all Informatica Dev & Prod Environment. | 07/Nov/25 9:09 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251107-070856.png¦width=629,alt="image-20251107-070856.png"! | 07/Nov/25 9:09 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251107-070933.png¦width=629,alt="image-20251107-070933.png"! | 12/Nov/25 8:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-12 08:22
AM20-244 | Tag Validations for PROS | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820182 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-28 09:00 | 2025-11-14 11:11 |  | 2025-11-14 11:11 |  | 0 | As a Cloud governance engineer I want to validate that all resources and workloads related to newly migrated applications have the correct mandatory tags applied so that we can ensure accurate cost allocation, compliance reporting and automation alignment across all PROS account Acceptance Criteria: * Tags for all applicable application resource type ( EC2, EBS, RDS, S3 lamda, ALB/NLB, Cloudwatch log groups) are successfully captured. * If there are any tags not available then manually updated successfully * Validations runs across all migrated resources and as per agreed format |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:32 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;216600 | [5 empty] | 57600 | 0 | 216600 | 3.76 | 57600 | 0 | 216600 | [12 empty] | 07/Nov/25 9:07 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251107-070750.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1179411 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4310b374 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l61v: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_146887020_*¦*_10041_*:*_1_*:*_717589963_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_146887020_*¦*_10041_*:*_1_*:*_717589963_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_146887020_*¦*_10041_*:*_1_*:*_717589963_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_146887020_*¦*_10041_*:*_1_*:*_717589963_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 14:21 | 3_*:*_1_*:*_146887020_*¦*_10041_*:*_1_*:*_717589963_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 4:20 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will Start checking all the tags are in place for PROS environment and will update them. | 06/Nov/25 11:35 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;All mandatory tags are being updated for PROS environment including Cloud watch Alarms. | 07/Nov/25 9:07 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251107-070750.png¦width=629,alt="image-20251107-070750.png"! | 14/Nov/25 11:11 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-14 11:11
AM20-243 | Centralized Utilization CloudWatch Dashboard | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820131 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-28 08:37 | 2025-11-14 10:59 |  | 2025-11-14 10:59 |  | 0 | As a cloud finops engineer I want to view utilization metrics of all workloads across all child accounts in one place so that I can identify performance inefficiencies and optimize cost Acceptance Criteria: CloudWatch cross account observability is enabled between Parent and child accounts CloudWatch Dashboards show metrics from EC2, RDS,EKS,S3 and Lamda for each environment Metrics are visualized per account, environment and service * CPU utilization (EC2) * Disk Performance (EC2) * NetworkIn NetworkOut (EC2) * Memory utilization (RDS) * IO performance (RDS) * Storage usage (S3) * Error Rate (S3) * Invocation health (Lamda) * Traffic (ALB/NLB) * Availability - Helthyhostcount (ALB/NLB) * Account utilization score (Cross Account) * Tag compliance (Cross account) CloudWatch Dashboard auto refreshes daily and supports drill down views |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | create the dashboard for all cross accounts.;14/Nov/25 8:29 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;275400 | [5 empty] | 57600 | 57600 | 275400 | 4.78 | 57600 | 57600 | 275400 | [12 empty] | 12/Nov/25 2:00 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251112-115953.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182044 | 12/Nov/25 2:01 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251112-120058.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182047 | 13/Nov/25 12:11 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-101129.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182802 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5149805 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l5u3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-07 06:59 | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 07/Nov/25 8:59 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start working on this US whatever resources are created we will create and update the custom metric as per accounts and will try to create the Cloudwatch dashboard and alerts accordingly. | 12/Nov/25 1:59 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created the dashboard for all cross accounts on the *SAA_Audit* account. Dashboard Name : *Central Dashboard* This Dashboards show metrics from EC2, RDS,EKS,S3 and Lamda for each environment. | 12/Nov/25 2:00 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251112-115953.png¦width=714,alt="image-20251112-115953.png"! Screenshot has been attached as an evidence that the Dashboard has been created. | 12/Nov/25 2:01 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251112-120058.png¦width=714,alt="image-20251112-120058.png"! | 12/Nov/25 4:09 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Now checking for the tag compliance policy. | 13/Nov/25 12:11 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;For Cross account utilization score we have Dashboard in Payer Account which is out organization management account. We can see all account wise score , costing as well as percentage. !image-20251113-101129.png¦width=714,alt="image-20251113-101129.png"! | 14/Nov/25 8:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Tag Compliance remained pending due to some tag policy disable issue. Will taking this in next sprint. | 14/Nov/25 10:56 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;As discussed in the Sprint review call we will have to get in touch with leigh for his approval for enabling the Tag policy for the Cross account thatâ€™s why this Tag compliance part we are taking in next sprint. | 14/Nov/25 10:59 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | Done | 2025-11-14 10:59
AM20-242 | flysaa Backend - Application alerting | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820107 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-28 08:09 | 2025-11-14 11:07 |  | 2025-11-14 11:07 |  | 0 | As devops expert I would like to configure application error from workloads running on our EKS cluster to be collected, classified and alerted via cloudwatch so that appropriate alert is passed to Servicenow via SNS/lamda function or Event bridge. Acceptance Criteria: * All the application specific errors are captured for alerting successfully * The alerts are being sent to ServiceNow with agreed format |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Deployed error Alarms to backend production account for fabric and amadeus.;14/Nov/25 8:17 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fd7ba2e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07d | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:39 | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Had a Discussion with Yashwant, will be reaching out to Hoosen for creating a request to deploy alarms to production. | 11/Nov/25 8:26 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Hoosen has created a change request for deploying the alarms, will be working on it when we get the timeslot allocated to deploy in production since we are not deploying alarms on backend dev and preprod. | 14/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed alarms on Production EKS Cluster. | 14/Nov/25 11:07 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-14 11:07
AM20-234 | Other resources remediation - Config, GuardDuty, EC2, RDS and etc | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818710 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-10-27 08:32 | 2025-10-28 11:23 |  |  |  | 0 | Remediate dependencies services. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ff5f38c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzxn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have remediated dependencies services failed controls | [26 empty] | 1817984 | AM20-225 | Security controls remediation - Informatica and PROS Aws accounts | Done | 2025-10-28 11:21
AM20-233 | IAM users and groups remediation | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818707 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-10-27 08:31 | 2025-10-28 11:22 |  |  |  | 0 | Delete unwanted IAM users from the accounts. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [11 empty] | 10944 | 10944 |  | 0 | 10944 | 10944 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7ac1b938 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzx7: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 11:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have deleted migration user used during migration with programmatic keys. | [26 empty] | 1817984 | AM20-225 | Security controls remediation - Informatica and PROS Aws accounts | Done | 2025-10-28 11:21
AM20-232 | Security group and NACL rules remediation | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818704 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-10-27 08:30 | 2025-10-28 11:20 |  |  |  | 0 | Should restrict port 22, 3389, 1433, 3306 from all traffic 0.0.0.0/0 across all the AWS accounts. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [11 empty] | 17856 | 17856 |  | 0 | 17856 | 17856 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3bed953e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzwr: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 11:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SG inbound rules are updated to restrict port to allow all traffic 0.0.0.0/0 | [26 empty] | 1817984 | AM20-225 | Security controls remediation - Informatica and PROS Aws accounts | Done | 2025-10-28 11:20
AM20-231 | Resources inventory | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Diksha Koul | Medium | 1818700 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-10-27 08:28 | 2025-11-02 19:49 |  |  |  | 0 | Get the resource inventory for the below accounts: * 746669190453Â FlySAA_CMS_Backend_DevQA * 216989128782 FlySAA_CMS_Backend_PreProd * 396608788916Â FlySAA_CMS_Backend_Prod * 209479274829Â SAA TM1 * 345594574792Â SAA Airnavx * 536697265099Â SAA_NEXIOAV_PROD * 307946680641Â SAA_Informatica_DEV * 536697248966Â SAA_Informatica_PROD * 650251698621Â SAA_PROS_PROD |  | Aravind Raj | Diksha Koul |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 02/Nov/25 7:48 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;Resource Inventory.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176266 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@39f20e89 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzwb: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-28 06:38 | [13 empty] | 28/Oct/25 8:37 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start collecting all data for the given accounts as per the acceptance criteria. And will attach that here for the review. | 29/Oct/25 10:01 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;For Airnavx , informatica dev & prod and Tm1 resource details are fetched in excel sheet but for few resources i donâ€™t have permission to see the list or table. | 02/Nov/25 7:47 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The inventory sheet has been completed from my end also attached in the US. but the resources for which i donâ€™t have permission infront of them i have added no permission comment. | 02/Nov/25 7:48 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[^Resource Inventory.xlsx] | [23 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-11-02 19:49
AM20-230 | EC2, Codebuild and pipeline cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818698 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-10-27 08:27 | 2025-10-28 14:26 |  |  |  | 0 | As a DevOps, I want to validate if any unwanted resource out of codebuild, codepipeline or EC2 instances are running under flysaa backend accounts. If found, that resource should be deleted to optimize cost. Acceptance Criteria: Cleanup is performed w.r.t. EC2, codebuild, codepipeline on flysaa backend accounts |  | Aravind Raj | Sanjot Fotedar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@24f99243 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzw3: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-28 12:19 | [13 empty] | 28/Oct/25 2:18 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;2 early stage Bastion Hosts in flysaa dev account were manually created and have now been terminated as they were not managed by Terraform or aligned with naming standards. Rest all good in dev, preprod and prod | 28/Oct/25 2:26 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have seen 2 instance got terminated. | [25 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-10-28 14:26
AM20-229 | Patch Solution cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818696 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-10-27 08:27 | 2025-11-14 20:26 |  |  |  | 0 |  |  | Aravind Raj | Faisal Sayed |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@698194ac | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzvv: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-31 09:18 | [13 empty] | 31/Oct/25 11:17 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;The Patching instances are still needed, it shall be in stopped state when not in use and terminated once the patching demo is done which has been postponed. [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] [~accountid:712020:54791a09-30fd-4ab7-8a1d-068b13e544d8] | [26 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-11-14 20:26
AM20-228 | Ec2 Cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818694 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-10-27 08:26 | 2025-10-28 14:28 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4bebd3dc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzvn: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 2:28 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Sanjot has cleaned up 2 ec2 instance from backend dev. | [26 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-10-28 14:27
AM20-227 | Cloud Watch CleanUp for Preprod | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Shreyash Talwekar | Medium | 1818692 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-10-27 08:24 | 2025-10-31 13:57 |  |  |  | 0 | Remove unwanted alarm from the al the environment's, and have only important alarms configured in preprod infra. |  | Aravind Raj | Shreyash Talwekar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 31/Oct/25 12:48 PM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251031-104843.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176008 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@528b4111 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzvf: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-30 09:37 | [13 empty] | 30/Oct/25 11:36 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Currently alarms are required to test SMS sharing implementation. | 31/Oct/25 12:47 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;I have removed all Flysaa Backend alarms related to error patterns in pods , api healthcheck alarms , pod cpu/memory check alarms and RDS alarms in preprod account. Attaching pipeline screenshot for reference. !image-20251031-104843.png¦width=524,alt="image-20251031-104843.png"! | [25 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-10-31 13:57
AM20-226 | Resources cleanup - Aws accounts | Done | 6 | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1817985 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-10-24 10:02 | 2025-11-14 20:28 |  | 2025-11-14 20:28 |  | 0 | As part of cost optimization we have planned to take a inventory of AWS resources deployed already. Further to cleanup unwanted and unutilized resources. |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 86400 | 86400 |  | 0 | 172800 | 172800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@47ec6456 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kwlv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 18 | [97 empty] | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [65 empty] | YES | YES |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [42 empty] | Done | 2025-11-14 20:28
AM20-225 | Security controls remediation - Informatica and PROS Aws accounts | Done | 6 | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1817984 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-10-24 10:02 | 2025-10-28 11:48 |  | 2025-10-28 11:48 |  | 0 | Remediate a failed controls from the industry standards. |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;28/Oct/25 11:47 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 86400 | 28800 | 57600 | 0.66 | 115200 | 57600 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@932097d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kwln: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_339746032 |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_339746032 | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_339746032 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_339746032 | [65 empty] | YES | YES | 2025-10-28 06:05 | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_339746032 | [12 empty] | 28/Oct/25 8:05 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PROS account CIS, AWS FSBP, NIST failed controls were remediated. Security score will update after 24 hours. | 28/Oct/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Informatica Dev and prod account failed controls were remediated. | 28/Oct/25 11:47 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;few controls align to s3 and account is in failed state since s3 deployed using terraform should remediate through terraform itself and other account related should be done by Vodacom. | 28/Oct/25 11:48 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Failed controls were remediated in Pros and informatica environments. | [26 empty] | Done | 2025-10-28 11:48
AM20-214 | Prepare Low Level design for migrating public DNS zones from on prem to AWS Route 53 | Done | 8 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1813226 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-17 16:46 | 2025-11-12 08:17 |  | 2025-11-12 08:17 |  | 0 | As Cloud solution architect I want to prepare a detailed low level design document for migration of existing public DNS zones from on-premises infrastructure to AWS Route 53 so that the implementation team has comprehensive technical reference covering architecture, configuration, dependencies, security and cutover details Acceptance criteria: LLD should define and include below points current state DNS architecture including list of zones, record types, TTLs, dependencies and authoritative name servers Target AWS architecture - including Route53 hosted zone hierarchy, account placement (centralized vs distributed), IAM roles/policies, query, logging, tagging and cross account access model record migration strategy and mapping describing how each existing record type (A,CNAME,MX,TXT,SPF,DKIM,SRV,ALIAS) will be represented in Route53 and any TTL adjustment needed Zone creation and import procedure - specifying tools( terraform, CLI), validation steps and naming conventions Cutover and roll back plan - covering TTL reduction timelines, registrat name server updates, validation and backout process Monitoring and alerting approach - query logging , health check, Cloudwatch integration, alerts channels (SNS/ServiceNow) Security and compliance considerations - access controls, audit logging. DNSSEC enablement plan and approval workflows Operational runbooks - pre-migration validation, cutover execution and post migration verification steps Risks, assumption, dependency |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1e65abb1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v04b | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 18 | [97 empty] | 3_*:*_1_*:*_951626717_*¦*_10041_*:*_1_*:*_1178762675_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_951626717_*¦*_10041_*:*_1_*:*_1178762675_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_951626717_*¦*_10041_*:*_1_*:*_1178762675_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_951626717_*¦*_10041_*:*_1_*:*_1178762675_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-11 06:33 | 3_*:*_1_*:*_951626717_*¦*_10041_*:*_1_*:*_1178762675_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 11/Nov/25 8:32 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Moving this to review as Sankalp has Jira access issues. | 12/Nov/25 8:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-11-12 08:17
AM20-213 | Lambda function to observe state in cloudwatch alarms configured for monitoring other lambda | Done | 2 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1812682 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-17 09:02 | 2025-10-31 17:23 |  | 2025-10-31 17:23 |  | 0 | As Product manager I would like to create Lambda function to observe state in cloudwatch alarms configured for monitoring other lambda function and send Â alert payload to servicenow as per the shared format to servicenow so that any failure of lamda is captured and remediation can be initiated. # Create Eventbridge to monitor the state change in alarm. # Create Lambda function to send alarm notifications to ServiceNow when threshold is breached. # Configure event bridge as the trigger for lambda function |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;31/Oct/25 11:21 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f18c499 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kag3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-27 04:51 | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 27/Oct/25 6:51 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will review the description & configuration needs and will connect with Shreyash for getting more clarity. Once I get the whole picture will move the story to In Progress. | 31/Oct/25 11:20 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Create Eventbridge to monitor the state change in alarm. - Done # Create Lambda function to send alarm notifications to ServiceNow when threshold is breached. - Done # Configure event bridge as the trigger for lambda function - Done Tested it with a test alarm event. [~accountid:712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8] | 31/Oct/25 5:23 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though no demo was provided, based on Faisal comments approving it. | [27 empty] | Done | 2025-10-31 17:23
AM20-212 | PROS ¦¦ Alert integration with ServiceNow | Done | 0 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811853 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-16 11:07 | 2025-10-31 17:28 |  | 2025-10-31 17:28 |  | 0 | Acceptance Criteria: Perform validations post integration with ServiceNow ServiceNow team confirms that payload is reaching to servicenow and all the inputs including tags are reaching to Servicenow without any changes needed. formal Signoff from servicenow team needed |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [26 empty] | AM20-211 |  |  | 31/Oct/25 2:24 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;Re_ Confirmation on PROS-Prod Alarm Notification.eml;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176071 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5f6051c6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k7bb: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_21679719_*¦*_10041_*:*_1_*:*_595258194_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_690798371 |  | 3_*:*_1_*:*_21679719_*¦*_10041_*:*_1_*:*_595258194_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_690798371 | 3_*:*_1_*:*_21679719_*¦*_10041_*:*_1_*:*_595258194_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_690798371 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_21679719_*¦*_10041_*:*_1_*:*_595258194_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_690798371 | [65 empty] | YES | YES | 2025-10-31 12:24 | 3_*:*_1_*:*_21679719_*¦*_10041_*:*_1_*:*_595258194_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_690798371 | [12 empty] | 31/Oct/25 2:23 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Confirmation taken form the Service Now Team regarding the Alert Notification generation for PROS Prod. Attaching the email for reference. | 31/Oct/25 2:24 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^Re_ Confirmation on PROS-Prod Alarm Notification.eml] | 31/Oct/25 5:28 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-10-31 17:28
AM20-211 | Informatica ¦¦ Alert integration with ServiceNow | Done | 4 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811851 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-16 11:06 | 2025-10-31 09:35 |  | 2025-10-31 09:35 |  | 0 | Acceptance Criteria: Perform validations post integration with ServiceNow ServiceNow team confirms that payload is reaching to servicenow and all the inputs including tags are reaching to Servicenow without any changes needed. formal Signoff from servicenow team needed |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [9 empty] | AM20-212 |  |  |  | 28/Oct/25 6:58 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251028-165729.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174301 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@104a0167 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k7b7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 |  | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | [65 empty] | YES | YES | 2025-10-23 13:19 | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | [12 empty] | 23/Oct/25 3:19 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Service Now integration with cloud watch through IAM role were completed. And [~accountid:712020:54791a09-30fd-4ab7-8a1d-068b13e544d8] created all required ALARM for the key metrics for Informatica Prod and Dev account already and i have reviewed it. | 28/Oct/25 6:58 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have checked with Priyanka and service now team they are getting the alerts as per they requested. !image-20251028-165729.png¦width=629,alt="image-20251028-165729.png"! Attaching the email confirmation evidence for the reference. | 31/Oct/25 9:35 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Integration completed with servicenow and mail confirmation received hence accepting user story to be done | [27 empty] | Done | 2025-10-31 09:35
AM20-209 | PROS ¦¦ Application monitoring and Alerting | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1811843 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-16 10:58 | 2025-11-12 08:24 |  | 2025-11-12 08:24 |  | 0 | AS Product owner I would like to configure alerting and monitoring for application specific alerts. Acceptance Criteria: Health/ready endpoints: health (basic)/ ready (deps checked) *Alerts*: non-2XX or latency > P95 target for 3-5 mins Startup time and failures: boot duration count of failed boots *Alerts*: boot>5sec or > 1 failed start in 15 mins Unhandled exceptions: total and by class module *Alerts*: error rate > 2% of requests for 5 mins Log anomaly rate: ERROR/WARN per minute vs baseline *Alert*: Spike above learned baseline Critical transaction success rate ( e.g login) *Alert*: Success<98% of 10 mins |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;31/Oct/25 11:27 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [9 empty] | AM20-208 |  |  | 31/Oct/25 11:27 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;RE_ Informatica & PROS __ Application monitoring.eml;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175947 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4d798cc9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v079 | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_72739_*¦*_10041_*:*_1_*:*_1297682389_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_72739_*¦*_10041_*:*_1_*:*_1297682389_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_72739_*¦*_10041_*:*_1_*:*_1297682389_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_72739_*¦*_10041_*:*_1_*:*_1297682389_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-31 09:27 | 3_*:*_1_*:*_72739_*¦*_10041_*:*_1_*:*_1297682389_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 31/Oct/25 11:27 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Attaching email where we have got email confirmation, that the alarms and monitoring is not needed since the client already have it in place. Hence, closing the story with this comment and also attaching the email for reference. | 31/Oct/25 11:27 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^RE_ Informatica & PROS __ Application monitoring.eml] | 12/Nov/25 8:24 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-12 08:24
AM20-208 | Informatica Server ¦¦ Application monitoring and Alerting | Cancelled | 4 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811839 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-16 10:57 | 2026-01-04 09:03 |  |  |  | 0 | AS Product owner I would like to configure alerting and monitoring for application specific alerts. Acceptance Criteria: Health/ready endpoints: health (basic)/ ready (deps checked) *Alerts*: non-2XX or latency > P95 target for 3-5 mins Startup time and failures: boot duration count of failed boots *Alerts*: boot>5sec or > 1 failed start in 15 mins Unhandled exceptions: total and by class module *Alerts*: error rate > 2% of requests for 5 mins Log anomaly rate: ERROR/WARN per minute vs baseline *Alert*: Spike above learned baseline Critical transaction success rate ( e.g login) *Alert*: Success<98% of 10 mins |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [9 empty] | AM20-209 |  |  |  | 31/Oct/25 11:28 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;RE_ Informatica & PROS __ Application monitoring.eml;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175948 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5ed55214 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k78z: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-27 04:33 | [13 empty] | 23/Oct/25 8:27 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;[~accountid:712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb] Please update comments in this story to reflect progress | 27/Oct/25 6:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;will configure (Health/ready endpoints: health (basic)/ ready (deps checked)) using synthetics & canary. | 31/Oct/25 11:28 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Attaching email where we have got email confirmation, that the alarms and monitoring is not needed since the client already have it in place. Hence, closing the story with this comment and also attaching the email for reference. | 31/Oct/25 11:28 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^RE_ Informatica & PROS __ Application monitoring.eml] | 31/Oct/25 5:27 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Since business has rejected the requirement | [25 empty] | Done | 2025-10-31 17:26
AM20-207 | Implement JSON Message Parsing in AWS sandbox ActiveMQ POC | Done | 4 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811820 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-16 10:55 | 2025-10-31 17:25 |  | 2025-10-31 17:25 |  | 0 | As part of validating AWS ActiveMQ integration with a Spring Boot application, we will deploy Producerâ€“Consumer.java files to conduct POC to include JSON message parsing capability. The Producer will publish structured JSON messages to ActiveMQ queue, and Consumer will parse and process the JSON payload. This will help validate end-to-end message exchange, parsing logic, and overall integration readiness in AWS sandbox environment. *Acceptance Criteria* * Deploy ActiveMQ in AWS Sandbox environment. * ActiveMQ broker is accessible from Spring Boot application in EC2 windows of AWS sandbox. * Producer publishes a sample JSON message to ActiveMQ queue. * Consumer retrieves the message and successfully parses the JSON payload using a standard parser (e.g., Jackson). * Parsed data fields are printed for verification. * Message transmission and parsing flow verified end-to-end without errors. |  | Sanjot Fotedar | Sumit Nikam | Yashwant Thakur |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;24/Oct/25 10:15 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 57600 | 28800 | 28800 | [12 empty] | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124615.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174186 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124631.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174189 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124648.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174188 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124656.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174187 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5c659eaf | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k74r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-23 13:51 | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 23/Oct/25 3:51 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Following steps are completed: * We have deployed ActiveMQ in AWS sandbox account. * Deploy EC2 windows server manually in same sandbox account align under same network with MQ server. * Tested successfully MQ server connectivity from EC2 windows server. * Installed JDK-17 version , maven to support java spring boot applications. * Developed and deployed java application with pom.xml | 28/Oct/25 2:50 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;* Developed [Producer.java¦http://Producer.java] to publish JSON messages to AWS ActiveMQ queue. * Developed [ConsumerTest.java¦http://Consumer.java] to consume and parse JSON messages. * Verified successful message send/receive flow over SSL connection. * Validated JSON parsing using Jackson and confirmed expected output. * Resolved encoding and dependency issues during build. * End-to-end functionality tested in AWS sandbox account. * MQ server Dashboard shows expected outcome. !image-20251028-124615.png¦width=443,alt="image-20251028-124615.png"! !image-20251028-124631.png¦width=443,alt="image-20251028-124631.png"! !image-20251028-124648.png¦width=443,alt="image-20251028-124648.png"! !image-20251028-124656.png¦width=443,alt="image-20251028-124656.png"! | 31/Oct/25 12:31 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;We have reviewed implementation in sandbox and could see working messaging flow from provider to the consumer via AmazonMQ running with ActiveMQ broker. Next step is to modify the config and test config based on feedback from Amadeus. | 31/Oct/25 5:25 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-10-31 17:25
AM20-206 | MQ ¦¦ Provisioning of Dev and Prod Servers using terraform | To Do | 0 | None( Backlog) |  |  | Sanket Kale | Medium | 1811817 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-16 10:54 | 2025-10-31 08:25 |  |  |  | 0 | AS a product owner I would like to provision EC2 servers for MQ for both Dev and Prod so that we can proceed with fresh installation of MQ Acceptance Criteria: * EC2 servers for both Dev and Prod are provisioned successfully * Tagging for the workloads successful based on agreed format * CloudWatch integration with EC2 workloads is successful * IAM/Policies defined and implemented successfully | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@172a75be | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g4 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-10-16 10:54
AM20-201 | AirNavX ¦¦ Application monitoring and Alerting | Done | 6 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1801368 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-10-07 09:57 | 2026-01-04 08:43 | 2026-01-04 09:13 | 2026-01-04 08:43 |  | 0 | AS Product owner I would like to configure alerting and monitoring for application specific alerts. Acceptance Criteria: All the attached alerts must be configured in Cloudwatch /SNS/ Lamda/ so that for each occurance, the error is sent to ServiceNow for incident creation/generation. |  | Diksha Koul | Faisal Sayed | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  | Adding Lambda for accessing URL and monitoring status using cloudwatch alarms. Also sending ServiceNow events when the threshold is breached. ;02/Jan/26 9:52 AM;17cb9418-1850-4923-932b-7098ec51b6bb;43200 | [5 empty] | 86400 | 43200 | 43200 | 0.5 | 86400 | 43200 | 43200 | [12 empty] | 11/Dec/25 10:35 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;RE airnavX alarm requirements.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194363 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@747ca5f3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 21 | [97 empty] | 3_*:*_2_*:*_1826706492_*¦*_10041_*:*_2_*:*_851221150_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_4844844325 |  | 3_*:*_2_*:*_1826706492_*¦*_10041_*:*_2_*:*_851221150_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_4844844325 | 3_*:*_2_*:*_1826706492_*¦*_10041_*:*_2_*:*_851221150_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_4844844325 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_1826706492_*¦*_10041_*:*_2_*:*_851221150_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_4844844325 | [65 empty] | YES | YES | 2025-11-20 05:23 | 3_*:*_2_*:*_1826706492_*¦*_10041_*:*_2_*:*_851221150_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_4844844325 | [12 empty] | 20/Nov/25 7:23 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status:* Blocked. *Reason:* Awaiting finalization of approach. Application monitoring will be configured post cutover. *Options under discussion:* # Convert current instance license (pending resolution). # Redeploy instance with required RHEL subscription. | 24/Nov/25 8:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status:* Blocked *Update:* The option to convert the current instance license is now resolved. Awaiting AirnavX cutover; application monitoring will be implemented post-cutover. | 28/Nov/25 11:41 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;To be taken up post completion of AirnavX cutover | 18/Dec/25 8:38 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started working on the the URL for alerting as per Albertâ€™s requirement. | 02/Jan/26 9:55 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Alarms are setup in airnavx account to monitor accessibility to airnavx URLs and trigger notifications when the URL is unavailable for 15 minutes. Example payload: {"Name": "AirNavX-AirnavX_AppHealth-base-down","IP Address": "NA","Fully Qualified Domain Name": "[airnavxpub.flysaa.com¦http://airnavxpub.flysaa.com]","Company": "VFSA","Hostname": "[airnavxpub.flysaa.com¦http://airnavxpub.flysaa.com]","Department": "App DevOps Team","Operating System": "Amazon Linux","DNS Domain": "[airnavxpub.flysaa.com¦http://airnavxpub.flysaa.com]","Disk Space (GB)": "NA","RAM (MB)": "4000","CPU Count": "2","CPU core count": "2","Alarm Time": "2026-01-02 06:08:49 UTC","Account ID": "345594574792","Environment": "Airnavx","MetricName": "ActuatorHealth","Current State": "ALARM","Reason": "Threshold Crossed: 1 out of the last 3 datapoints [1.0 (02/01/26 05:53:00)] was less than the threshold (2.0) (minimum 3 datapoints for OK -> ALARM transition)."} | 04/Jan/26 8:43 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2026-01-04 08:43
AM20-200 | PROS ¦ Cut-Over Instance | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | Medium | 1801097 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-10-07 08:38 | 2025-10-28 11:52 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [30 empty] | 28/Oct/25 11:51 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251028-095148.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174003 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6de063c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0izhv: | [167 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 11:51 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PROS cutover is carried out successfully, have archived the servers in application migration service. !image-20251028-095148.png¦width=423,alt="image-20251028-095148.png"! | [26 empty] | 1773952 | AM20-170 | PROS ¦¦ Cutover | Done | 2025-10-28 11:52
AM20-199 | PROS ¦ Test-Over Instance | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | Medium | 1801095 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-10-07 08:38 | 2025-10-17 11:08 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@32a969b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0izhn: | [167 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 07/Oct/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Server replication is still on-going after completion of initial sync will start launching test instance. have updated the launch templet based on the LLD document. | 09/Oct/25 6:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test launch instance hand over is completed, awaiting for the response back from the application owner. | 17/Oct/25 11:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;connectivity issue is resolved, have received date to perform cutover. | [24 empty] | 1773952 | AM20-170 | PROS ¦¦ Cutover | Done | 2025-10-17 11:08
AM20-198 | Push to FlySAA backend Alarm related code to the bitbucket in prod environment. | Done | 0 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1800257 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-10-06 10:58 | 2025-10-20 16:06 |  |  |  | 0 | Add existing terraform code to create CloudWatch alarms and other required AWS resources into the bitbucket. Â Add alarms for following: Â Kubernetes microservice CPU and Memory consumption alarms for Amadeus and Fabric microservices. Â Error Patterns observed in microservice logs. Â Healthcheck API endpoint return status monitoring. Â Configured Alerts to monitor RDS metrics. Â Also create EventBridges to capture alarm state change (Ok â†’ Alarm and Alarm â†’ Ok). Â Create Lambda jobs to be triggered by EventBridge which in turn sends notification to ServiceNow using existing SNS topics. | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@235e656e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0iw3n: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 17 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | Done | 2025-10-20 16:06
AM20-197 | Informatica ¦¦ Alerting and Monitoring Solution | Done | 4 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1800159 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-10-06 10:18 | 2025-10-17 07:17 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment. Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O. * Dashboards are created to monitor key services. * SNS Alert should be generated if Informatica server is stopped. |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 09/Oct/25 9:21 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251009-071913.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1165179 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3ac6b815 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ivor: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 09:08 | [13 empty] | 06/Oct/25 11:07 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start creating the dashboard and alerting for Informatica Dev and Prod environment. | 06/Oct/25 12:13 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I enabled the CloudWatch metrics for Informatica Dev and Prod for CPU, memory, disc, network I/O. Dashboards are also created to monitor key services. --- *DONE.* Now Alerting and monitoring needs to be created with proper naming and threshold values â€“ *PENDING*. | 07/Oct/25 12:19 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Created alarms and monitoring for informatica prod and dev for CPU and Status Check failed â€“ *DONE.* | 08/Oct/25 12:38 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;All alerts including the Disk and memory utilization for Informatica Prod and Dev has been created with proper naming and threshold value. --- *DONE.* | 09/Oct/25 9:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251009-071913.png¦width=1575,height=673,alt="image-20251009-071913.png"! Have created the Informatica prod and dev alerting rules setup the threshold value for them. | 09/Oct/25 10:46 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Moving this US to in review to Aravind. If require any modification. | 13/Oct/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have reviewed has some query will discuss with diksha and close. | 15/Oct/25 11:58 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Aravind reviewed the changes and gave his approval now we can move it to PO approval. | 17/Oct/25 7:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | Done | 2025-10-17 07:17
AM20-196 | Adding alarms for AWS account config changes. | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Shreyash Talwekar | Medium | 1799088 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2025-10-03 10:46 | 2025-10-03 10:48 |  |  |  | 0 | Add terraform code to configure below mentioned alarms for observing the cloudwatch logs regarding any changes done on AWS account. {noformat}AWSConfigChanges = { metric = "AWSConfigChanges", pattern = "{($.eventName = \"PutBucketPolicy\") ¦¦ ($.eventName = \"RunInstances\") ¦¦ ($.eventName = \"ModifyDBInstance\") ¦¦ ($.eventName = \"PutRolePolicy\")}" }, SecurityGroupChanges = { metric = "SecurityGroupChanges", pattern = "{($.eventName = \"CreateSecurityGroup\") ¦¦ ($.eventName = \"DeleteSecurityGroup\") ¦¦ ($.eventName = \"AuthorizeSecurityGroupIngress\") ¦¦ ($.eventName = \"AuthorizeSecurityGroupEgress\") ¦¦ ($.eventName = \"RevokeSecurityGroupIngress\") ¦¦ ($.eventName = \"RevokeSecurityGroupEgress\") ¦¦ ($.eventName = \"ModifySecurityGroupRules\")}" }, CMKDisablingOrDeletion = { metric = "CMKDisablingOrDeletion", pattern = "{($.eventName = \"DisableKey\") ¦¦ ($.eventName = \"ScheduleKeyDeletion\")}" }, CloudTrailConfigurationChanges = { metric = "CloudTrailConfigurationChanges", pattern = "{($.eventName = \"CreateTrail\") ¦¦ ($.eventName = \"UpdateTrail\") ¦¦ ($.eventName = \"DeleteTrail\") ¦¦ ($.eventName = \"StartLogging\") ¦¦ ($.eventName = \"StopLogging\") ¦¦ ($.eventName = \"PutEventSelectors\")}" }, ConsoleAuthenticationFailures = { metric = "ConsoleAuthenticationFailures", pattern = "{($.eventName = \"ConsoleLogin\") && ($.responseElements.ConsoleLogin = \"Failure\")}" }, ConsoleSignInWithoutMFA = { metric = "ConsoleSignInWithoutMFA", pattern = "{($.eventName = \"ConsoleLogin\") && ($.responseElements.ConsoleLogin = \"Success\") && ($.requestParameters.mfaAuthenticated = \"false\")}" }, IAMPolicyChanges = { metric = "IAMPolicyChanges", pattern = "{($.eventName = \"CreatePolicy\") ¦¦ ($.eventName = \"DeletePolicy\") ¦¦ ($.eventName = \"PutPolicy\") ¦¦ ($.eventName = \"AttachRolePolicy\") ¦¦ ($.eventName = \"DetachRolePolicy\") ¦¦ ($.eventName = \"AttachUserPolicy\") ¦¦ ($.eventName = \"DetachUserPolicy\")}" }, NACLChanges = { metric = "NACLChanges", pattern = "{($.eventName = \"CreateNetworkAcl\") ¦¦ ($.eventName = \"DeleteNetworkAcl\") ¦¦ ($.eventName = \"CreateNetworkAclEntry\") ¦¦ ($.eventName = \"DeleteNetworkAclEntry\") ¦¦ ($.eventName = \"ReplaceNetworkAclEntry\") ¦¦ ($.eventName = \"ModifyNetworkAcl\")}" }, NetworkGatewayChanges = { metric = "NetworkGatewayChanges", pattern = "{($.eventName = \"CreateVpnGateway\") ¦¦ ($.eventName = \"DeleteVpnGateway\") ¦¦ ($.eventName = \"AttachVpnGateway\") ¦¦ ($.eventName = \"DetachVpnGateway\") ¦¦ ($.eventName = \"ModifyVpnGateway\") ¦¦ ($.eventName = \"CreateTransitGateway\") ¦¦ ($.eventName = \"DeleteTransitGateway\") ¦¦ ($.eventName = \"ModifyTransitGateway\") ¦¦ ($.eventName = \"CreateTransitGatewayAttachment\") ¦¦ ($.eventName = \"DeleteTransitGatewayAttachment\") ¦¦ ($.eventName = \"ModifyTransitGatewayVpcAttachment\")}" }, RootAccountUsage = { metric = "RootAccountUsage", pattern = "{($.userIdentity.type = \"Root\")}" }, RouteTableChanges = { metric = "RouteTableChanges", pattern = "{($.eventName = \"CreateRouteTable\") ¦¦ ($.eventName = \"DeleteRouteTable\") ¦¦ ($.eventName = \"CreateRoute\") ¦¦ ($.eventName = \"DeleteRoute\") ¦¦ ($.eventName = \"AssociateRouteTable\") ¦¦ ($.eventName = \"DisassociateRouteTable\") ¦¦ ($.eventName = \"ReplaceRouteTableAssociation\")}" }, S3BucketPolicyChanges = { metric = "S3BucketPolicyChanges", pattern = "{($.eventName = \"PutBucketPolicy\") ¦¦ ($.eventName = \"DeleteBucketPolicy\")}" }, UnauthorizedAPICalls = { metric = "UnauthorizedAPICalls", pattern = "{($.errorCode = \"AccessDenied\") ¦¦ ($.errorCode = \"UnauthorizedOperation\")}" }, VPCChanges = { metric = "VPCChanges", pattern = "{($.eventName = \"CreateVpc\") ¦¦ ($.eventName = \"DeleteVpc\") ¦¦ ($.eventName = \"ModifyVpcAttribute\") ¦¦ ($.eventName = \"CreateSubnet\") ¦¦ ($.eventName = \"DeleteSubnet\") ¦¦ ($.eventName = \"ModifySubnetAttribute\") ¦¦ ($.eventName = \"AssociateRouteTable\") ¦¦ ($.eventName = \"DisassociateRouteTable\") ¦¦ ($.eventName = \"CreateInternetGateway\") ¦¦ ($.eventName = \"DeleteInternetGateway\") ¦¦ ($.eventName = \"AttachInternetGateway\") ¦¦ ($.eventName = \"DetachInternetGateway\") ¦¦ ($.eventName = \"CreateNatGateway\") ¦¦ ($.eventName = \"DeleteNatGateway\")}" }{noformat} |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43895d15 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ir97: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [41 empty] | 1786761 | AM20-182 | Push to FlySAA backend Alarm related code to the bitbucket in dev and preprod environment | Done | 2025-10-03 10:48
AM20-195 | Adding Lambda for generating sonar scan reports | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Shreyash Talwekar | Medium | 1799079 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2025-10-03 10:43 | 2025-10-03 10:48 |  |  |  | 0 | Adding terraform code to create Lambda and API Gateway for generating sonar scan reports. |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@62438a0e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ir8b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 03/Oct/25 10:45 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Added lambda module and api gateway module and updated the api gateway url in sonar server webhook. | [26 empty] | 1786761 | AM20-182 | Push to FlySAA backend Alarm related code to the bitbucket in dev and preprod environment | Done | 2025-10-03 10:44
AM20-194 | POC for replacing IBM MQ with AWS MQ | To Do | 0 | None( Backlog) |  |  |  | Medium | 1795168 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-30 17:36 | 2025-09-30 17:36 |  |  |  | 0 | [57 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63afd04c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akq: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:36
AM20-192 | MQ ¦¦ Application comms metrics preparation and implementation | To Do | 0 | None( Backlog) |  |  | Satya Varanasi | Medium | 1795166 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-30 17:35 | 2025-10-31 08:25 |  |  |  | 0 | AS Network expertise I want to define, track and baseline and validate network communication metrics including subnets, connectivity with downstream/3rd party applications and network rules so that the applicationcan be migrated to the cloud without connectivity failures, security gaps or performance degradation Acceptance Criteria: Application specific subnets (CIDR range, VPC design, Private/public allocation) documented Overlapping IP ranges validated against downstream and 3rd party integrations subnet utilization % captured E2E connectivity map prepared: application <->DB<->downstream services <->3rd party APIs Latency, Packet loss, throughput baselined from VDC/onprem to cloud traget points DNS resolution | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3842a4ec | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g1 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:35
AM20-191 | MQ ¦¦ DR and BackUp | To Do | 0 | None( Backlog) |  |  |  | Medium | 1794158 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-30 10:24 | 2025-10-16 10:42 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Informatica-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@415fe9df | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v08 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 10:24
AM20-189 | Trellix integration with MQ | Blocked | 2 | None( Backlog) |  |  | Satya Varanasi | Medium | 1794150 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-30 10:19 | 2025-10-31 11:05 |  |  |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan MQ workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in MQ server * Trellix is able to access MQ account successfully and perform scanning |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b924c6e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g04 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-27 14:04 | [13 empty] | 27/Oct/25 4:03 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This action need to addressed once server build completes. | [29 empty] | To Do | 2025-09-30 10:19
AM20-188 | MQ ¦¦ Monitoring and Alert Solution | Blocked | 4 | None( Backlog) |  |  | Diksha Koul | Medium | 1794147 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-30 10:17 | 2025-11-02 19:42 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if MQ server is stopped |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c39a10 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-02 17:42 | [13 empty] | 02/Nov/25 7:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over* : After creation of the MQ EC2 instance we can start the creation of MQ monitoring and alerting solution. | [29 empty] | To Do | 2025-09-30 10:17
AM20-186 | MQ¦¦ Migration Agent comms Metrics implementation | Blocked | 2 | Sprint 16 | 2025-10-13 | 2025-10-24 | Satya Varanasi | Medium | 1794120 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-30 10:14 | 2025-10-31 08:25 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@692cf397 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g9 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-17 09:19 | [13 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | [29 empty] | To Do | 2025-09-30 10:14
AM20-185 | MQ-PROD ¦¦Setup Subnet, NACL and SG Creation and Validation | Done | 3 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1794109 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-30 10:12 | 2025-10-31 09:34 |  | 2025-10-31 09:34 |  | 0 | As AWS network expert I would like to setup the security group and NACL for MQ so that access for MQ allow secure access to allow communication with its services while ensuring access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for MQ or related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [13 empty] | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090000.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175254 | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090022.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175253 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@680e7164 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0i6ob: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 17 | [97 empty] | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [65 empty] | YES | YES | 2025-10-17 09:19 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [12 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 27/Oct/25 4:05 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working on it. | 30/Oct/25 11:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to requirement i have done platform setup. Subnets: ¦Subnet address¦Range of addresses¦Useable IPs¦Hosts¦Divide¦Used Status¦App Name¦ ¦10.40.0.224/28¦10.40.0.224 - 10.40.0.239¦10.40.0.225 - 10.40.0.238¦14¦Divide¦Done¦MQ PROD PRIVATE¦ ¦10.40.0.240/28¦10.40.0.240 - 10.40.0.255¦10.40.0.241 - 10.40.0.254¦14¦Divide¦Done¦MQ PROD PUBLIC¦ ¦10.40.1.32/28¦10.40.1.32 - 10.40.1.47¦10.40.1.33 - 10.40.1.46¦14¦Divide¦Done¦MQ PROD DR¦ ¦10.40.1.48/28¦10.40.1.48 - 10.40.1.63¦10.40.1.49 - 10.40.1.62¦14¦Divide¦Done¦MQ PROD DR¦ Subnets screen: !image-20251030-090022.png¦width=597,alt="image-20251030-090022.png"! EC2 connectivity screen: !image-20251030-090000.png¦width=597,alt="image-20251030-090000.png"! | 31/Oct/25 9:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though MQ migration is put on hold however since the objective and acceptance criteria is met, approving the User story to close | [26 empty] | Done | 2025-10-31 09:34
AM20-184 | Patch Managment documentation | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1787130 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-19 16:49 | 2025-11-27 09:26 | 2025-11-26 12:52 | 2025-11-01 11:23 |  | 0 | As Product owner, I would like to document patch management solutioning with flow and details so that business and stakeholders are aligned with process and may refer it as ready references Acceptance Criteria: * Patch management techincal flow with expectation * Clear bifurcations of process for Windows and Linux/RHEL servers * IAM role details for patch management * Account structure explained and step by step process on performing patch management solutions * Considerations, Assumptions and dependencies * Documentation consists of handover process to include steps for adding new OS versions and repositories * Patching Dashboard access, explanation * Patching housekeeping process. |  | Faisal Sayed | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  | ;01/Nov/25 11:11 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;201600 | ;12/Nov/25 10:23 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;7200 | ;20/Nov/25 7:38 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;36000 | ;21/Nov/25 7:17 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;1800 | ;21/Nov/25 4:03 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;1800 |  | 57600 | 0 | 248400 | 4.31 | 57600 | 0 | 248400 | [12 empty] | 25/Nov/25 10:46 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;Patching Document (5afa381b-c368-42af-8f50-0b2741be8b15).docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1188961 | 12/Nov/25 6:31 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;Patching Document (5cc9c8a6-10d5-47b9-bccc-65c546fb0f32).docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1181554 | 21/Nov/25 4:03 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;Patching Document (6b6cca10-f985-468b-bffb-03edaf59f037).docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1188122 | 21/Nov/25 7:17 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;Patching Document (8d14d1d1-0966-4ffe-bf17-19130c542362).docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187514 | 20/Nov/25 8:24 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;Patching Document (c9b81946-0108-428a-ba98-c00afe73e1e0).docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186881 | 13/Nov/25 11:01 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;Patching Document (cb93f516-c747-43c2-9235-57b894a70a6b).docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182684 | 06/Nov/25 2:41 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;Patching Document.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1179020 | [11 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1bc4ed81 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hczv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | [94 empty] | 3_*:*_2_*:*_2766783047_*¦*_10041_*:*_1_*:*_920282425_*¦*_13940_*:*_2_*:*_7783738 |  | 3_*:*_2_*:*_2766783047_*¦*_10041_*:*_1_*:*_920282425_*¦*_13940_*:*_2_*:*_7783738 | 3_*:*_2_*:*_2766783047_*¦*_10041_*:*_1_*:*_920282425_*¦*_13940_*:*_2_*:*_7783738 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_2766783047_*¦*_10041_*:*_1_*:*_920282425_*¦*_13940_*:*_2_*:*_7783738 | [65 empty] | YES | YES | 2025-10-06 03:29 | 3_*:*_2_*:*_2766783047_*¦*_10041_*:*_1_*:*_920282425_*¦*_13940_*:*_2_*:*_7783738 | [12 empty] | 06/Oct/25 5:29 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* * Documentation prepared and published. * This will remain an *ongoing process* as additional updates are required: ** Add details after successful implementation of *email reporting feature*. ** Incorporate updates post-demo as part of this sprint. Story will continue to track these enhancements within the current sprint. | 27/Oct/25 6:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* * Reviewed document (feedback from Yashwant) and identified required changes: ** Template update. ** Added *Synopsis* section. ** Added *Reviewed By* section. ** Current doc contained excessive code; will move code to a separate document and link it in the main doc. ** Clear separation between *mandatory patching steps* and *optional configuration steps*. * Implemented ~50% of changes; remaining updates will be completed within this week. | 01/Nov/25 11:07 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Communicated with [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] for reviewing the document by [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] . | 01/Nov/25 11:09 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Reviewed the documentation by [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] and this version has been approved. Closing the story. | 01/Nov/25 11:23 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Reviewed and approved by Satya Varanasi. | 01/Nov/25 5:11 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Story to be reviewed by Satya, accordingly it will proceed [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] | 01/Nov/25 6:10 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Story has already been reviewed and approved, please check the mail. | 03/Nov/25 11:55 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Assigning the story to Satyasairam for his review and feedback on Patch management document [~accountid:712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb] | 06/Nov/25 2:41 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^Patching Document.docx] | 10/Nov/25 2:16 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The DOC has been reviewed by me and Yashwant and we have observed some missing pointers. Comments on your documents:Â * It was observed that you added each account name whilst some of the account name missing like PROS, Backend Prod, Either you put names of all applications (spoke accounts) or make one statement that the said solution is applicable for all spoke accounts. Avoid repetition of same statements for each account. * After point 3 (compliance report), you directly mentioned full form of workloads, create new section called "Abbreviation or Glossary right before table * On Access the Compliance reporting dashboard - IAM role is missing ( not everyone should access the dashboard) * There is no view of Patch Compliance Dashboard * Assumptions sections are not there in the document still Â * Live screen of demo is also not available. Please check above missing points from DOC and same has need to be populated for further. Hence i have reassigning back to you for further. | 12/Nov/25 6:30 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Feedback points have been addressed and incorporated into the document. Moving the item to *Pending PO Approval* and assigning to [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] for further review and approval. | 12/Nov/25 6:31 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^Patching Document (5cc9c8a6-10d5-47b9-bccc-65c546fb0f32).docx] | 13/Nov/25 11:00 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Feedback points have been addressed and incorporated into document. Uploading the latest version. | 13/Nov/25 11:01 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^Patching Document (cb93f516-c747-43c2-9235-57b894a70a6b).docx] | 14/Nov/25 8:25 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;DOC looks fine and modified according to our feedback. Please check once. | 15/Nov/25 2:38 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;We need to revisit the documents based on demo we had today and ensure that we have step by step process covered. The document must cover all pre-requisite and steps. it does not cover error that we saw yesterday where aws command is not recognised and it is a must to have prerequisite | 20/Nov/25 7:38 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Finding:* The system PATH variable reconfiguration was specific to an Informatica development instance only. AWS CLI is installed and configured on all Windows instances across accounts without any PATH-related issues. Therefore, this finding is isolated to a single instance. Rebuild steps for the system PATH variable, including all essential directories, will be documented. | 20/Nov/25 7:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Document version has been incremented to reflect the latest changes. Uploading the file. | 20/Nov/25 8:22 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^Patching Document (c9b81946-0108-428a-ba98-c00afe73e1e0).docx] | 21/Nov/25 7:16 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* The disk space requirement has been documented as a prerequisite, including the recommended safe space for patch installation. The document version has been incremented to reflect these changes, and the updated document has been uploaded. | 21/Nov/25 7:17 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^Patching Document (8d14d1d1-0966-4ffe-bf17-19130c542362).docx] | 21/Nov/25 4:02 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Based on feedback, the document now includes clear segregation of *Requisites* under a single heading. Additionally, *Rationale* and *Troubleshooting* sections have been separated into their respective headings for improved clarity and structure. | 21/Nov/25 4:03 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^Patching Document (6b6cca10-f985-468b-bffb-03edaf59f037).docx] | 25/Nov/25 7:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to suggestions DOC has been modified and the same has been reviewed. | 25/Nov/25 10:45 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* * Added prerequisite for *Trellix whitelisting*. * Documented *finding, impact, and resolution steps* related to Trellix blocking installers and {{.lnk}} & SSH files during patching. * Updated document version to reflect these changes. | 25/Nov/25 10:46 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^Patching Document (5afa381b-c368-42af-8f50-0b2741be8b15).docx] | 27/Nov/25 9:26 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved |  |  |  | Done | 2025-11-27 09:26
AM20-183 | PROS ¦¦ Migration agent installation | Done | 0 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786910 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-19 14:01 | 2025-10-17 07:17 |  |  |  | 0 | AS AWS Product owner I want to install migration agents in both source and target accounts so that workloads can be discovered replicated and migrated securly and reliable into AWS, capture disk, network activity and replicate workloads in AWS Acceptance Criteria: *Replication receiver* - Given the target AWS account is selected when the migration service creates replication servers or staging area subnets then the target account provisions EC2 instances and storage for replication *IAM trust policies* - The migration hub service role is created in the target account when the source account publishes replication traffic, then cross account IAM trust allows replication without manual credential handling *Networking and Security* - The replication server is deployed in a VPC when traffic flows from source to target then it uses encrypted channels and passes through SG/NACLrules validated against compliance baselines *Resources readiness* - Migrated workloads are created in the target when cutover happens the EC2, RDS and AWS service provision successfully in the correct subnet, AZ and security group *Monitoring and rollback* - Agents are sending replication data when a failure occurs then alerts are generated in CoudWatch/SNS and rollback to the last stable snapshot is possible |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5de8572e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hc4b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:15 | [13 empty] | 24/Sep/25 8:14 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Need to check with Sinjun/Wanda for change request initiation for agent installation. | 25/Sep/25 5:25 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change has been submitted â€œCHG0067735â€ and approved, we required Sinjun support for Agent installation. | 26/Sep/25 12:19 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still Migration agent comms not implemented and it is under approval process. | 09/Oct/25 4:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Agent has been installed on all 3 PROS servers and test instance has been created and handed over to customer for connectivity testing. Hence i am closing this story. | 17/Oct/25 7:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:17
AM20-182 | Push to FlySAA backend Alarm related code to the bitbucket in dev and preprod environment | Done | 8 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786761 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-19 12:09 | 2025-10-06 07:59 |  |  |  | 0 | Add existing terraform code to create CloudWatch alarms and other required AWS resources into the bitbucket. Add alarms for following: # Kubernetes microservice CPU and Memory consumption alarms for Amadeus and Fabric microservices. # Error Patterns observed in microservice logs. # Healthcheck API endpoint return status monitoring. # Configured Alerts to monitor RDS metrics. Also create EventBridges to capture alarm state change (Ok â†’ Alarm and Alarm â†’ Ok). Create Lambda jobs to be triggered by EventBridge which in turn sends notification to ServiceNow using existing SNS topics. |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7d9f3978 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hatj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-29 08:07 | [13 empty] | 29/Sep/25 10:07 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Added alerts for monitor error patterns in microservice logs for dev account . Added alerts for monitor cpu, memory and container restart for dev account for dev account . | [29 empty] | Done | 2025-10-06 07:59
AM20-181 | TM1 ¦¦ Alerts renaming & Configuration | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786760 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-19 12:06 | 2025-10-06 07:59 |  |  |  | 0 | As Product owner I would like to rename alerts and configuration based on agreement with ServiceNow team *Acceptance Criteria*: TM1 alarm renaming completed successfully and configurations updated |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 24/Sep/25 1:56 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250924-115610.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1158311 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@26e51892 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-23 08:55 | [13 empty] | 23/Sep/25 10:54 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I have started creating the alarms with correct naming & threshold value which were agreed with the customer and service now team previously. | 24/Sep/25 1:56 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20250924-115610.png¦width=1580,height=467,alt="image-20250924-115610.png"! Have created alarms as per correct naming and configuration updated. | 29/Sep/25 6:53 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Moving this to In review to Aravind to check the configuration. | 03/Oct/25 12:42 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have modified the alarm for disk and memory configuration, other alarm are looking good. | [26 empty] | Done | 2025-10-06 07:59
AM20-180 | AirNavX ¦¦ Validation for SG and NACL | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Satya Varanasi | Medium | 1786688 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-19 11:13 | 2025-10-06 08:41 |  |  |  | 0 | As Product owner I would like to validate SG and NACL in AirnavX account so that to ensure that is correctly configured as required and netwrok access is restricted to least privilege, compliant with security standards and traceable to the right owners *Acceptance Criteria*: Ingress Rule: * Validate only required ports are open * Check if the rules are restricted to known source IPs or SGs * Avoid overly permissive rules like ALL Traffic/ All Ports Egress Rule: * Confirm outbound rules are limited to required destinations/services * Avoid all traffic / 0.0.0.0/0 * Remove duplicate or unused rules * Check if multiple rules overlap unnecessarily * Validate SGs have proper tags (name, environment, owner) for traceability * Confirm unused SGs are not attached to ENIs NACL: * Check both inbound and outbound rules match expected traffic flow * validate rule numbers and ensure no conflicts/overlaps * Ensure the implicit DENY is preserved and only necessary allow rules are added * Avoid overly permissive entries * Since NACL are stateless, confirm return traffic rules exist for each allowed inbound connection * Validate that the correct subnets are associated with the right NACL * Avoid leaving critical subnets with the default NACL explicitly required * Confirm VPC flow logs are enabled for subnets tied to NACLs to validate actual traffic patterns against intended rules |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@f3dd427 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hatf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-25 15:29 | [13 empty] | 25/Sep/25 5:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Airnavx Comms has been implemented and the need to configure respective account and initiate testing. Currently team working on server deployment process, once done we will configure rules and will initiate testing. | 06/Oct/25 8:41 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Comms has been implemented, NACL and SG is setup. App owner is able to access and install the application. Hence closing the story | [28 empty] | Done | 2025-10-06 08:41
AM20-177 | MQ Migration - POC ¦¦ Sandbox environment | Done | 8 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1785826 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-18 12:54 | 2025-11-15 14:39 | 2025-11-21 13:35 | 2025-11-15 14:39 |  | 0 | Set up aÂ sandbox environmentÂ using AmazonMQ to test the proposed approach in collaboration with the Amadeus team. |  | Harsh Chandra | Sumit Nikam | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Prepared rough arch design for PoC purpose based on available info.;14/Nov/25 8:20 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | Analyzed cpp parser info shared by Sampi ;14/Nov/25 8:20 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Further analysis done based on Amadeus feedback and ICP document.;14/Nov/25 8:21 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Created PoC environment with Public IP (EIP) allocated to NLB, ActiveMQ broker from AmazonMQ, a windows and linux instance for testing with necessary connectivity.;14/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | Analyzed sample message along with cpp parser further.;14/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 |  | 115200 | 14400 | 100800 | 0.87 | 115200 | 14400 | 100800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@79b4a52 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h70b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | Sprint 18 | [95 empty] | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 |  | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | [65 empty] | YES | YES | 2025-09-24 06:14 | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | [12 empty] | 24/Sep/25 8:13 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Amadeus shared document has been reviewed. Setup in sandbox has been started. | 26/Sep/25 8:11 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;A sample queue with ActiveMQ being created. Following up with Sampi for parser requirements. | 29/Sep/25 8:28 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Additional dependencies identified during POC. Have asked Amadeus to check and confirm: # *Supported Protocols* Which message protocols do you recommend for integration with Amadeus? * OpenWire/JMS (ActiveMQ) * AMQP 0-9-1 (RabbitMQ) # *IBM MQ Header Mapping* Which IBM MQ MQMD fields are mandatory for Amadeus integration (e.g., Format=1AIEDI, ReplyToQ, CorrelationID)? If we use Amazon MQ (ActiveMQ) or RabbitMQ, can these fields be provided as JMS/AMQP properties (e.g., JMSReplyTo, JMSCorrelationID, custom header x-format=1AIEDI)? If not, do you have a mapping guide for IBM MQMD to JMS/AMQP headers? # *Character Set and Separators* Do you require character set B with binary EDIFACT separators (0x1D, 0x1F, 0x1C), or do you also accept printable characters (+, :, ')? If both are accepted, is there a preferred encoding for production? # *Maximum Message Size* What is the maximum supported message size for messages exchanged with Amadeus? # *EDIFACT Envelope Validation* Do you validate the UNB/UNH/UNT/UNZ envelopes on your side, or should we handle this validation before sending messages? # *Message Persistence* Should we configure all messages as persistent, or should we match the persistence settings from the ICP (e.g., LinkA3 non-persistent, others persistent)? # *Dead-Letter Queue (DLQ) Handling* Do you require a specific dead-letter queue (DLQ) contract on our side, or is a standard broker-level DLQ sufficient? If a DLQ contract is required, do you expect a specific queue name or message format? # *Synchronous Request/Reply SLAs* What are the expected SLAs (response time, timeout, retry policy) for synchronous request/reply flows (Association Codes O/T)? | 30/Sep/25 8:19 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Following up with Sampi for MQ parsers for analysis. Following up with Amadeus for configuration details. | 01/Oct/25 4:32 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Discussion done with Sampi to understand current parsing configs and queues in use. We have given overview of AmazonMQ based setup and asked for rest of the parsers for further analysis. | 06/Oct/25 8:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Awaiting inputs on configuration details from application owner, hence will be spilled over. | 17/Oct/25 11:21 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 30/Oct/25 9:48 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Information received from Amadeus but needs to be spilled over to next sprint since we do not have sufficient time to complete within current sprint. | 07/Nov/25 7:57 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;One to One message mapping is working as expected. We are facing challenges for following: 1. Sync Communication among producer and consumer # One to Many message delivery being checked further. | 10/Nov/25 8:17 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Custom header addition has been added in message exchange. Testing in progress | 12/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Unable to parse properties as per instructions from Amadeus. Checking further. Following up with Sampi in parallel to get test messages for testing parsing capability. | 13/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Working on MQMD fields as per ICP document from Amadeus. | 14/Nov/25 11:54 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;POC has been carried out for Pegasys app parser as a part of which, Existing CPP based SDN Split parser was converted to the java based parser which was using ActiveMQ library. A sample message was then sent to Pegasys input queue {{PEGASYS.OUT.UAT}} And based on message content, rewritten parser running with java analyzed the content and routed the incoming message to one of the following output queues based on the content and rules defined: {noformat}parser.queue.star=PEGASYS.STAR.UAT parser.queue.mng=PEGASYS.MNG.UAT parser.queue.cimp=PEGASYS.CIMP.UAT parser.queue.sip=PEGASYS.SIP.OUT parser.queue.icargo=PEGASYS.ICARGO.UAT parser.queue.err=MNG.PEGASYS.ERR.UAT{noformat} | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | Done | 2025-11-15 14:39
AM20-176 | SMS Alerting Implementation | Done | 6 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1785825 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-18 12:52 | 2025-10-31 17:22 |  | 2025-10-31 17:22 |  | 0 | As a cloud product owner I want application and platform alerts to be delivered via SMS from a dedicated long code so that on call engineers and stakeholders receive time critical notifications Acceptance criteria: *E2E SMS on P1/P2* - Given the cloudWatch alarm changes to ALARM with severity ðŸ˜›1 when the alarm event is routed via EventBridge to the SNS topic than all active on-call receipients for the app+env recieve an SMS within 60s and message body includes app, env, alarm name, severity, runbook link and ACK instruction ¦¦*Severity*¦¦*objective signals*¦¦*examples*¦¦ ¦P1 - Critical, user impact¦harsh outage, data loss, security incdences¦API 5xx>10% 5m in production, RDS storage<5% 10m. certificate expiry < 3days, guard duty, unauthrized access¦ ¦P2 - Degradation,Urgent¦performance, throughput, redundancy lost,¦EKS node group<N healthy, ALB healthy, RDS IOPS deviation, CPU utilization, disk innode,¦ ¦P3 - Action soon¦Capacity/Ops issues, repeated flaps¦log patterns,¦ ¦P4 - Informational¦chnages , warnings, failures without user impact¦Daily back ok, lamda changes, deloyment success¦ *Delivery logging and metrics* - Given SMS messages are sent when carriers return delivery statuses then statuses are captured in CloudWatch logs and S3 and dashboards show sends, successes, failures, per country breakdown *Retry and escalations ( in the event of SMS failure)* - Given a send gets a transient failure when the system retries with backoff( up to 3 times in 5 minutes) then on persistent failure an escalation SMS is triggered to secondary contacts and a ticket is created in ServiceNow with failure details *Deduplication and storm control* - Given multiple identical alarms fire within 5 minutes when routing occurs then recipients receive at most one SMS per unique alarm/signature per 5 minute window and a summary SMS is sent after 15 minutes if >5 deduped alerts occurred. |  | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Initially worked on gathering additional information regarding message size limit for SMS in case of long text message sent. Initiated questionaire in AWS community portal to get in depth costing based on message length , worked on restructuring SMS notification to avoid additional costing for SMS. Discussed with Gayaz to get company information to initiate dedicated long code generation (currently using shared pool of origination identities). Worked on updating existing Lambda jobs to support sending SMS alerts and working on fetching amount spent in SMS notification to apply a cost guard rail and send only priority message in case of spent exceeds 80 % limit. ;31/Oct/25 1:17 PM;17cb9418-1850-4923-932b-7098ec51b6bb;115200 | [5 empty] | 86400 | 0 | 115200 | 1.33 | 86400 | 0 | 115200 | [11 empty] | AM20-253 | 31/Oct/25 1:09 PM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251031-110848.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176021 | 31/Oct/25 1:09 PM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251031-110913.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176022 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@78a09d31 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h703: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 |  | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | [65 empty] | YES | YES | 2025-10-03 06:27 | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | [12 empty] | 03/Oct/25 8:26 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Awaiting Go ahead from Husein/Eugene to proceed with this requirement | 14/Oct/25 8:22 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Sign off received to go ahead with SMS alerting requirement | 20/Oct/25 7:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;spill over reason- need company contact details and other relevant information to generate a request for long code on AWS support. | 24/Oct/25 8:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Requested for additional details from Gayaz as asked by AWS support for proceeding with Long code generation request and account spent limit increase. | 30/Oct/25 11:34 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;we have done changes in lambda script to support sending sms for error pattern alerts , test sms was successfully sent to Gayaz. Working on adding similar support for other alarm types as well, also working on implementing other requirements like sending only p1 message if budget is crossed over 80% and opt-in/opt-out functionality. | 31/Oct/25 12:11 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Issue split into: ¦AM20-253¦SMS Alerting implementation- Opt in/Opt out¦ | 31/Oct/25 1:10 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We have configured SMS based alerts for Flysaa Backend Alarms and assigned Priorities to the alerts based on above table. *Error Patterns in Pod logs* : P3 *Api HealthCheck Fail for pod* : P1 *CPU consumption or Memory consumption or Container restart alarm* : P2 For RDS: *When RDS instance is down* : P1 *When RDS cert expiry is < 30 days* : P1 (We check cert expiry daily but SMS notification will only be sent when < 30 days are remaining ) *RDS metrics alarms like CPU utilization, read/write iops* : P2 *RDS metrics when available free space is less than 10 %* : P1 Please find attached screenshots for SMS sent to Gayaz !image-20251031-110848.png¦width=537,alt="image-20251031-110848.png"! !image-20251031-110913.png¦width=463,alt="image-20251031-110913.png"! | 31/Oct/25 5:22 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;SMS sent to Customer and mail confirmation received | [22 empty] | Done | 2025-10-31 17:22
AM20-175 | Monitor and Alert on daily Cloudwatch log costs | Done |  | Sprint 14 | 2025-09-15 | 2025-09-26 | Aravind Raj | Medium | 1781403 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-15 08:34 | 2025-09-22 08:46 |  |  |  | 0 | As a clous infrastructure product owner I want to assess the daily CloudWatch logs costs and trigger an alarm if cost exceeds defined threshold so that I can detect excessive log injestion/retention and take timely action to optimize costs Use SAA-Audit account, account id : 300204747992 for implementation Acceptance Criteria: # *Daily Cost Assessment* System must fetch daily CloudWatch cost usage ( log storage + injestion + insight queries) from AWS cost explorer or Cloud watch Metrices Must provide breakdown by account and log group # *Threshold Configuration* Ability to set daily cost thresholds Alarm must be raised if daily costs exceed threshold # *Alerting Mechanism* Alerts should be sent via SNS->integrated notification channels (Email/ServiceNow) Alarm must be included impacted account, service (CloudWatch Logs) cost for the day and % deviation from baseline # *Historical Trend* Dashboard view showing last 7/30 days of CloudWatch daily cost trends Helps identify if cost spike in an anamaly or a graduate increase # *Operational Validations* Test run with synthetic high volume logging to validate alarm triggers Verify no false positives when daily costs are with threshold |  | Aravind Raj | Onkar Mirajkar | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fad0cf8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0gp97: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-17 05:55 | [13 empty] | 17/Sep/25 7:55 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Threshold Configuration -----Done Ability to set daily cost thresholds Alarm must be raised if daily costs exceed threshold Alerting Mechanism ----Done IF cost usage is above 2$ email will be trigeered | 17/Sep/25 7:56 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Dashboard view is pending | 19/Sep/25 8:18 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Dashboard is created and demo given to Yashwant. | 22/Sep/25 8:46 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have seen a short demo on friday itself, the dashboard and notification looks fine. | [23 empty] | 1772224 | AM20-164 | AirNavX ¦¦ Budget Management Configuration | Done | 2025-09-22 08:46
AM20-174 | CloudWatch provisioning and monitoring using terraform | Done | 6 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1774966 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-08 07:00 | 2025-11-15 14:38 |  | 2025-11-15 14:38 |  | 0 | As DevOps expert I want to develop terraform script for cloudwatch (cloudwatch log groups, metric namespaces, KMS encryption, retention and resource policies)provisioning and configure for EC2 monitoring so that we get reliable metrics,logs, dashboard and alerts across accounts with least privilege access and consistent tagging Acceptance criteria: log groups for ec2/system,ec2/app and ec2/audit exist per environment with kms_key_id and retention resources policies allow PutLogEvents from target accounts/roles only Default dashboards foldering/naming convention: <env>-<team>-<service>-<components> All resources have tags: environment, onwer,DataClass,Criticality Acceptance Criteria: |  | Harsh Chandra | Sanket Kale | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [13 empty] | 02/Nov/25 11:38 AM;17f3b5ec-bc2f-4bb8-86c7-0ecec05034a7;Screenshot 2025-11-02 145537.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176258 | 02/Nov/25 11:38 AM;17f3b5ec-bc2f-4bb8-86c7-0ecec05034a7;Screenshot 2025-11-02 145614.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176257 | 02/Nov/25 11:38 AM;17f3b5ec-bc2f-4bb8-86c7-0ecec05034a7;Screenshot 2025-11-02 150111.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176256 | 02/Nov/25 11:38 AM;17f3b5ec-bc2f-4bb8-86c7-0ecec05034a7;Screenshot 2025-11-02 150756.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176259 | 17/Oct/25 11:23 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;image-20251017-092300.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1169672 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@44aed3e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0g0e3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | [94 empty] | 3_*:*_2_*:*_1247979274_*¦*_10041_*:*_1_*:*_3891257986_*¦*_13940_*:*_2_*:*_6436963 |  | 3_*:*_2_*:*_1247979274_*¦*_10041_*:*_1_*:*_3891257986_*¦*_13940_*:*_2_*:*_6436963 | 3_*:*_2_*:*_1247979274_*¦*_10041_*:*_1_*:*_3891257986_*¦*_13940_*:*_2_*:*_6436963 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_1247979274_*¦*_10041_*:*_1_*:*_3891257986_*¦*_13940_*:*_2_*:*_6436963 | [65 empty] | YES | YES | 2025-10-17 09:16 | 3_*:*_2_*:*_1247979274_*¦*_10041_*:*_1_*:*_3891257986_*¦*_13940_*:*_2_*:*_6436963 | [12 empty] | 17/Oct/25 11:15 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Will be taken up in Sprint 17 because assigned resource was working on other priority requirements. | 17/Oct/25 11:23 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Observability solution model !image-20251017-092300.png¦width=661,alt="image-20251017-092300.png"! | 29/Oct/25 8:16 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;EC2 creation and log group creation code is completed. Working on Monitoring and Alerting | 31/Oct/25 5:34 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;No comments/evidence added to allow me to close US | 02/Nov/25 11:44 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Created the all resources in sandbox account ec2 instance: Flysaa-sbox-AppServer001 System Log group: /ec2/Flysaa-sbox-AppServer001/i-002836beef3512824-syslog App log group: /ec2/Flysaa-sbox-AppServer001/app/i-002836beef3512824-nginx-error Cloudwatch Alarm: flysaa-sbox-observability-alerts I have attached the screenshots above in the attachements | 15/Nov/25 2:38 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-15 14:38
AM20-173 | Trellix integration with PROS | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773956 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-05 06:33 | 2025-10-30 08:26 |  | 2025-10-30 08:26 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan PROS workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in PROS server * Trellix is able to access PROS account successfully and perform scanning |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 29/Oct/25 8:43 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-064238.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174346 | 29/Oct/25 8:53 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-065302.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174368 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bb75c16 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [65 empty] | YES | YES | 2025-09-24 07:35 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [12 empty] | 24/Sep/25 9:34 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;To get this US completed we have to complete Building up the EC2 instance and then only the Trellix agent reconfiguration will get done to scan the PROS workloads for any vulnerabilities, malware reporting. | 03/Oct/25 9:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* Pros connectivity issue is still going and its pending from there end. Also, the EC2 instance creation is yet not started so thatâ€™s why this US will go to the spill over to next sprint. | 17/Oct/25 11:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* The EC2 instance creation is just completed on the last day of the sprint. Thatâ€™s why the US was not able to complete in this sprint now after completion of the EC2 instances we can follow up with sinjun and get the update regarding the Trellix integration with PROS account. | 29/Oct/25 8:26 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation from Sinjun that the Trellix integration is done for PROS account servers. Have shared the email with sinjun. | 29/Oct/25 8:43 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-064238.png¦width=629,alt="image-20251029-064238.png"! Attaching his confirmation which i got over teams | 29/Oct/25 8:53 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-065302.png¦width=629,alt="image-20251029-065302.png"! | 30/Oct/25 8:26 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-30 08:26
AM20-172 | PROS ¦¦ Monitoring and Alerting Servers post migration | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773954 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-05 06:13 | 2025-10-31 17:21 |  | 2025-10-31 17:21 |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if PROS service is stopped |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@37ad6335 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 |  | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [65 empty] | YES | YES | 2025-10-31 12:27 | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [12 empty] | 31/Oct/25 2:26 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Post Migration: I have installed the SSM Agent for all the PROS prod instances. Configured CloudWatch Agent. Created Systems Manager Parameters for the CloudWatch Agent to fetch the config. Custom Metrics part completed. Monitoring done. Alerts generated for the metrics. | 31/Oct/25 5:20 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-10-31 17:21
AM20-171 | PROS¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773953 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-05 06:09 | 2025-10-17 07:16 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4ce03565 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:04 | [13 empty] | 24/Sep/25 8:04 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS migration agent comms has been implemented. SAA = REQ0056503 (CHG0067695) CSOC = CHR0027812 | 25/Sep/25 5:24 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still CSOC under approval, also we have identified as some miss match in Agent Comms. I have updated and shared to Wanda for CSOC updation. | 06/Oct/25 8:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over - Comms implementation delayed from SAA, hence will be spilled over and worked upon in subsequent sprint | 09/Oct/25 4:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration agent comms has been implemented and agent has been installed n all 3 PROS servers, Created test instance and handover to customer for testing. | 17/Oct/25 7:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:16
AM20-170 | PROS ¦¦ Cutover | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773952 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-05 06:08 | 2025-10-31 18:04 |  | 2025-10-31 18:04 |  | 0 | As AWS expert I would be performing the cutover for PROS application. Acceptance Criteria: * Replication from on-prem is successfully stopped using API calls * Back up of PROS VDC Server * Monitoring disable - VDC Server * Shutting down Informatica application in VDC * Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining PROS Server to the AD * MAT Testing completed successfully by SAA * Deploy the Test instance with the network components * Deploy cutover actual instance * Wait for the launch instance check the status checks * configure required SSM and CW agent |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 31/Oct/25 11:09 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;RE_ PROS Server Cutover - Migratiom.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175913 | 28/Oct/25 11:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251028-095312.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174005 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4900724c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwr7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 |  | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | [65 empty] | YES | YES | 2025-10-03 07:24 | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | [12 empty] | 03/Oct/25 9:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Only after the server migration we would be able to do cutover so this US will be blocked. | 17/Oct/25 11:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cut over is planned on 27th Oct as per client request, since this will be spillover. | 28/Oct/25 11:52 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SSM agent installation and cloud watch installation is completed followed by domain join. | 28/Oct/25 11:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have sent a mail to application owner on the confirmation for closing cutover, upon receiving same will close this US. !image-20251028-095312.png¦width=423,alt="image-20251028-095312.png"! | 28/Oct/25 5:31 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;client facing some FTP issue, after it resolved this US can be closed | 31/Oct/25 11:08 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Cutover completed as per the email from Pieter Scheepers ( app owner)- email attached | 31/Oct/25 6:04 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [23 empty] | Done | 2025-10-31 18:04
AM20-169 | PROS ¦¦ database restoration | Done | 0 | Sprint 14 | 2025-09-15 | 2025-09-26 | Fahim Mulla | Medium | 1773951 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:b2e2abba-5056-4f1e-a865-78841b29ab10 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-05 05:57 | 2025-09-19 09:50 |  |  |  | 0 | As a DBA I want to restore a MYSQL database hosted on AWS from a backup so that I can recover from failures, refresh lower environments or validate DR readiness Acceptance Criteria: * DBA can restore MYSQL from snapshot or PITE in same region * Restore DB uses correct subnet group,SG, Parameter groups * KMS encryption applied to restored DB * PITR restores to chosen timestamp with +-1 minaccuracy * Post restore DBA validates - schema exists, table count match, last transaction ID mateched source (if PITR) * Monitoring enabled (CPUUtilization, FreeStorageSpace, DatabaseConnections) * Access restricted by IAM and SG rules * All restore actions are logged in CloudTrail |  | Fahim Mulla | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:b2e2abba-5056-4f1e-a865-78841b29ab10 | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 17/Sep/25 7:53 AM;7f828717-d8f6-4eae-b82a-b6ba0cff270e;RE minutes SAA II Alignment on PROS connectivity pre-requisites.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1154264 | 19/Sep/25 9:49 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;minutes_ SAA II Alignment on PROS connectivity pre-requisites.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1156090 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2ac02e42 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-16 11:36 | [13 empty] | 16/Sep/25 1:36 PM;712020:b2e2abba-5056-4f1e-a865-78841b29ab10;As per the discussion Final Backup Done and stored in S3 via NetBackup in VDC. To be kept as is. This database will remain in VDC | 19/Sep/25 9:49 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Closing this ticket as PROS DB will now stay on prem. Refer attached email | [25 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-09-19 09:50
AM20-168 | PROS ¦¦ setup and validate SG and NACL | Done | 2 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1773949 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-05 05:39 | 2025-10-17 07:14 |  |  |  | 0 | As AWS network expert I would like to setup the security group and NACL for PROS so that access for Pros allow secure access to allow communication with its services while ensureing access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for PROSor related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1df9f068 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwq3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-25 15:31 | [13 empty] | 25/Sep/25 5:31 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SG and NACL setup has been completed, application ports relevant port need to be configured, this will be ready once test server setup process ready. | 09/Oct/25 4:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SG & NACL has been configured and handed over to customer. | 17/Oct/25 7:14 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-10-17 07:14
AM20-167 | PROS ¦¦ Establish connectivity port opening and firewall connectivity | Done | 3 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1773948 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-05 05:34 | 2025-09-22 08:50 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2f2b180d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwpv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-12 06:14 | [13 empty] | 12/Sep/25 8:14 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;On 11th the app owner Pieter has confirmed as we can go with single subnet for all 3 servers, Now i have initiated comms preparation. | 19/Sep/25 3:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been sent (16th Sep) and validated by Pieter on on 17th Sep 2025, again send mail to Pieter asking about any additional SITA side flows required or not. | 19/Sep/25 4:12 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Received feedback from Pieter and prepared final comms for SITA/VDC. Sent for LIFT and CSOC submiss towards for implementation. | 19/Sep/25 4:14 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Hence the action with SAA side, hence i am closing this Story. | [26 empty] | Done | 2025-09-22 08:50
AM20-166 | AirNavX ¦¦ Port opening, NACL and SG group Whitelisting | Done | 5 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772278 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-03 10:18 | 2025-09-22 08:50 |  |  |  | 0 | As a cloud infrastructure engineer I want to provision NACL, Security groups and port whitelisting with validated connectivity so that the new application can be securly deployed in AWS with controlled access, compliance to security standards and verified communication paths Acceptance Criteria: * Security groups are created per application tier * required inbound and outbound rules are defined for each tier ( HTTPS: 443 inbound from ALB to web, DB port 3306 from App SG) * no overly permissive rules (0.0.0.0/0) NACL config: * Network ACL applied at subnet level with stateless allow/deny rules for required application port * Both inbound and outbound NACL rules are explicitly documented * Default NACLs are not used Whitelisting: * External IP range for trusted users/ partners are whitelisted * Whitelisting rules are implemented at the SG/NACL level based on environment needs * Documentation include source IPs, purpose and without expiry date Connectivity validations: * E2E connectivity test performed APP--DBflow, External user ---Application endpoint (via ALB/API Gateway) * Connectivity validated using tools like telnet, nc and AWS connectivity tests * Validated evidence captured in the deployment checklist Security and compliance: * All configurations follow least privilege principle * Changes are auditable in CloudTrail with tagging (App, Env, Owner, ChangeID) Deliverable: * SG & NACL rule tables (port, protocol, source/destination) * Whitelist IP registry with owners and validity * Validation test results signed off by infra + security team |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4a97e1ad | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq8r: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-19 14:18 | [13 empty] | 19/Sep/25 4:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared and implemented. with the help of LIFT and CSOC. VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 19/Sep/25 4:19 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Bhavesh we have changed subnet from /27 to /28 and updated comms and shared Sita for implementation. | 19/Sep/25 4:21 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on Albert SITA has been implemented comms via subnet level. according to management i am closing this request and i will working on validation part with new request. | 19/Sep/25 4:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on Albert SITA has been implemented comms via subnet level. according to management i am closing this request and i will working on validation part with new request. | [26 empty] | Done | 2025-09-22 08:50
AM20-165 | Informatica Server ¦¦ Budget Management Configuration | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772227 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-03 09:52 | 2025-09-22 08:50 |  |  |  | 0 | As AWS expert I would like to configure Informatica budget management and alerts so that stakeholders gets the frequent notifications on budgets and alerts if the budget crosses threshold Acceptance Criteria: * Budget management for Informatica is configured successfully * Alerts triggered if the budget crosses 80%, 85% and 90% of Threshold |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [10 empty] | AM20-164 |  |  | 18/Sep/25 10:44 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250918-084430.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1155401 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3d312d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq0n: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-09 06:44 | [13 empty] | 09/Sep/25 8:43 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Today will start creating the budget on the management account for Informatica Dev and Prod environment. | 09/Sep/25 11:00 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created the budget for Informatica Dev and Prod in Payers management account with threshold as 80%,85% & 90%. Now, will add the account in the Lambda function and also will add app. owner mail id & will test it. | 15/Sep/25 11:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have added the Account name and application owner email ids in lambda function also tested the budget alerting and we are successfully getting the alerts for budget management. | 17/Sep/25 9:13 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8; !image-20250918-084430.png¦width=852,height=577,alt="image-20250918-084430.png"! Attaching the evidence screenshot that the budget we have created are able to get the emails and details if it exceeded the threshold value 85%. | 18/Sep/25 2:46 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Demo was given to Yashwant but want Aravind to review it. | 22/Sep/25 8:36 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;the threshold of budget should be calculated based on the all the resources involved in the architecture and LLD, though its modifiable, i would suggest to update the value in firsthand itslef. | [24 empty] | Done | 2025-09-22 08:50
AM20-164 | AirNavX ¦¦ Budget Management Configuration | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772224 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-03 09:51 | 2025-09-22 08:50 |  |  |  | 0 | As AWS expert I would like to configure AirNavX budget management and alerts so that stakeholders gets the frequent notifications on budgets and alerts if the budget crosses threshold Acceptance Criteria: * Budget management for AirNavX is configured successfully * Alerts triggered if the budget crosses 80%, 85% and 90% of Threshold |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [9 empty] | AM20-165 |  |  |  | 18/Sep/25 10:42 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250918-084042.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1155392 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7cf7b049 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq0j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-09 06:42 | [13 empty] | 09/Sep/25 8:42 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created the Budget on management account for Airnavx now will be adding the account and application owner mail idâ€™s in the lambda function. | 09/Sep/25 11:01 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have set the threshold value to 80%, 85% & 90% now will add the account details and application owner mail id in the lambda function. | 15/Sep/25 11:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have added the Account name and application owner email ids in lambda function also tested the budget alerting and we are successfully getting the alerts for budget management. | 18/Sep/25 10:42 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8; !image-20250918-084042.png¦width=860,height=569,alt="image-20250918-084042.png"! Attached is the screenshot as an evidence that we are getting the alert email if the threshold value exceeds more than the utilized budget value. | 18/Sep/25 2:45 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Demo was given to Yashwant today still wants Aravind to review the same. | 22/Sep/25 8:36 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;the threshold of budget should be calculated based on the all the resources involved in the architecture and LLD, though its modifiable, i would suggest to update the value in firsthand itself. | [24 empty] | Done | 2025-09-22 08:50
AM20-163 | AirNavX ¦¦ DR Setup and Backup | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772205 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-03 09:43 | 2025-11-15 14:39 |  | 2025-11-15 14:39 |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Informatica-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;14/Nov/25 8:19 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;230400 | ;14/Nov/25 8:20 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;28800 | ;14/Nov/25 3:37 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;57600 |  |  |  | 57600 | 0 | 316800 | 5.5 | 57600 | 0 | 316800 | [12 empty] | 14/Nov/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251114-061617.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1183951 | 14/Nov/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251114-061715.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1183950 | 14/Nov/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251114-061854.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1183952 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3d404a54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 18 | [95 empty] | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 |  | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | [65 empty] | YES | YES | 2025-09-08 07:57 | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | [12 empty] | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 17/Oct/25 11:18 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over reason - Blocked due to ongoing app installation issues, currently worked upon by app owner; post which this story will be progressed in subsequent sprint | 14/Nov/25 8:18 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;AirNavX DR setup completed as well as daily weekly backup has been configured the same working fine. Backup relvent: !image-20251114-061617.png¦width=612,alt="image-20251114-061617.png"! !image-20251114-061715.png¦width=589,alt="image-20251114-061715.png"! DR: !image-20251114-061854.png¦width=597,alt="image-20251114-061854.png"! | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-15 14:39
AM20-162 | Trellix integration with AirnavX | Done | 1 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-03 09:40 | 2025-11-12 08:22 |  | 2025-11-12 08:22 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan AirNavX workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in AirNavX server * Trellix is able to access AirnavX account successfully and perform scanning |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 05/Nov/25 3:41 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ Trellix scanning status for New AWS AirNavV servers.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1178115 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f4c84b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 18 | [95 empty] | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [65 empty] | YES | YES | 2025-09-08 07:56 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [12 empty] | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 30/Sep/25 7:40 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working with Sinjun for trellix installation on these 2 servers. | 06/Oct/25 8:39 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Working with Sinjun for Trellix installation, hence will be spilled over | 09/Oct/25 4:29 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Sinjun Albert is going to install Trellix and he will confirm once integration done. | 17/Oct/25 11:17 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over reason - Blocked due to ongoing app installation issues, currently worked upon by app owner; post which this story will be progressed in subsequent sprint | 05/Nov/25 3:41 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Trellix software installed on New AWS AirNavX servers. All AirNavX servers able to discover from Trellix admin server and same has been confirmed by Sinjun. Attaching reference for support. [^RE_ Trellix scanning status for New AWS AirNavV servers.msg] | 12/Nov/25 8:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | Done | 2025-11-12 08:22
AM20-161 | AirNavX ¦¦ Monitoring and Alert solution | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772183 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-09-03 09:35 | 2025-10-06 07:58 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if AirNavX server is stopped |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 03/Oct/25 9:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251003-073517.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1162022 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c7985 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-09 06:37 | [13 empty] | 09/Sep/25 8:37 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;We will start the US after getting the EC2 instance and application deployed on the AWS environment thatâ€™s why the US is blocked. | 22/Sep/25 10:01 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Spill Over : Due to connectivity issue going on and EC2 instance deployement pending go ahead from customer side. this story goes in spill over in this sprint. | 29/Sep/25 6:54 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Ec2 instances has been created on Friday so from today i will start the to set up the cloud metrics alerts. | 29/Sep/25 3:50 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;CPU utilization alert and dashboard has been created in Audit account. Now will be creating the network I/O and status check failed alerts. | 30/Sep/25 12:41 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The server status check failed alerts has been created and added to dashboard also we have added the network I/O to the dashboard in the Audit account. --*-Done* *Pending* : For disk and memory need to install the cloud watch agent and custom metrics need to be added on all AirnavX servers. Then only will be able to add the alerting for the Memory and disk metrics to dashboard. | 03/Oct/25 9:36 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251003-073517.png¦width=1178,height=647,alt="image-20251003-073517.png"! Created all alerts and dashboard as per the acceptance criteria and also used agreed naming and threshold value by the customer itself. | 03/Oct/25 12:42 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have modified the alarm for disk and memory configuration, other alarm are looking good. | [23 empty] | Done | 2025-10-06 07:58
AM20-159 | Informatica Server - Cutover for Prod | Done |  | Sprint 13 | 2025-09-01 | 2025-09-12 | Aravind Raj | Medium | 1768422 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-28 15:13 | 2025-09-30 18:36 |  |  |  | 0 |  |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;30/Sep/25 6:36 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;43200 | [5 empty] | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [12 empty] | 30/Sep/25 6:35 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250930-163551.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1160875 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7b96ec0c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fb2j: | [167 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 07:23 | [13 empty] | 05/Sep/25 9:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Informatica Test server is launched and trying to fix RDP connectivity issue. Only after the test instance confirmation we will be able to deploy cutover, so this will be a spillover. | 30/Sep/25 6:35 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250930-163551.png¦width=669,height=443,alt="image-20250930-163551.png"! | [25 empty] | 1751440 | AM20-140 | Informatica Server ¦¦ Cutover | Done | 2025-09-30 18:36
AM20-158 | Informatica Server - Cutover for Dev | Done |  | Sprint 13 | 2025-09-01 | 2025-09-12 | Satya Varanasi | Medium | 1768419 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-28 15:12 | 2025-10-01 08:24 |  |  |  | 0 |  |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4db6c5dd | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fb23: | [167 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-08 07:54 | [13 empty] | 08/Sep/25 9:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to be action after connectivity test, still connectivity having some issues from SITA compass and SAP raise side. | 30/Sep/25 7:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change has been approved, scheduled change today on 11:00 AM SAST. | 01/Oct/25 8:13 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica DEV server cutover has been completed and app owner and Wanda has been tested initial connectivity. Hence i am closing this Story. | [24 empty] | 1751440 | AM20-140 | Informatica Server ¦¦ Cutover | Done | 2025-10-01 08:24
AM20-157 | Informatica ¦¦ Custom application Metrics | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1761210 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-21 10:44 | 2025-10-06 07:58 |  |  |  | 0 | # Configure & install cw agent. # Refer email for metrics to be monitored. # Create alerts as per approval in the email. |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@407cb340 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0elc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-17 06:01 | [13 empty] | 17/Sep/25 8:01 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Informatica Accounts (Dev & Prod) cutover is yet to be done. Actual workloads are yet to be migrated. Hence, blocked. | 01/Oct/25 8:24 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Configure & install cw agent - Done # Refer email for metrics to be monitored - Done # Create alerts as per approval in the email - Done | [28 empty] | Done | 2025-10-06 07:58
AM20-156 | Airnavx ¦¦ Lift Request creation | Done | 1 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | Medium | 1761196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-21 10:37 | 2025-09-08 06:34 |  |  |  | 0 | As Network expert I have to raise Lift request so that Network Firewall implementation CSOC request for port, routing connectivity can be established with VDC Acceptance criteria: Post Lift request, firewall, port and routing connectivity is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@70851109 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0el9v: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 08:42 | [13 empty] | 05/Sep/25 10:41 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;AirNavX Lift request has been created and completed. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Network team confirmed as routing in place hence no routing required. CSOC and under implementation process from VDC/SITA side. | 08/Sep/25 6:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-09-08 06:34
AM20-155 | Airnavx ¦¦ EC2 Creation using terraform code | Cancelled | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satyabrata Sahoo | Medium | 1760710 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:4b8d8093-596d-4394-a074-4a9a9636f86f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-21 07:50 | 2026-01-04 09:03 |  |  |  | 0 | As AWS Expert I would like to provision EC2 using terraform so that I can handover to SAA for Airnavx installation Acceptance Criteria: EC2 provisioned successfully using approved AMI Tags applied automatically Instance must have SSM agent installed SSH is enabled only via bastion host Guardduty must detect and monitor instance Instance must publish logs to CloudWatch EC2 must register with org monitoring/alerting |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b9d343f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejt7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | [103 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 06:38 | [13 empty] | 05/Sep/25 8:37 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Closing this as this is a duplicate of [https://vodacom.atlassian.net/browse/AM20-131¦https://vodacom.atlassian.net/browse/AM20-131¦smart-link], hence closing the ticket | [26 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-05 08:38
AM20-154 | PROS ¦¦ Pre-requisite of Network components | Done | 3 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1760705 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-21 07:37 | 2025-09-19 11:21 |  |  |  | 0 | As AWS expert I would like to create/configuration required network pre-requisite so that later on EC2 instance can be provisioned in PROS account Acceptance criteria: The parent account must share private subnet with PROS account using AWS RAM the sharing also includes route tables The IAM user/role in the child account Security group are created in shared VPC NACL are attached at the subnet level |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [13 empty] | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152123.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153300 | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152137.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153299 | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152151.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153301 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3397a03b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejsb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-28 06:31 | [13 empty] | 28/Aug/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;I am looking final LLD based on that i will created required Subnets against platform ready ness. | 12/Sep/25 8:12 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Pieter, all servers can be migrated under single subnet, and there is no requirement for DB server. I have initiated the Platform readyness. | 15/Sep/25 5:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS application platform/network setup has been completed. ¦PROS¦3¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.192/28¦10.40.1.192 - 10.40.1.207¦10.40.1.193 - 10.40.1.206¦14¦/28¦AZ1¦Â ¦ ¦PROS(DR)¦3¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.224/28¦10.40.1.224 - 10.40.1.239¦10.40.1.225 - 10.40.1.238¦14¦/28¦Â ¦AZ2¦ !image-20250915-152123.png¦width=405,height=211,alt="image-20250915-152123.png"! !image-20250915-152137.png¦width=406,height=166,alt="image-20250915-152137.png"! !image-20250915-152151.png¦width=408,height=117,alt="image-20250915-152151.png"! | 16/Sep/25 4:23 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;validated internet is working with the subnet. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:21
AM20-153 | Nexio ¦¦ Alarm Solution | Done | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1760700 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-21 07:25 | 2025-09-08 06:33 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if Nexio server is stopped |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 02/Sep/25 4:23 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;Trellix alarms for CPU,MEMORY,DISK,STATUSFAILEDCHECK.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1146818 | 05/Sep/25 1:00 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image (4).png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148618 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@be8ff55 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejrn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 12:34 | [13 empty] | 25/Aug/25 2:33 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;* CloudWatch metrics are enabled for CPU, memory, disc, network I/O â€“ *Done* * Dashboards are created to monitor key services also alarms have been created â€“ *Done* | 28/Aug/25 2:10 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the update from sinjun regarding the alerts so will be creating the alerts as per finalized naming and severity sheet for Nexio av | 01/Sep/25 4:20 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Created few alarms for FLYSAA CPU & Memory and StatusCheckFailed as per the finalized naming from sinjun & bhavish end. Other alarms will be created after reviewing the created ones. | 02/Sep/25 4:23 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!Trellix alarms for CPU,MEMORY,DISK,STATUSFAILEDCHECK.png¦width=947,height=324,alt="Trellix alarms for CPU,MEMORY,DISK,STATUSFAILEDCHECK.png"! Attached the screenshot of Cloud watch alarms that i created as per the finalized naming ,threshold and datapoints. Also, Dashboard has been created to monitor key services & SNS alert will be triggered if the Nexioav EC2 server status goes down or stopped. | 03/Sep/25 8:44 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Iâ€™m putting the US in review. | 05/Sep/25 8:41 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Awaiting the Review from Aravind side then only the US will get closed. | 05/Sep/25 1:00 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;the Alarms are getting triggering to Service Now properly attaching the screenshot evidence which i got from Priyanka for the reference. !image (4).png¦width=1090,height=573,alt="image (4).png"! | 08/Sep/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-09-08 06:33
AM20-152 | MQ ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Blocked | 0 | Sprint 16 | 2025-10-13 | 2025-10-24 | Satya Varanasi | Medium | 1758329 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-18 16:44 | 2025-10-31 11:06 |  |  |  | 0 |  |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4544ef36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g02 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-17 09:19 | [13 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | [29 empty] | To Do | 2025-08-18 16:44
AM20-149 | Informatica ¦¦ Port opening, NACL and SG group Whitelisting | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1755982 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-14 10:09 | 2025-09-08 06:34 |  |  |  | 0 |  |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 28800 |  | 0 | 57600 | 28800 | [13 empty] | 05/Sep/25 10:50 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250905-084935.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148455 | 05/Sep/25 10:50 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250905-084949.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148454 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@40ed7680 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0e0p7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-26 11:38 | [13 empty] | 26/Aug/25 1:37 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will be actioned after network and firewall setup implementation. So kept as blocked. | 28/Aug/25 8:34 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Firewall rules implementation has been completed. LiFT = CHG0067488 CSOC = CHR0026691 Still required validation, this will be validated after test instance available. | 01/Sep/25 8:05 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev side NACl/SG has been completed. Prod side basic setup done for domain join and remaining will be implemented today. | 04/Sep/25 8:23 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev/Prod side all ports has been whitelisted. Assigned servers to app team for testing. VDC side connectivity has been tested and working fine(Wanda has been confirmed). From Sita side customer needed FortiGate VPN access towards connecting to informatica subnets, Pieter has been requested user access and it is under approval process. | 05/Sep/25 10:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Currently SITA side testing going, EWS servers side, VDC side connectivity done. Connectivity testing point of view we will work on new user story, as per process implementation has been completed AWS side. !image-20250905-084935.png¦width=734,height=384,alt="image-20250905-084935.png"! !image-20250905-084949.png¦width=734,height=384,alt="image-20250905-084949.png"! | 08/Sep/25 6:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:34
AM20-148 | Informatica ¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1755978 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-14 10:07 | 2025-09-03 08:55 |  |  |  | 0 |  |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3237a818 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0e0or: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-26 11:39 | [13 empty] | 26/Aug/25 1:39 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Firewall rules implemented. Identified as connectivity not working. Initiated network troubleshooting call towards fixing. Identified as routing not configured. Requested LIFT for approval LIFT approval took 3days Monday CSOC request raised and routing has ben implemented. Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 28/Aug/25 8:18 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested connectivity from informatica Prod/Dev env. Initially Network team not configured Routing after new Lift and CSOC request issue got resolved. Reference Lift & CSOC details: Routing: # CSOC:CHR0026807 # LIFT:CHG0067489 App comms: # LiFT = CHG0067488 # CSOC = CHR0026691 AWS agent Comms: CSOC logged CHR0023951 LiFT logged CHG0066992 (RITM0051174) | 01/Sep/25 8:03 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested. Based on comms we have successfully completed agent installation for prod/Dev and setup test instance for the same. Hence sending request for closer. | 03/Sep/25 8:55 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-147 | TM1 ¦¦ SSM provisioning and CloudWatch Agent with cutover instance | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1752616 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-11 14:57 | 2025-08-25 06:33 |  |  |  | 0 | As AWS expert, I would like to provision SSM and Cloudwatch on TM1 cutover instance Acceotance criteria: SSM instance and Cloudwatch instance is successfully provisioned |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Aug/25 8:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Aug/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@777f120 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dnlf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-13 06:17 | [13 empty] | 13/Aug/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cloud watch agent setup is completed, will configure the config.json file to fetch relevant server metrics and application metrics. | 13/Aug/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;after cloud watch configuration will start working on setting up SSM agent. | 14/Aug/25 8:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SSM agent installation is success upon stopping MacAfee and excluding from Trellix service. | 25/Aug/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 06:33
AM20-146 | Backup using lifecycle management by Terraform | Done | 0 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sanket Kale | Medium | 1752552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-11 14:28 | 2025-08-25 08:52 |  |  |  | 0 |  |  | Sanket Kale | [5 empty] | 712020:91948faf-1676-4820-bf6b-d50a7992943e | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4eaa1670 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dndf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:52 | [13 empty] | 25/Aug/25 8:52 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;As discussed with Yashwant and Sankalp this is no more require to implement. So closing it. | [26 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 08:52
AM20-145 | Informatica Server - Prod ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1752123 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-11 11:37 | 2025-09-05 10:29 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [10 empty] | AM20-136 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1d85433a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dlmz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-29 06:01 | [13 empty] | 29/Aug/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As it is handled by Arvind so assign to Arvind. | 05/Sep/25 9:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Agent installation is completed and replication followed by initial sync is completed too. | 05/Sep/25 10:29 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-05 10:29
AM20-144 | Informatica ¦¦ connectivity with Sales force, SAP Raise and EDW with test server | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1751445 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-11 05:57 | 2025-09-22 08:49 |  |  |  | 0 | As product Owner I would like to establish seamless connectivity between Informatica server and saleforce/Terradata so that the functinality does not break Acceptance Criteria: Informatica server connectivity established successfully with both Salesforce and Terradata TGW attachments, route tables and propogation allows reachability from Informatica to Salesforce and Terraform CIDR only Pripary path (DX or VPN) with secondary path tested, failover keeps sessions with degraded SLO Path MTU validated without fragmentation affection FTP data channels Passive FTP is enforced in AWS client Each FTP server exposes a fixed passive port range and publish it on the client Security groups: egress from AWS app to on-prem TCP21 the agreed passive range; return traffic allowed on-prem firewall allows the Aws static egress IP for TCP 21 and passive range FTP ALG/instapection behavour documented and validated Server authentication: username/password or TLS client auth are stored in secret manager no reliance on public IP, all traffic stays private via TGW Name resolution works both ways AWS can resolve slaesforce.corp and terradata.corp via resolver outbound rules, negative lookups dont hit public DNS TGW flow logs show accepted flows for TCP 21 and passive port Cloudwatch alarm on tunnel/BGP state, connection failures, repeated 4XX/%XX FTP responses, transfer timeouts Application log capture: server filename, size, checksum, duration, success/fail code, logs centralized Concurrency limited tuned so both servers can be hit in parallel without timeouts SLO defined (ex: sustainable throughput) and documented Checksum validated after transfer VPN/DX failover tested mid-transfer client resumes without manual intervention drift detection enabled |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5cf8baca | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ddx3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 06:25 | [13 empty] | 12/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Relevant flows has been added under application flows. Once implementation done i will work further. | 25/Aug/25 8:55 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Spill over Reason: Still comms under approval and implementation so this need to action after comms implementation. | 08/Sep/25 10:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;EDW side issue got fixed and working, right now SAP raise Sita compass side need to fix. I have scheduled troubleshooting call with relevant stake holder towards fixing. Still connectivity is not resolved, so i am not closed this story and it is moving to current sprint. | 12/Sep/25 8:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SAP Raise side SR has been logged, it will be implemented today. | 19/Sep/25 2:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SAP rise team has been configured NAC,SG and Routing but still connectivity issue persists, while checking traceroute, the request moving out to SAP Rise gateway but not troughing to shared VPC & vice versa. Further validation there is No routes advertised from DX side, engaged SAP team asking how SAP rise will be connected but they are not sure. Finally we have identified SAP rise is connecting via Direct connect, this was analyzed with the help of current working connection. | 19/Sep/25 2:49 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Notified network team to advertise complete shared VPC Prod and Dev vpc ranges to avoid future issues. 10.40.0.0/18 and 10.42.0.0/21. | 19/Sep/25 2:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network team has bee advertise the range to SAP rise direct connect, after advertise the connectivity has been fixed. | 19/Sep/25 2:51 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;ticket information: Ticket ID 1163452562 & 1163792032 AWS Connectivity - FIREWALL RULES REQUIRED FOR CUSTOMER INFORMATICA & RISE COMMUNICATION | 19/Sep/25 2:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;I am resolving the story as connectivity has been fixed. | [21 empty] | Done | 2025-09-22 08:49
AM20-143 | Trellix Integration with Informatica servers | Done | 1 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satya Varanasi | High | 1751443 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-11 05:37 | 2025-10-06 08:38 |  |  |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan TM1 workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in TM1 server * Trellix is able to access TM1 account successfully and perform scanning |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@34aaf28e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabm:i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:57 | [13 empty] | 25/Aug/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will required to action on after implementation. | 28/Aug/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will required to action on after implementation. | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 01/Oct/25 8:15 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Cutover and Trellix integration has been completed successful. | [23 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-06 08:38
AM20-142 | Informatica ¦¦ Monitoring Servers post migration | Done | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satya Varanasi | Medium | 1751442 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-11 05:32 | 2025-10-06 08:37 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if Informatica server service is stopped |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a6a11cb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabm: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:57 | [13 empty] | 25/Aug/25 8:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Spill over Reason: This need to action after migration. | 28/Aug/25 8:32 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 30/Sep/25 7:39 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Cutover change has been approved, once change completes we will close this ticket. | [26 empty] | Done | 2025-10-06 08:37
AM20-141 | Informatica Server ¦¦ Back up and DR | Done | 5 | Sprint 13 | 2025-09-01 | 2025-09-12 | Aravind Raj | Critical | 1751441 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-11 05:29 | 2025-10-13 18:32 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Informatica-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM h2. Confluence content |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;30/Sep/25 6:38 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;13/Oct/25 6:32 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;43200 |  |  |  |  | 72000 | 0 | 72000 | 1 | 72000 | 0 | 72000 | [12 empty] | 13/Oct/25 6:32 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251013-163227.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1167346 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@76f244a1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabl: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | Sprint 16 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 07:22 | [13 empty] | 05/Sep/25 9:21 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Informatica Test server is launched and trying to fix connectivity issue. Only after the cutover launch we will be able to configure DR and backup solution for this server, so this will be a spillover. | 22/Sep/25 8:44 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This is a spillover due to the dependent userstory - [[AM20-140] Informatica Server ¦¦ Cutover - Jira¦https://vodacom.atlassian.net/browse/AM20-140], only after cutover we would be able to do backup and DR setup. | 30/Sep/25 6:37 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Since Cutover is completed have started working on setting UP DR, will be completing in sometime. | 03/Oct/25 9:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Backup is completed, DR is in progress, waiting for DR drill to complete. send a mail on asking for slot with app owner to perform DR drill, upon drill completion with complete this US. | 09/Oct/25 6:29 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;DR Drill is planned today with albert at 1:30PM, looking forward to complete the drill. | 13/Oct/25 6:32 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Drill is completed successfully. !image-20251013-163227.png¦width=1278,height=489,alt="image-20251013-163227.png"! | [24 empty] | Done | 2025-10-13 18:32
AM20-140 | Informatica Server ¦¦ Cutover | Done | 3 | Sprint 13 | 2025-09-01 | 2025-09-12 | Aravind Raj | Critical | 1751440 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-11 05:27 | 2025-10-06 07:58 |  |  |  | 0 | As AWS expert I would be performing the cutover for Informatica application. Acceptance Criteria: * Replication from on-prem is successfully stopped using API calls * Back up of informatica VDC Server * Monitoring disable - VDC Server * Shutting down Informatica application in VDC * Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [informatica-application.awsflysaa.com¦http://TM1-application.awsflysaa.com] Server to the AD * MAT Testing completed successfully by SAA |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;30/Sep/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;30/Sep/25 6:35 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 115200 | 28800 | 86400 | [12 empty] | 30/Sep/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250930-163418.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1160874 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1f84394d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 07:21 | [13 empty] | 05/Sep/25 9:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test server is launched and trying to fix connectivity issue. only after that cutover can be launched hence this will be a spillover. | 22/Sep/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This US is spillover since there were SAP connectivity issue. now the connectivity is resolved, we will be taking up this in this sprint. | 30/Sep/25 6:33 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;The Cut over is completed followed by user validation. Post cutover activities like SSM agent installation, Domain Join and Cloud watch agent installation all completed successfully. | 30/Sep/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250930-163418.png¦width=669,height=443,alt="image-20250930-163418.png"! | [26 empty] | Done | 2025-10-06 07:58
AM20-138 | Code Pipeline creation using Terraform in Sandbox | Done | 8 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1749627 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-07 10:32 | 2025-10-31 17:19 |  | 2025-10-31 17:19 |  | 0 | As Platform owner I want to create code pipeline POC in sandbox so that we can achieve a base module for centralizing CI/CD pipeline. *Acceptance Criteria*: * Code build and S3 and IAM role replica is created which is needed in code pipeline integration * Code pipeline base module is ready |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;30/Oct/25 6:52 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;86400 | ;30/Oct/25 6:52 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;10800 | ;31/Oct/25 10:55 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18120 |  |  |  | 115200 | 0 | 115320 | 1 | 115200 | 0 | 115320 | [12 empty] | 31/Oct/25 11:10 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251031-091042.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175916 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@648c36cb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v05i | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-28 06:19 | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 28/Oct/25 8:19 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Started work on codepipeline module for Github base repository. Feature branch â€œfeat/codepipeline2â€ is created for this. | 30/Oct/25 6:51 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Modules have been created in feature branch of base and component repositories [https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa/tree/feat/codepipeline2¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa/tree/feat/codepipeline2¦smart-link] [https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/tree/feat/codepipeline2¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/tree/feat/codepipeline2¦smart-link] These modules have been tested as well in sandbox aws account. Now in next sprint, we will focus on to have dependency of required modules like s3, iam roles, kms (if needed), codebuild to be integrated with codepipeline in Bitbucket repository alongwith modules creation in BB repo. | 31/Oct/25 11:10 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Following successful validation with â€œterraform planâ€, modules have now been pushed to remote feature branches of both base and component repositories. !image-20251031-091042.png¦width=459,alt="image-20251031-091042.png"! | 31/Oct/25 5:19 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-10-31 17:19
AM20-137 | Tagging validations for AWS workloads across environments | Done | 0 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1749567 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-07 10:12 | 2025-09-03 08:56 |  |  |  | 0 | As AWS expert, Tagging of all resources must be completed and verified |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@24bea93e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0daxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:59 | [13 empty] | 25/Aug/25 8:59 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill over :* I will be reviewing & Attaching the sheet here in US as on friday EOD sanjot & shreyash updated the tags and added them on sheet thatâ€™s why this story got spilled over. | 25/Aug/25 10:03 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have reviewed the sheet all tags are updated for all resources. [Validation sheet for Naming and tagging for FLYSAA_CMS_BACKEND DEV PREPROD & PROD.xlsx¦https://vodafone.sharepoint.com/:x:/r/sites/SouthAfricaAirlines/_layouts/15/Doc.aspx?sourcedoc=%7BD95F49D1-A6B2-4430-A48E-1925ADA79A0D%7D&file=Validation%20sheet%20for%20Naming%20and%20tagging%20for%20FLYSAA_CMS_BACKEND%20DEV%20PREPROD%20%26%20PROD.xlsx&action=default&mobileredirect=true] | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:56
AM20-136 | Informatica Server - Dev ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1749537 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-07 10:01 | 2025-09-03 08:56 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 57600 |  | 0 | 86400 | 57600 | [9 empty] | AM20-145 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b90196e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0datf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 14:28 | [13 empty] | 18/Aug/25 4:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev MGN template has been configured, now we are looking AWS migration agent installation on server for sync, Sinjun going to take care tomorrow for the same i have scheduled the call. | 19/Aug/25 5:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;While checking AWS agent connectivity not working, checking with network team for further troubleshooting/fixing the issue. CSOC request has-been createdâ€CINC0909706â€ | 25/Aug/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network routing not implemented, currently it under approval process. | 26/Aug/25 1:11 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Firewall rules implemented. # Configured MGN agent setup on AWS for dev server migration. # Identified as connectivity not working. # Initiated network troubleshooting call towards fixing. # Identified as routing not configured. # Requested LIFT for approval # LIFT approval took 3days # Monday CSOC request raised and routing has ben implemented. # Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 29/Aug/25 8:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev agent installation and Test instance setup has been complted. | 01/Sep/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The test instance connectivity has been completed. Communicated to Peter for connectivity testing. The ip address is: 10.42.0.46. Sending this request for closing. | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-135 | Rename Citrix account with informatica Prod: Re-establish Informatica ¦¦ Subnet Configuration and Setup platform | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1749511 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-07 09:46 | 2025-08-25 06:33 |  |  |  | 0 | As Network expert, I would like to provision subnet configuration for PROS application Acceptance criteria: * Subnet configuration completed successfully * Tagging of all network elements associated done succesfully * Traffic flow testing and validation is concluded |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153624.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141700 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153747.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141702 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-154222.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141701 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@e805dba | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dap7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 06:22 | [13 empty] | 12/Aug/25 8:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;We are looking account id rename or new id creation process accordingly i will proceed for next steps. | 19/Aug/25 5:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Citrix Account ID has been renamed with Informatica Prod â€œ536697248966 â€ƒâ€ƒ SAA_Informatica_PRODâ€ | 19/Aug/25 5:42 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet, NACL, RAM ,SG and connectivity has been established. !image-20250819-153624.png¦width=1417,height=750,alt="image-20250819-153624.png"! Connectivity has been tested and working fine. !image-20250819-153747.png¦width=1417,height=750,alt="image-20250819-153747.png"! ¦Informatica Prod-Public¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.0.208/28¦10.40.0.208 - 10.40.0.223¦10.40.0.209 - 10.40.0.222¦14¦/28¦ ¦Informatica Prod-Public(DR)¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.128/28¦10.40.1.128 - 10.40.1.143¦10.40.1.129 - 10.40.1.142¦14¦/28¦Â ¦AZ2¦ !image-20250819-154222.png¦width=1417,height=750,alt="image-20250819-154222.png"! | 19/Aug/25 5:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Assigning for review. | 21/Aug/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed with internet acess. | 25/Aug/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 06:33
AM20-134 | Cleanup of AWS workload from Control tower | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1749509 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-07 09:42 | 2025-08-21 14:26 |  |  |  | 0 | As application owner I would like to cleanup redundant workloads from AWS through control tower so that we can achieve optimum utilization Acceptance Criteria: Cleanup is done with all redundant workloads/account deleted |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 14/Aug/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250814-064049.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139647 | 18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250818-060958.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1140604 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@557a9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0daor: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-14 06:41 | [13 empty] | 14/Aug/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have initiated mail with vodacom team, will do followup. !image-20250814-064049.png¦width=1272,height=492,alt="image-20250814-064049.png"! | 18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250818-060958.png¦width=1277,height=470,alt="image-20250818-060958.png"! AWS account cleanup, followed by by account renaming is completed. | 21/Aug/25 2:25 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:26
AM20-133 | PROS ¦¦ LLD Creation | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sankalp Rai | Medium | 1749504 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-07 09:39 | 2025-10-06 08:07 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1809d79f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0danv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | Sprint 15 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 06:06 | [13 empty] | 06/Oct/25 8:05 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;LLD document created. | 06/Oct/25 8:07 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;[PROS_Low Level Design Document_v1.0.docx¦https://vodafone.sharepoint.com/:w:/r/sites/SouthAfricaAirlines/Shared%20Documents/Technical%20Documents/SAA%20Design%20documents/LLD%20Documents/Wave%202%20apps/PROS%20LLD/PROS_Low%20Level%20Design%20Document_v1.0.docx?d=w4faebf320e0f4c53aedb5b192660de4f&csf=1&web=1&e=jOZXIo] | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-10-06 08:07
AM20-132 | AirNavX ¦¦ Setup and Validate SG and NACL | Done | 8 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747567 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-05 12:18 | 2025-09-22 08:49 |  |  |  | 0 | As AWS network expert I would like to setup the security group and NACL for Airnavx so that access for aitnavx allow secure access to allow communication with its services while ensureing access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for AirNavX or related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a70d23c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d30b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:54 | [13 empty] | 25/Aug/25 8:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Spill over Reason: Still comms under review, once reviewed i will start action the same. | 28/Aug/25 8:36 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will be addressed once comms implementation done. | 08/Sep/25 9:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms Implementation request has been submitted, LIFT has been approved SITA side under approval process. This story will not be addressed until Comms implementation. | 19/Sep/25 4:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Bhavish Modified comms with /27 to /28 and the same has been shared to Albert. | 19/Sep/25 4:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Now SITA has been implemented flows and the same need to validated. According to management the validation will be managed with new Story, hence i am resolving this story. | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-22 08:49
AM20-131 | AirNavX ¦¦ Create all EC2 instance using Terraform | Done | 0 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747550 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-05 12:06 | 2025-09-08 06:36 |  |  |  | 0 | As Product owner I would like to create EC2 instance (linux instance) in AirnavX account using terraform as it is green field solution so that AirnavX can be installed successfully and workloads can be run securely with proper governance control Acceptance criteria: EDC2 instance is provisioned in the correct subnet and AZ based on environment EC2 instance is launched with approved AMI as per OS and application requirements Instance type is selected according to Memory - 64 GB and CPUÂ - 8 cpu's, with a possibility to increase to a larger instance type if required Appropriate security group is attached to allow only required inbound/outbound traffic Instance tagged correctly with meta data CloudWatch agent installed and configured to collect system metrics and logs SSM agent is installed and instance is visible in AWS System Manager for patching commands EC2 instance boots successfully and is reachable via expected methods (SSM) |  | Satyabrata Sahoo | Yashwant Thakur |  |  |  |  | 712020:4b8d8093-596d-4394-a074-4a9a9636f86f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [29 empty] | 05/Sep/25 8:46 PM;d60b2ee4-0111-46b4-bb96-1c8a6e11be41;image-20250905-184351.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148823 | 05/Sep/25 8:46 PM;d60b2ee4-0111-46b4-bb96-1c8a6e11be41;image-20250905-184556.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148824 | 05/Sep/25 8:54 PM;d60b2ee4-0111-46b4-bb96-1c8a6e11be41;image-20250905-184949.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148825 | 05/Sep/25 8:54 PM;d60b2ee4-0111-46b4-bb96-1c8a6e11be41;image-20250905-185401.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148826 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@65476f0e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2y3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 20:50 | [13 empty] | 18/Aug/25 10:49 PM;712020:4b8d8093-596d-4394-a074-4a9a9636f86f;Base Module preparation is in progress. | 25/Aug/25 7:47 AM;712020:4b8d8093-596d-4394-a074-4a9a9636f86f;Modular EC2 Machine Terraform Code is ready and working as expected as show case in Demo, with all type of feature. Here Two Enhancement is required to the code. * Even Monitoring is enabled, there is no configuration related to Monitoring * Even Logging is enabled, There is no configuration to Logging These two enhancement required to conclude the stories. Hence this will be spill over. | 05/Sep/25 8:46 PM;712020:4b8d8093-596d-4394-a074-4a9a9636f86f;Updated the IAM Modules to create Instance Profile: base module: [feat(instance_profile): add modules by satyabrata-sahoo_voda Â· Pull Request #40 Â· VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa/pull/40] component module: [feat(iam_role): add instance profile by satyabrata-sahoo_voda Â· Pull Request #44 Â· VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/pull/44] Update the SSM Instance role which can be utilized by EC2: [flysaa / airnavx-flysaa-aws-terraform-project / Commit c0e4a7011932 â€” Bitbucket¦https://bitbucket.org/flysaa/airnavx-flysaa-aws-terraform-project/commits/c0e4a7011932921b2b32a2cd9ff95ca1cb069f78] EC2 instance Base Module: [terraform-base-modules-vfsa/modules/ec2-instance/variables.tf at ec2-instance/v0.1.1 Â· VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa/blob/ec2-instance/v0.1.1/modules/ec2-instance/variables.tf] EC2 Instance Component Module: [terraform-component-modules-vfsa/modules/ec2-instance at ec2-instance/v0.1.2 Â· VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/tree/ec2-instance/v0.1.2/modules/ec2-instance] Read me file on GITHUB: [terraform-component-modules-vfsa/modules/ec2-instance/README.md at master Â· VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/blob/master/modules/ec2-instance/README.md] Readme file in Bitbucket: [flysaa / airnavx-flysaa-aws-terraform-project ec2-instance.md â€” Bitbucket¦https://bitbucket.org/flysaa/airnavx-flysaa-aws-terraform-project/src/main/ec2-instance.md] End user can handled any installation using the script and configure it. Here SSM and CloudAgent has been installed. !image-20250905-184351.png¦width=100%,alt="image-20250905-184351.png"! !image-20250905-184556.png¦width=100%,alt="image-20250905-184556.png"! !image-20250905-184949.png¦width=100%,alt="image-20250905-184949.png"! !image-20250905-185401.png¦width=100%,alt="image-20250905-185401.png"! | 08/Sep/25 6:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:35
AM20-130 | Documentation on Budget Management | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747516 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-05 11:46 | 2025-08-25 06:34 |  |  |  | 0 | As Product Owner, I would like to create a detailed documentation on Budget management solution Acceptance Criteria: Document should consist of below sections with detailed description. * IAM roles /groups and policy created for it * Details of any Lamda functions are configured * process to add users to the group to allow edit/view/remove privileges * Dashboard and configurations details * Process to change, update budget allocated, notification iteration etc. * Details of naming convention and tagging as applicable * Architectural diagram as applicable |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/Aug/25 12:23 PM;9e4636e8-9dfc-4a33-901b-fcd75015926a;AWS_Budget_Management.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1143135 | 14/Aug/25 7:01 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;Budget Documentation (24287a92-0ff3-4da3-9f2c-3378740b4c97).docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139610 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@58ed7f61 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2rv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-14 05:03 | [13 empty] | 14/Aug/25 7:02 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Document has been attached. Please verify [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] | 22/Aug/25 12:23 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;[^AWS_Budget_Management.docx] AWS Budget Document attached | 25/Aug/25 6:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 06:34
AM20-129 | Monitor health and logs of Lamda connector function to troubleshoot issue , if alerts in not processed | Done | 8 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747507 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-05 11:41 | 2025-08-25 06:32 |  |  |  | 0 | As Product owner I want to monitor health and logs of Lamda connector function so that I can troubleshoot issues quickly when alerts are not processed and ensure reliability of the alerting pipeline Acceptance Criteria: CloudWatch logs are enabled for the Lamda connector function to capture execution details, input events and error messages Cloudwatch Metrices (invocations, errors, throttles, duration) are available for function and updated in real time cloudwatch alarms are configured for * Errors >0 in last 5 minues * Throttles >0 * Duration exceeds timeout threshold A SNS is configured to capture failed Lamda execution Alerts from cloud watch are sent via SNS to notify ServiceNow CloudWatch Logs insights queries are available to quickly identify error trends and assist RCA Lamda health and alerting processing mertics are visulaized in a CloudWatch dashboard. |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 07/Aug/25 2:30 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1137015 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4db73908 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2qr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-07 12:31 | [13 empty] | 07/Aug/25 2:30 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[^LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx] Have attached the lambda detailed sheet. | 25/Aug/25 2:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;the alarms have been created for lambda functions in flysaa-backend and they are created for â€œerrorâ€, â€œthrottleâ€, â€œdurationâ€ and the thresholds are 1, 1 and 30sec respectively. the alarms notifications are now being sent to respective sns topics created which shall in-turn appear into service now dashboard as soon as the threshold values are met. | 25/Aug/25 6:32 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 06:32
AM20-128 | Patch Management ¦¦ Dashboard Enhancement | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1746156 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-04 14:39 | 2025-09-19 11:20 |  |  |  | 0 | As Product manager compliance dashboard needs to be enhance and should covered details of patch file Acceptance Criteria: Compliance dashboard need to patch details and account details |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4159e3f0 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cz63: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 20:35 | [13 empty] | 18/Aug/25 10:34 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Update for Patch Manager Monitoring, in the compliance bucket there are 3 folders created after creating the resource data sync but not for the target acc we need. i have changed certain policies and also added some permissions both in security as well as dev acc. I am waiting for the data to pop up and also i can trigger data collection forcefully via aws cloudshell command but i do not have access i have intimated Aravind for permission addition. and the data that is being collected is basically json and that is the format that we need for it to be visualized in cloudwatch. | 25/Aug/25 8:52 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;spillover: the data sync which has been created in the management acc theoretically should be able to fetch the summaries from target account and sync that data in the s3 bucket in central account. the steps that were tried to force a sync were: {code:json}Check if the Instance is Managed by Systems Manager Check Current Associations Check Current Inventory Data Create the Inventory Association Verify Association Creation Check Association Status Monitor Association Execution Check for Updated Inventory Data{code} All of these were done and created an association manually for it to be populated into s3 bucket yet it did not work. the permission policies are provided yet the target account data is not being synced. the issue was that resource data sync must be created in each of the target account which was earlier thought as not needed. have created ressource data sync and waiting for the data to be populated. | 28/Aug/25 8:34 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Spillover Revised Comment: I was troubleshooting the resource data sync that i created since theoretically, resource data sync in the management account was enough. After rigorous attempts to fix the issue and trying to find out the workarounds they all failed. At the end of the week, close to sprint closure I found the solution and applied it and the solution worked. Hence, the delay and also for the data to populate into the intended bucket it sometime takes 10-12 hrs. | 03/Sep/25 8:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# The Resource Data Sync has been troubleshoot correctly and is working as intended. # Lambda function has been created in backend-dev account so that it can brand all the instances as non-compliant initially. # EventBridge has been configured as such when any new instance is provisioned it shall be flagged as non-compliant using the lambda function mentioned in point no.2. # The data in S3 is being used to project it to CloudWatch and that is being do using a Lambda function which will create metrics from the data in S3. # CloudWatch Dashboard is created such that it will have visual data segregated acc to the Acc Ids. (which was requirement by Bhavish). | 08/Sep/25 6:35 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;need demo | 08/Sep/25 8:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: The story was completed sufficing all the acceptance criteria. Demo was not done due to unavailability, hence scheduling the demo for 9/9/2025 considering everyoneâ€™s availability. | 11/Sep/25 9:12 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Demo was provided. The methodology and implementation was agreed upon and approved. There was an ask to involve another accounts, in order to check the workability. The accounts addition was done successfully and the data is presented on the custom dashboard as well. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:20
AM20-127 | Patch Management ¦¦ Life Cycle ¦¦ Implement Retention Policy in S3 busket | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1746117 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-08-04 14:23 | 2025-08-20 08:10 |  |  |  | 0 | As Product Owner I want to implement retention policy on S3 server so that download files can be managed Acceptance Criteria: * Retention policy is implemented on S3 * Post retention period file getting deleted successfully |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@401c6aaa | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 07:07 | [13 empty] | 12/Aug/25 9:07 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Retention rule for central patching bucket is as follows: the rule is created for prefix filters like (windows/dev/, windows/preprod/, windows/prod/, linux/dev/, linux/preprod/, linux/prod/) After 60 days objects within the path shall expire. | 20/Aug/25 8:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-20 08:10
AM20-126 | Billing and other solution required roles | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741166 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-07-30 16:22 | 2025-08-11 09:19 |  |  |  | 0 |  |  | Aravind Raj | Onkar Mirajkar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | [29 empty] | 06/Aug/25 10:30 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;IAM Role Documention.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136095 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f932959 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckgr: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 08:31 | [13 empty] | 06/Aug/25 10:30 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;[^IAM Role Documention.docx] Please Review and Verify | [26 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-11 09:19
AM20-125 | IAM role used for Patch Solutions | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741163 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-07-30 16:20 | 2025-08-21 18:09 |  |  |  | 0 |  |  | Aravind Raj | Faisal Sayed |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@35ee02d7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckgj: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:32 | [13 empty] | 04/Aug/25 6:31 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*In Security Acc* # [saa-security-central-patch-bucket-windows-lambda-roleÂ ¦https://730335236533-kttygmoz.af-south-1.console.aws.amazon.com/go/view?arn=arn%3Aaws%3Aiam%3A%3A730335236533%3Arole%2Fsaa-security-central-patch-bucket-windows-lambda-role&source=lambda] # [ComplianceSyncLambdaRole¦https://730335236533-kttygmoz.af-south-1.console.aws.amazon.com/go/view?arn=arn%3Aaws%3Aiam%3A%3A730335236533%3Arole%2FComplianceSyncLambdaRole&source=lambda] # SAA_Security_WSUS_Central_Server_EC2_Role *In FlySAA-Backend-Dev Acc* # ssm-flysaa-backend-dev-spoke-windows-instance-role # [sm-flysaa-backend-dev-spoke-crossaccount-lambda-role-1¦https://746669190453-quvjamav.us-east-1.console.aws.amazon.com/iam/home?region=af-south-1#/roles/details/sm-flysaa-backend-dev-spoke-crossaccount-lambda-role-1] # [ssm-flysaa-backend-dev-spoke-crossaccount-lambda-role¦https://746669190453-quvjamav.us-east-1.console.aws.amazon.com/iam/home?region=af-south-1#/roles/details/ssm-flysaa-backend-dev-spoke-crossaccount-lambda-role] | 04/Aug/25 6:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;User Permissions: # EC2 Full Access. # Lambda Full Access # SSM Full Access # S3 Full Access # IAM Write Access | 12/Aug/25 10:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Provide me the policy list with the roles you have used. | 12/Aug/25 11:28 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;{adf:display=block} {"type":"table","attrs":{"isNumberColumnEnabled":false,"layout":"center","localId":"29cd7e76-bf6f-40fa-9142-c6fb8bb33df1"},"content":[{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Name Of Role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Account"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Permission Policies"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Permission Policy"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":4},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-flysaa-backend-dev-spoke-windows-instance-role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonS3FullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMManagedInstanceCore"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"KMSFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-flysaa-backend-dev-spoke-windows-instance-s3-policy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":4},"content":[{"type":"paragraph","content":[{"type":"text","text":"sm-flysaa-backend-dev-spoke-crossaccount-lambda-role-1"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AllowSSMExecution"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CloudWatchLogsFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Trust RealtionshipÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":3},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-flysaa-backend-dev-spoke-crossaccount-lambda-role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CloudWatchLogsFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-ec2-read-access"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]}]} {adf} | 12/Aug/25 11:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;{adf:display=block} {"type":"table","attrs":{"isNumberColumnEnabled":false,"layout":"center","localId":"4bd8311d-ebb8-4ed2-b8da-1e130a493dfb"},"content":[{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":5},"content":[{"type":"paragraph","content":[{"type":"text","text":"saa-security-central-patch-bucket-windows-lambda-role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWSLambdaBasicExecutionRole"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWSLambdaRole"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CrossAccountLambdaExecutionPolicy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"lambda-access-to-s3"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"StartAutomationRole-Linux"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"ComplianceSyncLambdaRole"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"lambda-permission-policy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":3},"content":[{"type":"paragraph","content":[{"type":"text","text":"SAA_Security_WSUS_Central_Server_EC2_Role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AllowPutToCentralPatchBucket"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMManagedInstanceCore"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CloudWatchAgentServerPolicy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]}]} {adf} | [22 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-21 18:09
AM20-124 | Terraform Role- resources creation required IAM role | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Sanket Kale | Medium | 1741159 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-07-30 16:15 | 2025-08-25 07:56 |  |  |  | 0 | Provide me all required roles and policy for the resource creation using terraform. Example : With Ec2 instance what all the policy you will be assigning with the role attached, in similar we many need for all the resources your creating using terraform. |  | Aravind Raj | Sanket Kale |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:91948faf-1676-4820-bf6b-d50a7992943e | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@57f5389f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckg3: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 05:07 | [13 empty] | 11/Aug/25 7:06 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;It will be spill over due to priority tasks of Nexio backup process. | [26 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-25 07:56
AM20-123 | Devops-Codepipeline,Codebuild,lambda,cloudwatch events and etc - IAM role | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Sanjot Fotedar | Medium | 1741150 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-07-30 16:12 | 2025-08-12 09:56 |  |  |  | 0 |  |  | Aravind Raj | Sanjot Fotedar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4e808ee9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckgn: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-08 06:22 | [13 empty] | 08/Aug/25 8:22 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Currently we have iam role only in dev account. The IAM role â€œarn:aws:iam::746669190453:role/flysaa-dev-backendbuildproject-roleâ€ has been refined in dev account to enforce least privilege access. Only the necessary permissions required for CodeBuild operations and associated resources have been retained. And this arn has been shared with aravind to review. | 12/Aug/25 9:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Provide me the role details in backend preprod and prod also along with the custom and AWS managed policy you have used. | 12/Aug/25 9:56 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Confirmed with sanjot there is no role created other by Dev team other than mentioned below. | [24 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-12 09:56
AM20-122 | EKS Cluster and other services required IAM role | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741147 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2025-07-30 16:10 | 2025-08-21 18:09 |  |  |  | 0 |  |  | Aravind Raj | Ravinder Godiyal Godiyal |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:7535df8d-3051-4556-b1c1-6a7195121b35 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1546fba | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cker: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:08 | [13 empty] | 11/Aug/25 10:07 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;Request [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] to update the spill over reason in the main user story being the assignee, i had to go on an emergency leave due to family exigency where we did not get a chance to formulate these details around. | 13/Aug/25 9:30 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;¦NAME¦Description¦ ¦flysaa-backend-dev-eks-deployer¦IAM Role to deploy EKS Cluster via Terraform¦ ¦eks-flysaa-dev-531cab81-argocd-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-aws-alb-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-aws-ebs-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-controlplane-role-34708c3e¦IAM Role for EKS Control Plane dynamically created by system with EKS Cluster creation¦ ¦eks-flysaa-dev-531cab81-ingress-nginx-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-karpenter-profile-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-KarpenterRole¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-sonarqube-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-workernode-role¦IAM Role for EKS Data Plane nodes managed by Karpenter¦ ¦eksctl-eks-flysaa-dev-531cab81-addon-iamservi-Role1-Wu60GGlLdLGi¦IAM Roles for EKS Cluster Add-ons¦ ¦eksctl-eks-flysaa-dev-531cab81-addon-iamservi-Role1-Y6EbqpTYxUCn¦IAM Roles for EKS Cluster Add-ons¦ ¦bitbucket-oidc-flysaa-role¦IAM Role for bitbucket replication to S3 bucket for CI/CD¦ ¦flysaa-backend-dev-codebuild-service-role¦IAM Service Role for codebuild projects¦ ¦ekstf-pipeline-codepipeline-role-4e353e4a¦IAM Service Role used by codepipeline which is dynamically created during runtime¦ ¦flysaa-backend-dev-ssminstancerole¦IAM Role to be used by bastion-hosts/jumpbox EC2 MachinesÂ ¦ As Discussed in our DS Call, Here are IAM Role details from Dev Environment, [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] request you to kindly make use of this information and fetch the same from all environments along with the respective permissions incorporated. | 13/Aug/25 10:06 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;Moving the subtask for review with [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] | 18/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have received dev env role, need to get the roles from preprod and prod along with policy. | [23 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-21 18:09
AM20-121 | AirNavx ¦¦ Subnet Configuration and Setup | Done | 3 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Medium | 1738825 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-29 13:20 | 2025-08-11 04:29 |  |  |  | 0 |  |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 57600 |  | 0 | 43200 | 57600 | [13 empty] | 06/Aug/25 12:00 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-08-06 151319-20250806-094320.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136194 | 06/Aug/25 12:00 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-08-06 151414-20250806-094415.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136196 | 06/Aug/25 12:00 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-08-06 151519-20250806-094519.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136193 | 06/Aug/25 12:00 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-08-06 151550-20250806-094551.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136195 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@719f8047 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cdub: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-05 16:23 | [13 empty] | 05/Aug/25 6:23 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Work initiated and subnet analysis and setup done, Testing is under progress | 06/Aug/25 12:00 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Reconfigured the Subnets according to LLD and tested internet connectivity via direct connect working fine. ¦AirnavX¦3¦ProductionÂ ¦Frontend¦10.40.0.0/18¦10.40.0.64/27¦10.40.0.64 - 10.40.0.95¦10.40.0.65 - 10.40.0.94¦28¦/27¦AZ1¦Â ¦ ¦AirnavX DR¦3¦ProductionÂ ¦Frontend¦10.40.0.0/18¦10.40.1.0/27¦10.40.1.0 - 10.40.1.31¦10.40.1.1 - 10.40.1.30¦28¦/27¦Â ¦AZ2¦ Reference inputs: !Screenshot 2025-08-06 151550-20250806-094551.png¦width=1418,height=798,alt="Screenshot 2025-08-06 151550-20250806-094551.png"! !Screenshot 2025-08-06 151519-20250806-094519.png¦width=1418,height=798,alt="Screenshot 2025-08-06 151519-20250806-094519.png"! !Screenshot 2025-08-06 151414-20250806-094415.png¦width=1418,height=798,alt="Screenshot 2025-08-06 151414-20250806-094415.png"! !Screenshot 2025-08-06 151319-20250806-094320.png¦width=1418,height=798,alt="Screenshot 2025-08-06 151319-20250806-094320.png"! | 08/Aug/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed the subnet creations. | 11/Aug/25 4:29 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:29
AM20-120 | Restrict Admin access to VOIS team by creating dedicated IAM role | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Medium | 1736354 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-28 10:24 | 2025-08-11 04:28 |  |  |  | 0 | As Product Owner, I want to restrict VOIS team to have Admin role so that all of them cannot be superseded rights and bring more control on AWS management Acceptance criteria: * IAM role to be created for everyone except Sankalp and Aravind from AWS perspective * IAM role for network creation to be created and role assign to Satya * IAM role for rest of team members is of developer |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6edd432e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0c5zn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 06:20 | [13 empty] | 06/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have shared the Excel with the user list to team, upon there confirmation ill start creating custom policy with user groups. | 08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;¦UserID¦IAM user¦UserGroup¦IAM Role¦ ¦raja0001¦Aravind¦VOIS_Admin¦No changes, use existing roles itself¦ ¦rais0003¦Sankalp¦VOIS_Admin¦No changes, use existing roles itself¦ ¦SatyasairamV¦SatyaSairam¦VOIS_Admin¦No changes, use existing roles itself¦ ¦godir001¦Ravinder¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦kiraj001¦Jitender¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Sanjot¦Sanjot¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦nikas001¦Sumit¦VOIS_Admin¦No changes, use existing roles itself¦ ¦FaisalSayed¦Faizal¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SanketKale¦Sanket¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦pathp002¦Pankaj¦VOIS_DBAdmin_Usergroup¦AWS_VOIS_DBAdmin_Role¦ ¦onkar¦Onkar¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦DikshaK¦Diksha¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SatyabrataS¦SatyaBrata¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Shreyash¦Shreyash¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Harsh¦Harsh¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Yashwant¦Yashwant¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Utkarsh¦Utkarsh¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ Â Â Access to User group given as below, ¦VOIS_InfraAdmin_Usergroup¦VOIS_DevOpsAdmin_Usergroup¦VOIS_DBAdmin_Usergroup¦ ¦VPC FullAccess¦CodeBuild FullAccess¦RDS Full Access¦ ¦EC2 FullAccess¦CodePipeline FullAccess¦DMS Full Access¦ ¦S3 FullAccess¦EKS FullAccess¦IAM Full Access¦ ¦CloudWatch FullAccess¦EC2 except delete¦CloudTrail except delete¦ ¦RDS FullAccess¦S3 FullAccess¦KMS except delete¦ ¦IAM FullAccess¦CloudWatch except delete¦CloudWatch except delete¦ ¦CloudTrailFullAccess¦RDS except delete¦Read only¦ ¦MacieFullAccess¦IAM FullAccess¦ ¦ ¦GuardDutyFullAccess¦System managerFullAccess¦ ¦ ¦SecurityHubFullAccess¦LambdaFullAccess¦ ¦ ¦System managerFullAccess¦Event bridgeFullAccess¦ ¦ ¦LambdaFullAccess¦CloudTrail except delete¦ ¦ ¦KMSFullAccess¦Read only¦ ¦ ¦ACMFullAccess¦Secrets managerFullAccess¦ ¦ ¦Aws ConfigFullAccess¦SNSFullAccess¦ ¦ ¦Event bridgeFullAccess¦SESFullAccess¦ ¦ ¦InspectorFullAccess¦ECR FullAccess¦ ¦ ¦SupportFullAccess¦KMS except delete¦ ¦ ¦SNSFullAccess¦Â ¦ ¦ ¦SESFullAccess¦ ¦ ¦ ¦ReadOnly¦ ¦ ¦ ¦Secrets managerFullAccess¦ ¦ ¦ ¦ECRFullAccess¦ ¦ ¦ Â Users have access to the below AWS accounts, Â ¦AWS Account¦Account Name¦ ¦300204747992¦Audit¦ ¦730335236533¦Security¦ ¦080284287007¦LogArchive¦ ¦339712943527¦Network¦ ¦864899875361¦SharedServices¦ ¦585768167545¦SharedVpcDev¦ ¦253490777663¦SharedVpcPreprod¦ ¦820242899278¦SharedVpcProd¦ ¦746669190453¦Backend dev¦ ¦216989128782¦Backend Preprod¦ ¦396608788916¦Backend Prod¦ ¦209479274829¦Tm1¦ ¦345594574792¦AirNAVx¦ ¦536697265099¦NexioAV¦ | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-119 | Nexio AV ¦¦ E2E Integration testing of ServiceNow monitoring | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1732203 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-23 16:32 | 2025-08-21 14:31 |  |  |  | 0 | As Product Owner I would like to review e2e testing completed with servicenow team for all wave 1 application so that we can confirm to business that in case of any issue service ticket would be raised Acceptance Criteria: * Tickets/issues are getting raised successfully against the alerts raise via cloudwatch for all Wave1 applications * ServiceNow team signoff received * Showcase (demo) provided to all relevant stakeholders |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 19/Aug/25 10:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141324 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1c3893f7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0brrj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-28 07:41 | [13 empty] | 28/Jul/25 9:41 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[https://vodacom.atlassian.net/browse/AM20-116¦https://vodacom.atlassian.net/browse/AM20-116¦smart-link] Only after completing the above US will start working on this story. | 28/Jul/25 3:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;After completion of Faisal story i will be proceeding with this US. | 11/Aug/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: Since the story was blocked due to configuration of monitoring and alerting on NexioAV ec2 instances (application specific) which was completed on 8th Aug 2025 (evening), Diksha did not get any time to validate end to end solution. Hence, the spillover. | 19/Aug/25 10:17 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have tried to triggered the alert to service now team. Now waiting for them to confirm from there side. | 19/Aug/25 10:33 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation for Priyanka and team the alerts are getting generated and tickets are being created in service now. Attaching the same screenshot for the reference. | 19/Aug/25 10:36 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image.png¦width=881,height=228,alt="image.png"! attaching the screenshot what service now team is getting the alerts for your reference from Priyanka and team. | 21/Aug/25 2:31 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:31
AM20-118 | Documentation on IAM and RBAC | Done | 5 | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | High | 1731884 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-23 14:42 | 2025-09-05 09:14 |  |  |  | 0 | As product owner, I like to document all the IAM - RBAC created to control the access of workloads and process to provision IAM, Terraform code location. Acceptance Criteria: Document completed having IAM roles name, purpose, Terraform code location( if applicable), Process to add respective resources |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;25/Aug/25 7:57 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;72000 | [5 empty] | 72000 | 43200 | 72000 | 1 | 72000 | 43200 | 72000 | [12 empty] | 05/Sep/25 9:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SAA_IAM Configuration_v1.1.doc;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148372 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2bce2e91 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0brrf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-30 14:24 | [13 empty] | 30/Jul/25 4:24 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created Sub story and assigned to respective members. | 11/Aug/25 7:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;due to VOIS user account modification IAM roles and policy is still a ongoing process, and other sub story need to be done | 11/Aug/25 7:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Hence this story would be spill over. | 14/Aug/25 8:44 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Waiting for sanket update on substory Will accumulate EKS roles with the help of ravinder excel sheet. | 25/Aug/25 7:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Received sanket data today will include that to the IAM document and close this by today. | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 07:55
AM20-117 | TM1 ¦¦ Configuring Application specific error in Cloudwatch for alerting | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730283 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-22 12:24 | 2025-08-11 04:28 |  |  |  | 0 | As a AWS expert I want to detect application specific error patterns in CloudWatch logs so that I can generate alerts for ServiceNow ticket creation and respond to runtime failure Acceptance Criteria: * Error pattern is defined and tested * Given an application output logs to cloudwatch when a known error occurs, then the pattern must correctly match that log * Metric filter is created - when error count exceeds the threshold then cloud watch alarm should trigger * Alert notification is sent, given the alarm is triggered when the condition is met then an alert must be sent to relevant teams |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [25 empty] | AM20-116 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3fa4464b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bnb3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:37 | [13 empty] | 04/Aug/25 6:37 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will start working on this from today. | 08/Aug/25 12:05 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Monitoring for specifically reporting & tm1serv application has been set. Alarm for Total Commit Usage has been created and configured to send those to ServiceNow. | 08/Aug/25 12:06 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Moving to Aravindâ€™s bucket for review. | 08/Aug/25 12:30 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;every cloud watch custom metrics are captured as error metrics and create an alarm for same. | 08/Aug/25 12:30 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;create a memoryutilization and disk utilization alarm and move to review | 08/Aug/25 8:43 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Monitoring metric is created for Overall Committed Memory Bytes and then further classified for each service that was mentioned in the mail. Alert has been created for â€œOverall Committed Memory Bytesâ€, so creating alarms for its further classification would be redundant. And in the email, we have a confirmation to create an alarm for â€œTotal Commit Sizeâ€ hence have created for â€œOverall Committed Memory Bytesâ€ and not for the per service. | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-116 | Nexio AV ¦¦ Configuring Application specific error in Cloudwatch for alerting | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730277 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-22 12:23 | 2025-08-11 04:28 |  |  |  | 0 | As a AWS expert I want to detect application specific error patterns in CloudWatch logs so that I can generate alerts for ServiceNow ticket creation and respond to runtime failure Acceptance Criteria: * Error pattern is defined and tested * Given an application output logs to cloudwatch when a known error occurs, then the pattern must correctly match that log * Metric filter is created - when error count exceeds the threshold then cloud watch alarm should trigger * Alert notification is sent, given the alarm is triggered when the condition is met then an alert must be sent to relevant teams |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [25 empty] | AM20-117 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a72bd8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bnaz: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:37 | [13 empty] | 04/Aug/25 6:36 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will start working on this from today. | 08/Aug/25 9:01 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Used â€œGet-Servicesâ€ command with flags like running and contains trellix to analyse services to be monitored. 8 services identified. Created script for monitoring commit size of each service and in the â€œ*NexioAV/ServiceMemory*â€ namespace and the Overall commit size of EC2 is being monitored in â€œ*System/Memory*â€ namespace. Created alarm for Overall Commit Size threshold is 20GB for now since there is no communication on what should the threshold unlike TM1. | 11/Aug/25 4:27 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-115 | Nexio AV ¦¦ Life Cycle Management ¦¦ Log Retention | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1730232 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-22 12:01 | 2025-08-11 07:59 |  |  |  | 0 | As Product Owner I would like to establish the life cycle management for log retention specific to Nexio AV account to have defined log retention policies for all critical log sources so that we can meet compliance, enable forensic investigation and optimize storage Acceptance Criteria: log retention policy is defined per account * Production env. - log retention period 90 days Â *Please note* that post retention period, these logs can either be deleted or moved to cold storage, which can be configured based on your confirmation however, data retrieval from cold storage is charged additionally. * All critical log sources are covered - cloudtrail, VPC flow logs, cloudwatch logs and other tools must be retained as per policy * Log retention is automated - log groups are created when they are detected * Logs reaches its retention threshold when the time expires it should either be deleted or moved to archive (cold storage) * Retention policy is editable so that it can be configured accordingly |  | Aravind Raj | Diksha Koul | Onkar Mirajkar | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [27 empty] | 06/Aug/25 9:45 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;Screenshot 2025-08-06 131412.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136044 | 29/Jul/25 9:39 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250729-073927.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1132067 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@410ec9e6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bn77: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-29 07:40 | [13 empty] | 29/Jul/25 9:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;No S3 bucket resource has been created on NEXIO AV as of now for retention period. !image-20250729-073927.png¦width=1545,height=507,alt="image-20250729-073927.png"! | 31/Jul/25 12:53 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Created Log metrics for NEXIO AV | 01/Aug/25 8:14 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created one life cycle rule for the deletion of logs after 90 days need to review it with Aravind. | 01/Aug/25 9:00 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;we will be having an confirmation email from the client and will be then implementing the retention life cycle rule on the centralized account as Logs will store to cold storage and retention days will be 90 days. | 05/Aug/25 11:11 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Retention rule has been created in the Log Archive account on S3 all environment as 90 days and also after 90 days it will get moved to cold storage. | 06/Aug/25 9:45 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!Screenshot 2025-08-06 131412.png¦width=934,height=354,alt="Screenshot 2025-08-06 131412.png"! Attaching the screenshot of the changes we have done in the log archive account. | 08/Aug/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Transition rule in place for centralized cloud trail logs to send to glacier after 90 days. | 11/Aug/25 7:59 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 07:59
AM20-114 | TM1 ¦¦ Life Cycle Management ¦¦ Log Retention | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1730214 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-22 11:59 | 2025-08-11 04:27 |  |  |  | 0 | As Product Owner I would like to establish the life cycle management for log retention specific to TM1 account to have defined log retention policies for all critical log sources so that we can meet compliance, enable forensic investigation and optimize storage Acceptance Criteria: log retention policy is defined per account * Production env. - log retention period 90 days Â *Please note* that post retention period, these logs can either be deleted or moved to cold storage, which can be configured based on your confirmation however, data retrieval from cold storage is charged additionally. * All critical log sources are covered - cloudtrail, VPC flow logs, cloudwatch logs and other tools must be retained as per policy * Log retention is automated - log groups are created when they are detected * Logs reaches its retention threshold when the time expires it should either be deleted ot moved to archive (cold storage) * Retention policy is auditable so that it can be configured accordingly |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Aug/25 8:18 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@b33f9af | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bn5n: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 06:18 | [13 empty] | 06/Aug/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Centralized bucket retention policy is added to move to glacier infrequent access after 90 days from standard class. | 11/Aug/25 4:27 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:27
AM20-113 | Nexio AV ¦¦ Back-UP via terraform | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730133 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-22 11:32 | 2025-08-20 08:11 |  |  |  | 0 | As AWS expert, I would like to provision Life Cycle manager with two schedule - * Incremental back up(daily back) * Full backup (Weekly) *Acceptance Criteria* : * The Life cycle manager has two schedule (Incremental and Full backup) successfully implemented * Back up must be automated using native AWS features and tools * Point-in-time recovery for database must be enabled to allow recovery to any second within retention window * Define retention policy and enforce retention ( 7 days, 35 days, monthly snapshot for 1 year) * Automatically transition of old backups to cold storage * Use AWS backup vault lock for Write once and Read many compliance * Backup must be encrypted at rest and in transit * Restore process is well documented and well tested * After restore data integrity checks and application consistency should be validated * Use AWS backup for central management of backup policies and vaults * Automate backup selection using resource tags * Backups must meet regulatory compliance like GDPR,HIPAA * and Audit trail of backup creation, deletion and restore events must be maintained * Periodic restore testing must be conducted and logged to validate data integrity * *AWS part:* * Use AWS config rules to enforce mandatory backup configurations * Use Cloudwatch to success/failure backups * Setup alerts for backup failure or missed backups via SNS * IAM Policies for access control to restrict who can create, view, delete and restore backups * All backup and restore operations must be logged in AWS Cloudtrail for traceability |  | Aravind Raj | Sanket Kale | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4dfe6877 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bmvv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 05:09 | [13 empty] | 11/Aug/25 7:09 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;This task will be spill over because the terraform script written by the Utkarsh is not match our expectations. I need to re write the new scripts from the scratch. | 13/Aug/25 8:19 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Utkarshâ€™s code is written for creating resources in AWS backup. I have executed the script for Nexio Prod. | 18/Aug/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;deleted unwanted 37 backup AMI taken by vault. backup config is updated with frequency and retention period. | 20/Aug/25 8:11 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-20 08:11
AM20-112 | TM1 ¦¦ E2E Integration testing of ServiceNow monitoring | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1729976 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-22 10:53 | 2025-08-21 14:33 |  |  |  | 0 | As Product Owner I would like to review e2e testing completed with servicenow team for all wave 1 application so that we can confirm to business that in case of any issue service ticket would be raised Acceptance Criteria: * Tickets/issues are getting raised successfully against the alerts raise via cloudwatch for all Wave1 applications * ServiceNow team signoff received * Showcase (demo) provided to all relevant stakeholders |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 19/Aug/25 1:26 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image (3).png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141522 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@98c0df5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bmab: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-28 07:32 | [13 empty] | 28/Jul/25 9:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Once after the TM1 cutover is completed we can proceed with this activity. | 11/Aug/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: Since the story was blocked due to configuration of monitoring and alerting on TM1 ec2 instances (application specific) which was completed on 8th Aug 2025 (evening), Diksha did not get any time to validate end to end solution. Hence, the spillover. | 19/Aug/25 10:40 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start working on this US from today. | 19/Aug/25 12:27 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Alerts are being generated and triggered now waiting for confirmation from Service now team to share the screenshot. | 19/Aug/25 1:26 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image (3).png¦width=1146,height=305,alt="image (3).png"! Attaching the screenshot which I got from service now team that they are getting the alerts generated by our side. | 21/Aug/25 2:33 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:33
AM20-111 | Configure respective IAM role for TM1 and Nexio business team for Budget management dashboard | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1729920 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-22 10:48 | 2025-08-11 04:27 |  |  |  | 0 | As Product owner I want to create IAM role specific for Budget management and add business representatives from TM1 and Nexio so that they can able to view dashboards and receive alerts in case these is an unexpected jump in cost or the threshold is crossed. Acceptance Criteria: * IAM role is created successfully * Nexio and TM1 business representative emails gets added in the foresaid role * Test is concluded to ensure emails are getting triggered successfully * walkthrough provided to the relevant stakeholders |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@53ee738a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bm4j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-05 08:17 | [13 empty] | 05/Aug/25 10:16 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;*Group Name* Naming Conventions is Given as "*TM1-Budget-Users-Group*" and "*NexioAv-Budget-Users-Group*" Â Â *Policy name* given Â as "*TM1-BudgetAccess-Policy*" and "*NexioAV-BudgetAccess-Policy*" *ViewAllBudget-Group* is created for only Viewing All Budgets with *ViewAllBudget-Policy* | 05/Aug/25 10:19 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Groups has been created for TM1 and NexioAV Budgets. Users from Respective Group can edit only respective Budgets | 11/Aug/25 4:27 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:26
AM20-110 | POC - Create Sustainability dashboards | To Do | 8 | Sprint 10 | 2025-07-21 | 2025-08-01 | Sankalp Rai | High | 1720042 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-14 10:26 | 2025-10-13 09:27 |  |  |  | 0 | As AWS Expert, I would create sustainability dashboard to access the power consumption, utilization and energy efficiency in alignment with well-architecture Acceptance Criteria * Enable AWS Sustainability Pillar in Well-Architected Reviews, optimize workloads for energy efficiency â€” right-sizing, minimizing network transfer, cold storage, etc. * Leverage S3 Lifecycle Policies & Intelligent Tiering |  | Harsh Chandra | Sankalp Rai |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63121580 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v09 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | Sprint 12 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:13 | [13 empty] | 11/Aug/25 10:12 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 12th August End Date: 21st August | 10/Sep/25 1:15 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Moving this to Backlog from Sprint 13 as suggested by Deepak Sharma, to currently focus on critical migration activities. This will be picked up in later sprints. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | To Do | 2025-10-13 09:27
AM20-109 | Create and Grant IAM policies for read-only and modify or edit permission for budget dashboards | Done | 0 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1720023 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-14 10:23 | 2025-08-11 04:26 |  |  |  | 0 | As AWS expert, I would like to create two custom IAM policies which can used for read-only and edit the budget respectively. Acceptance criteria: * Create one policy to view budget dashboard: * SAAViewBudget: allow to view the budget dashboard prepared for SAA * SAAUpdateBudget: allow to edit or modify the budget allocation through SAA dashboard * The implementation should be payer9 account Users assigned to these policies would only able to view or update the budget dashboard respectively. |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@45e0c06b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0atz7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-17 06:23 | [13 empty] | 17/Jul/25 8:22 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Acceptance criteria: ----*Done* * Create one policy to view budget dashboard: * SAAViewBudget: allow to view the budget dashboard prepared for SAA * SAAUpdateBudget: allow to edit or modify the budget allocation through SAA dashboard * The implementation should be payer9 account | 25/Jul/25 7:50 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Not created properly. As discussed in todays review call, IAM role needs to be created however we were shown only policy | 28/Jul/25 9:55 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Spill Over: Need to Create Users Group Permission including roles and permission--- *Pending* | 29/Jul/25 8:14 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Budgetwise edit permission granted to specific user*---Done* Budget users will only able to view others budget(They cant modify other budget except their own) *----Done* | 05/Aug/25 10:21 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Groups has been created for TM1 and NexioAV Budgets. Users from Respective Group can edit only respective Budgets. This Story is similar/related to [[AM20-111] Configure respective IAM role for TM1 and Nexio business team for Budget management dashboard - Jira¦https://vodacom.atlassian.net/browse/AM20-111] | 11/Aug/25 4:26 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:26
AM20-108 | Cost Anomaly Detection | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1719961 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-14 10:11 | 2025-07-28 09:58 |  |  |  | 0 | As AWS expert I would like to report any sudden spike in the cost against any of the application or accounts so that the concerned team can validate the reasoning and take appropriate action to ascertain reasons and take reactive measures Acceptance Criteria: < pre-req> : * Ensure all accounts are part of AWS Org. with consolidated billing enabled * Use the Payer9 account to see all account cost level Acceptance Criteria * Cost anomaly detection is enabled successfully * Anomaly monitor is is enabled * Anomaly subscription is successfully enabled using SNS * CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage * Use Amazon Athena or quicksight for stakeholder friendly dashboards * Graphical representation of the cost to be captured |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4d6b831e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0attv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-18 06:07 | [13 empty] | 18/Jul/25 8:07 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;* CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm *---Done* * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage *---Done* Cost anomaly detection is enabled successfully *---Done* * Anomaly monitor is is enabled *---Done* * Anomaly subscription is successfully enabled using SNS *---Done* | 23/Jul/25 8:08 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working on Amazon Athena or quicksight for stakeholder friendly dashboards ---*Done* | 24/Jul/25 7:38 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;As discussed with Yashwant, we need to track cost anomalies for specific AWS services and implement it separately for each account. | 24/Jul/25 8:57 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Cost anomalies detction for specific AWS services and implement it separately for each account. *---Done* Updated for Only TM1 account.(As discussed with Yashwant) | 28/Jul/25 9:58 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:58
AM20-104 | AWS Centralized dashboard CloudWatch Dashboard for Nexio AV to monitor Performance, cost optimization and security Metrics | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718753 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-11 10:27 | 2025-07-28 09:57 |  |  |  | 0 | As AWS expert, I would like to create centralized CloudWatch to capture Performance, Security and Cost metrics from across accounts. Acceptance Criteria: * CloudWatch dashboards can be created in one account (Payer9 account) anf pull metrics from other accounts * User cross account IAM roles to allow Payer9 account to read cloudwatch from other accounts * Add Widgets sourcing metrics from each account * Setup AWS config aggregator in the Payer9 account to collect configuration and compliance data across all members accounts * Performance metrics - Use below Cloudwatch metrics * EC2 : CPU, Network, Disk I/O * RDS: CPU, READ/Write IOPS * Lambda: Duration, Error Rate * and source these into widgets in the centralized dashboard * Security Metrics: Centralized Security Hub is already enabled, which can pull in findings from GuardDuty, Config, Macie, Cloudtrail, Inspector etc. |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60b85e0b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aofj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-23 14:43 | [13 empty] | 23/Jul/25 4:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Created Trellix Dash board with CPU, Memory and Disk usage. | 25/Jul/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dash board prepared for CPU, Disk, Network and memory for Trellix application. | 25/Jul/25 8:09 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sent for review | 27/Jul/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Could see the metrics for trellix server, moving to PO approval, | 28/Jul/25 9:57 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:57
AM20-103 | ServiceNow Integration with Wave 1 application accounts for migration | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1718215 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-10 20:03 | 2025-07-25 19:48 |  |  |  | 0 | As AWS expert I would like to setup ServiceNow monitoring with all the application accounts so that in case of any alerts generated via CloudWatch agents, it can be cascaded to ServiceNow to form an incident tickets Below applications are considered TM1, Patch managment, NexioAV, Informatica server Acceptance Criteria: * ServiceNow monitoring is setup successfully in all the accounts targeted to be used for respective application migration * API for serviceNow is successfully configured for non-prod as well as prod accounts respectively * ServiceNow team confirmation is received that API is transferring the information successfully * E2E validation is completed ( App account-->cloudwatch-->SNS topic-->alerts-->Servicenow monitoring-->ServiceNow |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [13 empty] | 17/Jul/25 5:53 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250717-155331.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1127871 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7ecd77e5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aoff: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-17 06:11 | [13 empty] | 17/Jul/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 and Nexio AV service now integration is completed, unit testing will be completed. | 17/Jul/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Only after the demo and approval patching server will be added to the service now integration | 17/Jul/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will add informatica server integration today. | 17/Jul/25 5:53 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Informatica aws account integration is completed, test with a test server working fine as expected. !image-20250717-155331.png¦width=647,height=465,alt="image-20250717-155331.png"! | 21/Jul/25 7:05 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;patch management server is expected to setup in security account, so ill be doing security account integration with service now by today. | 21/Jul/25 6:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Security account service now integration is completed unit test yet to be performed. | 25/Jul/25 7:48 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-25 19:48
AM20-102 | Trellix Integration with TM1 account | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1718212 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-10 19:55 | 2025-08-20 08:10 |  |  |  | 0 | As Network experts I would like to integrate Trellix servers with TM1 account so that it is able to scan TM1 workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in TM1 server * Trellix is able to access TM1 account successfully and perform scanning |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 13/Aug/25 12:38 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250813-103653.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139278 | 13/Aug/25 12:38 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250813-103711.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139279 | 13/Aug/25 12:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250813-104007.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139280 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5e9f2d9f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:099 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-17 06:11 | [13 empty] | 17/Jul/25 8:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Agent installed on TM1 test instance and tested, it is working fine. | 25/Jul/25 7:54 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 cutover got pending, this action needed TM1 server cutover/migration. | 13/Aug/25 12:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 cutover competed and testing done. | 13/Aug/25 12:38 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Sinjun the new AWS TM1 server integrated with New AWS-Trellix server. The reference images has been attached for reference. !image-20250813-103653.png¦width=100%,alt="image-20250813-103653.png"! !image-20250813-103711.png¦width=100%,alt="image-20250813-103711.png"! Product installation screen: !image-20250813-104007.png¦width=100%,alt="image-20250813-104007.png"! | 20/Aug/25 8:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-08-20 08:10
AM20-101 | Provision and manage Amazon Inspector V2 across AWS account using Terraform with master-member hierarchy | Done | 20 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1718164 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-10 18:48 | 2025-08-21 14:33 |  |  |  | 0 | As a cloud security engineer, I want to provision Amazon inspector across all accounts in my AWS org using a delegated administrator account so that I can perform centralized automated and continuous vulnerability scanning of EC2, ECR, and Lamda across all member accounts Acceptance Criteria: * Terraform must be enabled in Payer9 account * Terraform must register the Payer9 account for Inspector within AWS organization to allow Payer9 to manage inspector across member accounts * Terraform must enable Inspector in each member account by assuming a role into those accounts for all resource types (EC2,ECR, Lamda function) must be activated * Terraform must ensure that EC2 scanning is enabled, ECR scanning is continuous, Lamda scanning is turned on * Once enabled, findings for all member accounts must be accessible from delegated account via Inspector console * The terraform config must be reusable across multiple accounts and support by parameterized resources types * All terraform created resources must include standard tags for auditability * Integrate Inspector with security hub * Alert on critical CVEs using SNS/EventBridge * Raise alerts on high severity findings |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@35c15470 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aoa3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | Sprint 12 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-18 06:22 | [13 empty] | 18/Jul/25 8:22 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Need to send the email to Ismail about add the amazon inspector in trusted entity. | 22/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Email sent to Ismaail and leigh about Request to Enable Centralized Management for GuardDuty and Amazon Inspector and currently I am working on Terrafrom script to create the base module for resources | 23/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Leigh replied and asked to Ismaail for assisting. | 25/Jul/25 8:33 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;It will be spillover because there was a dependency on Ismail and he has updated on 23 July Only so thatâ€™s why I am not able to complete it on time. | 21/Aug/25 2:33 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. Please delete Amazon Inspector instances as it is POC | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:33
AM20-100 | Provision AWS GuardDuty using Terraform | Done | 10 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718154 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-10 18:04 | 2025-08-11 04:30 |  |  |  | 0 | As a cloud security engineer I want to provision and configure AWS GuardDuty using Terraform so that I can automatically detect and respond to potential threats in my AWS environment in a consistent and repeatable manner Acceptance Criteria: * Terraform must create a GuardDuty Detector in the primary AWS region. the detector must be enabled * for multiple AWS accounts Terraform must support creating a GuardDuty master-member relationship * Members must be invited and accepted automatically * GuardDuty should automatically published findings to the console API and this must not be disabled * Terraform must be modular to support enabling GuardDuty in any account and region * inputs like region, accountid, and enable flag must be configurable * All resources created via Terraform must include project defined tags * Forward GuardDuty findings to AWS security Hub or EventBridge |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@50808e38 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ansn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-22 06:28 | [13 empty] | 22/Jul/25 8:28 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Email sent to Ismaail and leigh about Request to Enable Centralized Management for GuardDuty and Amazon Inspector and currently I am working on Terrafrom script to create the base module for resources. | 23/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Leigh replied and asked to Ismaail for assisting. | 25/Jul/25 8:33 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;It will be spillover because there was a dependency on Ismail and he has updated on 23 July Only so thatâ€™s why I am not able to complete it on time. | 30/Jul/25 8:26 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script. Ready for the demo. | 11/Aug/25 4:30 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:30
AM20-99 | Disaster Recovery and Backup | In Progress |  | None( Epic) |  |  | Yashwant Thakur | Critical | 1717990 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-10 16:37 | 2025-11-13 08:02 |  |  |  | 0 | Automated Backup and Disaster Recovery Infrastructure via Terraform or manual |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [15 empty] | 432000 | 374400 | 86400 | [12 empty] | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133603.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175536 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133705.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175534 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175537 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133947.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175535 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2309b367 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-9 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | orange | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0anuj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-30 13:41 | [13 empty] | 30/Oct/25 3:40 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Validated PROS & Informatica backups, all are configure fine. Pros back up status: !image-20251030-133603.png¦width=612,alt="image-20251030-133603.png"! Policy: !image-20251030-133705.png¦width=597,alt="image-20251030-133705.png"! Informatica Prod Backup: !image-20251030-133909.png¦width=597,alt="image-20251030-133909.png"! Status: !image-20251030-133947.png¦width=597,alt="image-20251030-133947.png"! | 13/Nov/25 8:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Backup has been configured and working fine. DR step-up is done still sync in progress. Once sync completed we can initiate call for testing. | [28 empty] | In Progress | 2025-10-30 15:30
AM20-98 | PROS ¦¦ DR | Done | 3 | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | High | 1717973 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-07-10 16:24 | 2025-10-17 11:11 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [TM1-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [11 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@49626307 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-03 07:24 | [13 empty] | 03/Oct/25 9:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Only after the server migration we would be able to do DR so this US will be blocked. | 17/Oct/25 11:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;27th Oct planned for cutover, upon server availability we will initiate DR followed by drill. since this will be spillover | [25 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-17 11:08
AM20-97 | Transit Gateway setup for Dev environment | Done | 6 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1702418 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-06-30 09:48 | 2025-07-04 12:05 |  |  |  | 0 | As Network Expert, I would be able to setup Transit network gateway for Dev environment Acceptance Criteria: Transit Gateway is provisioned successfully in Dev environment. |  | Aravind Raj | Satya Varanasi |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [13 empty] | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132834.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121470 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132924.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121472 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133228.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121473 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133337.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121469 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133439.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121471 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67c2563b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i095nv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-01 16:49 | [13 empty] | 01/Jul/25 6:49 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;There is no Preprod env for 20+ app migration list, hence we are not setting up Preprod TG attachment, in case needed near future we will setup according to requirement. In this sprint we will setup TG attach for Dev env. | 03/Jul/25 3:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Common TG Attach has be setup on shared VPC dev Account and tested internet connectivity via informatica DEV subnet. !image-20250703-132834.png¦width=1306,height=662,alt="image-20250703-132834.png"! !image-20250703-132924.png¦width=1204,height=668,alt="image-20250703-132924.png"! TG-Attach subnets: !image-20250703-133228.png¦width=1243,height=475,alt="image-20250703-133228.png"! TG attachment details. !image-20250703-133337.png¦width=1189,height=448,alt="image-20250703-133337.png"! Subnet associations !image-20250703-133439.png¦width=1215,height=611,alt="image-20250703-133439.png"! | 04/Jul/25 12:05 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed, test server is working with internet. | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-04 12:05
AM20-95 | NexioAV (Trellix) ¦¦ DR | Done | 5 | Sprint 9 | 2025-07-07 | 2025-07-18 | Yashwant Thakur | High | 1699562 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-06-26 10:04 | 2025-07-25 19:48 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Trellix-application.awsflysaa.com¦http://TM1-application.awsflysaa.com] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [13 empty] | 24/Jul/25 11:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250724-091921.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1130283 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4121fe0a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i08p7v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 10 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-08 06:08 | [13 empty] | 08/Jul/25 8:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Setting up Trellix server with AWS DR service is in progress, upon successful installation of software will initiate a replication and complete the setup. | 09/Jul/25 7:32 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;DR setup is completed followed by initial replication, upon software installation we will start replication again and perform failover and failback upon requirement. | 09/Jul/25 7:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Moving to blocked as sinjun yet to install the software. | 17/Jul/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Agent installation is completed, TM1 and frontend prod server are added for testing. | 17/Jul/25 8:09 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;will coordinate with the application owner and initiate a replication back. | 21/Jul/25 7:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Failover and Failback will be performed after getting formal approval from the application owner. | 21/Jul/25 7:04 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;replication is initialized upon bhavish confirmation. | 24/Jul/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have scheduled a call with sinjun today 1.30PM, will perform DR drill and close this userstory. | 24/Jul/25 11:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250724-091921.png¦width=682,height=443,alt="image-20250724-091921.png"! | 25/Jul/25 7:48 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [17 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-07-25 19:48
AM20-94 | Nexio AV integration with TM1 environments to allow scanning | Done | 4 | Sprint 9 | 2025-07-07 | 2025-07-18 | Yashwant Thakur | High | 1698517 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-06-25 09:52 | 2025-07-25 19:47 |  |  |  | 0 | As Network expert, I would be helping integration of Trellix and TM1 so that trellix can scan TM1 servers. Acceptance Criteria: * TM1 servers can be access via trellix successfully * TM1 servers are scanned for any vulnerability by Trellix |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 23/Jul/25 8:13 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ SAA II Nexio AV LLD Walkthrough.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1129505 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6a53d9d8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i08j3n: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 10 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-01 06:21 | [13 empty] | 01/Jul/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Trellix setup not done, need to wait until trellix ready. | 17/Jul/25 8:11 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Agent installed on TM1 test instance and tested, it is working fine. | 23/Jul/25 8:13 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Successfully Trellix setup completed and tested TM1 server and frontend environments has been registered with new Trellix. [^RE_ SAA II Nexio AV LLD Walkthrough.msg] | 25/Jul/25 7:47 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-25 19:47
AM20-92 | Provisioning of EC2 via Terraform in Nexio AV account | Done | 4 | Sprint 9 | 2025-07-07 | 2025-07-18 | Yashwant Thakur | High | 1686366 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-06-04 11:40 | 2025-07-11 13:46 |  |  |  | 0 | As a AWS expert, I would expert, I would be able to provision EC2 instance in Nexio AV account using terraform code so that the AV can be installed by the respective application Admins Acceptance Criteria: * EC2 successfully gets provisioned in Nexio AV account by terraform code |  | Faisal Sayed | Satya Varanasi |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 08/Jul/25 8:55 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250708-065045.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1123568 | 08/Jul/25 8:55 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250708-065120.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1123569 | 08/Jul/25 8:55 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250708-065236.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1123567 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@621b3d4b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-03 13:53 | [13 empty] | 03/Jul/25 3:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Cloud watch agent installation is not automated via terraform, as we can see from the metrics. This action handled by Faisal so i am assigning this story to Faisal. | 04/Jul/25 12:19 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Implemented EC2 provisioning using Terraform with support for both Linux and Windows modules. Each module includes: * EC2 instance creation with the option for multiple encrypted EBS volumes. * Separate modules for Linux and Windows OS to allow tailored configurations. * Automated installation and configuration of SSM Agent and CloudWatch Agent. * Support for tagging across all provisioned resources. * IAM handling: ability to use an existing IAM instance profile or create a new one as needed, with optional support for custom IAM roles. The implementation ensures modularity, flexibility, and security compliance across environments. | 08/Jul/25 8:55 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to story things has been configured via terraform script. Tested instance storge and configured as encrypted volumes. !image-20250708-065236.png¦width=1309,height=628,alt="image-20250708-065236.png"! Cloud watch agent configured with memory and disk monitoring. !image-20250708-065045.png¦width=1300,height=608,alt="image-20250708-065045.png"! !image-20250708-065120.png¦width=1295,height=624,alt="image-20250708-065120.png"! | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-11 13:46
AM20-91 | ServiceNow Integration with FlySAA Back-end servers for error/ reporting | Done | 5 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1685592 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-06-03 13:59 | 2025-07-09 08:43 |  |  |  | 0 | As AWS expert, I should be able to integrate ServiceNow API with FlySAA Back-end server so that in case of any error/issues, alerts can be generated and transformed into tickets in ServiceNow. Acceptance Criteria: Tickets are generate in ServiceNow against Alerts that are getting generated for FlySAA Back-End server events successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [13 empty] | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064203.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124194 | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064240.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124193 | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064306.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124195 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@78ab6644 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:06 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-02 05:24 | [13 empty] | 02/Jul/25 7:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Integration have done for backend dev with service now *dev* endpoint. Integration have done for backend prod with service now *prod* endpoint. Preprod yet to configure. | 08/Jul/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will configure the preprod endpoint with service now integration today. | 09/Jul/25 7:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Servicenow preprod integration is completed unit testing will be performed by today. | 09/Jul/25 8:41 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;746669190453 FlySAA_CMS_Backend_DevQA 216989128782 FlySAA_CMS_Backend_PreProd 396608788916 FlySAA_CMS_Backend_Prod These backend environments set with the service now integration and expected to get all the tags of instance with an alarm details. | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250709-064203.png¦width=663,height=458,alt="image-20250709-064203.png"! !image-20250709-064240.png¦width=606,height=397,alt="image-20250709-064240.png"! !image-20250709-064306.png¦width=645,height=440,alt="image-20250709-064306.png"! | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-09 08:43
AM20-90 | POC for ServiceNow Integration with TM1 servers for error/ reporting | Done | 2 | Sprint 8 | 2025-06-23 | 2025-07-04 | Aravind Raj | High | 1685590 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-06-03 13:59 | 2025-06-20 08:56 |  |  |  | 0 | As AWS expert, I should be able to integrate ServiceNow API with TM1 server so that in case of any error/issues, alerts can be generated and transformed into tickets in ServiceNow. Acceptance Criteria: Tickets are generate in ServiceNow against Alerts that are getting generated for TM1 server events successfully |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6de32f87 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i06g9v: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-20 05:58 | [13 empty] | 20/Jun/25 7:57 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Yesterday have configured SNS topic with the new subscription which has endpoint of HTTPs protocol, have verified a service now dashboard where we were getting the alert as expected. | [26 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-20 08:56
AM20-88 | BackUP Server ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | Medium | 1681815 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-05-28 11:06 | 2025-06-13 14:36 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across BackUP server account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43003ef3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4f: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-05 06:17 | [13 empty] | 05/Jun/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Config and guard Duty is enabled and configured. Cloud Trails logging is enabled already. | 06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard rail implementation is applied for the S3 block public access | 13/Jun/25 2:36 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:36
AM20-87 | Backup Server ¦¦ Security compliance implementation | Done | 3 | Sprint 7 | 2025-06-09 | 2025-06-20 | Aravind Raj | Medium | 1681806 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-05-28 11:04 | 2025-06-12 17:41 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Backup Server *Acceptance Criteria*: * Renaming of PROS account to Back-Up Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 14400 | 43200 | 1 | 43200 | 14400 | 43200 | [12 empty] | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250612-153959.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1113715 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@48024563 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-09 05:41 | [13 empty] | 09/Jun/25 7:41 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will start working on enabling security frameworks like CIS, NIST, AWS FSBP. | 10/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled controls, will be working on the controls remediation. | 11/Jun/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;controls are implemented waiting for the security score to be update Â· | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CIS, NIST and FSBP controls were enabled and required controls remediated. !image-20250612-153959.png¦width=1279,height=626,alt="image-20250612-153959.png"! | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-12 17:41
AM20-86 | Informatica Server ¦¦ CloudTrail and Guard Rail implementation | Done | 2 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | Medium | 1681743 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-05-28 10:14 | 2025-06-13 14:36 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across informatica server (PROS) account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1eb85c02 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05trf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-05 06:17 | [13 empty] | 05/Jun/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Config and guard Duty is enabled and configured. Cloud Trails logging is enabled already. | 06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard rail implementation is applied for the S3 block public access | 13/Jun/25 2:36 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:36
AM20-85 | Informatica Server ¦¦ Security compliance implementation | Done | 3 | Sprint 7 | 2025-06-09 | 2025-06-20 | Aravind Raj | Medium | 1681739 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-05-28 10:12 | 2025-06-10 08:13 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of PROS account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;10/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;10/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 43200 | 0 | 57600 | 1.33 | 43200 | 0 | 57600 | [12 empty] | 10/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250610-061229.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1112272 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2572cbfb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05tqj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-06 06:15 | [13 empty] | 06/Jun/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will be start working on enabling the frameworks, followed by that will work controls implementation and remediation | 09/Jun/25 7:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CIS NIST and AWS FSBP security frameworks are enabled, in parallel controls were implemented and have completed remediation. Awaiting for the security score to update in security hub, | 10/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Updated security hub for the different controls; !image-20250610-061229.png¦width=1279,height=587,alt="image-20250610-061229.png"! | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-10 08:12
AM20-83 | ServiceNow Monitoring ¦¦ Prod Implementation | Done | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1673102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-05-14 12:51 | 2025-07-04 08:16 |  |  |  | 0 | As AWS solution architect, I would like to implement ServiceNow monitoring in prod environment so that alerts can be generated and reach to ServiceNow in form of Tickets for further actions. Acceptance Criteria: * Setup of ServiceNow integration to pull AWS receive data using EventBridge * Unautherized API calls from GuardDuty and Security Hub * Setup Cloudwatch alarms or rules for all the resources entitled to be monitored and send these to SNS topic * Create SNS topic * Configure SNS HTTPS configuration so that SNS can directly invoke HTTPS endpoints * AWS Lambda function created to forward SNS messages by parsing it and sends REST API requests to ServiceNow. * Attach the Lamda to the SNS topic * Set the credentials in AWS Secret Manager * Lamda function can reach the ServiceNow endpoint through API gateway by using HTTPS and Secure authentication |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;04/Jul/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cfb2e84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04h5f: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-26 06:17 | [13 empty] | 26/May/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 8:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting to get a exact tags to be passed to Ec2 instance to receive at service now. *New HTTPS endpoint will be shared by feroz for the production workloads.* | 25/Jun/25 8:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;From 24th June we had a call with feroz, where we expected to get the production servicenow endpoint by nest week to configure in SNS, hence waiting for same to start this user story. | 02/Jul/25 7:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PRODUCTION ServiceNow Instance: [https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws¦https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws] SNS topic is updated with a new subscription and backend prod integration is completed, unit test yet to start. | 04/Jul/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Right now the production environments like Backend, TM1, AirnavX accounts are integrated with the prod service now endpoint and SNS is configured to get the alerts. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-04 08:15
AM20-82 | MQ ¦¦ POC customer Demo | Blocked | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Sumit Nikam | High | 1672939 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-05-14 11:35 | 2026-01-08 08:48 | 2026-01-08 08:41 |  |  | 0 | As AWS architect, I would align with SAA stakeholders to give a demo on MQ PoC. *Acceptance Criteria*: * Demo given and next steps discussed with SAA. |  | Harsh Chandra | Sankalp Rai | Sumit Nikam |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67032dc2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pttb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 15 | Sprint 16 | Sprint 22 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 08:24 | [13 empty] | 20/May/25 10:23 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 26th May 2025 End Date: 30th May 2025 | 02/Jun/25 8:26 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;MQ has two option on AWS # Migrate existing MQ Servers to AWS # Use AWS Native MQ service We need a confirmation on approach from Sampi after which we will start working on LLD Document Moving to Blocked | 24/Sep/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Will be taken up once POC is completed in Sandbox | 17/Oct/25 11:21 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 30/Oct/25 9:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;LLD no longer needed To be considered for Modernization as per feedback from Gayaz. Next steps: # Analyze Amadeus response Perform PoC as per Amadeus requirements # Agreement with SAA based on PoC # SoW sigoff # Design Document # AmazonMQ Implementation # Queue by Queue migration | 08/Jan/26 8:48 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Awaiting for a go-ahead to setup a demo call with SAA. | [21 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | To Do | 2026-01-08 08:41
AM20-81 | AirNavX Account ¦¦ Security Compliance Implementation | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672716 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-05-14 10:25 | 2025-05-28 11:24 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of AirNavX account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250528-092239.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1106065 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@33a69e54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04ft7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-28 09:24 | [13 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Account - 345594574792 Controls were implemented and security score is updated is for all the three security standard frameworks- CIS, NIST and AWS FSBP !image-20250528-092239.png¦width=1279,height=589,alt="image-20250528-092239.png"! | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-28 11:24
AM20-80 | Citrix Account ¦¦ Security Compliance Implementation | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672714 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-05-14 10:24 | 2025-05-29 08:13 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of Citrix account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 57600 | 28800 | 28800 | [12 empty] | 29/May/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250529-061118.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1106445 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@24a352a5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04fsz: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-29 06:13 | [13 empty] | 29/May/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250529-061118.png¦width=1277,height=592,alt="image-20250529-061118.png"! The sercurity controls were implemented for all the below mentioned frameworks - CIS, NIST, AWS FSBP. security score is updated for reference. | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-29 08:13
AM20-79 | AirNavX ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672697 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-05-14 10:18 | 2025-05-22 08:19 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across AirNavX account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cdd392e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04fqr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 06:27 | [13 empty] | 20/May/25 8:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on enabling the cloud config and guard duty along with macie. | 22/May/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;below mentioned service were enabled. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-22 08:19
AM20-78 | Citrix ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672695 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-05-14 10:17 | 2025-05-22 08:19 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across Citrix account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4f5d9411 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04fqj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 06:27 | [13 empty] | 20/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on enabling the cloud config and guard duty along with macie. | 22/May/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;below mentioned service were enabled. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-22 08:19
AM20-76 | AirNavX ¦¦ Comms Matrix modification | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Yashwant Thakur | High | 1672499 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-05-14 09:08 | 2025-06-16 08:34 |  |  |  | 0 | As Network expert, I would be modifying the comms Metrices for AirNavX as the number of servers reduced to 3 servers instead of earlier scope of 5 servers. Acceptance Criteria: * Comms Metrics are successfully created * Sent for reviews to SITA team and agreement received |  | Harsh Chandra | Satya Varanasi | Sumit Nikam | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@40de4872 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04f2j: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-23 11:33 | [13 empty] | 23/May/25 1:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working it will be ready next week. | 27/May/25 8:12 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started and will be closed today or tomorrow. | 28/May/25 5:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;I have prepared 3 servers AirNavx comms and sending for review. | 16/Jun/25 8:32 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;This was checked and reviewed. | 16/Jun/25 8:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-16 08:34
AM20-75 | POC ¦¦ installing SSM agent and cloud watch agent for linux and windows server | Done | 20 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1669245 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-05-12 09:34 | 2025-06-29 20:14 |  |  |  | 0 | As AWS Expert, I should be able to provision Cloudwatch and SSM agent in sandbox Acceptance Criteria: ssm agent should help to connect to server and to do patch manager, wheras cloud watch agent to push the system logs to the cloud watch log group and to push custom metrics to the cloud watch dashboard |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Onkar Mirajkar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4bb35693 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i043kj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-14 17:07 | [13 empty] | 14/May/25 7:07 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Uninstalled SSM agent and Installed SSM agent -Done | 14/May/25 7:07 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Configured/Installed CloudWatch Agent manually on Ec2 instance | 14/May/25 7:08 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Automating the Installing process for CloudWatch Agent ---Pending | 21/May/25 8:49 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;I provided Faisal with an overview of the installation process for the CloudWatch Agent using SSM, and he has begun working on it using Terraform. | 29/May/25 10:14 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;+*What is being achieved via Terraform Automation Script:*+ # *Automated Provisioning* * Spins up EC2, sets IAM role + profile. * No manual SSH stepsâ€”even the agent install & config is done via user-data (and reinforced via SSM). # *Full Observability* * Metrics: CPU, memory, disk, network in the CWAgent namespace. * Logs: System logs (/var/log/messages, /var/log/secure) in CloudWatch Logs, with 14â€day retention. # *Resilience & Drift-Correction* * SSM association ensures the agent stays configured (you can re-run â€œterraform applyâ€ to heal it). * Pre-created Log Groups prevent silent failures due to missing groups. *â€œThe terraform script is battle tested in Sandbox Account via terraform locally installed.â€* | 11/Jun/25 8:26 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;The Terraform script has been completed, thoroughly tested, and all feedback has been incorporated. I will schedule another review to finalize it. | 16/Jun/25 10:03 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# *Used SSM Documents to Automate Agent Installation*Â * We leveraged *AWS SSM Run Command* documents instead of manual scripts or hardcoding logic.Â * Specifically, we used:Â * {{AWS-ConfigureAWSPackage}} to *install the CloudWatch Agent*Â * {{AmazonCloudWatch-ManageAgent}} to *configure and start the agent* using a *Parameter Store JSON config* named {{/Windows_Monitor_CW}}.Â Â *ðŸ”¹ 2. Embedded SSM Associations in Terraform*Â * Inside our *main EC2 Terraform project*, we embedded two {{aws_ssm_association}} resources:Â * *install_cwagent_windows* â€“ installs CloudWatch agentÂ * *configure_cwagent_windows* â€“ tells the agent to pull its config from {{/Windows_Monitor_CW}} in SSM Parameter Store and start itÂ * Both associations *target EC2 instances by tag*: {{CWAgent = EnabledÂ }} * The EC2 instances were pre-tagged via Terraform to ensure automatic targetingÂ Â *ðŸ”¹ 3. Created a Third Association to Force Re-fetch Config*Â * In some cases, the agent might need to re-fetch its config after the EC2 instance is up and the services are stable.Â * So we created a *third SSM association*: {{force_fetch_start_agentÂ }} * Uses {{AWS-RunPowerShellScript}} to run:Â {{& "C:\Program Files\Amazon\AmazonCloudWatchAgent\amazon-cloudwatch-agent-ctl.ps1" -a fetch-config -m ec2 -c ssm:/Windows_Monitor_CW -sÂ }} Â * This *manually triggers the fetch* of the config from SSM Parameter Store and starts the agent again if neededÂ Â *ðŸ”¹ 4. Split This Trigger into a Separate Terraform Directory*Â * To keep your deployment clean and *modular*, we:Â * Created a new folder: {{terraform/cwagent-trigger/Â }} * Placed only the {{force_fetch_start_agent}} logic in this moduleÂ * Why?Â * This allows you to *run it manually or conditionally* after core EC2 and SSM setups are completeÂ * Ensures *clean execution ordering* and better control in CI/CDÂ * Prevents early execution before the agent is even installedÂ Â *ðŸ”¹ 5. Designed for Platform-Specific Control*Â * Logic is gated with:Â {{count = var.platform == "windows" && var.enable_windows_ssm_association ? 1 : 0Â }} Â * Ensures this entire operation is *executed only for Windows instances*, as Linux would follow a different path.Â | 24/Jun/25 6:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have reviewed the server deployed SSM agent installed successfully. | 29/Jun/25 8:14 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [18 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:14
AM20-74 | Terraform Development ¦¦ Define CloudWatch Agent config and Automate Agent Start via Terraform | Done | 20 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1661298 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-05-02 11:58 | 2025-06-29 20:15 |  |  |  | 0 | As Devops Engineer, I would like to define the CloudWatch Agentâ€™s configuration and Automate Cloud Watch Agent start using Terraform so that the metrics and logs it collects are consistent across environments Acceptance Criteria: * Terraform manages the agent config JSON file as a template * The config files includes, CPU, Memory, disk and Network metrics and application/system log files paths. * The file is stored locally or pushed to EC2 during provisioning via user_data * Terraform - provisioned EC2 instances start the CloudWatch agent on boot * The agent fetches the config file and start sending data to CloudWatch * Verification - Metrics and logs appear in CloudWatch console post launch |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7aab33b8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4h: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-11 06:40 | [13 empty] | 11/Jun/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;* The Terraform script for configuring and starting the CloudWatch agent is ready for both Linux and Windows instances. * Linux automation is working as expected. * Faced issues with Windows agent installation during EC2 provisioning. * Initial approach used user data to download and install the CloudWatch agent. * Encountered failure due to network not being ready at the time of user data execution. * Attempted to resolve this with a 60-second sleep delay, but it was unsuccessful. * New approach identified: using SSM documents to automate agent installation post-boot. * Will implement this alternative and move the changes to code review. * A meeting will be scheduled following successful implementation. | 16/Jun/25 10:03 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# *Used SSM Documents to Automate Agent Installation*Â * We leveraged *AWS SSM Run Command* documents instead of manual scripts or hardcoding logic.Â * Specifically, we used:Â * {{AWS-ConfigureAWSPackage}} to *install the CloudWatch Agent*Â * {{AmazonCloudWatch-ManageAgent}} to *configure and start the agent* using a *Parameter Store JSON config* named {{/Windows_Monitor_CW}}.Â Â *ðŸ”¹ 2. Embedded SSM Associations in Terraform*Â * Inside our *main EC2 Terraform project*, we embedded two {{aws_ssm_association}} resources:Â * *install_cwagent_windows* â€“ installs CloudWatch agentÂ * *configure_cwagent_windows* â€“ tells the agent to pull its config from {{/Windows_Monitor_CW}} in SSM Parameter Store and start itÂ * Both associations *target EC2 instances by tag*: {{CWAgent = EnabledÂ }} * The EC2 instances were pre-tagged via Terraform to ensure automatic targetingÂ Â *ðŸ”¹ 3. Created a Third Association to Force Re-fetch Config*Â * In some cases, the agent might need to re-fetch its config after the EC2 instance is up and the services are stable.Â * So we created a *third SSM association*: {{force_fetch_start_agentÂ }} * Uses {{AWS-RunPowerShellScript}} to run:Â {{& "C:\Program Files\Amazon\AmazonCloudWatchAgent\amazon-cloudwatch-agent-ctl.ps1" -a fetch-config -m ec2 -c ssm:/Windows_Monitor_CW -sÂ }} Â * This *manually triggers the fetch* of the config from SSM Parameter Store and starts the agent again if neededÂ Â *ðŸ”¹ 4. Split This Trigger into a Separate Terraform Directory*Â * To keep your deployment clean and *modular*, we:Â * Created a new folder: {{terraform/cwagent-trigger/Â }} * Placed only the {{force_fetch_start_agent}} logic in this moduleÂ * Why?Â * This allows you to *run it manually or conditionally* after core EC2 and SSM setups are completeÂ * Ensures *clean execution ordering* and better control in CI/CDÂ * Prevents early execution before the agent is even installedÂ Â *ðŸ”¹ 5. Designed for Platform-Specific Control*Â * Logic is gated with:Â {{count = var.platform == "windows" && var.enable_windows_ssm_association ? 1 : 0Â }} Â * Ensures this entire operation is *executed only for Windows instances*, as Linux would follow a different path.Â | 24/Jun/25 6:55 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;cloud watch agent installation is done using terraform script, have enabled only memory and disk utilization as of now. | 29/Jun/25 8:14 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:15
AM20-73 | Terraform Development ¦¦ CloudWatch Agent deployment across multiple instances | Done | 0 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1661291 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-05-02 11:50 | 2025-06-29 20:15 |  |  |  | 0 | AS DevOps Engineer, I want to manage CloudWatch Agent deployment across multiple instances using Terraform so that the setup is consistent , Scalable and repeatable Acceptance Criteria: * Terraform module supports deploying CloudWatch agent setup to multiple EC2 instances * Changes to the config or deployment can be applied centrally via Terraform * Terraform State reflects current deployed infrastructure and config |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [45 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cbbbf77 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i06kuv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-16 06:26 | [13 empty] | 16/Jun/25 8:26 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;* The Terraform script for configuring and starting the CloudWatch agent is ready for both Linux and Windows instances. * Linux automation is working as expected. * Faced issues with Windows agent installation during EC2 provisioning. * Initial approach used user data to download and install the CloudWatch agent. * Encountered failure due to network not being ready at the time of user data execution. * Attempted to resolve this with a 60-second sleep delay, but it was unsuccessful. * New approach identified: using SSM documents to automate agent installation post-boot. * Will implement this alternative and move the changes to code review. * A meeting will be scheduled following successful implementation. | 16/Jun/25 10:04 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# *Used SSM Documents to Automate Agent Installation*Â * We leveraged *AWS SSM Run Command* documents instead of manual scripts or hardcoding logic.Â * Specifically, we used:Â * {{AWS-ConfigureAWSPackage}} to *install the CloudWatch Agent*Â * {{AmazonCloudWatch-ManageAgent}} to *configure and start the agent* using a *Parameter Store JSON config* named {{/Windows_Monitor_CW}}.Â Â *ðŸ”¹ 2. Embedded SSM Associations in Terraform*Â * Inside our *main EC2 Terraform project*, we embedded two {{aws_ssm_association}} resources:Â * *install_cwagent_windows* â€“ installs CloudWatch agentÂ * *configure_cwagent_windows* â€“ tells the agent to pull its config from {{/Windows_Monitor_CW}} in SSM Parameter Store and start itÂ * Both associations *target EC2 instances by tag*: {{CWAgent = EnabledÂ }} * The EC2 instances were pre-tagged via Terraform to ensure automatic targetingÂ Â *ðŸ”¹ 3. Created a Third Association to Force Re-fetch Config*Â * In some cases, the agent might need to re-fetch its config after the EC2 instance is up and the services are stable.Â * So we created a *third SSM association*: {{force_fetch_start_agentÂ }} * Uses {{AWS-RunPowerShellScript}} to run:Â {{& "C:\Program Files\Amazon\AmazonCloudWatchAgent\amazon-cloudwatch-agent-ctl.ps1" -a fetch-config -m ec2 -c ssm:/Windows_Monitor_CW -sÂ }} Â * This *manually triggers the fetch* of the config from SSM Parameter Store and starts the agent again if neededÂ Â *ðŸ”¹ 4. Split This Trigger into a Separate Terraform Directory*Â * To keep your deployment clean and *modular*, we:Â * Created a new folder: {{terraform/cwagent-trigger/Â }} * Placed only the {{force_fetch_start_agent}} logic in this moduleÂ * Why?Â * This allows you to *run it manually or conditionally* after core EC2 and SSM setups are completeÂ * Ensures *clean execution ordering* and better control in CI/CDÂ * Prevents early execution before the agent is even installedÂ Â *ðŸ”¹ 5. Designed for Platform-Specific Control*Â * Logic is gated with:Â {{count = var.platform == "windows" && var.enable_windows_ssm_association ? 1 : 0Â }} Â * Ensures this entire operation is *executed only for Windows instances*, as Linux would follow a different path.Â | 24/Jun/25 6:54 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;terraform script is enabled with the SSM agent installation, a server deployed in sandbox and have verified it. | 29/Jun/25 8:15 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:15
AM20-70 | Informatica Server ¦¦ CloudTrail and Guardrail Implementation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | High | 1660685 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-04-30 13:36 | 2025-05-09 08:04 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across NexioAV account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;09/May/25 8:04 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6098bb44 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bmz: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-09 06:04 | [13 empty] | 09/May/25 8:04 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWs config, along with security hub is enabled to capture controls status. Followed by that Guard Duty and AWS macie is enabled. | [26 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-09 08:04
AM20-69 | Nexio AV ¦¦ CloudTrail and GuardDuty & AWS config Implementation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | High | 1660681 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-04-30 13:35 | 2025-05-07 08:28 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across NexioAV account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;07/May/25 8:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@319a088e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bmj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-06 06:25 | [13 empty] | 06/May/25 8:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cloud Trails logs to push S3 bucket were implemented already through SCP, now working with guard duty and AWs config enablement. | 07/May/25 8:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard Duty and AWs config is enabled, along with trail. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-07 08:28
AM20-68 | Informatica Server ¦¦ Subnet creation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660595 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-04-30 12:49 | 2025-06-29 20:13 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Nexio AV application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Nexio AV and the configured based on the approved comms matrix |  | Aravind Raj | Harsh Chandra | Satya Varanasi | Shreyash Talwekar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 27/Jun/25 3:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-135131.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119370 | 27/Jun/25 3:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-135223.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119371 | 27/Jun/25 5:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155229.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119409 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@435a4769 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-16 08:08 | [13 empty] | 16/May/25 10:07 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Waiting for terraform code towards build this. | 20/May/25 5:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Deepak and team, this need to be addressed with terraform code the same has been prepared by Utkarsh, until core not ready this story may not possible to address. | 10/Jun/25 2:03 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still â€œShreyashâ€ checking Utkarsh script, this story depending with script testing and execution. | 16/Jun/25 9:06 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Terraform script is under modification by â€œShreyashâ€, as per his update it will be ready this week. Hence this is the reason for spill over Sprint7 to Sprint8. | 16/Jun/25 9:15 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Currently working on updating terraform script based on latest naming convention requirement. | 18/Jun/25 11:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The script is managing by â€œShreyashâ€ so i am assigning this task to him, once his work completes he will reassign to me. | 23/Jun/25 1:58 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We were able to create AWS resources (mentioned in previous mail ) using terraform scripts on sharedvpc-dev account. To address some requirements like adding naming conventions and state file management, we will have to add some changes in terraform scripts. Due to current sprint activities I might not be able to work on the changes in this sprint. | 27/Jun/25 3:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Prod Subnet/Route table has been created, & tested internet access and same working fine. !image-20250627-135131.png¦width=1261,height=434,alt="image-20250627-135131.png"! !image-20250627-135223.png¦width=1112,height=588,alt="image-20250627-135223.png"! sh-5.2$ ping [http://google.com¦http://google.com¦smart-link] PING [http://google.com¦http://google.com¦smart-link] (142.251.47.238) 56(84) bytes of data. 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=1 ttl=108 time=20.5 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=2 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=3 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=4 ttl=108 time=19.7 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=5 ttl=108 time=19.8 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=6 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=7 ttl=108 time=19.7 ms ^C --- [http://google.com¦http://google.com¦smart-link] ping statistics --- 7 packets transmitted, 7 received, 0% packet loss, time 6010ms rtt min/avg/max/mdev = 19.630/19.800/20.473/0.282 ms sh-5.2$ hostname [ip-10-40-0-213.awsflysaa.com¦http://ip-10-40-0-213.awsflysaa.com] sh-5.2$ ifconfig ens5: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 9001 inet 10.40.0.213 netmask 255.255.255.240 broadcast 10.40.0.223 inet6 fe80::4a7:ebff:fe03:c075 prefixlen 64 scopeid 0x20<link> ether 06:a7:eb:03:c0:75 txqueuelen 1000 (Ethernet) RX packets 1653 bytes 293385 (286.5 KiB) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 1809 bytes 265312 (259.0 KiB) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0 lo: flags=73<UP,LOOPBACK,RUNNING> mtu 65536 inet 127.0.0.1 netmask 255.0.0.0 inet6 ::1 prefixlen 128 scopeid 0x10<host> loop txqueuelen 1000 (Local Loopback) RX packets 12 bytes 1020 (1020.0 B) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 12 bytes 1020 (1020.0 B) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0. | 27/Jun/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev Subnet and route table has been created. !image-20250627-155229.png¦width=1259,height=431,alt="image-20250627-155229.png"! | 27/Jun/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet creation and sharing is done, have reviewed. | 29/Jun/25 8:13 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:13
AM20-67 | Informatica Server ¦¦ NACL and Security group creation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660593 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-04-30 12:47 | 2025-06-29 20:13 |  |  |  | 0 | As Network expert, I would be creating NACL and Security group along with inbound and outbound rules for Nexio AV Acceptance Criteria: NACL and Security group created successfully with all inbound and outbound rules |  | Aravind Raj | Harsh Chandra | Satya Varanasi | Shreyash Talwekar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 27/Jun/25 3:51 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-134901.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119369 | 27/Jun/25 3:51 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-134948.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119368 | 27/Jun/25 5:54 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155416.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119411 | 27/Jun/25 5:54 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155445.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119410 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4189bc9b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bbn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-16 08:01 | [13 empty] | 16/May/25 10:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Waiting for terraform code towards build this. | 20/May/25 5:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Deepak and team, this need to be addressed with terraform code the same has been prepared by Utkarsh, until core not ready this story may not possible to address. | 10/Jun/25 2:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still â€œShreyashâ€ checking Utkarsh script, this story depending with script testing and execution. | 16/Jun/25 9:06 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Terraform script is under modification by â€œShreyashâ€, as per his update it will be ready this week. Hence this is the reason for spill over Sprint7 to Sprint8. | 18/Jun/25 11:11 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The script is managing by â€œShreyashâ€ so i am assigning this task to him, once his work completes he will reassign to me. | 23/Jun/25 1:59 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We were able to create AWS resources (mentioned in previous mail ) using terraform scripts on sharedvpc-dev account. To address some requirements like adding naming conventions and state file management, we will have to add some changes in terraform scripts. Due to current sprint activities I might not be able to work on the changes in this sprint. | 27/Jun/25 3:46 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Prod NACL/SG has been created, & tested internet access and same working fine. !image-20250627-134901.png¦width=1092,height=400,alt="image-20250627-134901.png"! !image-20250627-134948.png¦width=1308,height=579,alt="image-20250627-134948.png"! sh-5.2$ ping [http://google.com¦http://google.com¦smart-link] PING [http://google.com¦http://google.com¦smart-link] (142.251.47.238) 56(84) bytes of data. 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=1 ttl=108 time=20.5 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=2 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=3 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=4 ttl=108 time=19.7 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=5 ttl=108 time=19.8 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=6 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=7 ttl=108 time=19.7 ms ^C --- [http://google.com¦http://google.com¦smart-link] ping statistics --- 7 packets transmitted, 7 received, 0% packet loss, time 6010ms rtt min/avg/max/mdev = 19.630/19.800/20.473/0.282 ms sh-5.2$ hostname [ip-10-40-0-213.awsflysaa.com¦http://ip-10-40-0-213.awsflysaa.com] sh-5.2$ ifconfig ens5: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 9001 inet 10.40.0.213 netmask 255.255.255.240 broadcast 10.40.0.223 inet6 fe80::4a7:ebff:fe03:c075 prefixlen 64 scopeid 0x20<link> ether 06:a7:eb:03:c0:75 txqueuelen 1000 (Ethernet) RX packets 1653 bytes 293385 (286.5 KiB) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 1809 bytes 265312 (259.0 KiB) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0 lo: flags=73<UP,LOOPBACK,RUNNING> mtu 65536 inet 127.0.0.1 netmask 255.0.0.0 inet6 ::1 prefixlen 128 scopeid 0x10<host> loop txqueuelen 1000 (Local Loopback) RX packets 12 bytes 1020 (1020.0 B) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 12 bytes 1020 (1020.0 B) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0. | 27/Jun/25 5:54 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev: NACL/SG got created. !image-20250627-155416.png¦width=1246,height=457,alt="image-20250627-155416.png"! !image-20250627-155445.png¦width=1155,height=624,alt="image-20250627-155445.png"! | 27/Jun/25 6:13 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;NACL and Route table created for informatica environment, route entry and NACL rules to be created upon network requirement. | 29/Jun/25 8:13 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [17 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-29 20:13
AM20-66 | Informatica Server account (Formerly PROS) ¦¦ Security compliance Implementation | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | High | 1660212 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-04-30 10:27 | 2025-05-13 07:43 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of PROS account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;13/May/25 7:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;13/May/25 7:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 13/May/25 7:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250513-054135.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1099412 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1dbe4a84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a3f: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-09 06:12 | [13 empty] | 09/May/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on the CIS, NIST and AWS FSBP controls enablement followed by remediation. | 13/May/25 7:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Pros Production account controls were implemented and score got updated successfully. !image-20250513-054135.png¦width=1272,height=587,alt="image-20250513-054135.png"! | 13/May/25 7:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Dev account of PROS yet to implemented. | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-13 07:42
AM20-65 | Nexio AV ¦¦ Security compliance Implementation | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | High | 1660206 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-04-30 10:22 | 2025-05-13 07:39 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Nexio AV account *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;13/May/25 7:39 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;13/May/25 7:39 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 13/May/25 7:38 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250513-053834.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1099411 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@26327809 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a2j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-07 06:31 | [13 empty] | 07/May/25 8:30 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Security compliance implemented, awaiting for the security score to update. | 13/May/25 7:38 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Controls were implemented and score updated successfully. !image-20250513-053834.png¦width=1276,height=567,alt="image-20250513-053834.png"! | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-13 07:39
AM20-64 | PROS ¦¦ Back-UP using Terraform | Done | 4 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | High | 1660115 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-04-30 09:59 | 2025-10-31 09:32 |  | 2025-10-31 09:32 |  | 0 | As AWS expert, I would like to provision backup using terraform * Incremental back up(daily back) * Full backup (Weekly) *Acceptance Criteria* : * The Life cycle manager has two schedule (Incremental and Full backup) successfully implemented * Back up must be automated using native AWS features and tools * Point-in-time recovery for database must be enabled to allow recovery to any second within retention window * Define retention policy and enforce retention ( 7 days, 35 days, monthly snapshot for 1 year) * Automatically transition of old backups to cold storage * Use AWS backup vault lock for Write once and Read many compliance * Backup must be encrypted at rest and in transit * Restore process is well documented and well tested * After restore data integrity checks and application consistency should be validated * Use AWS backup for central management of backup policies and vaults * Automate backup selection using resource tags * Backups must meet regulatory compliance like GDPR,HIPAA * and Audit trail of backup creation, deletion and restore events must be maintained * Periodic restore testing must be conducted and logged to validate data integrity * *AWS part:* * Use AWS config rules to enforce mandatory backup configurations * Use Cloudwatch to success/failure backups * Setup alerts for backup failure or missed backups via SNS * IAM Policies for access control to restrict who can create, view, delete and restore backups * All backup and restore operations must be logged in AWS Cloudtrail for traceability |  | Harsh Chandra | Onkar Mirajkar | Sanket Kale | Satya Varanasi | Yashwant Thakur |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;AM20-99_attachments.zip;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175550 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133603.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175548 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133705.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175552 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175549 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133947.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175551 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@558af396 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v9 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 15 | Sprint 16 | Sprint 17 | [93 empty] | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 |  | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | [65 empty] | YES | YES | 2025-05-29 08:54 | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | [12 empty] | 29/May/25 10:53 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;To be checked with Utkarsh and Satyabrata for terraform automation | 04/Jun/25 8:10 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;h6. TM1 ¦¦ Back-UP Backups will performed via DLM | 11/Jun/25 8:36 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;This is blocked due to Arvind Story as its not migrated | 25/Sep/25 9:28 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;currently working on wrapper module | 30/Sep/25 7:59 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;As per discuss with Aravind the server is not spined up as of now. | 30/Oct/25 3:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Validated and configured fine. PROS and informatica PROD servers backups has been configured and running fine. Daily backup with 7 days retention and weekly backup with 90 days retention. [^AM20-99_attachments.zip] !image-20251030-133705.png¦width=597,alt="image-20251030-133705.png"! !image-20251030-133947.png¦width=597,alt="image-20251030-133947.png"! !image-20251030-133909.png¦width=597,alt="image-20251030-133909.png"! !image-20251030-133603.png¦width=597,alt="image-20251030-133603.png"! | 31/Oct/25 9:32 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved as Backup is implemented successfully for PROS | [20 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-31 09:32
AM20-63 | Creating Transit Gateway attachment with centralized subnet in Shared VPC account | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-04-30 09:51 | 2025-06-02 09:20 |  |  |  | 0 | As Network expert I would like to Create Transit Gateway attachment with centralized subnet in Shared VPC account *Acceptance Criteria*: * Transit Gateway attachment is successfully created with centralized subnet |  | Harsh Chandra | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100033 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052941.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100030 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-053047.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100031 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-053208.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100032 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-074925.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103901 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-074943.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103902 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075022.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103900 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075049.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103899 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075143.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103903 | [9 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@64ab5b36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i039pn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-07 16:16 | [13 empty] | 07/May/25 6:15 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dedicated TG attachment subnet created and attached. Testing is pending. | 12/May/25 7:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Test will be initiated today | 14/May/25 7:34 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TG attachment has been configured. Need to test internet connectivity with other accounts. All details shared below. ¦10.40.1.160/28¦10.40.1.160 - 10.40.1.175¦10.40.1.161 - 10.40.1.174¦14¦/28¦AZ1¦Â ¦ ¦10.40.1.176/28¦10.40.1.176 - 10.40.1.191¦10.40.1.177 - 10.40.1.190¦14¦/28¦Â ¦AZ2¦ !image-20250514-052909.png¦width=1135,height=580,alt="image-20250514-052909.png"! !image-20250514-052941.png¦width=1126,height=583,alt="image-20250514-052941.png"! Route table; !image-20250514-053047.png¦width=1126,height=536,alt="image-20250514-053047.png"! Interface associations: !image-20250514-053208.png¦width=1137,height=568,alt="image-20250514-053208.png"! | 14/May/25 5:08 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Common TG attach created and working for multi account, but still need to test further with different scenarios. This required further testing for closer. | 14/May/25 7:13 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;All tests done and working according to our requirement. | 19/May/25 11:26 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Could not verify the routing to internet Routing to internet to be verified and updated Assigning back to [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 19/May/25 5:57 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Routes has been showed overcall. All are configured according to requirement. S C:\Windows\system32> tracert [http://google.com¦http://google.com¦smart-link] Â Tracing route to [http://google.com¦http://google.com¦smart-link] [192.178.54.142] over a maximum of 30 hops: Â Â 1Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 2Â Â Â <1 msÂ Â Â <1 msÂ Â Â <1 msÂ 172.22.2.132---> security account---going to IGW Â 3Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 4Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 5Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 6Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 7Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 99.83.116.121---> AWS datacenter Â 8Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 172.253.65.163---> Google DC Â 9Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 192.178.73.217---->google dc 10Â Â Â 18 msÂ Â Â 18 msÂ Â Â 18 msÂ [tzjnba-ah-in-f14.1e100.net¦http://tzjnba-ah-in-f14.1e100.net] [192.178.54.142]--->google dc Â Trace complete. PS C:\Windows\system32> | 20/May/25 5:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This story reassigned yesterday for routing validation so this will be closed this sprint. | 22/May/25 9:52 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As discussed we have validated routing entries and tracert has been updated with details. Subnets: !image-20250522-074925.png¦width=1109,height=569,alt="image-20250522-074925.png"! !image-20250522-074943.png¦width=1114,height=569,alt="image-20250522-074943.png"! Roue table: !image-20250522-075022.png¦width=1112,height=520,alt="image-20250522-075022.png"! !image-20250522-075049.png¦width=1107,height=559,alt="image-20250522-075049.png"! !image-20250522-075143.png¦width=1100,height=565,alt="image-20250522-075143.png"! Please review the same. | 30/May/25 2:46 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Review Done Transitioning to PO approval | 02/Jun/25 9:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-02 09:19
AM20-62 | Alignment of AWS account in Control tower | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | Highest | 1660079 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2025-04-30 09:47 | 2025-05-19 08:11 |  |  |  | 0 | As AWS expert, I would like to perform clean-up the account in control tower that is not needed and perform changes in control tower w.r.t changes in optimization of workload utilization *Acceptance Criteria*: * Clean-up account in control tower is successfully completed * Identified workload utilization are optimized successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;19/May/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@44b8caa8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i039nf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-14 06:28 | [13 empty] | 14/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will connect with takura today and initiate a modification to the hierarchy of AWS accounts under AWS organizations. | 19/May/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CMS Front Dev/QA > FLYSAA OU (Workload OU) Backend > FLYSAA OU (Workload OU) 730335236533 AWS_SAA_Security (Check for services) >>Infra OU 339712943527 AWS_SAA_Network (Check for Services) >> > Infra OU Â | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-19 08:09
AM20-60 | Terraform Development ¦¦ Creation of Outbound and inbound rules in Security group | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1651502 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 12:15 | 2025-11-14 15:29 |  | 2025-11-14 15:29 |  | 0 | As Terraform expert, I want to be creating security group with configurable inbound and outbound rules using terraform code, so that I can control access to EC2 instance Acceptance Criteria: * Define variable for CIDRs, ports and subnets * Security group resources is created in terraform * Inbound rules allow SSH from configurable CIDR blocks * Application inbound rule and comms metric needs to populated for SG * Outbound rules allow return traffic on the same ports. * Each rule use aws_security_group_rule resources * VPC id is passed as variable * add rule description and tags. * Provision to add or deny additional inbound and outbound rules with limit of max. 35 rules can be added |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4da9d53d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 18 | [97 empty] | 3_*:*_1_*:*_428274148_*¦*_10041_*:*_1_*:*_17696354483_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_428274148_*¦*_10041_*:*_1_*:*_17696354483_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_428274148_*¦*_10041_*:*_1_*:*_17696354483_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_428274148_*¦*_10041_*:*_1_*:*_17696354483_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:03 | 3_*:*_1_*:*_428274148_*¦*_10041_*:*_1_*:*_17696354483_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:02 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;We are ready with the code but testing is pending. we are not able to test because sandbox automation is not working. | [26 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-11-14 15:29
AM20-59 | Nexio AV ¦¦ NACL and Security group creation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1651444 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 11:32 | 2025-06-02 11:49 |  |  |  | 0 | As Network expert, I would be creating NACL and Security group along with inbound and outbound rules for Nexio AV Acceptance Criteria: NACL and Security group created successfully with all inbound and outbound rules |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 23/May/25 1:31 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250523-112008.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1104629 | 23/May/25 1:31 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250523-112040.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1104627 | 23/May/25 1:31 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250523-113036.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1104628 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2fa45b90 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a2r: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-07 16:24 | [13 empty] | 07/May/25 6:23 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This task will be completed on Thursday. | 14/May/25 7:37 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Depending with automation. Checking with â€œUtkarsh Kumarâ€ | 16/May/25 10:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Waiting for terraform code towards build this. | 20/May/25 5:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Deepak and team, this need to be addressed with terraform code the same has been prepared by Utkarsh, until core not ready this story may not possible to address. | 23/May/25 1:31 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Created NACL and Security groups. !image-20250523-112008.png¦width=1097,height=477,alt="image-20250523-112008.png"! !image-20250523-112040.png¦width=1092,height=475,alt="image-20250523-112040.png"! Security Group for TrellixAV: !image-20250523-113036.png¦width=1097,height=631,alt="image-20250523-113036.png"! Please review for the same. | 30/May/25 2:46 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Review Done Transitioning to PO approval | 02/Jun/25 9:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | 02/Jun/25 11:49 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-02 11:49
AM20-58 | TM1 ¦¦ DR | Done | 1 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | Medium | 1651426 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 11:21 | 2025-09-05 10:28 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [TM1-application.awsflysaa.com¦http://TM1-application.awsflysaa.com] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Aug/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 14400 | 14400 | 28800 | 2 | 14400 | 14400 | 28800 | [12 empty] | 18/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250818-061411.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1140609 | 05/Sep/25 9:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250905-071551.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148373 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f013e1f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4i:y | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-13 15:59 | [13 empty] | 13/Jun/25 5:58 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked with TM1 Agent Installation - [https://vodacom.atlassian.net/browse/FCBEM-593¦https://vodacom.atlassian.net/browse/FCBEM-593¦smart-link] | 18/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 DR setup is configured and replication agent is installed in target server. !image-20250818-061411.png¦width=1270,height=538,alt="image-20250818-061411.png"! | 18/Aug/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;DR drill can be performed to perform a actual DR failover and failback application team should approve. | 21/Aug/25 6:08 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;DR drill will be a spill over as testing team is available on 25th Aug. | 02/Sep/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Scheduling a call today with george for DR drill. | 05/Sep/25 9:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Dr drill is completed, and got a confirmation from george. !image-20250905-071551.png¦width=1277,height=489,alt="image-20250905-071551.png"! | 05/Sep/25 10:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved * | [20 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-09-05 10:28
AM20-57 | TM1 ¦¦ Monitoring Servers post migration | Done | 1 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | High | 1651402 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 11:09 | 2025-08-25 06:31 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if TM1 server service is stopped |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 20/Aug/25 6:27 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250820-162717.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1142337 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2a36f4c8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4i:z | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-13 15:59 | [13 empty] | 13/Jun/25 5:58 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked with TM1 Agent Installation - [https://vodacom.atlassian.net/browse/FCBEM-593¦https://vodacom.atlassian.net/browse/FCBEM-593¦smart-link] | 13/Aug/25 12:42 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 cutover completed and monitoring enable but need to create TM1 dash board. | 18/Aug/25 4:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 dashboard has been created under 20Plus apps dashboard. | 19/Aug/25 5:46 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Alerts has been configured and currently in review stage. | 20/Aug/25 6:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Service now team the alerts has been reaching to from cloud watch dash board. Attaching reference screen shot. !image-20250820-162717.png¦width=1910,height=508,alt="image-20250820-162717.png"! | 21/Aug/25 6:09 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed | 25/Aug/25 6:31 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-08-25 06:31
AM20-56 | TM1 ¦¦ Cutover | Done | 4 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | High | 1651369 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 10:54 | 2025-08-20 08:10 |  |  |  | 0 | As AWS expert I would be performing the cutover for TM1 application. Acceptance Criteria: * Replication from on-prem is successfully stopped using API calls * Back up of TM1 VDC Server * Monitoring disable - VDC Server * Shutting down TM1 application in VDC * Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [TM1-application.awsflysaa.com¦http://TM1-application.awsflysaa.com] Server to the AD * MAT Testing completed successfully by SAA |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Aug/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 14/Aug/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250814-063655.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139643 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3da06808 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4i:x | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-04 06:12 | [13 empty] | 04/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for agent installation to complete | 13/Jun/25 5:58 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked with TM1 Agent Installation - [https://vodacom.atlassian.net/browse/FCBEM-593¦https://vodacom.atlassian.net/browse/FCBEM-593¦smart-link] | 27/Jul/25 10:00 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Performance testing is in progress. | 13/Aug/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have initiated a cutover and instance is up with the data and application. Testing is done awaiting for an formal approval on confirmation to finalize the cutover. have added server to the [awsflysaa.com¦http://awsflysaa.com] domain, installed cloud watch agent inside the server successfully. | 14/Aug/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cutover completed marking finalize cutover !image-20250814-063655.png¦width=1271,height=479,alt="image-20250814-063655.png"! | 20/Aug/25 8:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-08-20 08:10
AM20-55 | Adding windows server to the AWS managed AD | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651361 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 10:51 | 2025-05-02 16:56 |  |  |  | 0 | As AWS expert, I would be creating Powershell script for Windows server to integrate AWS-AD. Acceptance Criteria: * Powershall script is created successfully and should be able to integrate AWS-AD |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 57600 | 28800 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5e39db2e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02a6b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 06:19 | [13 empty] | 24/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 test instance is added to the AWS managed AD server using a manual approach itself. | 24/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;i documented the process we can use this for future reference. | 02/May/25 4:56 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Approved from Yashwant behalf due to his Jira login issue | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-24 08:20
AM20-54 | Terraform Development ¦¦ Creation of Outbound and inbound rules in NACL | Done | 8 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1651313 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 10:35 | 2025-11-28 12:00 | 2025-11-27 08:27 | 2025-11-28 12:00 |  | 0 | As Terraform expert, I want to be creating a network ACL with inbound and outbound rules using terraform code, so that I can apply stateless packet filtering at the subnet level Acceptance Criteria: * Define variable for CIDRs, ports and subnets * NACL resources is created and associated with target subnets * Application relevant flows needs to be populated * Application inbound rule and comms metric needs to populated for NACL * Outbound rules allow return traffic on the same ports. * Each rule has a unique number and direction * Rules are parameterized for environment flexibility * add rule description and tags. * Provision to add or deny additional rules with max of 20 rules to be allowed for NACL |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@442b4964 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mrnr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 19 | [96 empty] | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-20 07:06 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 20/Nov/25 9:06 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Working on base module code of terraform script. It will be completed by this Friday EOD. | 27/Nov/25 8:24 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform script completed and NACL resource created in sandbox environment. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-11-28 12:00
AM20-53 | ServiceNow ¦¦ E2E Test validations for TM1 | Done | 2 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1651027 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 08:16 | 2025-07-04 08:12 |  |  |  | 0 | As AWS engineer, I want to test the full alert pipeline from event generation on TM1 to incident creation in ServiceNow so that we can confirm end-to-end functionality Acceptance Criteria: * A simulated error in TM1 triggers the CloudWatch rule * SNS publishes the event * Lamda sends the data to ServiceNow * A ticket is created in ServiceNow with correct details |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;04/Jul/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@54dd1363 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:04 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-02 05:26 | [13 empty] | 02/Jul/25 7:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PRODUCTION ServiceNow Instance: [https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws¦https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws] TM1 server to be integrated with the service now endpoint. | 04/Jul/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Servicenow integration followed by unit test is completed, the SNS topic is configured to get the alerts. | [25 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-04 08:12
AM20-52 | ServiceNow ¦¦ Logging and Monitoring | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651021 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 08:11 | 2025-06-20 08:17 |  |  |  | 0 | As an AWS expert, I want to monitor the health and logs of the Lamda connector function so that I can troubleshoot issues when alerts arenâ€™t processed properly Acceptance Criteria: * CloudWatch logs are enabled for Lambda * Metrics and dashboards are available for monitoring invocations, failures and response times. |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/May/25 9:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103910 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60acf139 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0285v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | [108 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 05:45 | [13 empty] | 02/May/25 7:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function to invoke the cloud watch is created and working as expected, Cloud watch dashboard for metrics will be created only after the workloads moved to cloud. service now monitoring can be in place only after successful integration with connector and service now PAAS endpoint. | 16/May/25 9:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have given demo with the email endpoints, waiting for the https endpoint to be received from SAA team to work with full functionality, | 22/May/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have received a endpoint today, yet to update SNS topic endpoint. https://sonicboom_em_saa_7161:wusEwo>G*Xmw@?XOA74\!pm0cx2.[4N;oFz<\!7vSE@liftdev.service-now.com/api/sn_em_connector/em/inbound_event?source=aws&sys_id=870cc1dfc3a5a6d04022f9777a013157 | 22/May/25 9:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 26/May/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 26/May/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;With respect to the endpoint have sent a mail to ashton, but there was response yet. awaiting on same. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. Â· | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 7:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Service now integration is completed with a new subscription HTTPS endpoint, have created a Cloud watch alarm for testing purpose which triggers a SNS as result service now dashboard receives a alert. | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-20 08:17
AM20-51 | ServiceNow ¦¦ Lamda function as SNS Subscriber | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651014 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 08:05 | 2025-05-02 16:57 |  |  |  | 0 | As a Cloud engineer, I want a Lamda function subscribed to the SNS topic so that it can process alerts and forward them to ServiceNow Acceptance Criteria: * The Lamda function is triggered on new SNS messages * It parses event data and sends an HTTP POST request to ServiceNow |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 | ;25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@353710af | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0284j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 03:49 | [13 empty] | 24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Working with the lambda function python script, since the function needs to works with cross account for getting the tags. initially the lambda function developed to get the tags from the same account, whereas here the requirement is to get the tag to Audit account to trigger a SNS. | 25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function is created in Audit account -300204747992, and its working fine as expected. | 02/May/25 4:57 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-25 06:34
AM20-50 | ServiceNow ¦¦ EventBridge Integration | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651004 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 07:58 | 2025-05-02 16:57 |  |  |  | 0 | As a DevOps engineer, I want to create an EventBridge rule that routes error events to an SNS topic so that alerts are propagated automatically Acceptance Criteria: * The EventBridge rule captures relevant error events. * The rule sends events to the SNS topic as the target |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 5:46 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 | ;25/Apr/25 6:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@433031d0 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0282b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 03:47 | [13 empty] | 24/Apr/25 5:47 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created a Event bridge rule for a default cloud watch alarm, this will invoke the lambda function. | 25/Apr/25 6:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Event bridge rule created and working fine as expected in audit account -300204747992 | 02/May/25 4:57 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-25 06:35
AM20-49 | ServiceNow ¦¦ CloudWatch Rule for Error detection | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650995 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 07:52 | 2025-05-18 14:39 |  |  |  | 0 | As a AWS engineer, I want to create CloudWatch alarms to send error-level logs to be notified of infrastructure issues Acceptance criteria: * CloudWatch metric filters to be configured to match specific error patterns or log levels |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fabfe65 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0280b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 06:03 | [13 empty] | 29/Apr/25 8:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will review utkarsh terraform script and will assign this story to him. | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed. | 07/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;We can use utkarsh terraform script for cloud watch alarm creation, but sns topic cant be modified so we need manual update to SNS access policy. | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:39 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [22 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:39
AM20-48 | Informatica Server ¦¦ Assessment & LLD | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650978 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-16 07:41 | 2025-05-18 14:39 |  |  |  | 0 | As Application expert I would be conducting assessment on Informatica server and document the low level design to record the migration approach and design *Acceptance Criteria*: * Document Low level design containing AWS infrastructure and approach to migrate informatica servers for sign-off. |  | Harsh Chandra | Sumit Nikam |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [10 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1bfd6374 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i027wj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 13:57 | [13 empty] | 29/Apr/25 3:56 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Have got details from Pieter. To be documented. | 02/May/25 11:02 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Assessment document prepared based on received inputs: [Informatica - Assessment.docx¦https://vodafone.sharepoint.com/:w:/r/sites/SouthAfricaAirlines/Shared%20Documents/20%20+%20app%20migration/20+%20Applications%20planning/Assessment%20Documentation/Assessment%20word%20files/Informatica%20-%20Assessment.docx?d=w42d28a53768b4302b78338d1c28a23e5&csf=1&web=1&e=OPyJH9] Few open points regarding application have been raised with Pieter. Document might be updated based on same. | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:39
AM20-47 | Nexio AV ¦¦ Firewall Rule creation | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Satya Varanasi | Medium | 1650869 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-15 16:12 | 2025-06-10 14:09 |  |  |  | 0 | As AWS expert I will be creating firewall rules for Nexio AV application so that security compliance can be met Acceptance Criteria: * Firewall rules are created and sent to Vodacom implementation |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@76b1f9b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:y | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:45 | [13 empty] | 29/Apr/25 7:44 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;FW rules will be implemented after comms implementation. This may need to move next sprint. | 20/May/25 5:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This Story dependency with comms implementation, the same with SAA team. Once SAA team actioned this story will be handled and closed until that this will not possible to address.(Note: it may move next sprint also) | 10/Jun/25 2:09 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;No longer needed based on recent conversation. * Based on request from Sinjun, the migration approach for Trellix/NexioAV has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-10 14:09
AM20-46 | Nexio AV ¦¦ establish internet connectivity via TGW | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650868 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-15 16:11 | 2025-05-18 14:38 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Harsh Chandra | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  | ;02/May/25 12:35 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;14400 | [5 empty] | 14400 | 0 | 14400 | 1 | 14400 | 0 | 14400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1e57c316 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:x | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:43 | [13 empty] | 29/Apr/25 7:43 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;internet connectivity has ben setup, sending for review | 02/May/25 12:37 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Tested through SSM {quote}Ping to 8.8.8.8 working Tracert to 8.8.8.8 working{quote} Forwarding for PO Approval | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:38
AM20-45 | Nexio AV ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 5 | 2025-05-12 | 2025-05-23 | Satya Varanasi | High | 1650865 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-15 16:10 | 2025-06-10 14:08 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5c904e9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akl: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 15:23 | [13 empty] | 20/May/25 5:23 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This Story dependency with comms implementation, the same with SAA team. Once SAA team actioned this story will be handled and closed until that this will not possible to address.(Note: it may move next sprint also) | 10/Jun/25 2:08 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0; No longer needed based on recent conversation. * Based on request from Sinjun, the migration approach for Trellix/NexioAV has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. Â | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-10 14:08
AM20-44 | Nexio AV ¦¦ Subnet creation | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | Medium | 1650863 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-15 16:08 | 2025-06-02 11:36 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Nexio AV application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Nexio AV and the configured based on the approved comms matrix |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 14/May/25 7:21 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-05-14 104729-20250514-051730.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100027 | 14/May/25 7:21 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-05-14 105036-20250514-052037.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100026 | 14/May/25 7:24 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052415.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100028 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-072934.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103886 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-073009.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103885 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-073047.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103887 | [12 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@77400985 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:t | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:40 | [13 empty] | 29/Apr/25 7:39 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Relevant subnet has been created, sending for review. | 02/May/25 12:22 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;IP Details ¦¦Nexio AV¦¦Production¦¦10.40.0.176/28¦¦10.40.0.176 - 10.40.0.191¦¦10.40.0.177 - 10.40.0.190¦¦14¦¦AZ1¦¦Â ¦¦ ¦¦Nexio AV (DR)¦Production¦10.40.0.192/28¦10.40.0.192 - 10.40.0.207¦10.40.0.193 - 10.40.0.206¦14¦Â ¦AZ2¦ ¦¦TG ATTACH-Subnet¦Production¦10.40.1.160/28¦10.40.1.160 - 10.40.1.175¦10.40.1.161 - 10.40.1.174¦14¦AZ1¦Â ¦ ¦¦TG ATTACH-Subnet¦Production¦10.40.1.176/28¦10.40.1.176 - 10.40.1.191¦10.40.1.177 - 10.40.1.190¦14¦Â ¦AZ2¦ Route table still need to cleaned up and updated properly. Assigning back the ticket to [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 07/May/25 6:21 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on route table cleanup. | 14/May/25 7:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets already created. IP CIDR Details for prod/DR ¦10.40.0.176/28¦10.40.0.176 - 10.40.0.191¦10.40.0.177 - 10.40.0.190¦14¦/28¦AZ1¦Â ¦ ¦10.40.0.192/28¦10.40.0.192 - 10.40.0.207¦10.40.0.193 - 10.40.0.206¦14¦/28¦Â ¦AZ2¦ Subnet info: !Screenshot 2025-05-14 104729-20250514-051730.png¦width=1117,height=580,alt="Screenshot 2025-05-14 104729-20250514-051730.png"! !Screenshot 2025-05-14 105036-20250514-052037.png¦width=1128,height=586,alt="Screenshot 2025-05-14 105036-20250514-052037.png"! Please review. | 14/May/25 7:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Attached route table screen shots. !image-20250514-052415.png¦width=1130,height=531,alt="image-20250514-052415.png"! | 19/May/25 11:08 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Action Item: Change the Name to Trellix AV from Nexio AV Correct the AZ for DR Route to be tested for correct routing Assigning back to Satya for correction | 19/May/25 6:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sankalp updated me to change NexioAV to Trellix AV. I will update and assign it to Sankalp. | 20/May/25 5:16 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation done and assigned for review, and it has been reassigned for modification and routing validation. Find below reviewer comments. Action Item: Change the Name to Trellix AV from Nexio AV(New requirement according to app name) Correct the AZ for DR (resource name change) Route to be tested for correct routing | 22/May/25 9:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on inputs modification has been done. !image-20250522-072934.png¦width=1103,height=563,alt="image-20250522-072934.png"! !image-20250522-073009.png¦width=1107,height=575,alt="image-20250522-073009.png"! Route Table: !image-20250522-073047.png¦width=1107,height=526,alt="image-20250522-073047.png"! Please check and review the same. | 30/May/25 2:45 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Review done Transitioning to PO Approval | 02/Jun/25 11:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [16 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-02 11:36
AM20-43 | ServiceNow ¦¦ Secure Integration with Cloud ServiceNow | Done | 8 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650451 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-15 11:52 | 2025-07-11 13:46 |  |  |  | 0 | As a AWS Cloud architect, I want the Amazon SNS to securely connect to the on-prem ServiceNow instance so that error alerts can be logged as incidents. Acceptance Criteria: * ServiceNow API credentials are stored securely in AWS Secrets manager * Network connectivity is verified via NAT gateway/VPN * HTTP request to ServiceNow are authenticated and secure |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;13/May/25 11:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;24/Jun/25 1:30 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;10/Jul/25 9:30 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;57600 |  |  |  | 115200 | 0 | 115200 | 1 | 115200 | 0 | 115200 | [12 empty] | 15/May/25 11:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;Ashton response on delay for SNow endpoint.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100994 | 22/May/25 9:56 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103907 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5538b454 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 08:59 | [13 empty] | 02/May/25 10:58 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Current State: AWS Level configuration of ServiceNow with Lambda Function and SNS is complete. Next Steps: # Setup a call with ServiceNow Cloud team to do the POC # Setup SNS to Push notifications to ServiceNow # Setup required matrices # Validate the functionality. # Get Sign-off on successful Setup | 15/May/25 11:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Delay from ServiceNow app owner ( Ashton) in providing the ServiceNow API endpoint, conversations comms screenshot attached. Potential spill over [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] | 20/May/25 10:18 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;¦Setup on AWS in complete. API endpoint is to be provided by Ashton Steyn. Once the end point is added to SNS, we would be able to test if the notification is received correctly in ServiceNow Cloud. Next Step would be to showcase this entire setup to Denise and Bhavesh and get Sign off. Action Points API EndPoint pending on Ashton Steyn. Need Availability of Denise and Bhavesh to showcase the POC and get SignOff on the POC¦ | 22/May/25 9:57 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 02/Jun/25 8:22 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;API Provided by Ashton, could not be configured in SNS Topic. We are getting error â€œURL is not valid, INVALIDâ€ We are waiting for an update from Ashton on how to resolve this error. | 19/Jun/25 7:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Call planned with ServiceNow team on 19th June to provide walkthrough and clarify open queries, needed to proceed with next steps [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] | 24/Jun/25 1:30 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Setup Completed POC Completed End Point for Prod to be provided by service now team (Feroz). | 10/Jul/25 9:30 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Setup >> Completed POC >> Completed End Point for Prod to be provided by service now team (Feroz) >> Completed Moving to review for closure | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-42 | ServiceNow ¦¦ SNS Topic for Alerts | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650429 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-15 11:45 | 2025-05-18 14:38 |  |  |  | 0 | AS AWS Expert, I want to create an Amazon SNS topic so that AWS services can be publish alert messages to it. Acceptance Criteria: * AN SNS topic is created * Permissions are set to allow EventBridge and Lamda to publish to it * The topic supports the subscription |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@505787e3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [66 empty] | Unit Tested | [51 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-06 06:23 | [13 empty] | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed, and will modify the required configurations. Â· | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:38
AM20-41 | TM1 ¦¦ Replicated Test server creation | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1648987 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-14 10:31 | 2025-05-02 16:57 |  |  |  | 0 | AS AWS expert, I would be provisioning TM1 test server as replica server to allow to perform initial validations *Acceptance Criteria*: * TM1 replica test server is successfully created * Internal team is able to access server successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;21/Apr/25 11:47 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;24/Apr/25 5:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1f9453f2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:r | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-21 09:47 | [13 empty] | 21/Apr/25 11:46 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test Launch instance is launched with the help of launch template, able to telnet the TM1 server from bastion host. Waiting for TM1 local account credentials to login to server and verify the connectivity. | 24/Apr/25 5:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Server handover to application team yesterday, hence marking this to done status | 02/May/25 4:57 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-24 05:45
AM20-40 | TM1 ¦¦ Firewall Rule creation | Done | 2 | Sprint 3 | 2025-04-14 | 2025-04-25 | Sankalp Rai | Medium | 1644189 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-07 08:16 | 2025-04-21 09:03 |  |  |  | 0 | As AWS expert I will be creating firewall rules for TM1 application so that security compliance can be met Acceptance Criteria: * Firewall rules are created and sent to Vodacom implementation |  | Sankalp Rai | [5 empty] | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [5 empty] | ;17/Apr/25 11:05 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b493d0d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-14 07:44 | [13 empty] | 14/Apr/25 9:44 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Call Pending on Firewall placement. Call scheduled for 15th April 2025 Vodacom: Leigh to manage the Firewall and create Rules on Firewall VOIS: Raise request for Firewall Rule in the provided Format | 17/Apr/25 11:06 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;AWS Network Firewall is for monitoring internet traffic coming into AWS and going out of AWS. TM1 does not require any connectivity over internet. Connectivity to TerraData is being done internally Some of the VMs under TerraData right now are being moved to Shared VPC. SAP Rise connectivity is not required. Since TM1 does not require internet connectivity, there is no need to create AWS Network Firewall rules for TM1 Moving to in review for closure | [25 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-21 09:03
AM20-37 | AWS_SAA_Network ¦¦ Security Compliance Implementation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642120 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-02 15:33 | 2025-05-02 16:58 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on *Account no: 339712943527â€ƒâ€ƒAWS_SAA_Network* *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/Apr/25 9:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Network-Acccount-FailedControls.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1092887 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@749b116f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00tcp: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-15 06:22 | [13 empty] | 15/Apr/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on implementing dependency services for CIS, NIST and FSBP | 17/Apr/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed enabling Guard Duty, Macie, Security Hub, followed by this have implemented controls for CIS, NIST, AWS FSBP standards. Still there are few failed controls to be remediated, since the implementation of services done by vodacom, will expect their support in implementing the controls. if the controls cannot be implemented will get a confirmation on the failed control list to close this user story. | 22/Apr/25 9:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;[^Network-Acccount-FailedControls.csv] Failed controls list to work with vodacom team, hence marking this story to done status. | 02/May/25 4:58 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-04-22 09:53
AM20-36 | AWS_SAA_Security ¦¦ Security Compliance Implementation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642119 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-02 15:32 | 2025-05-02 16:58 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on *Account no: 30335236533â€ƒâ€ƒAWS_SAA_Security* *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cb06c96 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00tcn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-09 06:21 | [13 empty] | 09/Apr/25 8:21 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled dependencies service like security hub, macie, guard duty for the compliance controls, will start working on the remediation towards other controls. | 14/Apr/25 8:18 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed implementing controls, awaiting for security score update. Will close this story along with score update. | 17/Apr/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed enabling Guard Duty, Macie, Security Hub, followed by this have implemented controls for CIS, NIST, AWS FSBP standards. Still there are few failed controls to be remediated, since the implementation of services done by vodacom, will expect their support in implementing the controls. if the controls cannot be implemented will get a confirmation on the failed control list to close this user story. | 24/Apr/25 5:50 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is not able to enable with the access i have, so requested vodacom team to support. | 28/Apr/25 4:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is enabled after SCP modification, for failed controls vodacom will do the remediation. | 02/May/25 4:58 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-04-28 16:01
AM20-35 | Payer Account ¦¦ Security Compliance Implementation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642106 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-02 15:31 | 2025-05-02 16:58 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on *Account no: 195973603339â€ƒâ€ƒvod001_001_payer9* *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/Apr/25 9:52 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Payer-Account-FailedControls.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1092883 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1b290b3c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00tcj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-15 06:23 | [13 empty] | 15/Apr/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on implementing dependency services for CIS, NIST and FSBP | 17/Apr/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed enabling Guard Duty, Macie, Security Hub, followed by this have implemented controls for CIS, NIST, AWS FSBP standards. Still there are few failed controls to be remediated, since the implementation of services done by vodacom, will expect their support in implementing the controls. if the controls cannot be implemented will get a confirmation on the failed control list to close this user story. | 22/Apr/25 9:52 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;[^Payer-Account-FailedControls.csv] Failed controls list to work with vodacom team, hence marking this story to done status. | 02/May/25 4:58 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-04-22 09:52
AM20-34 | TM1 ¦¦ Integration of AWS IAM roles with TM1 AWS Account Instance using JSON | Done | 10 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642068 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-02 14:50 | 2025-07-11 13:46 |  |  |  | 0 | As AWS expert, I would be integrating AWS IAM roles with TM1 Instance Acceptance criteria: * IAM roles are created successfully * Integration of defined IAM roles with TM1 instance so that user is able to access the TM1 instance. |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5190a6ea | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-09 07:30 | [13 empty] | 09/Jul/25 9:29 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Following are the details of the role created: role_arn = "arn:aws:iam::209479274829:role/TM1-IAMRole-EC2InstanceProfile" role_name = "TM1-IAMRole-EC2InstanceProfile" Account details: 209479274829 (SAA-TM1) Custom Role Details: The role covers the equivalent of â€œAmazonSSMManagedInstanceCoreâ€, basic CloudWatch Agent permissions, and general S3 access. _*NOTE*: THE FOLLOWING HAS BEEN ACHIEVED USING TERRAFORM._ | 09/Jul/25 9:30 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;.json file of the custom role is as follows: { Â "Version": "2012-10-17", Â "Statement": [ Â Â { Â Â Â "Sid": "SSMManagedInstanceCorePermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssm:DescribeAssociation", Â Â Â Â "ssm:GetDeployablePatchSnapshotForInstance", Â Â Â Â "ssm:GetDocument", Â Â Â Â "ssm:DescribeDocument", Â Â Â Â "ssm:GetManifest", Â Â Â Â "ssm:GetParameter", Â Â Â Â "ssm:GetParameters", Â Â Â Â "ssm:ListAssociations", Â Â Â Â "ssm:ListInstanceAssociations", Â Â Â Â "ssm:PutInventory", Â Â Â Â "ssm:PutComplianceItems", Â Â Â Â "ssm:PutConfigurePackageResult", Â Â Â Â "ssm:UpdateAssociationStatus", Â Â Â Â "ssm:UpdateInstanceAssociationStatus", Â Â Â Â "ssm:UpdateInstanceInformation" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "SSMMessageGatewayPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssmmessages:CreateControlChannel", Â Â Â Â "ssmmessages:CreateDataChannel", Â Â Â Â "ssmmessages:OpenControlChannel", Â Â Â Â "ssmmessages:OpenDataChannel" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "EC2MessagesPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ec2messages:AcknowledgeMessage", Â Â Â Â "ec2messages:DeleteMessage", Â Â Â Â "ec2messages:FailMessage", Â Â Â Â "ec2messages:GetEndpoint", Â Â Â Â "ec2messages:GetMessages", Â Â Â Â "ec2messages:SendReply" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "CloudWatchAgentPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "logs:CreateLogGroup", Â Â Â Â "logs:CreateLogStream", Â Â Â Â "logs:PutLogEvents", Â Â Â Â "logs:DescribeLogGroups", Â Â Â Â "logs:DescribeLogStreams", Â Â Â Â "cloudwatch:PutMetricData" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "S3AccessPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "s3:GetObject", Â Â Â Â "s3:PutObject", Â Â Â Â "s3:ListBucket" Â Â Â ], Â Â Â "Resource": "*" Â Â } Â ] } | 11/Jul/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed IAM roles is having required permissions | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-33 | Comms metrics creation for Informatica server | Done | 6 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642050 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-02 14:37 | 2025-05-18 14:37 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for Informatica server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability created * Low level design documentation including proposed architecture completed Server names to be provided by [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] |  | Harsh Chandra | Satya Varanasi | Sumit Nikam |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3c3333a4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0r: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-17 15:34 | [13 empty] | 17/Apr/25 5:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Due to other activities i am not able to manage this task in this sprint. it required to move other sprint. | 07/May/25 6:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;VDC side DEV/PROD comms has been created, Working on sita side and the same will be ready on Thursday EOD | 12/May/25 7:52 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;comms has been completed, i will initiate review communication | 16/May/25 8:39 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Comm matrix has been verified as per available information. | 18/May/25 2:37 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:37
AM20-32 | TM1 Migration activity with tagging | Done |  | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642044 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-02 14:24 | 2025-04-17 08:31 |  |  |  | 0 | As Application Expert, I would be migrating TM1 server from on-prem to AWS using migration tool Acceptance Criteria: TM1 migration is successfully migrated to AWS from on-prem. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;17/Apr/25 8:31 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;144000 | [5 empty] | 144000 | 0 | 144000 | 1 | 144000 | 0 | 144000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5e70c07a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00szn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-08 10:32 | [13 empty] | 08/Apr/25 12:31 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 migration is completed, awaiting for application commsmatrix implementation status, upon confirmation will launch test instance and will ask application owner to test and confirm functionality. | 09/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Expecting to do the testing of Application related port connectivity bw on-premises and AWS along with satyasairam, post that will launch the test over instance. | 14/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Still awaiting for the connectivity confirmation. | 15/Apr/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for comms matrix implementation, upon completion will launch test instance. | 17/Apr/25 8:29 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*Test launch instance is launched and will add this server to the AWS active directory(*[*awsflysaa.com*¦http://awsflysaa.com]*),* after NACL and SG implementation will handover application to the owner to test the functionality. | 17/Apr/25 8:30 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Tags: ¦App_tier¦Application¦ ¦AppName¦TM1-application¦ ¦Business_Unit¦TBD¦ ¦CostCenter¦SAA¦ ¦CreatedBy¦AWS-MGN¦ ¦DisasterRecovery¦Enabled¦ ¦Environment¦Production¦ ¦Instance_Size¦TBD¦ ¦Instance_Type¦TBD¦ ¦Name¦fmtvmap01¦ ¦Owner¦TBD¦ | [21 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-17 08:31
AM20-31 | Bastion Host creation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642039 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-02 14:20 | 2025-04-17 14:16 |  |  |  | 0 | As AWS expert, I would be creating two Bastion host by launching Private EC2 instance and AMI for preferred operating system and configure Security groups and apply Inbound and Outbound Rule * One for Internal Migration team (having internet access) * Another for Nexio and Customer access with RDS enabled Acceptance Criteria: * Bastion host provisioned successfully * access is provided to Nexio and business team by SSH client and connect to bastion host public IP adddress using private key |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;17/Apr/25 2:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 57600 | 14400 | 28800 | 0.5 | 57600 | 14400 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@327eec44 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00syj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-15 16:18 | [13 empty] | 15/Apr/25 6:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Separate Network setup with internet gateway and pubic IP will be required for shared service account 864899875361, after network setup would create bastion server for internal team usage. [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] may need your help in setting up network. | 17/Apr/25 2:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;I have created a Bastion host in network account and have customized RDP port number from 3389 to *54925* for security measures. Â As we all know the jump server can be RDP accessed by two user in parallel, have created a user account named *VOIS_User01 and VOIS_User02* with Administrator privilege, password will be shared separately. Â Bastion Host Details; Â *Server name: Bastion-Host-Internal* *Server IP: 16.28.7.145(ElasticIP)* *Server RDP Port: 54925* | 17/Apr/25 2:16 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Bastion host for Nexio will be created after sometime. | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-17 14:16
AM20-30 | POC -AWS Patch Manager ¦¦ Create a patch baseline for installing Windows/RHEL Service Packs | Done | 8 | Sprint 3 | 2025-04-14 | 2025-04-25 | Faisal Sayed | High | 1642024 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-04-02 14:08 | 2025-06-13 14:35 |  |  |  | 0 | As AWS architect I would be creating patch baselines for windows Server. Acceptance Criteria: Patch Manager has been created successfully |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Onkar Mirajkar | Sankalp Rai | Yashwant Thakur | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [6 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 23/May/25 8:09 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;Re_ Centralized Multi-Account Patching with AWS System Manger Patch Manger.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1104373 | 09/May/25 12:00 PM;9e4636e8-9dfc-4a33-901b-fcd75015926a;System Patch Manger.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1098376 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@b983d7e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/1 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 1 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00svf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | [108 empty] | 1 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-05 06:16 | [13 empty] | 05/May/25 8:15 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Able to install patches on multi-account ec2 instance using Systems Manager Automation. | 05/May/25 8:16 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working on patch policy | 08/May/25 8:12 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working with Lambda and amazon bridge event to automate the patching process for patch policy to run specific dates | 08/May/25 3:29 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Created lambda function and event bridge to automate patch multi-account setup | 09/May/25 8:01 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Need to update document | 09/May/25 12:02 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Document attached in the Jira sent for review to Arvind | 12/May/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Document is reviewed, automation with lambda is captured. | 18/May/25 2:37 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Since the desired solution objective could not be achieved, rejecting this ticket to in progress. As agreed, onkar needs to rework based on agreement. Solution provided by Aravind needs to be developed as POC. as communicated and mentioned by Yashwant. Rejecting on behalf of Yashwant as he has login issues in Jira | 20/May/25 1:24 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Spoke to Venkat on the issue we are facing with centralized patch management and the limitation to use it in multi-account setup in AWS. Quick Setup as work around for Multi-Account Setup, however this service is not available in CapeTown (SA) region. Venkat has agreed to raise this with AWS. As next Step: # compose email stating the solution we are trying to achieve for patching, the limitations we have come across and all the solution we have and what limitations these solutions have. # Venkat will forward this AWS and work on setting up a call to discuss this issue. # Align with AWS on best possible solution/workaround to achieve the desired state | 21/May/25 10:34 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Email has been sent to Venkat, stating what we are trying to achieve, Limitations identified and workarounds tried.Â | 09/Jun/25 8:22 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;As per call, We have tried to download the packages from server which is having Internet connectivity and tried to update on Private Ec2 instances which is working successfully | 13/Jun/25 12:55 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Centralized EC2 Patch Management (Cross-Account)*{{ â€” AchievedÂ }} Â {{Â }}*Key Outcomes*{{:Â }} # Â *Central Patch Repository in Shared Services Account*{{Â }} * Â {{Created `saa-central-patch-bucket` in }}*af-south-1*{{, configured securely.Â }} * {{Uploaded Linux `.rpm` and Windows `.msu` patches to S3 manually & via scripts.Â }} Â # *SSM-Compatible EC2 Instances in Target Accounts*{{Â }} Â {{Launched both Linux & Windows instances without public IPs.Â }} {{Attached custom IAM roles that:Â }} * Â {{Allow full SSM and `s3:GetObject` access to central bucket.Â }} * {{Assume trust with `ec2.amazonaws.com`.Â }} Â # *Patch Acquisition*{{Â }} * Â {{Downloaded Linux patches using SSM Run Command (manual S3 sync).Â }} * {{Downloaded Windows patches (KB5058392) using RDP, installed AWS CLI manually, then uploaded to S3.Â }} Â # *AWS CLI Installed on Windows EC2 (No Internet)*{{Â }} * Â {{Used temporary public IP â†’ installed AWS CLI â†’ removed IP.Â }} Â # *Tested SSM Agent Connectivity*{{Â }} Â {{Verified instances registered to SSM without public IP using:Â }} * Â {{ VPC endpoints (`ssm`, `ssmmessages`, `ec2messages`, `s3`)Â }} * {{ IAM and SGs allowing HTTPS (`tcp/443`)Â }} Â # *Enabled Patch Deployment via SSM Run Command*{{Â }} Â {{Used SSM to:Â }} * Â {{Copy patches from EC2 to central S3Â }} * {{Test patch install commands (`wusa` for `.msu`, `yum` for `.rpm`)}} | 13/Jun/25 2:35 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [14 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:35
AM20-29 | CSA assessment | Done | 8 | Sprint 2 | 2025-03-31 | 2025-04-11 | Sumit Nikam | Medium | 1627466 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-12 18:08 | 2025-04-04 20:08 |  |  |  | 0 | As application architect I would assess current CSA application architecture, functional complexity, ease of migration, current and future scalability requirements, dependencies between different components and data consistency across services. Acceptance Criteria: Document consisting of current and to-be architecture, proposed microservices,, dependencies and data consistency approach is successfully completed |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;02/Apr/25 6:36 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 |  |  | 115200 | 21600 | 93600 | 0.81 | 115200 | 21600 | 93600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@11a4dc28 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 4 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxso7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-26 06:12 | [13 empty] | 26/Mar/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;High level plan for CSA Modernization has been prepared, reviewed internally and shared with Vodacom. Next step is to prepare for SOW document. | 01/Apr/25 7:11 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Working along with Yashwant for SOW document preparation and review | 02/Apr/25 6:36 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Reviewing functional details shared by Sampi | 04/Apr/25 3:26 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Follow-up discussion completed with Sampi. | 04/Apr/25 8:08 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. SOW completed | [22 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-04-04 20:08
AM20-27 | Informatica Server ¦¦ LLD preparation | Done | 6 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1610565 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-02-19 06:06 | 2025-10-13 09:23 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Sankalp Rai | Yashwant Thakur |  |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;24/Jun/25 1:32 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;11/Aug/25 10:10 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7d2f4e8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a2v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | [104 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-10 14:18 | [13 empty] | 10/Mar/25 4:18 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 10/Mar/25 4:24 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder >> Call to Scheduled on or before 12th* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 20/May/25 10:24 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;1st Draft Complete. Need to review internally revised Start Date: 19th May 2025 End date: 23rd May 2025 | 24/Jun/25 1:32 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Review with customer is completed Awaiting information requested from Application Owner | 11/Aug/25 5:04 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-10-13 09:23
AM20-26 | ServiceNow ¦¦ LLD preparation | Done | 4 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1610563 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-02-19 06:00 | 2025-04-21 09:02 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for ServiceNow application so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed |  | Aravind Raj | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;14/Apr/25 9:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;115200 | [5 empty] | 57600 | 0 | 115200 | 2 | 57600 | 0 | 115200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4842827b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 3/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 3 | 75 | 1 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsnj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 2 | Sprint 3 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-10 14:19 | [13 empty] | 10/Mar/25 4:19 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 12/Mar/25 8:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;ServiceNow LLD is prepared, formatting is in progress, will complete and attach the document here. | 14/Apr/25 9:39 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Completed: 10th April 2025 Presentation to be done on Wednesday 16th April 2025 Review done by: [~accountid:712020:5d317226-2402-463f-bda5-c2cac5f43c13] and Deepak | [24 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-04-21 09:02
AM20-25 | NexioAV ¦¦ Connectivity Traceability (Comms matrix) preparation | Done | 4 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satya Varanasi | High | 1610560 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-02-19 05:45 | 2025-05-30 15:37 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for Nexio AV application so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability created * Comms Matrix sent for reviews |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@666dfeae | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/4 |  | 0 | [66 empty] | Peer Reviewed | Unit Tested | [50 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 4 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kh: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | [107 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-02-24 10:43 | [13 empty] | 24/Feb/25 12:43 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Assigning to Satyasairam Varanasi | 27/Feb/25 8:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Looking IP requirement for this app | 28/Feb/25 8:29 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on IP subnets according to frontend, backend and DB subnet, right we are gathering data. | 17/Mar/25 8:05 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started PROS comms preparation | 07/Apr/25 9:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;NexioAV comms prepared, Need to Review with Santanu, this is moved to next sprint because we are working on TM1 App. | 14/Apr/25 9:39 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms matrix has been prepared. | 24/Apr/25 8:23 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;AWS migration agent comms has been sent for review and CRQ process. | 29/Apr/25 7:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Wanda reviewed and initiated the CRQ process. | 16/May/25 10:36 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per management, i need to wait until further confirmation. | 20/May/25 5:12 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared and shared to SAA team (Wanda) for CRQ submission towards implementing flows. This task not completed earlier Sprint due to dependency with SAA team.(SAA team busy with Ransomware cyber attack), still no clarity from SAA team regarding app migrations. | 23/May/25 11:15 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms CRQ 'CHG0065629â€ has be schedule, but implementation is pending due temporary on hold, Wanda asked us to cross check with Donald for further process and same has been updated Yashwant. | 30/May/25 3:37 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to todays NexioAV LLD call, this is no longer required. According to call we will create new VM and handover to Sinjun Weston. ================== * Based on request from Sinjun, the migration approach for Trellix has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. | [15 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-05-30 15:37
AM20-23 | Nexio AV ¦¦ LLD creation | Done | 2 | Sprint 2 | 2025-03-31 | 2025-04-11 | Yashwant Thakur | High | 1619786 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 07:16 | 2025-05-18 14:41 |  |  |  | 0 | As AWS architect, I would create LLD for Nexio AV application migration *Acceptance Criteria*: * Low level design documentation including proposed architecture completed |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;13/May/25 11:21 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [9 empty] | AM20-22 |  |  | 13/May/25 11:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;TrellixAV_DesignDocument_v1.1.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1099634 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28a7c8e2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsmv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 3 | Sprint 4 | Sprint 5 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-13 09:38 | [13 empty] | 13/May/25 11:38 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Document has been prepared for Trellix AV ePO server migration to AWS ¦Backup PolicyÂ ¦To be discussed with customer and finalized¦ ¦DR Policy¦To be discussed with customer and finalized¦ [^TrellixAV_DesignDocument_v1.1.docx] First Draft of LLD is attached Moving to In Review until we can share it with customer and Finalize the Document | 18/May/25 2:41 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [25 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-05-18 14:41
AM20-22 | Citrix ¦¦ LLD creation | Done | 6 | Sprint 4 | 2025-04-28 | 2025-05-09 | Sankalp Rai | High | 1619785 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 07:14 | 2025-06-13 12:51 |  |  |  | 0 | As AWS architect, I would create LLD for Citrix application migration *Acceptance Criteria*: * Low level design documentation including proposed architecture completed |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 28800 |  | 0 | 86400 | 28800 | [9 empty] | AM20-23 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b60bc29 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 4 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02775: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-20 08:23 | [13 empty] | 20/May/25 10:22 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;¦Needs discussion with customer on approach to be taken. We can either move with Greenfield Deployment or Migrate the exiting setup to AWS. The call was scheduled for 12th May, however that call did not as Nilesh and Team were not available. Follow-up mail for rescheduling the call has been sent. No Update from customer. We will be able to provide start date and end only after we finalize the approach.Â ¦ ¦ ¦ | 02/Jun/25 8:28 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Need to setup call with Nilesh on Citrix licences on cloud and on the approach for migration to AWS. | 02/Jun/25 8:29 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Moving to Blocked | 13/Jun/25 12:51 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;New business case needed, hence marking this as closed. | [23 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-06-13 12:51
AM20-21 | Network elements created for TM1 based on LLD | Done | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Sankalp Rai | High | 1609050 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-02-17 10:23 | 2025-04-21 09:02 |  |  |  | 0 | AS AWS architect, I would be create VPC, Subnet, routing and load balancer required for TM1 based on LLD *Acceptance Criteria* : VPC, Subnet created, Load balancer created in AWS. |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;17/Apr/25 11:14 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;57600 | [5 empty] | 28800 | 0 | 57600 | 2 | 28800 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@75cd043 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 3/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 3 | 75 | 1 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsmf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 2 | Sprint 3 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-04 05:45 | [13 empty] | 04/Mar/25 7:44 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms matrix has been updated according to app classification. | 17/Apr/25 11:14 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Subnet > created Route table > Created SG > Created NACL > Created there is limit to create 40 inbound and 40 outbound flows. team is currently trying to find a resolution for additional flow. All Firewall flow > Implemented and Tested Sending for PO Approval | [25 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-04-21 09:02
AM20-20 | Network elements created for AirNavX on LLD | Done | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Sankalp Rai | High | 1609046 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-02-17 10:22 | 2025-04-21 09:01 |  |  |  | 0 | AS AWS architect, I would be establishing connectivity for AirNavX from AWS to other dependent applications as per comms matrices so that the data transfer and its respective integration journey is able to be completed successfully. Below connectivity to be established *Acceptance Criteria* : AirNavX connectivity with dependent applications are raised successfully |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;17/Apr/25 11:08 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;57600 | [5 empty] | 28800 | 0 | 57600 | 2 | 28800 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f13e2d7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 2/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 2 | 50 | 2 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsm7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 2 | Sprint 3 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-02-28 06:20 | [13 empty] | 28/Feb/25 8:19 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on IP subnets according to frontend, backend and DB subnet, right we are gathering data. | 04/Mar/25 7:44 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms matrix has been updated according to app classification. | 17/Apr/25 11:08 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Subnet > Created Route Table > Created NACL > Created SG > Created Sending for PO Approval | [24 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-04-21 09:01
AM20-19 | Security and compliance implementation on PEGASYS account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622536 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-05 10:54 | 2025-03-21 12:15 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on Pegasys account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in TM1, Teammate account * NIST policy implementation successfully done in TM1, Teammate account * AWSFSBP policy implementation successfully done in TM1, Teammate account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [10 empty] | AM20-18 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@792d09b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxstj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-21 10:14 | [13 empty] | 21/Mar/25 12:14 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Marking as Done, as pegasys account migration still on discussion. | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-21 12:14
AM20-18 | Security and compliance implementation on PROS account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622524 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-05 10:49 | 2025-03-17 08:08 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on PROS account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in PROS DEV account * NIST policy implementation successfully done in PROS DEV account * AWSFSBP policy implementation successfully done in PROS DEV account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Mar/25 2:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [8 empty] | AM20-19 | AM20-17 |  |  | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250317-060821.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1079558 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a53b25a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxson: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-13 06:02 | [13 empty] | 13/Mar/25 8:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on the controls with the dependency services for the security frameworks. | 14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;The controls were implemented in Pros DEV account, Pros Production account will be picked up in separate user story. | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250317-060821.png¦width=1277,height=642,alt="image-20250317-060821.png"! | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-14 14:22
AM20-17 | Security and compliance implementation on ServiceNow account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622522 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-05 10:49 | 2025-03-17 08:07 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on ServiceNow account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in TM1, Teammate account * NIST policy implementation successfully done in TM1, Teammate account * AWSFSBP policy implementation successfully done in TM1, Teammate account |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;13/Mar/25 8:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;13/Mar/25 8:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [8 empty] | AM20-18 |  |  |  | 17/Mar/25 8:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250317-060657.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1079556 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4d1248d4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsof: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 14:47 | [13 empty] | 11/Mar/25 4:46 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Account access have received, have started working on implementing framework controls. | 13/Mar/25 8:00 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Controls are implemented, waiting for the security score to update, upon update will work on controls if any fails. | 14/Mar/25 2:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Security Score is updated in hub. | 17/Mar/25 8:06 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250317-060657.png¦width=1277,height=651,alt="image-20250317-060657.png"! | [23 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-14 14:18
AM20-16 | TM1 ¦¦ establish internet connectivity via TGW | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620885 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 16:49 | 2025-04-15 16:22 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [26 empty] | AM20-15 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@232fa3c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxslz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-01 17:41 | [13 empty] | 01/Apr/25 7:40 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Internet connectivity has-been established and tested. | 04/Apr/25 10:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Internet setup has been completed and tested working fine. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-14 09:39
AM20-15 | Airnavx ¦¦ establish internet connectivity via NAT Gateway and TGW | In Review | 0 | Sprint 1 | 2025-03-17 | 2025-03-28 | Sankalp Rai | High | 1620884 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 16:49 | 2025-04-21 10:55 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-10 | AM20-16 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@13dfa190 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akp: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-21 07:32 | [13 empty] | 21/Apr/25 9:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Please review | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | In Progress | 2025-04-08 08:20
AM20-14 | TM1 ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 10 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620851 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 16:20 | 2025-08-05 12:26 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [8 empty] | AM20-11 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6582c1ff | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxslr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | [108 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-08 06:24 | [13 empty] | 08/Apr/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms implemented From VDC, SITA now need to follow-up with Leigh for AWS firewall rules implementation. | 08/Apr/25 5:17 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been implemented, we are testing ports with test box, once all done we will create new SG will whitelist ports. | 22/Apr/25 3:54 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;NACL and SG has been setup, still Teradata side pending, checking with Leigh. | 24/Apr/25 8:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Connectivity got implemented testing also done successful. | 29/Apr/25 7:48 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 apps mat testing done successful. Teradata connectivity port20,21 &22 will be established after moving relevant resources to shared vpc. For app migration there is no dependency. | 18/May/25 2:40 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [21 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:40
AM20-13 | Airnavx ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620850 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 16:19 | 2025-09-08 06:36 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [8 empty] | AM20-10 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4559db6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 8 | Sprint 9 | Sprint 12 | Sprint 13 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-25 06:58 | [13 empty] | 25/Jun/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Harsh and Deepak update, this need to address after TM1 and informatica servers network action, hence i am keeping this as blocked(As per Harsh update) | 28/Jul/25 8:51 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Currently app under LLD review once review done i will initiate comms for the same. SO this will be moved to next sprint. | 04/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on it according to recent LLD call review. | 07/Aug/25 8:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared, with latest subnet details, i will initiate mail communication with customer/app owner for flows review or in case any additional flows needed they should notify further process. | 12/Aug/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Shared comms to app owner for review and add in case needed any additional flows for the same. | 25/Aug/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms under validation by app owner, so this is right story for spill over to this sprint. | 26/Aug/25 1:04 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Initially after follow-up customer prepared and send comms. # During review i identified as comms as not prepared right way and reshared the same comms to customer for validation. # After continuous 3 days follow-up we have received comms from customer as on date 25th Aug 10:00 PM. # There is no sufficient time to manage this story in this sprint due delay with customer. # Note: It has been communicated customer and management regularly but he took longer time to manage. | 29/Aug/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Reviewed and prepared AirNavX comms for VDC/SITA sheets and same sent app owner for LIFT/CSOC request towards implementation. | 03/Sep/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been reviewed and submitted to app owner for further process. | 03/Sep/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Albert has been submitted requested LIFT and CSOC request for ports androuting implementation. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 03/Sep/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The below is the current status: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Routing already in place hance not required any action on this and making this as completed.) | 08/Sep/25 6:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [15 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:36
AM20-11 | TM1 ¦¦ Migration tool installation | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620533 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 12:54 | 2025-04-07 10:45 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the TM1 SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | Working with nexio team on troubleshooting the replication issue and configuring required services to get the agent installation successful followed by replication.;07/Apr/25 10:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [5 empty] | AM20-14 | AM20-4 | [23 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@106887e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnnb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:26 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This user story is blocked due to [https://vodacom.atlassian.net/browse/AM20-14¦https://vodacom.atlassian.net/browse/AM20-14¦smart-link] the network setup, upon completion of network will pick this one up. | 21/Mar/25 12:19 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet is shared, requested [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] to create a connectivity between on-premises to cloud. After the connectivity established, will be able to pick this migration agent toll installation for TM1. | 25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created a replication template and post launch template, waiting for the connectivity to be established between on-premises and TM1 AWS account. | 27/Mar/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Shared Agent and access details to vodacom team, have raised CRQ request for agent installation. 28th is planned for agent installation followed by replication will be initiated. | 04/Apr/25 11:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;On-prem to AWS Connectivity is established, Agent installation is getting failed due to multiple time of attempt, now waiting for restart of server from the logs. will try to install again and update the proceeding's here, | 07/Apr/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Replication is in progress, waiting for initial snapshot to be created. | 07/Apr/25 10:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Though agent installation completed, marking this story to done. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-07 10:45
AM20-10 | Nexio AV¦¦ Migration tool installation / New Set-up | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620531 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 12:53 | 2025-06-05 08:32 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the Nexio AV SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [6 empty] | AM20-13 | AM20-15 | [5 empty] | 05/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;NexioAV-Replacement.pdf;https://vodacom.atlassian.net/rest/api/3/attachment/content/1110196 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ac52572 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:u | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:25 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked due to [https://vodacom.atlassian.net/browse/AM20-15¦https://vodacom.atlassian.net/browse/AM20-15¦smart-link] network story, upon completion will pick this up. | 21/Mar/25 12:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AirnavX migration discussion is still on-going, post that network setup will be created along with connectivity. After the connectivity established, will be able to pick this migration agent toll installation for AitnavX. | 02/May/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for Network setup with internet access to be in place with all required route entry. | 16/May/25 8:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting on network matrix implementation and confirmation. waiting for centralized subnet on transit gateway creation and confirmation from [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 04/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Story to be dropped, migration is not applicable for this application whereas fresh installation is planned with a new EC2 instance. | 05/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;[^NexioAV-Replacement.pdf] | 05/Jun/25 8:32 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Requirement is changed as part of attached email, hence closing this one. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-05 08:31
AM20-8 | AirNavX ¦¦ Subnet creation using terraform | Done | 0 | Sprint 1 | 2025-03-17 | 2025-03-28 | Sankalp Rai | High | 1620392 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 11:52 | 2025-04-21 09:01 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for AirnavX application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for AirNavX and the configured based on the approved comms matrix |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4777a0ee | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnaf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:52 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 09/Apr/25 5:44 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets has been created. Please review | 17/Apr/25 11:10 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Subnet was created manually Subnet > created Route table > Created SG > Created NACL > Created AD Firewall flow > Implemented Send for PO Approval | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-21 09:01
AM20-7 | Teammate ¦¦ subnet creation using terraform | Done | 2 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620382 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 11:49 | 2025-04-14 09:39 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Teammate application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Teammate and the configured based on the approved comms matrix |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@776c05e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 3 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-04 08:58 | [13 empty] | 04/Apr/25 10:58 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets has been created | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-14 09:39
AM20-6 | AWS Infra Readiness for Migration | To Do |  | None( Epic) |  |  |  | High | 1620376 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 11:47 | 2025-03-04 11:47 |  |  |  | 0 | AWS Platform for all 20+ application must be ready which includes provisioning of AWS workloads in respective application account, Security & Industry standard compliance implementation, connectivity, RBAC and resource tagging in place | [23 empty] | 3398400 | 2736000 | 748920 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6680bbd | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-13 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | dark_green | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxn7b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-03-04 11:47
AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | To Do |  | None( Epic) |  |  |  | High | 1620369 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 11:46 | 2025-03-04 11:46 |  |  |  | 0 | Application migration (re-hosting or re-platforming of on-prem applications to AWS cloud. The activities includes, deployment of DMS tool in SAA servers, migration related activities, configuration, 3rd party application connectivity's, setting up of issue resolution, backup and restore validations, DR, DNS change, UAT, Delta migration, issue fixes and final handover activities | [23 empty] | 1713600 | 864000 | 835200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6d20c765 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-6 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | green | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxn5r: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-03-04 11:46
AM20-4 | TM1 ¦¦ Subnet creation using terraform | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Satya Varanasi | Medium | 1620359 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 11:42 | 2025-04-15 16:09 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for TM1 application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for TM1 and the configured based on the approved comms matrix |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-11 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a96537d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnn3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:53 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 04/Apr/25 10:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation got completed Manuel. As terraform not ready. While creating this TM1 subnets. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-07 10:11
AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | To Do |  | None( Epic) |  |  |  | High | 1620350 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 11:35 | 2025-03-04 11:35 |  |  |  | 0 | Application migration (re-hosting or re-platforming of on-prem applications to AWS cloud. The activities includes, deployment of DMS tool in SAA servers, migration related activities, configuration, 3rd party application connectivity's, setting up of issue resolution, backup and restore validations, DR, DNS change, UAT, Delta migration, issue fixes and final handover activities | [23 empty] | 273600 | 100800 | 144000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3525bd44 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-3 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | yellow | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxn1b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-03-04 11:35
AM20-2 | AWS Infra Readiness for Migration | In Progress |  | None( Epic) |  |  |  | High | 1620340 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2025-03-04 11:27 | 2025-03-04 11:27 |  |  |  | 0 | AWS Platform for all 20+ application must be ready which includes provisioning of AWS workloads in respective application account, Security & Industry standard compliance implementation, connectivity, RBAC and resource tagging in place |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [15 empty] | 1137600 | 950400 | 187200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4545cda9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-2 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | dark_yellow | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxmzj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | In Progress | 2025-03-04 11:27
AM20-312 | PROS ¦¦ Migration agent installation | Done | 0 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786910 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 20:14 | 2026-01-15 23:22 |  |  |  | 0 | AS AWS Product owner I want to install migration agents in both source and target accounts so that workloads can be discovered replicated and migrated securly and reliable into AWS, capture disk, network activity and replicate workloads in AWS Acceptance Criteria: *Replication receiver* - Given the target AWS account is selected when the migration service creates replication servers or staging area subnets then the target account provisions EC2 instances and storage for replication *IAM trust policies* - The migration hub service role is created in the target account when the source account publishes replication traffic, then cross account IAM trust allows replication without manual credential handling *Networking and Security* - The replication server is deployed in a VPC when traffic flows from source to target then it uses encrypted channels and passes through SG/NACLrules validated against compliance baselines *Resources readiness* - Migrated workloads are created in the target when cutover happens the EC2, RDS and AWS service provision successfully in the correct subnet, AZ and security group *Monitoring and rollback* - Agents are sending replication data when a failure occurs then alerts are generated in CoudWatch/SNS and rollback to the last stable snapshot is possible |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5de8572e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hc4b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:15 | [13 empty] | 24/Sep/25 8:14 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Need to check with Sinjun/Wanda for change request initiation for agent installation. | 25/Sep/25 5:25 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change has been submitted â€œCHG0067735â€ and approved, we required Sinjun support for Agent installation. | 26/Sep/25 12:19 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still Migration agent comms not implemented and it is under approval process. | 09/Oct/25 4:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Agent has been installed on all 3 PROS servers and test instance has been created and handed over to customer for connectivity testing. Hence i am closing this story. | 17/Oct/25 7:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:17
AM20-313 | MQ Migration - POC ¦¦ Sandbox environment | Done | 8 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1785826 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 20:29 | 2026-01-28 22:34 | 2025-11-21 13:35 | 2025-11-15 14:39 |  | 0 | Set up aÂ sandbox environmentÂ using AmazonMQ to test the proposed approach in collaboration with the Amadeus team. |  | Harsh Chandra | Sumit Nikam | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Prepared rough arch design for PoC purpose based on available info.;14/Nov/25 8:20 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | Analyzed cpp parser info shared by Sampi ;14/Nov/25 8:20 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Further analysis done based on Amadeus feedback and ICP document.;14/Nov/25 8:21 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Created PoC environment with Public IP (EIP) allocated to NLB, ActiveMQ broker from AmazonMQ, a windows and linux instance for testing with necessary connectivity.;14/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | Analyzed sample message along with cpp parser further.;14/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 |  | 115200 | 14400 | 100800 | 0.87 | 115200 | 14400 | 100800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@79b4a52 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h70b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | Sprint 18 | [95 empty] | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 |  | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | [65 empty] | YES | YES | 2025-09-24 06:14 | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | [12 empty] | 24/Sep/25 8:13 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Amadeus shared document has been reviewed. Setup in sandbox has been started. | 26/Sep/25 8:11 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;A sample queue with ActiveMQ being created. Following up with Sampi for parser requirements. | 29/Sep/25 8:28 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Additional dependencies identified during POC. Have asked Amadeus to check and confirm: # *Supported Protocols* Which message protocols do you recommend for integration with Amadeus? * OpenWire/JMS (ActiveMQ) * AMQP 0-9-1 (RabbitMQ) # *IBM MQ Header Mapping* Which IBM MQ MQMD fields are mandatory for Amadeus integration (e.g., Format=1AIEDI, ReplyToQ, CorrelationID)? If we use Amazon MQ (ActiveMQ) or RabbitMQ, can these fields be provided as JMS/AMQP properties (e.g., JMSReplyTo, JMSCorrelationID, custom header x-format=1AIEDI)? If not, do you have a mapping guide for IBM MQMD to JMS/AMQP headers? # *Character Set and Separators* Do you require character set B with binary EDIFACT separators (0x1D, 0x1F, 0x1C), or do you also accept printable characters (+, :, ')? If both are accepted, is there a preferred encoding for production? # *Maximum Message Size* What is the maximum supported message size for messages exchanged with Amadeus? # *EDIFACT Envelope Validation* Do you validate the UNB/UNH/UNT/UNZ envelopes on your side, or should we handle this validation before sending messages? # *Message Persistence* Should we configure all messages as persistent, or should we match the persistence settings from the ICP (e.g., LinkA3 non-persistent, others persistent)? # *Dead-Letter Queue (DLQ) Handling* Do you require a specific dead-letter queue (DLQ) contract on our side, or is a standard broker-level DLQ sufficient? If a DLQ contract is required, do you expect a specific queue name or message format? # *Synchronous Request/Reply SLAs* What are the expected SLAs (response time, timeout, retry policy) for synchronous request/reply flows (Association Codes O/T)? | 30/Sep/25 8:19 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Following up with Sampi for MQ parsers for analysis. Following up with Amadeus for configuration details. | 01/Oct/25 4:32 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Discussion done with Sampi to understand current parsing configs and queues in use. We have given overview of AmazonMQ based setup and asked for rest of the parsers for further analysis. | 06/Oct/25 8:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Awaiting inputs on configuration details from application owner, hence will be spilled over. | 17/Oct/25 11:21 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 30/Oct/25 9:48 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Information received from Amadeus but needs to be spilled over to next sprint since we do not have sufficient time to complete within current sprint. | 07/Nov/25 7:57 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;One to One message mapping is working as expected. We are facing challenges for following: 1. Sync Communication among producer and consumer # One to Many message delivery being checked further. | 10/Nov/25 8:17 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Custom header addition has been added in message exchange. Testing in progress | 12/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Unable to parse properties as per instructions from Amadeus. Checking further. Following up with Sampi in parallel to get test messages for testing parsing capability. | 13/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Working on MQMD fields as per ICP document from Amadeus. | 14/Nov/25 11:54 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;POC has been carried out for Pegasys app parser as a part of which, Existing CPP based SDN Split parser was converted to the java based parser which was using ActiveMQ library. A sample message was then sent to Pegasys input queue {{PEGASYS.OUT.UAT}} And based on message content, rewritten parser running with java analyzed the content and routed the incoming message to one of the following output queues based on the content and rules defined: {noformat}parser.queue.star=PEGASYS.STAR.UAT parser.queue.mng=PEGASYS.MNG.UAT parser.queue.cimp=PEGASYS.CIMP.UAT parser.queue.sip=PEGASYS.SIP.OUT parser.queue.icargo=PEGASYS.ICARGO.UAT parser.queue.err=MNG.PEGASYS.ERR.UAT{noformat} | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | Done | 2025-11-15 14:39
AM20-314 | Security group and NACL rules remediation | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818704 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-06 21:50 | 2026-02-06 22:04 |  |  |  | 0 | Should restrict port 22, 3389, 1433, 3306 from all traffic 0.0.0.0/0 across all the AWS accounts. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [11 empty] | 17856 | 17856 |  | 0 | 17856 | 17856 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3bed953e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzwr: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 11:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SG inbound rules are updated to restrict port to allow all traffic 0.0.0.0/0 | [26 empty] | 1817984 | AM20-225 | Security controls remediation - Informatica and PROS Aws accounts | Done | 2025-10-28 11:20
AM20-315 | Informatica Server ¦¦ Security compliance implementation | Done | 3 | Sprint 7 | 2025-06-09 | 2025-06-20 | Aravind Raj | Medium | 1681739 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 14:56 | 2026-01-23 17:38 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of PROS account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;10/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;10/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 43200 | 0 | 57600 | 1.33 | 43200 | 0 | 57600 | [12 empty] | 10/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250610-061229.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1112272 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2572cbfb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05tqj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-06 06:15 | [13 empty] | 06/Jun/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will be start working on enabling the frameworks, followed by that will work controls implementation and remediation | 09/Jun/25 7:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CIS NIST and AWS FSBP security frameworks are enabled, in parallel controls were implemented and have completed remediation. Awaiting for the security score to update in security hub, | 10/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Updated security hub for the different controls; !image-20250610-061229.png¦width=1279,height=587,alt="image-20250610-061229.png"! | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-10 08:12
AM20-316 | Review Memory dashboard and alarm of all application hosted in AWS and configure the right dashboard for memory utilization | Done | 4 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1866169 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 14:49 | 2026-01-19 17:26 | 2025-12-14 17:51 | 2025-12-12 11:19 |  | 0 | As product Manager I want to correct the current memory related dashboard for all applications in alignment with TM1 application which is already corrected by Aravind |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;03/Dec/25 7:29 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;21600 | ;07/Dec/25 1:47 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;09/Dec/25 12:42 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;25320 |  |  |  | 57600 | 0 | 57720 | 1 | 57600 | 0 | 57720 | [12 empty] | 09/Dec/25 12:52 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251209-105119.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1193693 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@14947356 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7xb: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 |  | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | [65 empty] | YES | YES | 2025-12-03 05:28 | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | [12 empty] | 03/Dec/25 7:28 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Started working on 2 Account and will complete the remaining oneâ€™s by today. | 07/Dec/25 1:49 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have updated the Memory Committed Bytes for all the Windows servers for all the accounts. Need to review it with faisal. And then will move this story to PO approval. | 09/Dec/25 12:43 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Completed the activity and updated the Memory Committed Bytes Name and Threshold value for all accounts. | 09/Dec/25 12:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251209-105119.png¦width=641,alt="image-20251209-105119.png"! Evidence has been attached from one of the account for which the Memory Committed bytes has been updated. | 12/Dec/25 11:19 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-12-12 11:19
AM20-317 | PROS ¦¦ Migration agent installation | Done | 0 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786910 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 21:54 | 2026-01-16 23:41 |  |  |  | 0 | AS AWS Product owner I want to install migration agents in both source and target accounts so that workloads can be discovered replicated and migrated securly and reliable into AWS, capture disk, network activity and replicate workloads in AWS Acceptance Criteria: *Replication receiver* - Given the target AWS account is selected when the migration service creates replication servers or staging area subnets then the target account provisions EC2 instances and storage for replication *IAM trust policies* - The migration hub service role is created in the target account when the source account publishes replication traffic, then cross account IAM trust allows replication without manual credential handling *Networking and Security* - The replication server is deployed in a VPC when traffic flows from source to target then it uses encrypted channels and passes through SG/NACLrules validated against compliance baselines *Resources readiness* - Migrated workloads are created in the target when cutover happens the EC2, RDS and AWS service provision successfully in the correct subnet, AZ and security group *Monitoring and rollback* - Agents are sending replication data when a failure occurs then alerts are generated in CoudWatch/SNS and rollback to the last stable snapshot is possible |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5de8572e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hc4b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:15 | [13 empty] | 24/Sep/25 8:14 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Need to check with Sinjun/Wanda for change request initiation for agent installation. | 25/Sep/25 5:25 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change has been submitted â€œCHG0067735â€ and approved, we required Sinjun support for Agent installation. | 26/Sep/25 12:19 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still Migration agent comms not implemented and it is under approval process. | 09/Oct/25 4:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Agent has been installed on all 3 PROS servers and test instance has been created and handed over to customer for connectivity testing. Hence i am closing this story. | 17/Oct/25 7:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:17
AM20-318 | Trellix integration with AirnavX | Done | 1 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 13:04 | 2026-02-06 14:32 |  | 2025-11-12 08:22 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan AirNavX workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in AirNavX server * Trellix is able to access AirnavX account successfully and perform scanning |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 05/Nov/25 3:41 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ Trellix scanning status for New AWS AirNavV servers.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1178115 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f4c84b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 18 | [95 empty] | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [65 empty] | YES | YES | 2025-09-08 07:56 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [12 empty] | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 30/Sep/25 7:40 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working with Sinjun for trellix installation on these 2 servers. | 06/Oct/25 8:39 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Working with Sinjun for Trellix installation, hence will be spilled over | 09/Oct/25 4:29 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Sinjun Albert is going to install Trellix and he will confirm once integration done. | 17/Oct/25 11:17 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over reason - Blocked due to ongoing app installation issues, currently worked upon by app owner; post which this story will be progressed in subsequent sprint | 05/Nov/25 3:41 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Trellix software installed on New AWS AirNavX servers. All AirNavX servers able to discover from Trellix admin server and same has been confirmed by Sinjun. Attaching reference for support. [^RE_ Trellix scanning status for New AWS AirNavV servers.msg] | 12/Nov/25 8:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | Done | 2025-11-12 08:22
AM20-319 | Terraform Development ¦¦ Creation of Outbound and inbound rules in NACL | Done | 8 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1651313 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 14:14 | 2026-01-29 16:31 | 2025-11-27 08:27 | 2025-11-28 12:00 |  | 0 | As Terraform expert, I want to be creating a network ACL with inbound and outbound rules using terraform code, so that I can apply stateless packet filtering at the subnet level Acceptance Criteria: * Define variable for CIDRs, ports and subnets * NACL resources is created and associated with target subnets * Application relevant flows needs to be populated * Application inbound rule and comms metric needs to populated for NACL * Outbound rules allow return traffic on the same ports. * Each rule has a unique number and direction * Rules are parameterized for environment flexibility * add rule description and tags. * Provision to add or deny additional rules with max of 20 rules to be allowed for NACL |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@442b4964 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mrnr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 19 | [96 empty] | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-20 07:06 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 20/Nov/25 9:06 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Working on base module code of terraform script. It will be completed by this Friday EOD. | 27/Nov/25 8:24 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform script completed and NACL resource created in sandbox environment. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-11-28 12:00
AM20-320 | AirNavX ¦¦ Application monitoring and Alerting | Done | 6 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1801368 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 13:07 | 2026-01-15 14:16 | 2026-01-04 09:13 | 2026-01-04 08:43 |  | 0 | AS Product owner I would like to configure alerting and monitoring for application specific alerts. Acceptance Criteria: All the attached alerts must be configured in Cloudwatch /SNS/ Lamda/ so that for each occurance, the error is sent to ServiceNow for incident creation/generation. |  | Diksha Koul | Faisal Sayed | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  | Adding Lambda for accessing URL and monitoring status using cloudwatch alarms. Also sending ServiceNow events when the threshold is breached. ;02/Jan/26 9:52 AM;17cb9418-1850-4923-932b-7098ec51b6bb;43200 | [5 empty] | 86400 | 43200 | 43200 | 0.5 | 86400 | 43200 | 43200 | [12 empty] | 11/Dec/25 10:35 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;RE airnavX alarm requirements.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194363 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@747ca5f3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 21 | [97 empty] | 3_*:*_2_*:*_1826706492_*¦*_10041_*:*_2_*:*_851221150_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_4844844325 |  | 3_*:*_2_*:*_1826706492_*¦*_10041_*:*_2_*:*_851221150_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_4844844325 | 3_*:*_2_*:*_1826706492_*¦*_10041_*:*_2_*:*_851221150_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_4844844325 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_1826706492_*¦*_10041_*:*_2_*:*_851221150_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_4844844325 | [65 empty] | YES | YES | 2025-11-20 05:23 | 3_*:*_2_*:*_1826706492_*¦*_10041_*:*_2_*:*_851221150_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_4844844325 | [12 empty] | 20/Nov/25 7:23 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status:* Blocked. *Reason:* Awaiting finalization of approach. Application monitoring will be configured post cutover. *Options under discussion:* # Convert current instance license (pending resolution). # Redeploy instance with required RHEL subscription. | 24/Nov/25 8:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status:* Blocked *Update:* The option to convert the current instance license is now resolved. Awaiting AirnavX cutover; application monitoring will be implemented post-cutover. | 28/Nov/25 11:41 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;To be taken up post completion of AirnavX cutover | 18/Dec/25 8:38 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started working on the the URL for alerting as per Albertâ€™s requirement. | 02/Jan/26 9:55 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Alarms are setup in airnavx account to monitor accessibility to airnavx URLs and trigger notifications when the URL is unavailable for 15 minutes. Example payload: {"Name": "AirNavX-AirnavX_AppHealth-base-down","IP Address": "NA","Fully Qualified Domain Name": "[airnavxpub.flysaa.com¦http://airnavxpub.flysaa.com]","Company": "VFSA","Hostname": "[airnavxpub.flysaa.com¦http://airnavxpub.flysaa.com]","Department": "App DevOps Team","Operating System": "Amazon Linux","DNS Domain": "[airnavxpub.flysaa.com¦http://airnavxpub.flysaa.com]","Disk Space (GB)": "NA","RAM (MB)": "4000","CPU Count": "2","CPU core count": "2","Alarm Time": "2026-01-02 06:08:49 UTC","Account ID": "345594574792","Environment": "Airnavx","MetricName": "ActuatorHealth","Current State": "ALARM","Reason": "Threshold Crossed: 1 out of the last 3 datapoints [1.0 (02/01/26 05:53:00)] was less than the threshold (2.0) (minimum 3 datapoints for OK -> ALARM transition)."} | 04/Jan/26 8:43 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2026-01-04 08:43
AM20-321 | MQ¦¦ Migration Agent comms Metrics implementation | Blocked | 2 | Sprint 16 | 2025-10-13 | 2025-10-24 | Satya Varanasi | Medium | 1794120 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 15:31 | 2026-02-03 19:17 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@692cf397 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g9 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-17 09:19 | [13 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | [29 empty] | To Do | 2025-09-30 10:14
AM20-322 | Patch Management ¦¦ Dashboard Enhancement | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1746156 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 19:03 | 2026-01-27 22:04 |  |  |  | 0 | As Product manager compliance dashboard needs to be enhance and should covered details of patch file Acceptance Criteria: Compliance dashboard need to patch details and account details |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4159e3f0 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cz63: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 20:35 | [13 empty] | 18/Aug/25 10:34 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Update for Patch Manager Monitoring, in the compliance bucket there are 3 folders created after creating the resource data sync but not for the target acc we need. i have changed certain policies and also added some permissions both in security as well as dev acc. I am waiting for the data to pop up and also i can trigger data collection forcefully via aws cloudshell command but i do not have access i have intimated Aravind for permission addition. and the data that is being collected is basically json and that is the format that we need for it to be visualized in cloudwatch. | 25/Aug/25 8:52 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;spillover: the data sync which has been created in the management acc theoretically should be able to fetch the summaries from target account and sync that data in the s3 bucket in central account. the steps that were tried to force a sync were: {code:json}Check if the Instance is Managed by Systems Manager Check Current Associations Check Current Inventory Data Create the Inventory Association Verify Association Creation Check Association Status Monitor Association Execution Check for Updated Inventory Data{code} All of these were done and created an association manually for it to be populated into s3 bucket yet it did not work. the permission policies are provided yet the target account data is not being synced. the issue was that resource data sync must be created in each of the target account which was earlier thought as not needed. have created ressource data sync and waiting for the data to be populated. | 28/Aug/25 8:34 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Spillover Revised Comment: I was troubleshooting the resource data sync that i created since theoretically, resource data sync in the management account was enough. After rigorous attempts to fix the issue and trying to find out the workarounds they all failed. At the end of the week, close to sprint closure I found the solution and applied it and the solution worked. Hence, the delay and also for the data to populate into the intended bucket it sometime takes 10-12 hrs. | 03/Sep/25 8:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# The Resource Data Sync has been troubleshoot correctly and is working as intended. # Lambda function has been created in backend-dev account so that it can brand all the instances as non-compliant initially. # EventBridge has been configured as such when any new instance is provisioned it shall be flagged as non-compliant using the lambda function mentioned in point no.2. # The data in S3 is being used to project it to CloudWatch and that is being do using a Lambda function which will create metrics from the data in S3. # CloudWatch Dashboard is created such that it will have visual data segregated acc to the Acc Ids. (which was requirement by Bhavish). | 08/Sep/25 6:35 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;need demo | 08/Sep/25 8:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: The story was completed sufficing all the acceptance criteria. Demo was not done due to unavailability, hence scheduling the demo for 9/9/2025 considering everyoneâ€™s availability. | 11/Sep/25 9:12 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Demo was provided. The methodology and implementation was agreed upon and approved. There was an ask to involve another accounts, in order to check the workability. The accounts addition was done successfully and the data is presented on the custom dashboard as well. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:20
AM20-323 | MQ ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Blocked | 0 | Sprint 16 | 2025-10-13 | 2025-10-24 | Satya Varanasi | Medium | 1758329 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 16:08 | 2026-01-31 16:15 |  |  |  | 0 |  |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4544ef36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g02 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-17 09:19 | [13 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | [29 empty] | To Do | 2025-08-18 16:44
AM20-324 | Documentation on Budget Management | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747516 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 14:38 | 2026-01-19 17:35 |  |  |  | 0 | As Product Owner, I would like to create a detailed documentation on Budget management solution Acceptance Criteria: Document should consist of below sections with detailed description. * IAM roles /groups and policy created for it * Details of any Lamda functions are configured * process to add users to the group to allow edit/view/remove privileges * Dashboard and configurations details * Process to change, update budget allocated, notification iteration etc. * Details of naming convention and tagging as applicable * Architectural diagram as applicable |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/Aug/25 12:23 PM;9e4636e8-9dfc-4a33-901b-fcd75015926a;AWS_Budget_Management.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1143135 | 14/Aug/25 7:01 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;Budget Documentation (24287a92-0ff3-4da3-9f2c-3378740b4c97).docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139610 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@58ed7f61 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2rv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-14 05:03 | [13 empty] | 14/Aug/25 7:02 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Document has been attached. Please verify [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] | 22/Aug/25 12:23 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;[^AWS_Budget_Management.docx] AWS Budget Document attached | 25/Aug/25 6:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 06:34
AM20-325 | Rehosting & Replatforming of applications from on-Prem to AWS | To Do |  | None( Epic) |  |  |  | High | 1620369 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 15:08 | 2026-01-19 17:34 |  |  |  | 0 | Application migration (re-hosting or re-platforming of on-prem applications to AWS cloud. The activities includes, deployment of DMS tool in SAA servers, migration related activities, configuration, 3rd party application connectivity's, setting up of issue resolution, backup and restore validations, DR, DNS change, UAT, Delta migration, issue fixes and final handover activities | [23 empty] | 1713600 | 864000 | 835200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6d20c765 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-6 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | green | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxn5r: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-03-04 11:46
AM20-326 | AirNavX Account ¦¦ Security Compliance Implementation | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672716 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-01 16:00 | 2026-02-01 18:04 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of AirNavX account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250528-092239.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1106065 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@33a69e54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04ft7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-28 09:24 | [13 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Account - 345594574792 Controls were implemented and security score is updated is for all the three security standard frameworks- CIS, NIST and AWS FSBP !image-20250528-092239.png¦width=1279,height=589,alt="image-20250528-092239.png"! | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-28 11:24
AM20-327 | Nexio AV ¦¦ E2E Integration testing of ServiceNow monitoring | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1732203 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 16:20 | 2026-01-29 19:02 |  |  |  | 0 | As Product Owner I would like to review e2e testing completed with servicenow team for all wave 1 application so that we can confirm to business that in case of any issue service ticket would be raised Acceptance Criteria: * Tickets/issues are getting raised successfully against the alerts raise via cloudwatch for all Wave1 applications * ServiceNow team signoff received * Showcase (demo) provided to all relevant stakeholders |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 19/Aug/25 10:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141324 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1c3893f7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0brrj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-28 07:41 | [13 empty] | 28/Jul/25 9:41 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[https://vodacom.atlassian.net/browse/AM20-116¦https://vodacom.atlassian.net/browse/AM20-116¦smart-link] Only after completing the above US will start working on this story. | 28/Jul/25 3:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;After completion of Faisal story i will be proceeding with this US. | 11/Aug/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: Since the story was blocked due to configuration of monitoring and alerting on NexioAV ec2 instances (application specific) which was completed on 8th Aug 2025 (evening), Diksha did not get any time to validate end to end solution. Hence, the spillover. | 19/Aug/25 10:17 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have tried to triggered the alert to service now team. Now waiting for them to confirm from there side. | 19/Aug/25 10:33 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation for Priyanka and team the alerts are getting generated and tickets are being created in service now. Attaching the same screenshot for the reference. | 19/Aug/25 10:36 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image.png¦width=881,height=228,alt="image.png"! attaching the screenshot what service now team is getting the alerts for your reference from Priyanka and team. | 21/Aug/25 2:31 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:31
AM20-328 | Handover of Patching solution | Done | 4 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1866136 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 22:13 | 2026-01-12 23:25 | 2025-12-14 17:52 | 2025-12-12 11:19 |  | 0 | As product owner I want Diksha to take handover along with Satya from Faisal so that she can support customer |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [5 empty] | ;09/Dec/25 12:43 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;10/Dec/25 3:38 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 09/Dec/25 12:55 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251209-105350.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1193694 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@58f0f8fd | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7xd: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-09 10:45 | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 09/Dec/25 12:45 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started the Hands on for patching first worked on pre-requisites and AWS cli and cloud watch agent installation on the Sandbox EC2 instance. The Session has been recorded as well. | 09/Dec/25 12:55 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251209-105350.png¦width=641,alt="image-20251209-105350.png"! This server is created as a Test Patching server for the Windows patching activity. As of now this has been kept in stopped state later after the patching will get done we will delete the server moving further. The below pointers has been completed. * *Provisioned Test Environment* ** Deployed a test EC2 instance in the designated sandbox environment. * *Network Configuration* ** Configured VPC endpoints to enable *private connectivity for AWS Systems Manager (SSM)*, ensuring secure management without requiring a public IP. * *Identity and Access Management (IAM)* ** Created IAM roles, policies, and instance profiles for EC2 to support required permissions. ** Implemented a *cross-account IAM role* for Lambda in the security account, enabling patching operations in the sandbox environment. ** Updated trust relationships to align with cross-account access requirements. * *Instance Setup and Agent Installation* ** Downloaded and installed *AWS CLI*, *CloudWatch Agent*, and *SSM Agent* on the EC2 instance. ** Deployed a custom compliance reporting script within the instance. * *Automation and Management* ** Authored and deployed a *custom SSM document* to support patching and compliance workflows. | 10/Dec/25 3:37 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Below pending points are also covered today and the handover of the patching is completed. * *S3 Bucket Configuration* ** Set up an Amazon S3 bucket with the required folder structure. ** Apply appropriate *IAM permissions* and *bucket policies* to ensure secure access. ** Configure *S3 event notifications* to trigger downstream processes as needed. * *Lambda Automation for Patching* ** Develop and deploy a Lambda function to *automate patching activities* within the sandbox account. ** Ensure the Lambda function uses the *cross-account IAM role* created today, granting it the necessary permissions to execute patching tasks in the sandbox environment. ** Validate the Lambda execution policy and trust relationship for compliance and least-privilege access. | 10/Dec/25 3:38 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[Recap: Patch Implementation - Internal Tuesday, December 9 ¦ Meeting ¦ Microsoft Teams¦https://teams.microsoft.com/l/meetingrecap?driveId=b%21d5bfbASx8UyuyN5zJPY_C1jj3vg4dqxGo4vsecE4YZu3kE97HxTiSrSKd-pI-KUx&driveItemId=016NKAQFNQOEZURWCDERFYBPVICI6NDJX2&sitePath=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQCwcTNI2EMkS4C-qBI80ab6Af6L1MuuoLAsP4web0CEjFk&fileUrl=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQCwcTNI2EMkS4C-qBI80ab6Af6L1MuuoLAsP4web0CEjFk&iCalUid=040000008200E00074C5B7101A82E00800000000A47F206EE268DC01000000000000000010000000321233C36A404C46934C1B5B72B7F07A&threadId=19%3Ameeting_ZjBlZDVhMjMtNDI4ZC00NjQ5LThiMzgtM2FiMDhhNTIyZDg2%40thread.v2&organizerId=8f4c76ce-ca6e-44bd-bbde-0eb6186f9df7&tenantId=68283f3b-8487-4c86-adb3-a5228f18b893&callId=76b0f585-b89d-412b-b23f-2527a464dab5&threadType=Meeting&meetingType=Scheduled&subType=RecapSharingLink_RecapChiclet] [Recap: Patch Implementation - Internal Wednesday, December 10 ¦ Meeting ¦ Microsoft Teams¦https://teams.microsoft.com/l/meetingrecap?driveId=b%21d5bfbASx8UyuyN5zJPY_C1jj3vg4dqxGo4vsecE4YZu3kE97HxTiSrSKd-pI-KUx&driveItemId=016NKAQFKGUFQPO2BR7VC3OZIJ4T4BALUJ&sitePath=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQBGoWD3aDH9RbdlCeT4EC6JAf1ANE41qecWYg-ZpI8nWPs&fileUrl=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQBGoWD3aDH9RbdlCeT4EC6JAf1ANE41qecWYg-ZpI8nWPs&iCalUid=040000008200E00074C5B7101A82E00800000000F3F48BFDF868DC01000000000000000010000000D320B3E36531F44C8156C61B7DCD0871&threadId=19%3Ameeting_YTQ3OGI1ODMtM2JjMy00YTkzLTlhNjQtYWUwMGY4OTFlZDAz%40thread.v2&organizerId=8f4c76ce-ca6e-44bd-bbde-0eb6186f9df7&tenantId=68283f3b-8487-4c86-adb3-a5228f18b893&callId=3fb32e76-7aa1-40f8-a245-6ac6fdac8f6c&threadType=Meeting&meetingType=Scheduled&subType=RecapSharingLink_RecapChiclet] Both recording links has been attached above. | [26 empty] | Done | 2025-12-12 11:19
AM20-329 | TM1 ¦¦ Migration tool installation | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620533 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 12:34 | 2026-01-16 15:04 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the TM1 SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | Working with nexio team on troubleshooting the replication issue and configuring required services to get the agent installation successful followed by replication.;07/Apr/25 10:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [5 empty] | AM20-14 | AM20-4 | [23 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@106887e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnnb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:26 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This user story is blocked due to [https://vodacom.atlassian.net/browse/AM20-14¦https://vodacom.atlassian.net/browse/AM20-14¦smart-link] the network setup, upon completion of network will pick this one up. | 21/Mar/25 12:19 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet is shared, requested [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] to create a connectivity between on-premises to cloud. After the connectivity established, will be able to pick this migration agent toll installation for TM1. | 25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created a replication template and post launch template, waiting for the connectivity to be established between on-premises and TM1 AWS account. | 27/Mar/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Shared Agent and access details to vodacom team, have raised CRQ request for agent installation. 28th is planned for agent installation followed by replication will be initiated. | 04/Apr/25 11:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;On-prem to AWS Connectivity is established, Agent installation is getting failed due to multiple time of attempt, now waiting for restart of server from the logs. will try to install again and update the proceeding's here, | 07/Apr/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Replication is in progress, waiting for initial snapshot to be created. | 07/Apr/25 10:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Though agent installation completed, marking this story to done. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-07 10:45
AM20-330 | Bastion Host creation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642039 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 13:39 | 2026-02-01 16:53 |  |  |  | 0 | As AWS expert, I would be creating two Bastion host by launching Private EC2 instance and AMI for preferred operating system and configure Security groups and apply Inbound and Outbound Rule * One for Internal Migration team (having internet access) * Another for Nexio and Customer access with RDS enabled Acceptance Criteria: * Bastion host provisioned successfully * access is provided to Nexio and business team by SSH client and connect to bastion host public IP adddress using private key |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;17/Apr/25 2:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 57600 | 14400 | 28800 | 0.5 | 57600 | 14400 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@327eec44 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00syj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-15 16:18 | [13 empty] | 15/Apr/25 6:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Separate Network setup with internet gateway and pubic IP will be required for shared service account 864899875361, after network setup would create bastion server for internal team usage. [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] may need your help in setting up network. | 17/Apr/25 2:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;I have created a Bastion host in network account and have customized RDP port number from 3389 to *54925* for security measures. Â As we all know the jump server can be RDP accessed by two user in parallel, have created a user account named *VOIS_User01 and VOIS_User02* with Administrator privilege, password will be shared separately. Â Bastion Host Details; Â *Server name: Bastion-Host-Internal* *Server IP: 16.28.7.145(ElasticIP)* *Server RDP Port: 54925* | 17/Apr/25 2:16 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Bastion host for Nexio will be created after sometime. | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-17 14:16
AM20-331 | Pegasys LLD Creation | To Do | 0 | None( Backlog) |  |  |  | Medium | 1832851 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 20:37 | 2026-01-11 21:18 |  |  |  | 0 |  |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@ab71d36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g002 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-11 14:48
AM20-332 | Connectivity via Lamda and registering the account under patching management | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824389 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 16:38 | 2026-01-30 19:15 |  | 2025-11-14 11:12 |  | 0 | Connectivity via Lamda for Patching and Register Informatica Dev & Prod environment and AirNavx Prod via security account so that Patching activites can be carried out in these accounts |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Nov/25 2:43 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5dd220d9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_419736642_*¦*_10041_*:*_1_*:*_115097831_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_419736642_*¦*_10041_*:*_1_*:*_115097831_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_419736642_*¦*_10041_*:*_1_*:*_115097831_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_419736642_*¦*_10041_*:*_1_*:*_115097831_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-01 16:21 | 3_*:*_1_*:*_419736642_*¦*_10041_*:*_1_*:*_115097831_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 01/Nov/25 6:20 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Infra level pre-requisites has been completed for the accounts to be registered under Patching Solution. IAM Roles. IAM Policies. Instance Profiles. Instance Tagging. Lambda Functions. S3 Permission Policies. S3 Folder Structure. And inter-instance level requisites like AWS CLI installation compliance reporting scripts is achieved for the migrated instances. | 14/Nov/25 11:12 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-11-14 11:12
AM20-333 | POC - Create Sustainability dashboards | To Do | 8 | Sprint 10 | 2025-07-21 | 2025-08-01 | Sankalp Rai | High | 1720042 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 16:15 | 2026-01-29 19:15 |  |  |  | 0 | As AWS Expert, I would create sustainability dashboard to access the power consumption, utilization and energy efficiency in alignment with well-architecture Acceptance Criteria * Enable AWS Sustainability Pillar in Well-Architected Reviews, optimize workloads for energy efficiency â€” right-sizing, minimizing network transfer, cold storage, etc. * Leverage S3 Lifecycle Policies & Intelligent Tiering |  | Harsh Chandra | Sankalp Rai |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63121580 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v09 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | Sprint 12 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:13 | [13 empty] | 11/Aug/25 10:12 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 12th August End Date: 21st August | 10/Sep/25 1:15 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Moving this to Backlog from Sprint 13 as suggested by Deepak Sharma, to currently focus on critical migration activities. This will be picked up in later sprints. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | To Do | 2025-10-13 09:27
AM20-334 | Informatica Server ¦¦ CloudTrail and Guard Rail implementation | Done | 2 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | Medium | 1681743 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 21:04 | 2026-01-11 00:21 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across informatica server (PROS) account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1eb85c02 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05trf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-05 06:17 | [13 empty] | 05/Jun/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Config and guard Duty is enabled and configured. Cloud Trails logging is enabled already. | 06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard rail implementation is applied for the S3 block public access | 13/Jun/25 2:36 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:36
AM20-335 | ServiceNow Monitoring ¦¦ Prod Implementation | Done | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1673102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-01 15:19 | 2026-02-01 18:24 |  |  |  | 0 | As AWS solution architect, I would like to implement ServiceNow monitoring in prod environment so that alerts can be generated and reach to ServiceNow in form of Tickets for further actions. Acceptance Criteria: * Setup of ServiceNow integration to pull AWS receive data using EventBridge * Unautherized API calls from GuardDuty and Security Hub * Setup Cloudwatch alarms or rules for all the resources entitled to be monitored and send these to SNS topic * Create SNS topic * Configure SNS HTTPS configuration so that SNS can directly invoke HTTPS endpoints * AWS Lambda function created to forward SNS messages by parsing it and sends REST API requests to ServiceNow. * Attach the Lamda to the SNS topic * Set the credentials in AWS Secret Manager * Lamda function can reach the ServiceNow endpoint through API gateway by using HTTPS and Secure authentication |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;04/Jul/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cfb2e84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04h5f: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-26 06:17 | [13 empty] | 26/May/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 8:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting to get a exact tags to be passed to Ec2 instance to receive at service now. *New HTTPS endpoint will be shared by feroz for the production workloads.* | 25/Jun/25 8:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;From 24th June we had a call with feroz, where we expected to get the production servicenow endpoint by nest week to configure in SNS, hence waiting for same to start this user story. | 02/Jul/25 7:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PRODUCTION ServiceNow Instance: [https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws¦https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws] SNS topic is updated with a new subscription and backend prod integration is completed, unit test yet to start. | 04/Jul/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Right now the production environments like Backend, TM1, AirnavX accounts are integrated with the prod service now endpoint and SNS is configured to get the alerts. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-04 08:15
AM20-336 | Trellix Integration with TM1 account | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1718212 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 15:13 | 2026-01-20 18:44 |  |  |  | 0 | As Network experts I would like to integrate Trellix servers with TM1 account so that it is able to scan TM1 workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in TM1 server * Trellix is able to access TM1 account successfully and perform scanning |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 13/Aug/25 12:38 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250813-103653.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139278 | 13/Aug/25 12:38 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250813-103711.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139279 | 13/Aug/25 12:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250813-104007.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139280 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5e9f2d9f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:099 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-17 06:11 | [13 empty] | 17/Jul/25 8:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Agent installed on TM1 test instance and tested, it is working fine. | 25/Jul/25 7:54 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 cutover got pending, this action needed TM1 server cutover/migration. | 13/Aug/25 12:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 cutover competed and testing done. | 13/Aug/25 12:38 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Sinjun the new AWS TM1 server integrated with New AWS-Trellix server. The reference images has been attached for reference. !image-20250813-103653.png¦width=100%,alt="image-20250813-103653.png"! !image-20250813-103711.png¦width=100%,alt="image-20250813-103711.png"! Product installation screen: !image-20250813-104007.png¦width=100%,alt="image-20250813-104007.png"! | 20/Aug/25 8:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-08-20 08:10
AM20-337 | MQ Modernization POC ¦¦ Parser testing based on sample pegasys parser | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832848 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 15:15 | 2026-01-14 16:32 | 2025-11-28 11:15 | 2025-11-28 12:00 |  | 0 | As DevOps Engineer, I need to test few existing MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6bedb0f1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo0r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:26 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:26 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;CPP to Java: Parser to be re-written with line to line conversion to retain logic. | 20/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Java Parser Covering Following High-level Algorithm- # Input * Receive a raw text message body (rawMessage) from AmazonMQ PEGASYS.OUT.UAT. # Pre-check * If rawMessage is null or empty â†’ return ParseResult with error = true (this is defensive; in normal operation this should not happen). # stripId() â€“ remove ID block if present 3.1. Let msg = rawMessage. 3.2. If msg contains "\nM42": * Call stripId(msg): * Find index of " /ID ". * From there, find "ACARS\r\n". * Return: msg_before_ID + msg_from_ACARS_onwards. 3.3. Else: keep msg unchanged. . # Construct buff and newbuff 4.1. buff = msg (the stripped or original message). 4.2. Append control chars: * CR = 13, NL = 10, ETX = 3. * newbuff = buff + CR + NL + ETX. # Split into lines & find .JNB 5.1. Split newbuff by '\n' into lines[]. 5.2. Search for first line where lines[i].startsWith(".JNB"). 5.3. If found, set counter = i + 1 (line after .JNB). 5.4. If not found or counter >= lines.length: * Default: create OutboundMessage(qMng, newbuff) â†’ MNG only. * Return this as ParseResult with error = false. # Extract relevant lines safely * line0 = lines[counter] (or "" if out of range). * line1 = lines[counter + 1] * line2 = lines[counter + 2] * line3 = lines[counter + 3] Using helpers: * safeLine(lines, index) â€“ returns "" if index out of range. # Extract tokens (T1, T2, etc.) safely Using safeSub(s, begin, endExclusive) to avoid index errors. 7.1. T1 = line0[0..3) â†’ message type (MVT, DIV, ASM, SSM, CGO, etc.). 7.2. T2 = line1[1..5) â†’ secondary code (CIRQ, CICX, etc.). 7.3. line1_0_2 = line1[0..2) â†’ used to check "SA". 7.4. line2_0_2 = line2[0..2) â†’ used to check "ED". 7.5. line3_0_3 = line3[0..3) â†’ used to check "TIM". # Prepare result container * outputs = new ArrayList<OutboundMessage>(); # Rule 1 (SSM/CGO â†’ ICARGO) * If T1 is "SSM" or "CGO": * outputs.add(new OutboundMessage(qIcargo, buff)); 10. Rule 2 (CIRQ/CICX â†’ SIP) * If T2 is "CIRQ" or "CICX": * Add OutboundMessage(qSip, buff) to outputs. * Return ParseResult(outputs, false, null) immediately 11. Rule 3 (MVT / DIV / ASM) 11.1. If T1 in { "MVT", "DIV", "ASM" }: 11.1.1 ASM + TIM * If T1 == "ASM" and line3_0_3 == "TIM": * Add OutboundMessage(qCimp, buff) (CIMP). * Add OutboundMessage(qIcargo, buff) (ICARGO). * Then continue. 11.1.2 MVT-specific * If T1 == "MVT": * If line1_0_2 == "SA" (SA flight): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG with CR/LF/ETX). * Add OutboundMessage(qIcargo, buff) (ICARGO). * If line2_0_2 == "ED": * Add OutboundMessage(qCimp, buff) (CIMP). * Add another OutboundMessage(qIcargo, buff) (ICARGO again â€“ same as C++ double-write). * Else (non-SA): * Add OutboundMessage(qMng, newbuff) (MNG only). 11.1.3 DIV/ASM (fallback) * Else (T1 is DIV or ASM without TIM rule): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG). 12. Rule 4 (other message types) * Else (T1 is not MVT, DIV, ASM, and not CIRQ/CICX): * Add OutboundMessage(qMng, newbuff) (MNG only). 13. Return final result * return new ParseResult(outputs, false, null); | 24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Additional parser related to Pegasys called SbrSplit has been shared by Sampi. Analysis has been started for the same. | 28/Nov/25 11:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SbrSplit parser - CPP has been converted into java based code. Repo structure has also been transformed to adopt microservice alike design. [https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git¦https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git] Parser to be tested in next sprint. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [25 empty] | Done | 2025-11-28 12:00
AM20-338 | (Airchef)Route 53 Migration & Security Creation. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Satya Varanasi | Medium | 1827698 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-10 18:58 | 2026-01-10 21:25 |  |  |  | 0 | h3. 1. *Record Migration & Cutover* * All DNS records migrated from the current provider to Route 53 without data loss. * Validation of record accuracy (A, AAAA, CNAME, MX, TXT, SRV, etc.) against the source. * Successful cutover: traffic resolves correctly via Route 53 after TTL expiry. * Rollback plan documented and tested in case of failure. h3. 2. *IAM Roles & Access Control* * IAM roles created with least privilege for Route 53 access. * Granular policies defined (e.g., read-only vs. admin). * Access logging enabled for auditing DNS changes. * Periodic review of IAM roles and policies for compliance. |  | Faisal Sayed | Sanket Kale | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 |  |  |  | ;12/Nov/25 10:24 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;10800 | ;13/Nov/25 9:44 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;7200 | ;13/Nov/25 5:03 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;14400 |  |  |  | 57600 | 25200 | 32400 | 0.56 | 57600 | 25200 | 32400 |  |  |  |  | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@732c0e00 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1tv: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-14 14:03 | [13 empty] | 10/Nov/25 7:09 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status: Blocked* Awaiting SAA approval for the updated DNS records associated with the airchef domain. Terraform provisioning is currently on hold until the DNS configuration is finalized. | 12/Nov/25 7:12 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* * Terraform-deployed Route 53 hosted zone and DNS records have been tested successfully in the *sandbox account* using IAM roles created for the test. * Access validation is complete and confirmed. * *Local DNS testing* will be tested today. * Post successful DNS validation, the sub-story will move to *Review*, and upon approval, transition to *Done*. | 13/Nov/25 4:59 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Update:* After creating the hosted zone and importing DNS records, local testing returned positive results. To validate further, the following steps were performed: h4. *Environment Setup* * *Launched 2 EC2 Instances* ({{t4g.micro}} in {{af-south-1}}): ** *Instance A:* DNS Client ** *Instance B:* DNS Forwarder ({{IP: 10.43.1.6}}) h4. *Security Group Configuration* * *SSH Access:* Port 22 * *DNS Communication:* Ports 53 (UDP/TCP) between instances * *ICMP:* Enabled for connectivity testing h4. *DNS Forwarder Configuration (Instance B)* * Installed *dnsmasq* as DNS caching/forwarding service * Configured forwarding to Route 53 nameservers: ** {{ns-1367.awsdns-42.org}} ** {{ns-74.awsdns-09.com}} ** {{ns-886.awsdns-46.net}} ** {{ns-1772.awsdns-29.co.uk}} * Enabled DNS caching (1000 entries) * Enabled query logging h4. *DNS Client Configuration (Instance A)* * Installed *bind-utils* ({{dig}}, {{nslookup}}) * Configured to query via Instance B h4. *Custom DNS Resolution Path* {noformat}Internet â†’ Instance A â†’ Instance B (dnsmasq) â†’ Route 53 â†’ Response{noformat} | 13/Nov/25 5:02 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status Transition:* Iâ€™m moving this item to the â€œ*In Review*â€ status under *Satya Sirâ€™s* bucket. Once itâ€™s approved, Iâ€™ll transition it to the â€œ*Pending PO Approval*â€ status in *Yashwantâ€™s bucket*. | 14/Nov/25 4:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Tested on sand box and working fine. | [22 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-14 16:02
AM20-339 | Network elements created for TM1 based on LLD | Done | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Sankalp Rai | High | 1609050 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 15:39 | 2026-02-05 16:32 |  |  |  | 0 | AS AWS architect, I would be create VPC, Subnet, routing and load balancer required for TM1 based on LLD *Acceptance Criteria* : VPC, Subnet created, Load balancer created in AWS. |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;17/Apr/25 11:14 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;57600 | [5 empty] | 28800 | 0 | 57600 | 2 | 28800 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@75cd043 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 3/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 3 | 75 | 1 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsmf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 2 | Sprint 3 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-04 05:45 | [13 empty] | 04/Mar/25 7:44 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms matrix has been updated according to app classification. | 17/Apr/25 11:14 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Subnet > created Route table > Created SG > Created NACL > Created there is limit to create 40 inbound and 40 outbound flows. team is currently trying to find a resolution for additional flow. All Firewall flow > Implemented and Tested Sending for PO Approval | [25 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-04-21 09:02
AM20-340 | MQ ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Blocked | 0 | Sprint 16 | 2025-10-13 | 2025-10-24 | Satya Varanasi | Medium | 1758329 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 21:02 | 2026-01-29 23:07 |  |  |  | 0 |  |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4544ef36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g02 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-17 09:19 | [13 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | [29 empty] | To Do | 2025-08-18 16:44
AM20-341 | Backup using lifecycle management by Terraform | Done | 0 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sanket Kale | Medium | 1752552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 12:54 | 2026-01-09 14:26 |  |  |  | 0 |  |  | Sanket Kale | [5 empty] | 712020:91948faf-1676-4820-bf6b-d50a7992943e | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4eaa1670 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dndf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:52 | [13 empty] | 25/Aug/25 8:52 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;As discussed with Yashwant and Sankalp this is no more require to implement. So closing it. | [26 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 08:52
AM20-342 | Review Memory dashboard and alarm of all application hosted in AWS and configure the right dashboard for memory utilization | Done | 4 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1866169 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 15:10 | 2026-01-20 18:30 | 2025-12-14 17:51 | 2025-12-12 11:19 |  | 0 | As product Manager I want to correct the current memory related dashboard for all applications in alignment with TM1 application which is already corrected by Aravind |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;03/Dec/25 7:29 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;21600 | ;07/Dec/25 1:47 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;09/Dec/25 12:42 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;25320 |  |  |  | 57600 | 0 | 57720 | 1 | 57600 | 0 | 57720 | [12 empty] | 09/Dec/25 12:52 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251209-105119.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1193693 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@14947356 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7xb: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 |  | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | [65 empty] | YES | YES | 2025-12-03 05:28 | 3_*:*_2_*:*_634374012_*¦*_10041_*:*_1_*:*_505700490_*¦*_13940_*:*_2_*:*_4451 | [12 empty] | 03/Dec/25 7:28 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Started working on 2 Account and will complete the remaining oneâ€™s by today. | 07/Dec/25 1:49 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have updated the Memory Committed Bytes for all the Windows servers for all the accounts. Need to review it with faisal. And then will move this story to PO approval. | 09/Dec/25 12:43 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Completed the activity and updated the Memory Committed Bytes Name and Threshold value for all accounts. | 09/Dec/25 12:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251209-105119.png¦width=641,alt="image-20251209-105119.png"! Evidence has been attached from one of the account for which the Memory Committed bytes has been updated. | 12/Dec/25 11:19 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-12-12 11:19
AM20-343 | Nexio AV ¦¦ Back-UP via terraform | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730133 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 19:27 | 2026-02-03 21:51 |  |  |  | 0 | As AWS expert, I would like to provision Life Cycle manager with two schedule - * Incremental back up(daily back) * Full backup (Weekly) *Acceptance Criteria* : * The Life cycle manager has two schedule (Incremental and Full backup) successfully implemented * Back up must be automated using native AWS features and tools * Point-in-time recovery for database must be enabled to allow recovery to any second within retention window * Define retention policy and enforce retention ( 7 days, 35 days, monthly snapshot for 1 year) * Automatically transition of old backups to cold storage * Use AWS backup vault lock for Write once and Read many compliance * Backup must be encrypted at rest and in transit * Restore process is well documented and well tested * After restore data integrity checks and application consistency should be validated * Use AWS backup for central management of backup policies and vaults * Automate backup selection using resource tags * Backups must meet regulatory compliance like GDPR,HIPAA * and Audit trail of backup creation, deletion and restore events must be maintained * Periodic restore testing must be conducted and logged to validate data integrity * *AWS part:* * Use AWS config rules to enforce mandatory backup configurations * Use Cloudwatch to success/failure backups * Setup alerts for backup failure or missed backups via SNS * IAM Policies for access control to restrict who can create, view, delete and restore backups * All backup and restore operations must be logged in AWS Cloudtrail for traceability |  | Aravind Raj | Sanket Kale | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4dfe6877 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bmvv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 05:09 | [13 empty] | 11/Aug/25 7:09 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;This task will be spill over because the terraform script written by the Utkarsh is not match our expectations. I need to re write the new scripts from the scratch. | 13/Aug/25 8:19 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Utkarshâ€™s code is written for creating resources in AWS backup. I have executed the script for Nexio Prod. | 18/Aug/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;deleted unwanted 37 backup AMI taken by vault. backup config is updated with frequency and retention period. | 20/Aug/25 8:11 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-20 08:11
AM20-344 | PROS ¦ Cut-Over Instance | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | Medium | 1801097 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-30 18:04 | 2026-01-30 21:15 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [30 empty] | 28/Oct/25 11:51 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251028-095148.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174003 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6de063c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0izhv: | [167 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 11:51 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PROS cutover is carried out successfully, have archived the servers in application migration service. !image-20251028-095148.png¦width=423,alt="image-20251028-095148.png"! | [26 empty] | 1773952 | AM20-170 | PROS ¦¦ Cutover | Done | 2025-10-28 11:52
AM20-345 | RDS default config changes in Dev environment | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Pankaj Pathak | Medium | 1869424 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-06 20:41 | 2026-02-06 21:22 | 2026-01-02 08:18 |  |  | 0 | h2. Summary Changes are needed for the RDS default configuration. This includes modifying the default port for MySQL and changing the default database user. h2. Context The current setup uses the default MySQL port and user. Adjustments are required for improved security and monitoring. h2. Acceptance criteria * Change the default port for MySQL RDS from 3306 to a different port. * Change the default database user from 'admin' to a different username. * Enable enhanced monitoring for the production instance. h2. Other information N/A |  | Aravind Raj | Pankaj Pathak |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb |  |  |  |  | ;11/Dec/25 3:56 PM;0bd64ee0-8d59-462f-ab15-54fcd1a1fb2b;28800 | [6 empty] | 43200 | 28800 |  |  | 43200 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2aacc09d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obsr: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-05 13:32 | [13 empty] | 05/Dec/25 3:31 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Awaiting application team to confirm feasibility post updating port number. | 11/Dec/25 12:41 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;This subtask has dependency over application team availability to transition the port change on RDS instance. | 11/Dec/25 3:26 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;RDS Database port has been updated and shared with [~accountid:712020:5d317226-2402-463f-bda5-c2cac5f43c13] . However default superuser name â€œAdminâ€ is immutable and canâ€™t be updated. It can only be changed during instance creation. | 12/Dec/25 10:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;I could see the custom RDS port changes made only to dev environment, so switching back to in progress state. Upon completing preprod and prod this US can be marked as closed. | 02/Jan/26 8:27 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;This has been discussed with Project Owner and agreed and understood that this change is only feasible on Dev environment because it require downtime and changes around firewall and other important network components. On Dev RDS we updated port details and â€œadminâ€ user canâ€™t be changed as it is immutable. | [22 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2026-01-02 08:31
AM20-346 | Nexio AV ¦¦ LLD creation | Done | 2 | Sprint 2 | 2025-03-31 | 2025-04-11 | Yashwant Thakur | High | 1619786 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 18:30 | 2026-01-20 19:35 |  |  |  | 0 | As AWS architect, I would create LLD for Nexio AV application migration *Acceptance Criteria*: * Low level design documentation including proposed architecture completed |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;13/May/25 11:21 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [9 empty] | AM20-22 |  |  | 13/May/25 11:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;TrellixAV_DesignDocument_v1.1.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1099634 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28a7c8e2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsmv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 3 | Sprint 4 | Sprint 5 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-13 09:38 | [13 empty] | 13/May/25 11:38 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Document has been prepared for Trellix AV ePO server migration to AWS ¦Backup PolicyÂ ¦To be discussed with customer and finalized¦ ¦DR Policy¦To be discussed with customer and finalized¦ [^TrellixAV_DesignDocument_v1.1.docx] First Draft of LLD is attached Moving to In Review until we can share it with customer and Finalize the Document | 18/May/25 2:41 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [25 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-05-18 14:41
AM20-347 | (Airchef)Terraform Implementation for Creation of Route 53 Hosted Zones & Records. | In Progress |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Sanket Kale | Medium | 1827709 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-02-02 18:07 | 2026-02-02 22:00 |  |  |  | 0 | *Acceptance Criteria:* * *Deploy Public Hosted Zone* Use Terraform to provision a *Route 53 public hosted zone* for the domain [*airchef.co.za*¦http://airchef.co.za]. * *Manage DNS Records via Terraform* Implement Terraform configurations to create and manage various DNS record types (A, CNAME, MX, TXT, etc.) within the hosted zone. |  | Faisal Sayed | Sanket Kale | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [20 empty] | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28df5c12 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1vn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-07 05:56 | [13 empty] | 07/Nov/25 7:56 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Code review completed from my side its working. Created and deployed the base and component modules. | 10/Nov/25 9:07 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and tested on Sandbox environment | 14/Nov/25 4:01 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code deployment done sandbox and same tested. | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | In Progress | 2025-11-20 08:59
AM20-348 | Informatica ¦¦ Alerting and Monitoring Solution | Done | 4 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1800159 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-25 20:45 | 2026-01-25 23:40 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment. Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O. * Dashboards are created to monitor key services. * SNS Alert should be generated if Informatica server is stopped. |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 09/Oct/25 9:21 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251009-071913.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1165179 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3ac6b815 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ivor: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 09:08 | [13 empty] | 06/Oct/25 11:07 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start creating the dashboard and alerting for Informatica Dev and Prod environment. | 06/Oct/25 12:13 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I enabled the CloudWatch metrics for Informatica Dev and Prod for CPU, memory, disc, network I/O. Dashboards are also created to monitor key services. --- *DONE.* Now Alerting and monitoring needs to be created with proper naming and threshold values â€“ *PENDING*. | 07/Oct/25 12:19 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Created alarms and monitoring for informatica prod and dev for CPU and Status Check failed â€“ *DONE.* | 08/Oct/25 12:38 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;All alerts including the Disk and memory utilization for Informatica Prod and Dev has been created with proper naming and threshold value. --- *DONE.* | 09/Oct/25 9:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251009-071913.png¦width=1575,height=673,alt="image-20251009-071913.png"! Have created the Informatica prod and dev alerting rules setup the threshold value for them. | 09/Oct/25 10:46 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Moving this US to in review to Aravind. If require any modification. | 13/Oct/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have reviewed has some query will discuss with diksha and close. | 15/Oct/25 11:58 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Aravind reviewed the changes and gave his approval now we can move it to PO approval. | 17/Oct/25 7:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | Done | 2025-10-17 07:17
AM20-349 | RDS Upgrade in Flysaa backend Dev environment | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1842266 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 20:56 | 2026-02-04 23:04 | 2025-11-26 08:48 | 2025-11-27 09:18 |  | 0 | h2. User story * When the RDS instance is upgraded, I want to ensure compatibility with MySQL 8.4 so that our application runs smoothly without issues. h2. Context The development RDS instance will be upgraded from MySQL version 5.7 to 8.4. This upgrade may affect the functionality and performance of the application. h2. Acceptance criteria * The RDS instance must be successfully upgraded to MySQL 8.4. * All application features should function correctly after the upgrade. * Performance benchmarks should be met post-upgrade. h2. Other information N/A |  | Pankaj Pathak | Yashwant Thakur |  |  |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7e1de089 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5lf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [65 empty] | YES | YES | 2025-11-20 06:25 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [12 empty] | 20/Nov/25 8:24 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;The upgrade from MySQL version 5.7.44 to 8.0.42 was successful. The DB instance is running smoothly. We asked the application team (Donald and Gavin) to confirm everything is functioning well on their end. We are awaiting their response to close this story. | 25/Nov/25 2:00 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Ticket moved to In review. As we have completed internal review. | 27/Nov/25 9:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Post upgrade, Business confirmed that BAU is working as expected hence approving | [27 empty] | Done | 2025-11-27 09:18
AM20-350 | PROS ¦¦ Back-UP using Terraform | Done | 4 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | High | 1660115 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-04 17:52 | 2026-02-04 21:14 |  | 2025-10-31 09:32 |  | 0 | As AWS expert, I would like to provision backup using terraform * Incremental back up(daily back) * Full backup (Weekly) *Acceptance Criteria* : * The Life cycle manager has two schedule (Incremental and Full backup) successfully implemented * Back up must be automated using native AWS features and tools * Point-in-time recovery for database must be enabled to allow recovery to any second within retention window * Define retention policy and enforce retention ( 7 days, 35 days, monthly snapshot for 1 year) * Automatically transition of old backups to cold storage * Use AWS backup vault lock for Write once and Read many compliance * Backup must be encrypted at rest and in transit * Restore process is well documented and well tested * After restore data integrity checks and application consistency should be validated * Use AWS backup for central management of backup policies and vaults * Automate backup selection using resource tags * Backups must meet regulatory compliance like GDPR,HIPAA * and Audit trail of backup creation, deletion and restore events must be maintained * Periodic restore testing must be conducted and logged to validate data integrity * *AWS part:* * Use AWS config rules to enforce mandatory backup configurations * Use Cloudwatch to success/failure backups * Setup alerts for backup failure or missed backups via SNS * IAM Policies for access control to restrict who can create, view, delete and restore backups * All backup and restore operations must be logged in AWS Cloudtrail for traceability |  | Harsh Chandra | Onkar Mirajkar | Sanket Kale | Satya Varanasi | Yashwant Thakur |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;AM20-99_attachments.zip;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175550 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133603.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175548 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133705.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175552 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175549 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133947.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175551 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@558af396 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v9 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 15 | Sprint 16 | Sprint 17 | [93 empty] | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 |  | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | [65 empty] | YES | YES | 2025-05-29 08:54 | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | [12 empty] | 29/May/25 10:53 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;To be checked with Utkarsh and Satyabrata for terraform automation | 04/Jun/25 8:10 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;h6. TM1 ¦¦ Back-UP Backups will performed via DLM | 11/Jun/25 8:36 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;This is blocked due to Arvind Story as its not migrated | 25/Sep/25 9:28 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;currently working on wrapper module | 30/Sep/25 7:59 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;As per discuss with Aravind the server is not spined up as of now. | 30/Oct/25 3:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Validated and configured fine. PROS and informatica PROD servers backups has been configured and running fine. Daily backup with 7 days retention and weekly backup with 90 days retention. [^AM20-99_attachments.zip] !image-20251030-133705.png¦width=597,alt="image-20251030-133705.png"! !image-20251030-133947.png¦width=597,alt="image-20251030-133947.png"! !image-20251030-133909.png¦width=597,alt="image-20251030-133909.png"! !image-20251030-133603.png¦width=597,alt="image-20251030-133603.png"! | 31/Oct/25 9:32 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved as Backup is implemented successfully for PROS | [20 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-31 09:32
AM20-351 | Lambda function to observe state in cloudwatch alarms configured for monitoring other lambda | Done | 2 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1812682 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 16:02 | 2026-01-18 16:45 |  | 2025-10-31 17:23 |  | 0 | As Product manager I would like to create Lambda function to observe state in cloudwatch alarms configured for monitoring other lambda function and send Â alert payload to servicenow as per the shared format to servicenow so that any failure of lamda is captured and remediation can be initiated. # Create Eventbridge to monitor the state change in alarm. # Create Lambda function to send alarm notifications to ServiceNow when threshold is breached. # Configure event bridge as the trigger for lambda function |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;31/Oct/25 11:21 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f18c499 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kag3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-27 04:51 | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 27/Oct/25 6:51 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will review the description & configuration needs and will connect with Shreyash for getting more clarity. Once I get the whole picture will move the story to In Progress. | 31/Oct/25 11:20 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Create Eventbridge to monitor the state change in alarm. - Done # Create Lambda function to send alarm notifications to ServiceNow when threshold is breached. - Done # Configure event bridge as the trigger for lambda function - Done Tested it with a test alarm event. [~accountid:712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8] | 31/Oct/25 5:23 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though no demo was provided, based on Faisal comments approving it. | [27 empty] | Done | 2025-10-31 17:23
AM20-352 | Route53 implementation using terraform - Phase 1 | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832849 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 17:26 | 2026-02-05 20:34 | 2025-11-28 10:20 | 2025-11-28 14:01 |  | 0 | As product owner I would like to implement Route53 got both airchef and [Flysaa.com¦http://Flysaa.com] |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;28/Nov/25 10:30 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 28/Nov/25 10:29 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251128-082851.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190433 | 28/Nov/25 10:29 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251128-082914.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190431 | 28/Nov/25 10:29 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251128-082937.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190432 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@709e087b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo0z: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_612662868_*¦*_10041_*:*_1_*:*_840707031_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_612662868_*¦*_10041_*:*_1_*:*_840707031_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_612662868_*¦*_10041_*:*_1_*:*_840707031_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_612662868_*¦*_10041_*:*_1_*:*_840707031_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-21 06:19 | 3_*:*_1_*:*_612662868_*¦*_10041_*:*_1_*:*_840707031_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 21/Nov/25 8:19 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code has been modified and implemented on network account. Zone file also imported. | 28/Nov/25 10:29 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Latest zone file imported, changed TTL values to 300 sec for quick propagation. Saket gave demo on the same. Hence sharing this story Yashwant Thakur. for closer. !image-20251128-082851.png¦width=612,alt="image-20251128-082851.png"! !image-20251128-082914.png¦width=597,alt="image-20251128-082914.png"! !image-20251128-082937.png¦width=597,alt="image-20251128-082937.png"! | 28/Nov/25 2:01 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-28 14:01
AM20-353 | Security Hardening Audit and Analysis for FLYSAA Backend | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Sumit Nikam | Medium | 1886488 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 14:37 | 2026-02-05 15:44 | 2026-01-08 08:41 |  |  | 0 | As an Internal Auditor, I want to review EKS control plane security configurations across all production accounts, IAM authentication and Kubernetes RBAC mappings, Audit Node & Worker Security Controls, Audit Network Security & Traffic Controls, Audit Pod & Workload Security Posture, Audit Secrets Management & Data Protection So that gaps against AWS and Kubernetes security benchmarks are identified, Acceptance Criteria * EKS cluster version documented per account * API endpoint exposure (public/private) recorded * Allowed CIDR ranges captured * Control plane logging status verified * Secrets encryption (KMS / default) documented * Evidence stored (CLI output / console screenshots) * Gaps mapped to CIS EKS benchmark controls * IAM users vs roles usage documented * aws-auth ConfigMap reviewed * Cluster-admin bindings identified * Namespace vs cluster scoped access recorded * IRSA adoption status captured * Evidence collected (RBAC YAML, IAM role list) * High-risk access clearly flagged * Node type (Managed / Self-managed / Fargate) documented * AMI patching and update mechanism recorded * Node IAM role permissions reviewed * IMDS version (v1/v2) verified * SSH access presence documented * Evidence retained (Launch Template / ASG config) * NetworkPolicy enforcement status recorded * Default deny posture verified * Ingress exposure documented (public/private) * WAF & TLS configuration reviewed * Egress paths documented * Evidence retained (manifests, ALB config) * Pod Security Standards status documented * Privileged pods identified * Containers running as root recorded * Linux capabilities usage reviewed * Secrets usage method documented * Evidence retained (pod specs, namespace labels) * Image registries used documented * Image scanning availability verified * CVE handling process reviewed * Image tagging strategy recorded * Admission control presence documented * Evidence captured (CI logs, ECR settings) * Secret storage mechanisms documented * Encryption at rest/in transit verified * Secrets rotation capability reviewed * Backup and restore process recorded * Evidence retained (KMS config, secret manifests) * Control plane & workload logs documented * Log centralization status verified * Runtime threat detection presence reviewed * Alerting and escalation paths documented * SIEM integration status captured * Evidence retained (CloudWatch, GuardDuty) * GitOps vs manual change model documented * Policy enforcement tooling identified * Change approval records reviewed * Ownership & RACI clarity assessed * CIS / ISO alignment documented * Findings categorized (High / Medium / Low) * Risk statement defined for each gap * Affected accounts listed * Evidence referenced * Recommendations documented separately * Executive summary prepared |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [11 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@26af9eed | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0px2z: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-08 06:30 | [13 empty] | 08/Jan/26 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Initial discovery has been started post discussion. Working on Kyverno issue first in-order to have necessary violations report. | [29 empty] | In Progress | 2026-01-08 08:28
AM20-354 | (Airchef)Terraform code generation for Route 53 Hosted Zone Creation & Record Migration. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Faisal Sayed | Medium | 1827706 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-24 13:35 | 2026-01-24 14:25 |  |  |  | 0 | Hosted Zone Creation Develop infrastructure-as-code to provision a Route 53 hosted zone for the specified domain. The configuration should support tagging, environment-specific naming, and be reusable across deployments. DNS Record Management Implement a declarative script to define and manage DNS records within the hosted zone. This should include support for common record types (A, CNAME, MX, TXT) with configurable TTLs and values. |  | Faisal Sayed | Sanket Kale |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e |  |  |  |  | ;12/Nov/25 10:17 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 |  |  |  |  | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@53b50383 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1v7: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:56 | [13 empty] | 07/Nov/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status: Blocked* Awaiting SAA approval for the updated DNS records associated with the {{airchef}} domain. Terraform provisioning is currently on hold until the DNS configuration is finalized. | 12/Nov/25 6:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status Update:* * Task moved from *Blocked* to *In Progress*. * Terraform code for Route 53 provisioning has been developed and handed over to *Sanket*. * *Next Action:* Sanket to review and execute the code in the *sandbox account* for validation. | 12/Nov/25 6:55 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform code has been successfully reviewed and tested in the sandbox environment, and all validations are positive. Â | 12/Nov/25 10:16 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Code has been reviewed, tested successfully, and validated. Moving the sub-story to *Done*. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-12 10:12
AM20-355 | AirNavX ¦¦ Validation for SG and NACL | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Satya Varanasi | Medium | 1786688 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 16:37 | 2026-01-23 18:09 |  |  |  | 0 | As Product owner I would like to validate SG and NACL in AirnavX account so that to ensure that is correctly configured as required and netwrok access is restricted to least privilege, compliant with security standards and traceable to the right owners *Acceptance Criteria*: Ingress Rule: * Validate only required ports are open * Check if the rules are restricted to known source IPs or SGs * Avoid overly permissive rules like ALL Traffic/ All Ports Egress Rule: * Confirm outbound rules are limited to required destinations/services * Avoid all traffic / 0.0.0.0/0 * Remove duplicate or unused rules * Check if multiple rules overlap unnecessarily * Validate SGs have proper tags (name, environment, owner) for traceability * Confirm unused SGs are not attached to ENIs NACL: * Check both inbound and outbound rules match expected traffic flow * validate rule numbers and ensure no conflicts/overlaps * Ensure the implicit DENY is preserved and only necessary allow rules are added * Avoid overly permissive entries * Since NACL are stateless, confirm return traffic rules exist for each allowed inbound connection * Validate that the correct subnets are associated with the right NACL * Avoid leaving critical subnets with the default NACL explicitly required * Confirm VPC flow logs are enabled for subnets tied to NACLs to validate actual traffic patterns against intended rules |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@f3dd427 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hatf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-25 15:29 | [13 empty] | 25/Sep/25 5:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Airnavx Comms has been implemented and the need to configure respective account and initiate testing. Currently team working on server deployment process, once done we will configure rules and will initiate testing. | 06/Oct/25 8:41 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Comms has been implemented, NACL and SG is setup. App owner is able to access and install the application. Hence closing the story | [28 empty] | Done | 2025-10-06 08:41
AM20-356 | Rehosting & Replatforming of applications from on-Prem to AWS | To Do |  | None( Epic) |  |  |  | High | 1620350 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 19:20 | 2026-01-23 19:35 |  |  |  | 0 | Application migration (re-hosting or re-platforming of on-prem applications to AWS cloud. The activities includes, deployment of DMS tool in SAA servers, migration related activities, configuration, 3rd party application connectivity's, setting up of issue resolution, backup and restore validations, DR, DNS change, UAT, Delta migration, issue fixes and final handover activities | [23 empty] | 273600 | 100800 | 144000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3525bd44 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-3 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | yellow | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxn1b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-03-04 11:35
AM20-357 | MQ ¦¦ POC customer Demo | Blocked | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Sumit Nikam | High | 1672939 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-27 19:50 | 2026-01-27 20:56 | 2026-01-08 08:41 |  |  | 0 | As AWS architect, I would align with SAA stakeholders to give a demo on MQ PoC. *Acceptance Criteria*: * Demo given and next steps discussed with SAA. |  | Harsh Chandra | Sankalp Rai | Sumit Nikam |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67032dc2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pttb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 15 | Sprint 16 | Sprint 22 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 08:24 | [13 empty] | 20/May/25 10:23 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 26th May 2025 End Date: 30th May 2025 | 02/Jun/25 8:26 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;MQ has two option on AWS # Migrate existing MQ Servers to AWS # Use AWS Native MQ service We need a confirmation on approach from Sampi after which we will start working on LLD Document Moving to Blocked | 24/Sep/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Will be taken up once POC is completed in Sandbox | 17/Oct/25 11:21 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 30/Oct/25 9:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;LLD no longer needed To be considered for Modernization as per feedback from Gayaz. Next steps: # Analyze Amadeus response Perform PoC as per Amadeus requirements # Agreement with SAA based on PoC # SoW sigoff # Design Document # AmazonMQ Implementation # Queue by Queue migration | 08/Jan/26 8:48 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Awaiting for a go-ahead to setup a demo call with SAA. | [21 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | To Do | 2026-01-08 08:41
AM20-358 | ServiceNow ¦¦ Lamda function as SNS Subscriber | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651014 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 15:27 | 2026-01-20 16:48 |  |  |  | 0 | As a Cloud engineer, I want a Lamda function subscribed to the SNS topic so that it can process alerts and forward them to ServiceNow Acceptance Criteria: * The Lamda function is triggered on new SNS messages * It parses event data and sends an HTTP POST request to ServiceNow |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 | ;25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@353710af | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0284j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 03:49 | [13 empty] | 24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Working with the lambda function python script, since the function needs to works with cross account for getting the tags. initially the lambda function developed to get the tags from the same account, whereas here the requirement is to get the tag to Audit account to trigger a SNS. | 25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function is created in Audit account -300204747992, and its working fine as expected. | 02/May/25 4:57 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-25 06:34
AM20-359 | Tagging Compliance implementation | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834929 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 15:12 | 2026-01-31 19:02 | 2025-11-27 08:26 | 2025-11-28 11:38 |  | 0 | As product owner I would like to setup tagging compliance in centralized Cloudwatch dashboard so that I know how many workloads are not been tagged and take corrective actions accordingly |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;20/Nov/25 8:27 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;21/Nov/25 7:56 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;25/Nov/25 10:41 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;26/Nov/25 3:33 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;27/Nov/25 4:17 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;7200 |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 27/Nov/25 4:17 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251127-141419.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190266 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fa2be84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mwv7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:50 | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:50 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Satya sir is checking with leigh regarding the tag policy enable part after updating the tag policy will start working on the Tag compliance part. | 19/Nov/25 1:33 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have Enabled the Tag Compliance policy for all account. Waiting for security score. | 21/Nov/25 7:55 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Security score is visible for all accounts now next step is we are disabling the ID on with we donâ€™t require this tag compliance policy for all accounts. | 23/Nov/25 2:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have disabled the Tag Compliance policy for all the non required resource IDâ€™s for all 17 mandatory accounts. 746669190453â€ƒâ€ƒFlySAA_CMS_Backend_DevQA 216989128782Â Â Â Â Â Â Â FlySAA_CMS_Backend_PreProd 396608788916â€ƒâ€ƒFlySAA_CMS_Backend_Prod 209479274829â€ƒâ€ƒSAA TM1 345594574792â€ƒâ€ƒSAA AirnavxÂ 536697265099â€ƒâ€ƒSAA_NEXIOAV_PROD 650251698621â€ƒâ€ƒSAA_PROS_PROD 307946680641â€ƒâ€ƒSAA_Informatica_DEV 536697248966â€ƒâ€ƒSAA_Informatica_PROD 195973603339â€ƒâ€ƒvod001_001_payer9 300204747992â€ƒâ€ƒSAA-AuditÂ 730335236533â€ƒâ€ƒAWS_SAA_Security 080284287007â€ƒâ€ƒSAA-LogArchive 339712943527â€ƒâ€ƒAWS_SAA_Network 585768167545Â Â Â Â Â Â Â SharedVPCDevQA() 253490777663Â Â Â Â Â Â Â SharedVPCPreProd() 820242899278Â Â Â Â Â Â Â SharedVPCProd() | 25/Nov/25 10:40 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;For the Untagged one IDâ€™s we are remediating the failed ones as much as we can for all 17 accounts before getting the centralized dashboard enabled for Tag compliance. | 26/Nov/25 9:04 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Tag compliance security score is 95% for all 17 Accounts and to make it 100% we need to Tag IAM Roles for all Accounts and Each account contains more than 60 IAM Roles which is not possible for a Single person to tag them. I need team support to tag those IAM roles as its a manual work no automation will help as they are the existing resources not the new ones. | 26/Nov/25 3:32 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*UPDATE :* With the Help of lambda function we were able to tag all the IAM roles for all 17 accounts. Except the oneâ€™s which are not handled by our team and we are not authorized to tag them. | 27/Nov/25 4:17 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251127-141419.png¦width=629,alt="image-20251127-141419.png"! Tags has been implemented for all resources and in the security account under Security Hub we can see all the tagged resources and the information. | 28/Nov/25 11:38 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. Saw the data presented in review call. satisfied with results | [21 empty] | Done | 2025-11-28 11:38
AM20-360 | Documentation on IAM and RBAC | Done | 5 | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | High | 1731884 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 13:56 | 2026-01-28 16:33 |  |  |  | 0 | As product owner, I like to document all the IAM - RBAC created to control the access of workloads and process to provision IAM, Terraform code location. Acceptance Criteria: Document completed having IAM roles name, purpose, Terraform code location( if applicable), Process to add respective resources |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;25/Aug/25 7:57 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;72000 | [5 empty] | 72000 | 43200 | 72000 | 1 | 72000 | 43200 | 72000 | [12 empty] | 05/Sep/25 9:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SAA_IAM Configuration_v1.1.doc;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148372 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2bce2e91 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0brrf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-30 14:24 | [13 empty] | 30/Jul/25 4:24 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created Sub story and assigned to respective members. | 11/Aug/25 7:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;due to VOIS user account modification IAM roles and policy is still a ongoing process, and other sub story need to be done | 11/Aug/25 7:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Hence this story would be spill over. | 14/Aug/25 8:44 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Waiting for sanket update on substory Will accumulate EKS roles with the help of ravinder excel sheet. | 25/Aug/25 7:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Received sanket data today will include that to the IAM document and close this by today. | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 07:55
AM20-361 | Informatica Server ¦¦ Subnet creation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660595 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-02 21:16 | 2026-02-03 00:39 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Nexio AV application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Nexio AV and the configured based on the approved comms matrix |  | Aravind Raj | Harsh Chandra | Satya Varanasi | Shreyash Talwekar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 27/Jun/25 3:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-135131.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119370 | 27/Jun/25 3:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-135223.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119371 | 27/Jun/25 5:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155229.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119409 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@435a4769 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-16 08:08 | [13 empty] | 16/May/25 10:07 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Waiting for terraform code towards build this. | 20/May/25 5:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Deepak and team, this need to be addressed with terraform code the same has been prepared by Utkarsh, until core not ready this story may not possible to address. | 10/Jun/25 2:03 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still â€œShreyashâ€ checking Utkarsh script, this story depending with script testing and execution. | 16/Jun/25 9:06 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Terraform script is under modification by â€œShreyashâ€, as per his update it will be ready this week. Hence this is the reason for spill over Sprint7 to Sprint8. | 16/Jun/25 9:15 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Currently working on updating terraform script based on latest naming convention requirement. | 18/Jun/25 11:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The script is managing by â€œShreyashâ€ so i am assigning this task to him, once his work completes he will reassign to me. | 23/Jun/25 1:58 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We were able to create AWS resources (mentioned in previous mail ) using terraform scripts on sharedvpc-dev account. To address some requirements like adding naming conventions and state file management, we will have to add some changes in terraform scripts. Due to current sprint activities I might not be able to work on the changes in this sprint. | 27/Jun/25 3:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Prod Subnet/Route table has been created, & tested internet access and same working fine. !image-20250627-135131.png¦width=1261,height=434,alt="image-20250627-135131.png"! !image-20250627-135223.png¦width=1112,height=588,alt="image-20250627-135223.png"! sh-5.2$ ping [http://google.com¦http://google.com¦smart-link] PING [http://google.com¦http://google.com¦smart-link] (142.251.47.238) 56(84) bytes of data. 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=1 ttl=108 time=20.5 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=2 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=3 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=4 ttl=108 time=19.7 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=5 ttl=108 time=19.8 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=6 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=7 ttl=108 time=19.7 ms ^C --- [http://google.com¦http://google.com¦smart-link] ping statistics --- 7 packets transmitted, 7 received, 0% packet loss, time 6010ms rtt min/avg/max/mdev = 19.630/19.800/20.473/0.282 ms sh-5.2$ hostname [ip-10-40-0-213.awsflysaa.com¦http://ip-10-40-0-213.awsflysaa.com] sh-5.2$ ifconfig ens5: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 9001 inet 10.40.0.213 netmask 255.255.255.240 broadcast 10.40.0.223 inet6 fe80::4a7:ebff:fe03:c075 prefixlen 64 scopeid 0x20<link> ether 06:a7:eb:03:c0:75 txqueuelen 1000 (Ethernet) RX packets 1653 bytes 293385 (286.5 KiB) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 1809 bytes 265312 (259.0 KiB) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0 lo: flags=73<UP,LOOPBACK,RUNNING> mtu 65536 inet 127.0.0.1 netmask 255.0.0.0 inet6 ::1 prefixlen 128 scopeid 0x10<host> loop txqueuelen 1000 (Local Loopback) RX packets 12 bytes 1020 (1020.0 B) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 12 bytes 1020 (1020.0 B) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0. | 27/Jun/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev Subnet and route table has been created. !image-20250627-155229.png¦width=1259,height=431,alt="image-20250627-155229.png"! | 27/Jun/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet creation and sharing is done, have reviewed. | 29/Jun/25 8:13 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:13
AM20-362 | Terraform Development ¦¦ Creation of Outbound and inbound rules in NACL | Done | 8 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1651313 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 13:04 | 2026-01-11 14:00 | 2025-11-27 08:27 | 2025-11-28 12:00 |  | 0 | As Terraform expert, I want to be creating a network ACL with inbound and outbound rules using terraform code, so that I can apply stateless packet filtering at the subnet level Acceptance Criteria: * Define variable for CIDRs, ports and subnets * NACL resources is created and associated with target subnets * Application relevant flows needs to be populated * Application inbound rule and comms metric needs to populated for NACL * Outbound rules allow return traffic on the same ports. * Each rule has a unique number and direction * Rules are parameterized for environment flexibility * add rule description and tags. * Provision to add or deny additional rules with max of 20 rules to be allowed for NACL |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@442b4964 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mrnr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 19 | [96 empty] | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-20 07:06 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 20/Nov/25 9:06 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Working on base module code of terraform script. It will be completed by this Friday EOD. | 27/Nov/25 8:24 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform script completed and NACL resource created in sandbox environment. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-11-28 12:00
AM20-363 | Airnavx ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620850 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 14:31 | 2026-01-13 14:39 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [8 empty] | AM20-10 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4559db6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 8 | Sprint 9 | Sprint 12 | Sprint 13 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-25 06:58 | [13 empty] | 25/Jun/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Harsh and Deepak update, this need to address after TM1 and informatica servers network action, hence i am keeping this as blocked(As per Harsh update) | 28/Jul/25 8:51 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Currently app under LLD review once review done i will initiate comms for the same. SO this will be moved to next sprint. | 04/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on it according to recent LLD call review. | 07/Aug/25 8:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared, with latest subnet details, i will initiate mail communication with customer/app owner for flows review or in case any additional flows needed they should notify further process. | 12/Aug/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Shared comms to app owner for review and add in case needed any additional flows for the same. | 25/Aug/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms under validation by app owner, so this is right story for spill over to this sprint. | 26/Aug/25 1:04 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Initially after follow-up customer prepared and send comms. # During review i identified as comms as not prepared right way and reshared the same comms to customer for validation. # After continuous 3 days follow-up we have received comms from customer as on date 25th Aug 10:00 PM. # There is no sufficient time to manage this story in this sprint due delay with customer. # Note: It has been communicated customer and management regularly but he took longer time to manage. | 29/Aug/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Reviewed and prepared AirNavX comms for VDC/SITA sheets and same sent app owner for LIFT/CSOC request towards implementation. | 03/Sep/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been reviewed and submitted to app owner for further process. | 03/Sep/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Albert has been submitted requested LIFT and CSOC request for ports androuting implementation. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 03/Sep/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The below is the current status: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Routing already in place hance not required any action on this and making this as completed.) | 08/Sep/25 6:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [15 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:36
AM20-364 | ServiceNow Monitoring ¦¦ Prod Implementation | Done | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1673102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-27 19:56 | 2026-01-27 20:59 |  |  |  | 0 | As AWS solution architect, I would like to implement ServiceNow monitoring in prod environment so that alerts can be generated and reach to ServiceNow in form of Tickets for further actions. Acceptance Criteria: * Setup of ServiceNow integration to pull AWS receive data using EventBridge * Unautherized API calls from GuardDuty and Security Hub * Setup Cloudwatch alarms or rules for all the resources entitled to be monitored and send these to SNS topic * Create SNS topic * Configure SNS HTTPS configuration so that SNS can directly invoke HTTPS endpoints * AWS Lambda function created to forward SNS messages by parsing it and sends REST API requests to ServiceNow. * Attach the Lamda to the SNS topic * Set the credentials in AWS Secret Manager * Lamda function can reach the ServiceNow endpoint through API gateway by using HTTPS and Secure authentication |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;04/Jul/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cfb2e84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04h5f: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-26 06:17 | [13 empty] | 26/May/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 8:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting to get a exact tags to be passed to Ec2 instance to receive at service now. *New HTTPS endpoint will be shared by feroz for the production workloads.* | 25/Jun/25 8:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;From 24th June we had a call with feroz, where we expected to get the production servicenow endpoint by nest week to configure in SNS, hence waiting for same to start this user story. | 02/Jul/25 7:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PRODUCTION ServiceNow Instance: [https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws¦https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws] SNS topic is updated with a new subscription and backend prod integration is completed, unit test yet to start. | 04/Jul/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Right now the production environments like Backend, TM1, AirnavX accounts are integrated with the prod service now endpoint and SNS is configured to get the alerts. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-04 08:15
AM20-365 | TM1 ¦¦ Cutover | Done | 4 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | High | 1651369 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 15:18 | 2026-01-15 16:34 |  |  |  | 0 | As AWS expert I would be performing the cutover for TM1 application. Acceptance Criteria: * Replication from on-prem is successfully stopped using API calls * Back up of TM1 VDC Server * Monitoring disable - VDC Server * Shutting down TM1 application in VDC * Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [TM1-application.awsflysaa.com¦http://TM1-application.awsflysaa.com] Server to the AD * MAT Testing completed successfully by SAA |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Aug/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 14/Aug/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250814-063655.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139643 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3da06808 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4i:x | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-04 06:12 | [13 empty] | 04/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for agent installation to complete | 13/Jun/25 5:58 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked with TM1 Agent Installation - [https://vodacom.atlassian.net/browse/FCBEM-593¦https://vodacom.atlassian.net/browse/FCBEM-593¦smart-link] | 27/Jul/25 10:00 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Performance testing is in progress. | 13/Aug/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have initiated a cutover and instance is up with the data and application. Testing is done awaiting for an formal approval on confirmation to finalize the cutover. have added server to the [awsflysaa.com¦http://awsflysaa.com] domain, installed cloud watch agent inside the server successfully. | 14/Aug/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cutover completed marking finalize cutover !image-20250814-063655.png¦width=1271,height=479,alt="image-20250814-063655.png"! | 20/Aug/25 8:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-08-20 08:10
AM20-366 | Alignment of AWS account in Control tower | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | Highest | 1660079 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-29 16:05 | 2026-01-29 18:37 |  |  |  | 0 | As AWS expert, I would like to perform clean-up the account in control tower that is not needed and perform changes in control tower w.r.t changes in optimization of workload utilization *Acceptance Criteria*: * Clean-up account in control tower is successfully completed * Identified workload utilization are optimized successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;19/May/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@44b8caa8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i039nf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-14 06:28 | [13 empty] | 14/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will connect with takura today and initiate a modification to the hierarchy of AWS accounts under AWS organizations. | 19/May/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CMS Front Dev/QA > FLYSAA OU (Workload OU) Backend > FLYSAA OU (Workload OU) 730335236533 AWS_SAA_Security (Check for services) >>Infra OU 339712943527 AWS_SAA_Network (Check for Services) >> > Infra OU Â | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-19 08:09
AM20-367 | POC -AWS Patch Manager ¦¦ Create a patch baseline for installing Windows/RHEL Service Packs | Done | 8 | Sprint 3 | 2025-04-14 | 2025-04-25 | Faisal Sayed | High | 1642024 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 13:23 | 2026-01-17 15:00 |  |  |  | 0 | As AWS architect I would be creating patch baselines for windows Server. Acceptance Criteria: Patch Manager has been created successfully |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Onkar Mirajkar | Sankalp Rai | Yashwant Thakur | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [6 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 23/May/25 8:09 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;Re_ Centralized Multi-Account Patching with AWS System Manger Patch Manger.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1104373 | 09/May/25 12:00 PM;9e4636e8-9dfc-4a33-901b-fcd75015926a;System Patch Manger.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1098376 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@b983d7e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/1 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 1 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00svf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | [108 empty] | 1 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-05 06:16 | [13 empty] | 05/May/25 8:15 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Able to install patches on multi-account ec2 instance using Systems Manager Automation. | 05/May/25 8:16 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working on patch policy | 08/May/25 8:12 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working with Lambda and amazon bridge event to automate the patching process for patch policy to run specific dates | 08/May/25 3:29 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Created lambda function and event bridge to automate patch multi-account setup | 09/May/25 8:01 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Need to update document | 09/May/25 12:02 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Document attached in the Jira sent for review to Arvind | 12/May/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Document is reviewed, automation with lambda is captured. | 18/May/25 2:37 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Since the desired solution objective could not be achieved, rejecting this ticket to in progress. As agreed, onkar needs to rework based on agreement. Solution provided by Aravind needs to be developed as POC. as communicated and mentioned by Yashwant. Rejecting on behalf of Yashwant as he has login issues in Jira | 20/May/25 1:24 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Spoke to Venkat on the issue we are facing with centralized patch management and the limitation to use it in multi-account setup in AWS. Quick Setup as work around for Multi-Account Setup, however this service is not available in CapeTown (SA) region. Venkat has agreed to raise this with AWS. As next Step: # compose email stating the solution we are trying to achieve for patching, the limitations we have come across and all the solution we have and what limitations these solutions have. # Venkat will forward this AWS and work on setting up a call to discuss this issue. # Align with AWS on best possible solution/workaround to achieve the desired state | 21/May/25 10:34 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Email has been sent to Venkat, stating what we are trying to achieve, Limitations identified and workarounds tried.Â | 09/Jun/25 8:22 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;As per call, We have tried to download the packages from server which is having Internet connectivity and tried to update on Private Ec2 instances which is working successfully | 13/Jun/25 12:55 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Centralized EC2 Patch Management (Cross-Account)*{{ â€” AchievedÂ }} Â {{Â }}*Key Outcomes*{{:Â }} # Â *Central Patch Repository in Shared Services Account*{{Â }} * Â {{Created `saa-central-patch-bucket` in }}*af-south-1*{{, configured securely.Â }} * {{Uploaded Linux `.rpm` and Windows `.msu` patches to S3 manually & via scripts.Â }} Â # *SSM-Compatible EC2 Instances in Target Accounts*{{Â }} Â {{Launched both Linux & Windows instances without public IPs.Â }} {{Attached custom IAM roles that:Â }} * Â {{Allow full SSM and `s3:GetObject` access to central bucket.Â }} * {{Assume trust with `ec2.amazonaws.com`.Â }} Â # *Patch Acquisition*{{Â }} * Â {{Downloaded Linux patches using SSM Run Command (manual S3 sync).Â }} * {{Downloaded Windows patches (KB5058392) using RDP, installed AWS CLI manually, then uploaded to S3.Â }} Â # *AWS CLI Installed on Windows EC2 (No Internet)*{{Â }} * Â {{Used temporary public IP â†’ installed AWS CLI â†’ removed IP.Â }} Â # *Tested SSM Agent Connectivity*{{Â }} Â {{Verified instances registered to SSM without public IP using:Â }} * Â {{ VPC endpoints (`ssm`, `ssmmessages`, `ec2messages`, `s3`)Â }} * {{ IAM and SGs allowing HTTPS (`tcp/443`)Â }} Â # *Enabled Patch Deployment via SSM Run Command*{{Â }} Â {{Used SSM to:Â }} * Â {{Copy patches from EC2 to central S3Â }} * {{Test patch install commands (`wusa` for `.msu`, `yum` for `.rpm`)}} | 13/Jun/25 2:35 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [14 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:35
AM20-368 | (Airchef)Terraform Implementation for Creation of Route 53 Hosted Zones & Records. | In Progress |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Sanket Kale | Medium | 1827709 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-15 20:21 | 2026-01-15 21:28 |  |  |  | 0 | *Acceptance Criteria:* * *Deploy Public Hosted Zone* Use Terraform to provision a *Route 53 public hosted zone* for the domain [*airchef.co.za*¦http://airchef.co.za]. * *Manage DNS Records via Terraform* Implement Terraform configurations to create and manage various DNS record types (A, CNAME, MX, TXT, etc.) within the hosted zone. |  | Faisal Sayed | Sanket Kale | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [20 empty] | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28df5c12 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1vn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-07 05:56 | [13 empty] | 07/Nov/25 7:56 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Code review completed from my side its working. Created and deployed the base and component modules. | 10/Nov/25 9:07 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and tested on Sandbox environment | 14/Nov/25 4:01 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code deployment done sandbox and same tested. | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | In Progress | 2025-11-20 08:59
AM20-369 | ServiceNow ¦¦ Logging and Monitoring | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651021 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 20:01 | 2026-01-26 20:59 |  |  |  | 0 | As an AWS expert, I want to monitor the health and logs of the Lamda connector function so that I can troubleshoot issues when alerts arenâ€™t processed properly Acceptance Criteria: * CloudWatch logs are enabled for Lambda * Metrics and dashboards are available for monitoring invocations, failures and response times. |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/May/25 9:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103910 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60acf139 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0285v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | [108 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 05:45 | [13 empty] | 02/May/25 7:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function to invoke the cloud watch is created and working as expected, Cloud watch dashboard for metrics will be created only after the workloads moved to cloud. service now monitoring can be in place only after successful integration with connector and service now PAAS endpoint. | 16/May/25 9:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have given demo with the email endpoints, waiting for the https endpoint to be received from SAA team to work with full functionality, | 22/May/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have received a endpoint today, yet to update SNS topic endpoint. https://sonicboom_em_saa_7161:wusEwo>G*Xmw@?XOA74\!pm0cx2.[4N;oFz<\!7vSE@liftdev.service-now.com/api/sn_em_connector/em/inbound_event?source=aws&sys_id=870cc1dfc3a5a6d04022f9777a013157 | 22/May/25 9:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 26/May/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 26/May/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;With respect to the endpoint have sent a mail to ashton, but there was response yet. awaiting on same. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. Â· | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 7:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Service now integration is completed with a new subscription HTTPS endpoint, have created a Cloud watch alarm for testing purpose which triggers a SNS as result service now dashboard receives a alert. | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-20 08:17
AM20-370 | Airnavx ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620850 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 18:26 | 2026-01-12 20:27 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [8 empty] | AM20-10 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4559db6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 8 | Sprint 9 | Sprint 12 | Sprint 13 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-25 06:58 | [13 empty] | 25/Jun/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Harsh and Deepak update, this need to address after TM1 and informatica servers network action, hence i am keeping this as blocked(As per Harsh update) | 28/Jul/25 8:51 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Currently app under LLD review once review done i will initiate comms for the same. SO this will be moved to next sprint. | 04/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on it according to recent LLD call review. | 07/Aug/25 8:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared, with latest subnet details, i will initiate mail communication with customer/app owner for flows review or in case any additional flows needed they should notify further process. | 12/Aug/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Shared comms to app owner for review and add in case needed any additional flows for the same. | 25/Aug/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms under validation by app owner, so this is right story for spill over to this sprint. | 26/Aug/25 1:04 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Initially after follow-up customer prepared and send comms. # During review i identified as comms as not prepared right way and reshared the same comms to customer for validation. # After continuous 3 days follow-up we have received comms from customer as on date 25th Aug 10:00 PM. # There is no sufficient time to manage this story in this sprint due delay with customer. # Note: It has been communicated customer and management regularly but he took longer time to manage. | 29/Aug/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Reviewed and prepared AirNavX comms for VDC/SITA sheets and same sent app owner for LIFT/CSOC request towards implementation. | 03/Sep/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been reviewed and submitted to app owner for further process. | 03/Sep/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Albert has been submitted requested LIFT and CSOC request for ports androuting implementation. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 03/Sep/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The below is the current status: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Routing already in place hance not required any action on this and making this as completed.) | 08/Sep/25 6:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [15 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:36
AM20-371 | Informatica Server ¦¦ CloudTrail and Guard Rail implementation | Done | 2 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | Medium | 1681743 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 12:26 | 2026-02-02 14:20 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across informatica server (PROS) account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1eb85c02 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05trf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-05 06:17 | [13 empty] | 05/Jun/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Config and guard Duty is enabled and configured. Cloud Trails logging is enabled already. | 06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard rail implementation is applied for the S3 block public access | 13/Jun/25 2:36 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:36
AM20-372 | Terraform code for route 53 implementation | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Satya Varanasi | Medium | 1835009 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-05 18:52 | 2026-02-05 20:10 | 2025-11-27 08:28 |  |  | 0 | [airchefs.co.za¦http://airchefs.co.za] hosted zone need to setup via Terraform. |  | Harsh Chandra | Sanket Kale | Satya Varanasi |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ca1ef33 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mx8b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-25 06:19 | [13 empty] | 25/Nov/25 8:19 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Hosted zone setup is completed on Network account and also validated with internal team. Updated the status as in review and reassign it to Satyasairam. | 27/Nov/25 10:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration done currently all pointing to [airchefs.co.za¦http://airchefs.co.za] is pointing to AWS. | [25 empty] | 1832849 | AM20-262 | Route53 implementation using terraform - Phase 1 | Done | 2025-11-27 10:24
AM20-373 | Devops-Codepipeline,Codebuild,lambda,cloudwatch events and etc - IAM role | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Sanjot Fotedar | Medium | 1741150 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-22 18:13 | 2026-01-22 20:04 |  |  |  | 0 |  |  | Aravind Raj | Sanjot Fotedar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4e808ee9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckgn: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-08 06:22 | [13 empty] | 08/Aug/25 8:22 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Currently we have iam role only in dev account. The IAM role â€œarn:aws:iam::746669190453:role/flysaa-dev-backendbuildproject-roleâ€ has been refined in dev account to enforce least privilege access. Only the necessary permissions required for CodeBuild operations and associated resources have been retained. And this arn has been shared with aravind to review. | 12/Aug/25 9:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Provide me the role details in backend preprod and prod also along with the custom and AWS managed policy you have used. | 12/Aug/25 9:56 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Confirmed with sanjot there is no role created other by Dev team other than mentioned below. | [24 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-12 09:56
AM20-374 | EKS public sharing | To Do |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Sumit Nikam | Medium | 1869422 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-26 15:35 | 2026-01-26 19:25 | 2026-01-08 08:37 |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3ef27d1f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obsj: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [41 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | To Do | 2025-11-28 11:12
AM20-375 | Tag Validations for AirNavX | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820186 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 20:50 | 2026-02-03 21:51 |  | 2025-11-14 10:58 |  | 0 | As a Cloud governance engineer I want to validate that all resources and workloads related to newly migrated applications have the correct mandatory tags applied so that we can ensure accurate cost allocation, compliance reporting and automation alignment across all AirNavX account Acceptance Criteria: * Tags for all applicable application resource type ( EC2, EBS, RDS, S3 lamda, ALB/NLB, Cloudwatch log groups) are successfully captured. * If there are any tags not available then manually updated successfully * Validations runs across all migrated resources and as per agreed format |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:33 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;246000 | [5 empty] | 28800 | 0 | 246000 | 8.54 | 28800 | 0 | 246000 | [12 empty] | 13/Nov/25 9:26 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-072628.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182486 | 13/Nov/25 12:08 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-100724.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182794 | 13/Nov/25 12:08 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-100827.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182795 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ffcb69e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l62j: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-06 06:25 | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 06/Nov/25 8:25 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will Start checking all the tags are in place for AirnavX environment and will update them. | 06/Nov/25 9:35 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;AirnavX code build & code piplines & s3 proper taggings are missing. | 12/Nov/25 2:23 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Followed up with satyabrata he is occupied with some tasks and will connect with me tomorrow for this US. | 13/Nov/25 9:26 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251113-072628.png¦width=631,alt="image-20251113-072628.png"! S3 tagging has been updated by AWS CLI command. Now checking for code build and pipline. | 13/Nov/25 12:08 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251113-100724.png¦width=714,alt="image-20251113-100724.png"! Evidence for code pipline and code build updated tags. !image-20251113-100827.png¦width=695,alt="image-20251113-100827.png"! | 14/Nov/25 10:58 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-14 10:58
AM20-376 | Route53 ¦¦ Alert Configuration | In Progress | 6 | Sprint 22 | 2026-01-05 | 2026-01-16 | Satya Varanasi | Medium | 1881343 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 15:36 | 2026-01-17 19:18 | 2026-01-08 08:39 |  |  | 0 | As a cloud infra platform team I want to implement automated alerting for Route53 DNS health, record changes and DNS health, record changes and DNS failover so that application teams and support teams can proactively detect outages, unauthorized changes and DNS failures across all AWS accounts. Acceptance Criteria: # Route 53 Health Check Alerts * Health checks must be created for all critical endpoints (HTTP, 1. HTTPS, TCP, or CloudWatch metric-based). * Â A CloudWatch alarm must automatically trigger if the health check status = Unhealthy. * Â Alarm must send a notification to an SNS topic configured for the environment (Dev/Pre-Prod/Prod). * Â Health check status must be visible on the central monitoring dashboard. # DNS Failover Alarms * Â Failover configurations (Primary/Secondary records) must be validated after deployment. * Â A CloudWatch alarm must trigger when Route 53 performs an automated failover action. Â Notification must include: * Â hosted zone name * Â record name * Â failover type (PRIMARY â†’ SECONDARY) * Â timestamp Â Application team must receive ServiceNow notification immediately. Â All failover events must be recorded in audit logs (CloudTrail). # Hosted Zone Change & Record Modification Alerts Â CloudTrail must be enabled for all Route 53 API events: * Â CreateHostedZone * Â ChangeResourceRecordSets * Â DeleteHostedZone 4.Â An EventBridge rule must detect record or zone changes and send alerts to SNS. Alert must contain: * user/role who made the change * old value vs new value * timestamp * AWS account ID # Unauthorized changes must automatically raise a ticket in ServiceNow/JIRA (if integrated). * All record changes must be stored for audit (S3/CloudTrail). * DNS Query Volume / Anomaly Alerts * Â CloudWatch metric "DNS Queries" must be monitored for abnormal spikes or drops. * Â CloudWatch Anomaly Detection must be configured with proper thresholds. * Â Alerts must trigger when query volume deviates beyond normal traffic window. * Â Notification must reach platform + application teams. * Â Alerts must indicate possible DDoS, misconfiguration, or routing issue.Â * DNS Latency or Resolver Issue Alerts * Â Route 53 Resolver metric "ResolverQueryError" or "DNS Resolution Failure" must be monitored. * Â Alerts must trigger when error rate exceeds threshold (ex: >5% errors for 5 mins). * Â Alerts must include resolver IP, VPC ID, region. * Â Incident must be auto-created in monitoring tool.Â # Alert Routing & Escalation * Â Alerts from all child accounts must centralize into a single parent-account SNS topic using cross-account permissions. * Â Separate channels must exist for PROD vs NON-PROD. * Â Severity mapping must follow organizational incident guidelines (SEV-1, SEV-2, SEV-3) # Â A centralized CloudWatch dashboard must show: * Â health check status * Â failover events * Â DNS query traffic * Â record change logs * Â Dashboard must be accessible from parent account to all authorized users. * Â Dashboard updated in near real-time (<1 min delay).Â # Security & Governance * Â IAM policies must restrict record modification to authorized roles. * Â All Route 53 API calls must be captured via CloudTrail. * Â Patchable misconfigurations (e.g., TTL mismatch, missing health checks) must be flagged automatically. * Â Alerts must comply with compliance policies (PCI, CIS benchmarks if applicable). # Integration Requirements * Â SNS must integrate with: * Â ServiceNowÂ * Alert payload must follow a standard message template. 10. Testing & Validation * Test failover must generate an alert. * Test manual record change must generate an audit alert. * Test endpoint failure must trigger "Unhealthy" alarm. |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2e5b4dfc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptvd: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-07 14:38 | [13 empty] | 07/Jan/26 4:38 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working on it. | [29 empty] | In Progress | 2026-01-08 08:27
AM20-377 | PROS ¦¦ Pre-requisite of Network components | Done | 3 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1760705 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 20:53 | 2026-02-03 23:46 |  |  |  | 0 | As AWS expert I would like to create/configuration required network pre-requisite so that later on EC2 instance can be provisioned in PROS account Acceptance criteria: The parent account must share private subnet with PROS account using AWS RAM the sharing also includes route tables The IAM user/role in the child account Security group are created in shared VPC NACL are attached at the subnet level |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [13 empty] | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152123.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153300 | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152137.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153299 | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152151.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153301 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3397a03b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejsb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-28 06:31 | [13 empty] | 28/Aug/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;I am looking final LLD based on that i will created required Subnets against platform ready ness. | 12/Sep/25 8:12 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Pieter, all servers can be migrated under single subnet, and there is no requirement for DB server. I have initiated the Platform readyness. | 15/Sep/25 5:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS application platform/network setup has been completed. ¦PROS¦3¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.192/28¦10.40.1.192 - 10.40.1.207¦10.40.1.193 - 10.40.1.206¦14¦/28¦AZ1¦Â ¦ ¦PROS(DR)¦3¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.224/28¦10.40.1.224 - 10.40.1.239¦10.40.1.225 - 10.40.1.238¦14¦/28¦Â ¦AZ2¦ !image-20250915-152123.png¦width=405,height=211,alt="image-20250915-152123.png"! !image-20250915-152137.png¦width=406,height=166,alt="image-20250915-152137.png"! !image-20250915-152151.png¦width=408,height=117,alt="image-20250915-152151.png"! | 16/Sep/25 4:23 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;validated internet is working with the subnet. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:21
AM20-378 | Informatica Server - Prod ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1752123 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 18:34 | 2026-01-29 18:41 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [10 empty] | AM20-136 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1d85433a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dlmz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-29 06:01 | [13 empty] | 29/Aug/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As it is handled by Arvind so assign to Arvind. | 05/Sep/25 9:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Agent installation is completed and replication followed by initial sync is completed too. | 05/Sep/25 10:29 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-05 10:29
AM20-379 | Migration of FLYSAA DNS Zones to AWS Route53 | To Do | 6 | None( Backlog) |  |  | Satya Varanasi | Medium | 1822276 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 19:14 | 2026-01-10 21:18 |  |  |  | 0 | As a cloud infrastructure Architect I want to migrate existing DNS zones from FLYSAA to AWS Route 53 so thar DNS management can be centralized with AWS, ensuring stability, availability and integration with other AWS services Acceptance Criteria: DNS Zone Discovery and Assessment * Existing FLYSAA DNS zones are inventoried and validated for record types (A, AAAA, CNAME, MA,TXT, SRV, NS, SOA, PTR etc.) * Dependencies on on-prem or third party systems are identified * Zone delegation hierarchy and authoritative name servers are documented * TTL Values and routing policies (simple, Weighted, latency, failover etc.) are reviewed for compatibility with Route53 Route 53 hosted Zone creation * Corresponding public/private hosted zones are created in Route 53 with identical zone names * Correct VPC associations are configured for private zones in the appropriate AWS accounts (dev, pre-prod and prod) * Hosted zones are tagged appropriately * Record Migration and Validation Record Migration and Validation * All DNS record from FLYSAA are migrated to Route 53 with matching values * Route 53 health checks and routing policies are configured as per existing logic * Random sample validation (at least 10%) of DNS resolution from client endpoints confirm accuracy * Validations confirm parity between source and target DNS records Cutover and Delegations * NS records in parent zones are updated to point to Route53 name servers * Change propagation and DNS TTL impact are communicated and managed * Post-cutover validation confirms DNS resolutions is working correctly from internal and external networks * A rollback plan is documented and tested before cutover Security, Audit and logging * Route53 DNS query logging is enabled to CloudWatch or S3 * Access to hosted zones is restricted using IAM roles and policies * GuardDuty and config rules validate DNS configuration integrity * Audit report is generated post migration with DNS record counts and comparison results Monitoring and Alerting * CloudWatch alarms are configured for health checks and DNS failure * SNS topics notify the platform operations team on failure or health check degradation * Dashboards display query metrics and latency per hosted zone Document * Update DNS architecture diagram reflects Route53 integration * SOPs for future DNS change requests are published in the knowledge base * Migration validation report is approved by the business |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [11 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5a13873 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g004 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-10-29 10:50
AM20-380 | Informatica ¦¦ Monitoring Servers post migration | Done | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satya Varanasi | Medium | 1751442 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 14:22 | 2026-01-28 14:32 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if Informatica server service is stopped |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a6a11cb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabm: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:57 | [13 empty] | 25/Aug/25 8:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Spill over Reason: This need to action after migration. | 28/Aug/25 8:32 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 30/Sep/25 7:39 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Cutover change has been approved, once change completes we will close this ticket. | [26 empty] | Done | 2025-10-06 08:37
AM20-381 | Lambda function to observe state in cloudwatch alarms configured for monitoring other lambda | Done | 2 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1812682 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 14:39 | 2026-02-05 14:48 |  | 2025-10-31 17:23 |  | 0 | As Product manager I would like to create Lambda function to observe state in cloudwatch alarms configured for monitoring other lambda function and send Â alert payload to servicenow as per the shared format to servicenow so that any failure of lamda is captured and remediation can be initiated. # Create Eventbridge to monitor the state change in alarm. # Create Lambda function to send alarm notifications to ServiceNow when threshold is breached. # Configure event bridge as the trigger for lambda function |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;31/Oct/25 11:21 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f18c499 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kag3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-27 04:51 | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 27/Oct/25 6:51 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will review the description & configuration needs and will connect with Shreyash for getting more clarity. Once I get the whole picture will move the story to In Progress. | 31/Oct/25 11:20 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Create Eventbridge to monitor the state change in alarm. - Done # Create Lambda function to send alarm notifications to ServiceNow when threshold is breached. - Done # Configure event bridge as the trigger for lambda function - Done Tested it with a test alarm event. [~accountid:712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8] | 31/Oct/25 5:23 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though no demo was provided, based on Faisal comments approving it. | [27 empty] | Done | 2025-10-31 17:23
AM20-382 | TM1 ¦¦ Configuring Application specific error in Cloudwatch for alerting | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730283 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 13:23 | 2026-01-23 13:32 |  |  |  | 0 | As a AWS expert I want to detect application specific error patterns in CloudWatch logs so that I can generate alerts for ServiceNow ticket creation and respond to runtime failure Acceptance Criteria: * Error pattern is defined and tested * Given an application output logs to cloudwatch when a known error occurs, then the pattern must correctly match that log * Metric filter is created - when error count exceeds the threshold then cloud watch alarm should trigger * Alert notification is sent, given the alarm is triggered when the condition is met then an alert must be sent to relevant teams |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [25 empty] | AM20-116 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3fa4464b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bnb3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:37 | [13 empty] | 04/Aug/25 6:37 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will start working on this from today. | 08/Aug/25 12:05 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Monitoring for specifically reporting & tm1serv application has been set. Alarm for Total Commit Usage has been created and configured to send those to ServiceNow. | 08/Aug/25 12:06 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Moving to Aravindâ€™s bucket for review. | 08/Aug/25 12:30 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;every cloud watch custom metrics are captured as error metrics and create an alarm for same. | 08/Aug/25 12:30 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;create a memoryutilization and disk utilization alarm and move to review | 08/Aug/25 8:43 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Monitoring metric is created for Overall Committed Memory Bytes and then further classified for each service that was mentioned in the mail. Alert has been created for â€œOverall Committed Memory Bytesâ€, so creating alarms for its further classification would be redundant. And in the email, we have a confirmation to create an alarm for â€œTotal Commit Sizeâ€ hence have created for â€œOverall Committed Memory Bytesâ€ and not for the per service. | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-383 | AWS Infra Readiness for Migration | In Progress |  | None( Epic) |  |  |  | High | 1620340 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 21:41 | 2026-02-05 22:39 |  |  |  | 0 | AWS Platform for all 20+ application must be ready which includes provisioning of AWS workloads in respective application account, Security & Industry standard compliance implementation, connectivity, RBAC and resource tagging in place |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [15 empty] | 1137600 | 950400 | 187200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4545cda9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-2 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | dark_yellow | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxmzj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | In Progress | 2025-03-04 11:27
AM20-384 | AWS_SAA_Security ¦¦ Security Compliance Implementation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642119 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 15:18 | 2026-01-15 16:09 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on *Account no: 30335236533â€ƒâ€ƒAWS_SAA_Security* *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cb06c96 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00tcn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-09 06:21 | [13 empty] | 09/Apr/25 8:21 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled dependencies service like security hub, macie, guard duty for the compliance controls, will start working on the remediation towards other controls. | 14/Apr/25 8:18 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed implementing controls, awaiting for security score update. Will close this story along with score update. | 17/Apr/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed enabling Guard Duty, Macie, Security Hub, followed by this have implemented controls for CIS, NIST, AWS FSBP standards. Still there are few failed controls to be remediated, since the implementation of services done by vodacom, will expect their support in implementing the controls. if the controls cannot be implemented will get a confirmation on the failed control list to close this user story. | 24/Apr/25 5:50 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is not able to enable with the access i have, so requested vodacom team to support. | 28/Apr/25 4:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is enabled after SCP modification, for failed controls vodacom will do the remediation. | 02/May/25 4:58 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-04-28 16:01
AM20-385 | Terraform code for route 53 implementation | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Satya Varanasi | Medium | 1835009 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-20 14:54 | 2026-01-20 18:33 | 2025-11-27 08:28 |  |  | 0 | [airchefs.co.za¦http://airchefs.co.za] hosted zone need to setup via Terraform. |  | Harsh Chandra | Sanket Kale | Satya Varanasi |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ca1ef33 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mx8b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-25 06:19 | [13 empty] | 25/Nov/25 8:19 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Hosted zone setup is completed on Network account and also validated with internal team. Updated the status as in review and reassign it to Satyasairam. | 27/Nov/25 10:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration done currently all pointing to [airchefs.co.za¦http://airchefs.co.za] is pointing to AWS. | [25 empty] | 1832849 | AM20-262 | Route53 implementation using terraform - Phase 1 | Done | 2025-11-27 10:24
AM20-386 | MQ POC -SbrSplit Parser Testing | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1863568 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 13:45 | 2026-02-06 16:46 | 2026-01-04 09:12 | 2026-01-02 11:05 |  | 0 | I need to test SbrSplit MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [5 empty] | ;17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;18000 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;23/Dec/25 8:26 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18120 | 115200 | 0 | 115320 | 1 | 115200 | 0 | 115320 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2372d0ee | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o64r: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 21 | [97 empty] | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-09 06:22 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 09/Dec/25 8:21 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Testing has been started. Few errors were identified during execution of jar files. Being checked further. | 11/Dec/25 8:17 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Still working on error fixes | 17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Errors have been fixed and initial testing has been completed. | [27 empty] | Done | 2026-01-02 11:05
AM20-387 | Backup using lifecycle management by Terraform | Done | 0 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sanket Kale | Medium | 1752552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 15:58 | 2026-01-16 16:11 |  |  |  | 0 |  |  | Sanket Kale | [5 empty] | 712020:91948faf-1676-4820-bf6b-d50a7992943e | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4eaa1670 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dndf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:52 | [13 empty] | 25/Aug/25 8:52 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;As discussed with Yashwant and Sankalp this is no more require to implement. So closing it. | [26 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 08:52
AM20-388 | Nexio AV ¦¦ CloudTrail and GuardDuty & AWS config Implementation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | High | 1660681 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-23 15:48 | 2026-01-23 17:31 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across NexioAV account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;07/May/25 8:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@319a088e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bmj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-06 06:25 | [13 empty] | 06/May/25 8:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cloud Trails logs to push S3 bucket were implemented already through SCP, now working with guard duty and AWs config enablement. | 07/May/25 8:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard Duty and AWs config is enabled, along with trail. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-07 08:28
AM20-389 | MQ POC ¦¦ MQ Parser Execution - Lambda integration testing & Message body validation | Done | 8 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1842282 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 16:14 | 2026-01-11 16:38 |  | 2025-11-28 07:36 |  | 0 | As Application product owner I would like to perform Lamda integration test with MQ parser and validate the messages output |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Nov/25 5:05 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;7200 | ;21/Nov/25 9:21 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;43200 | ;25/Nov/25 4:07 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;64800 |  |  |  | 115200 | 0 | 115200 | 1 | 115200 | 0 | 115200 | [12 empty] | 25/Nov/25 4:07 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251125-140722.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189321 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124739.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189722 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124758.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189723 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124816.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189725 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124826.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189726 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124840.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189721 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124850.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189724 | [11 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@21c31db9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5mz: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 15:05 | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 5:05 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Exploring feasible approaches for Lambda integration with MQ parser, since direct MQ - Lambda integration is not possible. | 21/Nov/25 8:27 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;we have configured lambda and tested workfow funtionality by pushing message to s3 bucket from SQS. Now we go with checking feasibility with pegasys application usecase | 25/Nov/25 4:07 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Another approach, we tried to integrate MQ queue â€œPEGASYS.OUT.UATâ€ directly to Lambda !image-20251125-140722.png¦width=459,alt="image-20251125-140722.png"! | 26/Nov/25 2:49 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Â We tried integrating both S3 and MQ with Lambda directly. Whenever message reaches to MQ queue, it should trigger lambda which doesnâ€™t happen. However we tested then by integrating s3 event type â€œPutâ€, as soon as any object is uploaded to s3 bucket, it triggers Lambda Â !image-20251126-124739.png¦width=443,alt="image-20251126-124739.png"! Â !image-20251126-124758.png¦width=443,alt="image-20251126-124758.png"! Â !image-20251126-124840.png¦width=443,alt="image-20251126-124840.png"! !image-20251126-124850.png¦width=443,alt="image-20251126-124850.png"! !image-20251126-124816.png¦width=443,alt="image-20251126-124816.png"! !image-20251126-124826.png¦width=443,alt="image-20251126-124826.png"! As next step in next sprint , we will raise support ticket with AWS to get more clarity on this approach of direct integration of lambda and MQ | 28/Nov/25 7:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-28 07:36
AM20-390 | Update ServiceNow Payloads with severity | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832856 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 16:12 | 2026-01-22 18:18 | 2025-11-25 08:24 | 2025-11-27 09:16 |  | 0 | As Product owner I would like to send severity to ServiceNow as well in the payload so that alerts can be classified based on Critical, High, Medium, Low and the incident can be generated accordingly. Acceptance Criteria: Lamda function to be updated with Severity SNS should be able to send mandatory parameters along with severity to ServiceNow successfully |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 115200 | 57600 | 72000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ed98b6b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo2j: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-19 10:36 | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 19/Nov/25 12:35 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Discussed with Aravind regarding adding severity to payload and tested execution for infra alarms in dev env. | 24/Nov/25 4:42 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Alarms payloads are now configured with severity field, working on updating list of alarms to be sent to ServiceNow. | 27/Nov/25 9:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:16
AM20-391 | Miscellaneous Cluster discovery | Done | 6 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1823345 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 21:17 | 2026-01-25 22:22 |  | 2025-11-14 11:13 |  | 0 | As Product and Application Architect I would like to analyse the Cabin crew application so that I can suggest the best possible way to modernize and migrate to AWS. Acceptance Criteria: * Application Overview and business context is captured ( Business criticality, use case, compliance and security needs, Pain point) * Current Architecture assessment ( Front end stack, Backend, integration, dabtabase, storage and compute requirements and assess modernize angles * Security and Governance - IAM and RBAC model, secret and configuration storage, certificate management, logging and audit requirements * Performance and Capacity utilization - CPU, memory and disk usage, scalability needs, Latency and throughput requirements are gathered * Dependency and integration landscape captured * Cost and Licensing requirements clarified (current cost of application, licenses etc.) * Modernization readiness documented * Modernization strategy proposed successfully * Operational readiness documented |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Had workshop with Gayaz and Donald to understand the requirements.;14/Nov/25 8:14 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | Analyzed requirements further.;14/Nov/25 8:15 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Prepared SOW draft;14/Nov/25 8:15 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | Amended SOW as per inputs from internal review and shared with Gayaz.;14/Nov/25 8:16 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 |  |  | 86400 | 7200 | 79200 | 0.91 | 86400 | 7200 | 79200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@27e6cfb4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ljt7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 12:29 | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 2:29 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;# New version of Lounge Tracker application has been under development which consists of a Frontend and a backend microservice component. The backend component will be connecting with 3rd party interfaces like (Discovery Bank, DragonPass etc.) for validations. The ask is to deploy a 'Miscellaneous' cluster which would be capable of hosting diverse set of application microservices with ease. # Focus needs to be on reliability, scalability, and security along with ease of use for this new cluster. # Following two additional projects are in pipeline and business discussions are underway: ## Middleware (Java based microservice which will act as a layer between Amadeus. More clarity is expected by Dec-25) ## Cabin Crew (Project in pipeline) # Â Separate workshops and solutioning will be done for this once business alignment is completed and requirements are finalized. # *Action* â€“ VOIS to share the updated scope of work document for the miscellaneous cluster and related deployments for Gayazâ€™s sign off. | 10/Nov/25 8:16 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Draft SOW document has been prepared. To be reviewed internally. | 13/Nov/25 8:14 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SOW document has been reviewed internally and shared with Gayaz and Vodacom both. | 14/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Followed up with Donald to confirm if there is any new update regarding requirements. There is none. We have already shared an SOW based on current understanding. Activity is completed for now. | 14/Nov/25 11:13 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-14 11:13
AM20-392 | ServiceNow ¦¦ E2E Test validations for TM1 | Done | 2 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1651027 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 19:46 | 2026-01-12 21:53 |  |  |  | 0 | As AWS engineer, I want to test the full alert pipeline from event generation on TM1 to incident creation in ServiceNow so that we can confirm end-to-end functionality Acceptance Criteria: * A simulated error in TM1 triggers the CloudWatch rule * SNS publishes the event * Lamda sends the data to ServiceNow * A ticket is created in ServiceNow with correct details |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;04/Jul/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@54dd1363 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:04 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-02 05:26 | [13 empty] | 02/Jul/25 7:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PRODUCTION ServiceNow Instance: [https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws¦https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws] TM1 server to be integrated with the service now endpoint. | 04/Jul/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Servicenow integration followed by unit test is completed, the SNS topic is configured to get the alerts. | [25 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-04 08:12
AM20-393 | MQ ¦¦ Monitoring and Alert Solution | Blocked | 4 | None( Backlog) |  |  | Diksha Koul | Medium | 1794147 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 19:07 | 2026-01-26 23:05 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if MQ server is stopped |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c39a10 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-02 17:42 | [13 empty] | 02/Nov/25 7:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over* : After creation of the MQ EC2 instance we can start the creation of MQ monitoring and alerting solution. | [29 empty] | To Do | 2025-09-30 10:17
AM20-394 | Cost Anomaly Detection | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1719961 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 13:12 | 2026-01-16 15:59 |  |  |  | 0 | As AWS expert I would like to report any sudden spike in the cost against any of the application or accounts so that the concerned team can validate the reasoning and take appropriate action to ascertain reasons and take reactive measures Acceptance Criteria: < pre-req> : * Ensure all accounts are part of AWS Org. with consolidated billing enabled * Use the Payer9 account to see all account cost level Acceptance Criteria * Cost anomaly detection is enabled successfully * Anomaly monitor is is enabled * Anomaly subscription is successfully enabled using SNS * CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage * Use Amazon Athena or quicksight for stakeholder friendly dashboards * Graphical representation of the cost to be captured |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4d6b831e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0attv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-18 06:07 | [13 empty] | 18/Jul/25 8:07 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;* CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm *---Done* * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage *---Done* Cost anomaly detection is enabled successfully *---Done* * Anomaly monitor is is enabled *---Done* * Anomaly subscription is successfully enabled using SNS *---Done* | 23/Jul/25 8:08 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working on Amazon Athena or quicksight for stakeholder friendly dashboards ---*Done* | 24/Jul/25 7:38 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;As discussed with Yashwant, we need to track cost anomalies for specific AWS services and implement it separately for each account. | 24/Jul/25 8:57 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Cost anomalies detction for specific AWS services and implement it separately for each account. *---Done* Updated for Only TM1 account.(As discussed with Yashwant) | 28/Jul/25 9:58 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:58
AM20-395 | Adding windows server to the AWS managed AD | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651361 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 16:18 | 2026-01-12 19:20 |  |  |  | 0 | As AWS expert, I would be creating Powershell script for Windows server to integrate AWS-AD. Acceptance Criteria: * Powershall script is created successfully and should be able to integrate AWS-AD |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 57600 | 28800 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5e39db2e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02a6b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 06:19 | [13 empty] | 24/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 test instance is added to the AWS managed AD server using a manual approach itself. | 24/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;i documented the process we can use this for future reference. | 02/May/25 4:56 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Approved from Yashwant behalf due to his Jira login issue | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-24 08:20
AM20-396 | RDS Upgrade in Flysaa backend Dev environment | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1842266 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 17:30 | 2026-01-10 18:56 | 2025-11-26 08:48 | 2025-11-27 09:18 |  | 0 | h2. User story * When the RDS instance is upgraded, I want to ensure compatibility with MySQL 8.4 so that our application runs smoothly without issues. h2. Context The development RDS instance will be upgraded from MySQL version 5.7 to 8.4. This upgrade may affect the functionality and performance of the application. h2. Acceptance criteria * The RDS instance must be successfully upgraded to MySQL 8.4. * All application features should function correctly after the upgrade. * Performance benchmarks should be met post-upgrade. h2. Other information N/A |  | Pankaj Pathak | Yashwant Thakur |  |  |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7e1de089 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5lf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [65 empty] | YES | YES | 2025-11-20 06:25 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [12 empty] | 20/Nov/25 8:24 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;The upgrade from MySQL version 5.7.44 to 8.0.42 was successful. The DB instance is running smoothly. We asked the application team (Donald and Gavin) to confirm everything is functioning well on their end. We are awaiting their response to close this story. | 25/Nov/25 2:00 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Ticket moved to In review. As we have completed internal review. | 27/Nov/25 9:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Post upgrade, Business confirmed that BAU is working as expected hence approving | [27 empty] | Done | 2025-11-27 09:18
AM20-397 | ServiceNow ¦¦ SNS Topic for Alerts | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650429 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 21:11 | 2026-01-14 22:17 |  |  |  | 0 | AS AWS Expert, I want to create an Amazon SNS topic so that AWS services can be publish alert messages to it. Acceptance Criteria: * AN SNS topic is created * Permissions are set to allow EventBridge and Lamda to publish to it * The topic supports the subscription |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@505787e3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [66 empty] | Unit Tested | [51 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-06 06:23 | [13 empty] | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed, and will modify the required configurations. Â· | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:38
AM20-398 | MQ-PROD ¦¦Setup Subnet, NACL and SG Creation and Validation | Done | 3 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1794109 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 14:48 | 2026-01-30 17:17 |  | 2025-10-31 09:34 |  | 0 | As AWS network expert I would like to setup the security group and NACL for MQ so that access for MQ allow secure access to allow communication with its services while ensuring access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for MQ or related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [13 empty] | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090000.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175254 | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090022.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175253 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@680e7164 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0i6ob: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 17 | [97 empty] | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [65 empty] | YES | YES | 2025-10-17 09:19 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [12 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 27/Oct/25 4:05 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working on it. | 30/Oct/25 11:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to requirement i have done platform setup. Subnets: ¦Subnet address¦Range of addresses¦Useable IPs¦Hosts¦Divide¦Used Status¦App Name¦ ¦10.40.0.224/28¦10.40.0.224 - 10.40.0.239¦10.40.0.225 - 10.40.0.238¦14¦Divide¦Done¦MQ PROD PRIVATE¦ ¦10.40.0.240/28¦10.40.0.240 - 10.40.0.255¦10.40.0.241 - 10.40.0.254¦14¦Divide¦Done¦MQ PROD PUBLIC¦ ¦10.40.1.32/28¦10.40.1.32 - 10.40.1.47¦10.40.1.33 - 10.40.1.46¦14¦Divide¦Done¦MQ PROD DR¦ ¦10.40.1.48/28¦10.40.1.48 - 10.40.1.63¦10.40.1.49 - 10.40.1.62¦14¦Divide¦Done¦MQ PROD DR¦ Subnets screen: !image-20251030-090022.png¦width=597,alt="image-20251030-090022.png"! EC2 connectivity screen: !image-20251030-090000.png¦width=597,alt="image-20251030-090000.png"! | 31/Oct/25 9:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though MQ migration is put on hold however since the objective and acceptance criteria is met, approving the User story to close | [26 empty] | Done | 2025-10-31 09:34
AM20-399 | MQ ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Blocked | 0 | Sprint 16 | 2025-10-13 | 2025-10-24 | Satya Varanasi | Medium | 1758329 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 19:20 | 2026-01-18 23:00 |  |  |  | 0 |  |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4544ef36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g02 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-17 09:19 | [13 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | [29 empty] | To Do | 2025-08-18 16:44
AM20-400 | AWS Infra Readiness for Migration | To Do |  | None( Epic) |  |  |  | High | 1620376 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 20:58 | 2026-01-12 21:05 |  |  |  | 0 | AWS Platform for all 20+ application must be ready which includes provisioning of AWS workloads in respective application account, Security & Industry standard compliance implementation, connectivity, RBAC and resource tagging in place | [23 empty] | 3398400 | 2736000 | 748920 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6680bbd | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-13 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | dark_green | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxn7b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-03-04 11:47
AM20-401 | Centralized Cluster Creation Strategy | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Sanjot Fotedar | Medium | 1885775 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 18:38 | 2026-01-30 21:22 | 2026-01-08 08:38 |  |  | 0 | As A platform Owner I want to create a detailed design document for centralized management of EKS cluster across multiple AWS child accounts from a central account so that the solution is secure, scalable, compliant and operationally ready before implementation Acceptance Criteria: *Architecture and Account structure* - * Parent, central management and child application accounts * hub and spoke model connectivity model * shared vs isolation responsibilities *EKS management Strategy* - * Centralized model * Namespace isolation strategy * Cluster ownership and lifecycle boundaries *IAM and Security design* - * Cross account IAM roles and trust relationship * K8s RBAC mapping * Least privileges access model * SCP usage and guardrails *Network and Connectivity design* - * VPC architecture per account * Connectivity via TGW /VPC peering * Control plane and data plane traffic flow * DNS resolution strategy *Governance and Policy Enforcement* - * Kubernetes admission controls (Kyverno) * naming, tagging and quota standards * Policy exception handling process *Observability and Logging* - * Centralized logging and metrics flow * Alerting and escalation paths *Security and Compliance* - * EKS security monitoring * Image scanning approach * Compliance reporting and audit readiness *Operation model* - * RACI matrix (L1/L2/L3) * Incident and change management process * upgrade and patching strategy * Backup and DR approach |  | Sanjot Fotedar | [5 empty] | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [5 empty] | ;07/Jan/26 7:23 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;7200 | [5 empty] | 115200 | 108000 | 7200 | 0.06 | 115200 | 108000 | 7200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43715548 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptve: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-07 17:24 | [13 empty] | 07/Jan/26 7:23 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Started work on this. Currently evaluating the framework for assessing multi-tenancy readiness of existing eks cluster. Identifying key focus areas for hardening -Â namespace isolation, RBAC scope, network segmentation, resource governance, policy enforcement. | [29 empty] | In Progress | 2026-01-07 19:21
AM20-402 | ServiceNow ¦¦ Lamda function as SNS Subscriber | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651014 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 21:51 | 2026-02-07 01:42 |  |  |  | 0 | As a Cloud engineer, I want a Lamda function subscribed to the SNS topic so that it can process alerts and forward them to ServiceNow Acceptance Criteria: * The Lamda function is triggered on new SNS messages * It parses event data and sends an HTTP POST request to ServiceNow |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 | ;25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@353710af | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0284j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 03:49 | [13 empty] | 24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Working with the lambda function python script, since the function needs to works with cross account for getting the tags. initially the lambda function developed to get the tags from the same account, whereas here the requirement is to get the tag to Audit account to trigger a SNS. | 25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function is created in Audit account -300204747992, and its working fine as expected. | 02/May/25 4:57 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-25 06:34
AM20-403 | AirNavX ¦¦ Subnet creation using terraform | Done | 0 | Sprint 1 | 2025-03-17 | 2025-03-28 | Sankalp Rai | High | 1620392 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 16:44 | 2026-01-26 20:38 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for AirnavX application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for AirNavX and the configured based on the approved comms matrix |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4777a0ee | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnaf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:52 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 09/Apr/25 5:44 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets has been created. Please review | 17/Apr/25 11:10 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Subnet was created manually Subnet > created Route table > Created SG > Created NACL > Created AD Firewall flow > Implemented Send for PO Approval | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-21 09:01
AM20-404 | Creating Transit Gateway attachment with centralized subnet in Shared VPC account | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-03 20:16 | 2026-02-03 20:33 |  |  |  | 0 | As Network expert I would like to Create Transit Gateway attachment with centralized subnet in Shared VPC account *Acceptance Criteria*: * Transit Gateway attachment is successfully created with centralized subnet |  | Harsh Chandra | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100033 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052941.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100030 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-053047.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100031 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-053208.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100032 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-074925.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103901 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-074943.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103902 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075022.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103900 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075049.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103899 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075143.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103903 | [9 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@64ab5b36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i039pn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-07 16:16 | [13 empty] | 07/May/25 6:15 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dedicated TG attachment subnet created and attached. Testing is pending. | 12/May/25 7:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Test will be initiated today | 14/May/25 7:34 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TG attachment has been configured. Need to test internet connectivity with other accounts. All details shared below. ¦10.40.1.160/28¦10.40.1.160 - 10.40.1.175¦10.40.1.161 - 10.40.1.174¦14¦/28¦AZ1¦Â ¦ ¦10.40.1.176/28¦10.40.1.176 - 10.40.1.191¦10.40.1.177 - 10.40.1.190¦14¦/28¦Â ¦AZ2¦ !image-20250514-052909.png¦width=1135,height=580,alt="image-20250514-052909.png"! !image-20250514-052941.png¦width=1126,height=583,alt="image-20250514-052941.png"! Route table; !image-20250514-053047.png¦width=1126,height=536,alt="image-20250514-053047.png"! Interface associations: !image-20250514-053208.png¦width=1137,height=568,alt="image-20250514-053208.png"! | 14/May/25 5:08 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Common TG attach created and working for multi account, but still need to test further with different scenarios. This required further testing for closer. | 14/May/25 7:13 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;All tests done and working according to our requirement. | 19/May/25 11:26 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Could not verify the routing to internet Routing to internet to be verified and updated Assigning back to [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 19/May/25 5:57 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Routes has been showed overcall. All are configured according to requirement. S C:\Windows\system32> tracert [http://google.com¦http://google.com¦smart-link] Â Tracing route to [http://google.com¦http://google.com¦smart-link] [192.178.54.142] over a maximum of 30 hops: Â Â 1Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 2Â Â Â <1 msÂ Â Â <1 msÂ Â Â <1 msÂ 172.22.2.132---> security account---going to IGW Â 3Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 4Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 5Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 6Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 7Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 99.83.116.121---> AWS datacenter Â 8Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 172.253.65.163---> Google DC Â 9Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 192.178.73.217---->google dc 10Â Â Â 18 msÂ Â Â 18 msÂ Â Â 18 msÂ [tzjnba-ah-in-f14.1e100.net¦http://tzjnba-ah-in-f14.1e100.net] [192.178.54.142]--->google dc Â Trace complete. PS C:\Windows\system32> | 20/May/25 5:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This story reassigned yesterday for routing validation so this will be closed this sprint. | 22/May/25 9:52 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As discussed we have validated routing entries and tracert has been updated with details. Subnets: !image-20250522-074925.png¦width=1109,height=569,alt="image-20250522-074925.png"! !image-20250522-074943.png¦width=1114,height=569,alt="image-20250522-074943.png"! Roue table: !image-20250522-075022.png¦width=1112,height=520,alt="image-20250522-075022.png"! !image-20250522-075049.png¦width=1107,height=559,alt="image-20250522-075049.png"! !image-20250522-075143.png¦width=1100,height=565,alt="image-20250522-075143.png"! Please review the same. | 30/May/25 2:46 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Review Done Transitioning to PO approval | 02/Jun/25 9:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-02 09:19
AM20-405 | EKS public sharing | To Do |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Sumit Nikam | Medium | 1869422 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-20 12:37 | 2026-01-20 14:41 | 2026-01-08 08:37 |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3ef27d1f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obsj: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [41 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | To Do | 2025-11-28 11:12
AM20-406 | Airnavx budget update | Done | 2 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834954 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 17:55 | 2026-01-10 20:04 | 2025-11-21 08:29 | 2025-11-27 09:17 |  | 0 | I would like to update budget of airnavx as per the revised LLD since the configuration of EC2 were change and budget should reflect the cost accordingly |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;20/Nov/25 8:19 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;36600 | [5 empty] | 28800 | 0 | 36600 | 1.27 | 28800 | 0 | 36600 | [12 empty] | 19/Nov/25 8:44 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251119-064353.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186120 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5ed5a68d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mwyr: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:49 | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:49 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will check the updated LLD document and will update the new pricing as per the updated one. | 19/Nov/25 8:44 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the Updated LLD v1.4 and updated the pricing in the management payers account as per the new LLD. !image-20251119-064353.png¦width=629,alt="image-20251119-064353.png"! same has been implemented in the budget account. | 27/Nov/25 9:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:17
AM20-407 | PROS ¦¦ DR | Done | 3 | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | High | 1717973 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 18:23 | 2026-01-18 19:56 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [TM1-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [11 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@49626307 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-03 07:24 | [13 empty] | 03/Oct/25 9:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Only after the server migration we would be able to do DR so this US will be blocked. | 17/Oct/25 11:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;27th Oct planned for cutover, upon server availability we will initiate DR followed by drill. since this will be spillover | [25 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-17 11:08
AM20-408 | Migration of FLYSAA DNS Zones to AWS Route53 | To Do | 6 | None( Backlog) |  |  | Satya Varanasi | Medium | 1822276 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 19:13 | 2026-01-12 20:30 |  |  |  | 0 | As a cloud infrastructure Architect I want to migrate existing DNS zones from FLYSAA to AWS Route 53 so thar DNS management can be centralized with AWS, ensuring stability, availability and integration with other AWS services Acceptance Criteria: DNS Zone Discovery and Assessment * Existing FLYSAA DNS zones are inventoried and validated for record types (A, AAAA, CNAME, MA,TXT, SRV, NS, SOA, PTR etc.) * Dependencies on on-prem or third party systems are identified * Zone delegation hierarchy and authoritative name servers are documented * TTL Values and routing policies (simple, Weighted, latency, failover etc.) are reviewed for compatibility with Route53 Route 53 hosted Zone creation * Corresponding public/private hosted zones are created in Route 53 with identical zone names * Correct VPC associations are configured for private zones in the appropriate AWS accounts (dev, pre-prod and prod) * Hosted zones are tagged appropriately * Record Migration and Validation Record Migration and Validation * All DNS record from FLYSAA are migrated to Route 53 with matching values * Route 53 health checks and routing policies are configured as per existing logic * Random sample validation (at least 10%) of DNS resolution from client endpoints confirm accuracy * Validations confirm parity between source and target DNS records Cutover and Delegations * NS records in parent zones are updated to point to Route53 name servers * Change propagation and DNS TTL impact are communicated and managed * Post-cutover validation confirms DNS resolutions is working correctly from internal and external networks * A rollback plan is documented and tested before cutover Security, Audit and logging * Route53 DNS query logging is enabled to CloudWatch or S3 * Access to hosted zones is restricted using IAM roles and policies * GuardDuty and config rules validate DNS configuration integrity * Audit report is generated post migration with DNS record counts and comparison results Monitoring and Alerting * CloudWatch alarms are configured for health checks and DNS failure * SNS topics notify the platform operations team on failure or health check degradation * Dashboards display query metrics and latency per hosted zone Document * Update DNS architecture diagram reflects Route53 integration * SOPs for future DNS change requests are published in the knowledge base * Migration validation report is approved by the business |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [11 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5a13873 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g004 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-10-29 10:50
AM20-409 | AWS_SAA_Security ¦¦ Security Compliance Implementation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642119 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 18:38 | 2026-01-22 19:50 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on *Account no: 30335236533â€ƒâ€ƒAWS_SAA_Security* *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cb06c96 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00tcn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-09 06:21 | [13 empty] | 09/Apr/25 8:21 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled dependencies service like security hub, macie, guard duty for the compliance controls, will start working on the remediation towards other controls. | 14/Apr/25 8:18 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed implementing controls, awaiting for security score update. Will close this story along with score update. | 17/Apr/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed enabling Guard Duty, Macie, Security Hub, followed by this have implemented controls for CIS, NIST, AWS FSBP standards. Still there are few failed controls to be remediated, since the implementation of services done by vodacom, will expect their support in implementing the controls. if the controls cannot be implemented will get a confirmation on the failed control list to close this user story. | 24/Apr/25 5:50 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is not able to enable with the access i have, so requested vodacom team to support. | 28/Apr/25 4:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is enabled after SCP modification, for failed controls vodacom will do the remediation. | 02/May/25 4:58 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-04-28 16:01
AM20-410 | NexioAV ¦¦ Connectivity Traceability (Comms matrix) preparation | Done | 4 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satya Varanasi | High | 1610560 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 12:33 | 2026-01-24 14:59 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for Nexio AV application so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability created * Comms Matrix sent for reviews |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@666dfeae | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/4 |  | 0 | [66 empty] | Peer Reviewed | Unit Tested | [50 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 4 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kh: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | [107 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-02-24 10:43 | [13 empty] | 24/Feb/25 12:43 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Assigning to Satyasairam Varanasi | 27/Feb/25 8:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Looking IP requirement for this app | 28/Feb/25 8:29 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on IP subnets according to frontend, backend and DB subnet, right we are gathering data. | 17/Mar/25 8:05 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started PROS comms preparation | 07/Apr/25 9:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;NexioAV comms prepared, Need to Review with Santanu, this is moved to next sprint because we are working on TM1 App. | 14/Apr/25 9:39 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms matrix has been prepared. | 24/Apr/25 8:23 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;AWS migration agent comms has been sent for review and CRQ process. | 29/Apr/25 7:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Wanda reviewed and initiated the CRQ process. | 16/May/25 10:36 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per management, i need to wait until further confirmation. | 20/May/25 5:12 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared and shared to SAA team (Wanda) for CRQ submission towards implementing flows. This task not completed earlier Sprint due to dependency with SAA team.(SAA team busy with Ransomware cyber attack), still no clarity from SAA team regarding app migrations. | 23/May/25 11:15 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms CRQ 'CHG0065629â€ has be schedule, but implementation is pending due temporary on hold, Wanda asked us to cross check with Donald for further process and same has been updated Yashwant. | 30/May/25 3:37 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to todays NexioAV LLD call, this is no longer required. According to call we will create new VM and handover to Sinjun Weston. ================== * Based on request from Sinjun, the migration approach for Trellix has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. | [15 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-05-30 15:37
AM20-411 | IAM roles need to created based on LLD. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Satya Varanasi | Medium | 1832050 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Satya Varanasi | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Satya Varanasi | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 2026-01-23 14:27 | 2026-01-23 16:12 |  |  |  | 0 | IAM roles need to be created. Â·Â Â Â Â Â Â Â IAM-based access with predefined roles: oÂ Â *DNSAdmin*Â â€“ Full Route 53 management. oÂ Â *DNSOperator*Â â€“ Modify records, no zone deletions. oÂ Â *DNSViewer*Â â€“ Read-only access. |  | Faisal Sayed | Satya Varanasi |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 |  |  |  |  | ;12/Nov/25 10:19 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fec0f31 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mkiz: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:41 | [13 empty] | 12/Nov/25 6:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Update* * Permission policies for *DNS Admin*, *DNS Operator*, and *DNS Viewer* have been configured. * These will be implemented in the *Management Account (ID: 195973603339)* after approval from *Staya Sir*. h3. *Next Steps* * Schedule a call with *Staya Sir* to review and obtain approval for policy implementation. * Post-approval, apply the policies in the Management Account and validate access controls. | 12/Nov/25 10:19 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Call has been scheduled and IAM roles have been successfully created. Moving the item to *Staya Sirâ€™s review bucket* and updating the status to *In Review*. | 14/Nov/25 8:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Roles has been created according to LLD on main account. | [24 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-14 08:10
AM20-412 | MQ ¦¦ Application comms metrics preparation and implementation | To Do | 0 | None( Backlog) |  |  | Satya Varanasi | Medium | 1795166 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 18:13 | 2026-01-16 19:55 |  |  |  | 0 | AS Network expertise I want to define, track and baseline and validate network communication metrics including subnets, connectivity with downstream/3rd party applications and network rules so that the applicationcan be migrated to the cloud without connectivity failures, security gaps or performance degradation Acceptance Criteria: Application specific subnets (CIDR range, VPC design, Private/public allocation) documented Overlapping IP ranges validated against downstream and 3rd party integrations subnet utilization % captured E2E connectivity map prepared: application <->DB<->downstream services <->3rd party APIs Latency, Packet loss, throughput baselined from VDC/onprem to cloud traget points DNS resolution | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3842a4ec | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g1 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:35
AM20-413 | Nexio AV ¦¦ Firewall Rule creation | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Satya Varanasi | Medium | 1650869 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 13:55 | 2026-01-22 14:10 |  |  |  | 0 | As AWS expert I will be creating firewall rules for Nexio AV application so that security compliance can be met Acceptance Criteria: * Firewall rules are created and sent to Vodacom implementation |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@76b1f9b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:y | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:45 | [13 empty] | 29/Apr/25 7:44 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;FW rules will be implemented after comms implementation. This may need to move next sprint. | 20/May/25 5:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This Story dependency with comms implementation, the same with SAA team. Once SAA team actioned this story will be handled and closed until that this will not possible to address.(Note: it may move next sprint also) | 10/Jun/25 2:09 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;No longer needed based on recent conversation. * Based on request from Sinjun, the migration approach for Trellix/NexioAV has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-10 14:09
AM20-414 | AWS_SAA_Security ¦¦ Security Compliance Implementation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642119 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 17:41 | 2026-01-31 19:30 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on *Account no: 30335236533â€ƒâ€ƒAWS_SAA_Security* *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cb06c96 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00tcn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-09 06:21 | [13 empty] | 09/Apr/25 8:21 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled dependencies service like security hub, macie, guard duty for the compliance controls, will start working on the remediation towards other controls. | 14/Apr/25 8:18 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed implementing controls, awaiting for security score update. Will close this story along with score update. | 17/Apr/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed enabling Guard Duty, Macie, Security Hub, followed by this have implemented controls for CIS, NIST, AWS FSBP standards. Still there are few failed controls to be remediated, since the implementation of services done by vodacom, will expect their support in implementing the controls. if the controls cannot be implemented will get a confirmation on the failed control list to close this user story. | 24/Apr/25 5:50 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is not able to enable with the access i have, so requested vodacom team to support. | 28/Apr/25 4:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is enabled after SCP modification, for failed controls vodacom will do the remediation. | 02/May/25 4:58 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-04-28 16:01
AM20-415 | POC -AWS Patch Manager ¦¦ Create a patch baseline for installing Windows/RHEL Service Packs | Done | 8 | Sprint 3 | 2025-04-14 | 2025-04-25 | Faisal Sayed | High | 1642024 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 15:23 | 2026-02-05 18:31 |  |  |  | 0 | As AWS architect I would be creating patch baselines for windows Server. Acceptance Criteria: Patch Manager has been created successfully |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Onkar Mirajkar | Sankalp Rai | Yashwant Thakur | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [6 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 23/May/25 8:09 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;Re_ Centralized Multi-Account Patching with AWS System Manger Patch Manger.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1104373 | 09/May/25 12:00 PM;9e4636e8-9dfc-4a33-901b-fcd75015926a;System Patch Manger.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1098376 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@b983d7e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/1 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 1 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00svf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | [108 empty] | 1 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-05 06:16 | [13 empty] | 05/May/25 8:15 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Able to install patches on multi-account ec2 instance using Systems Manager Automation. | 05/May/25 8:16 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working on patch policy | 08/May/25 8:12 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working with Lambda and amazon bridge event to automate the patching process for patch policy to run specific dates | 08/May/25 3:29 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Created lambda function and event bridge to automate patch multi-account setup | 09/May/25 8:01 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Need to update document | 09/May/25 12:02 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Document attached in the Jira sent for review to Arvind | 12/May/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Document is reviewed, automation with lambda is captured. | 18/May/25 2:37 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Since the desired solution objective could not be achieved, rejecting this ticket to in progress. As agreed, onkar needs to rework based on agreement. Solution provided by Aravind needs to be developed as POC. as communicated and mentioned by Yashwant. Rejecting on behalf of Yashwant as he has login issues in Jira | 20/May/25 1:24 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Spoke to Venkat on the issue we are facing with centralized patch management and the limitation to use it in multi-account setup in AWS. Quick Setup as work around for Multi-Account Setup, however this service is not available in CapeTown (SA) region. Venkat has agreed to raise this with AWS. As next Step: # compose email stating the solution we are trying to achieve for patching, the limitations we have come across and all the solution we have and what limitations these solutions have. # Venkat will forward this AWS and work on setting up a call to discuss this issue. # Align with AWS on best possible solution/workaround to achieve the desired state | 21/May/25 10:34 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Email has been sent to Venkat, stating what we are trying to achieve, Limitations identified and workarounds tried.Â | 09/Jun/25 8:22 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;As per call, We have tried to download the packages from server which is having Internet connectivity and tried to update on Private Ec2 instances which is working successfully | 13/Jun/25 12:55 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Centralized EC2 Patch Management (Cross-Account)*{{ â€” AchievedÂ }} Â {{Â }}*Key Outcomes*{{:Â }} # Â *Central Patch Repository in Shared Services Account*{{Â }} * Â {{Created `saa-central-patch-bucket` in }}*af-south-1*{{, configured securely.Â }} * {{Uploaded Linux `.rpm` and Windows `.msu` patches to S3 manually & via scripts.Â }} Â # *SSM-Compatible EC2 Instances in Target Accounts*{{Â }} Â {{Launched both Linux & Windows instances without public IPs.Â }} {{Attached custom IAM roles that:Â }} * Â {{Allow full SSM and `s3:GetObject` access to central bucket.Â }} * {{Assume trust with `ec2.amazonaws.com`.Â }} Â # *Patch Acquisition*{{Â }} * Â {{Downloaded Linux patches using SSM Run Command (manual S3 sync).Â }} * {{Downloaded Windows patches (KB5058392) using RDP, installed AWS CLI manually, then uploaded to S3.Â }} Â # *AWS CLI Installed on Windows EC2 (No Internet)*{{Â }} * Â {{Used temporary public IP â†’ installed AWS CLI â†’ removed IP.Â }} Â # *Tested SSM Agent Connectivity*{{Â }} Â {{Verified instances registered to SSM without public IP using:Â }} * Â {{ VPC endpoints (`ssm`, `ssmmessages`, `ec2messages`, `s3`)Â }} * {{ IAM and SGs allowing HTTPS (`tcp/443`)Â }} Â # *Enabled Patch Deployment via SSM Run Command*{{Â }} Â {{Used SSM to:Â }} * Â {{Copy patches from EC2 to central S3Â }} * {{Test patch install commands (`wusa` for `.msu`, `yum` for `.rpm`)}} | 13/Jun/25 2:35 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [14 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:35
AM20-416 | Tagging validations for AWS workloads across environments | Done | 0 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1749567 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 21:25 | 2026-02-02 22:36 |  |  |  | 0 | As AWS expert, Tagging of all resources must be completed and verified |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@24bea93e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0daxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:59 | [13 empty] | 25/Aug/25 8:59 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill over :* I will be reviewing & Attaching the sheet here in US as on friday EOD sanjot & shreyash updated the tags and added them on sheet thatâ€™s why this story got spilled over. | 25/Aug/25 10:03 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have reviewed the sheet all tags are updated for all resources. [Validation sheet for Naming and tagging for FLYSAA_CMS_BACKEND DEV PREPROD & PROD.xlsx¦https://vodafone.sharepoint.com/:x:/r/sites/SouthAfricaAirlines/_layouts/15/Doc.aspx?sourcedoc=%7BD95F49D1-A6B2-4430-A48E-1925ADA79A0D%7D&file=Validation%20sheet%20for%20Naming%20and%20tagging%20for%20FLYSAA_CMS_BACKEND%20DEV%20PREPROD%20%26%20PROD.xlsx&action=default&mobileredirect=true] | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:56
AM20-417 | Create and Grant IAM policies for read-only and modify or edit permission for budget dashboards | Done | 0 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1720023 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 13:06 | 2026-01-16 15:13 |  |  |  | 0 | As AWS expert, I would like to create two custom IAM policies which can used for read-only and edit the budget respectively. Acceptance criteria: * Create one policy to view budget dashboard: * SAAViewBudget: allow to view the budget dashboard prepared for SAA * SAAUpdateBudget: allow to edit or modify the budget allocation through SAA dashboard * The implementation should be payer9 account Users assigned to these policies would only able to view or update the budget dashboard respectively. |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@45e0c06b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0atz7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-17 06:23 | [13 empty] | 17/Jul/25 8:22 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Acceptance criteria: ----*Done* * Create one policy to view budget dashboard: * SAAViewBudget: allow to view the budget dashboard prepared for SAA * SAAUpdateBudget: allow to edit or modify the budget allocation through SAA dashboard * The implementation should be payer9 account | 25/Jul/25 7:50 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Not created properly. As discussed in todays review call, IAM role needs to be created however we were shown only policy | 28/Jul/25 9:55 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Spill Over: Need to Create Users Group Permission including roles and permission--- *Pending* | 29/Jul/25 8:14 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Budgetwise edit permission granted to specific user*---Done* Budget users will only able to view others budget(They cant modify other budget except their own) *----Done* | 05/Aug/25 10:21 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Groups has been created for TM1 and NexioAV Budgets. Users from Respective Group can edit only respective Budgets. This Story is similar/related to [[AM20-111] Configure respective IAM role for TM1 and Nexio business team for Budget management dashboard - Jira¦https://vodacom.atlassian.net/browse/AM20-111] | 11/Aug/25 4:26 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:26
AM20-418 | Patching New Requirement ¦¦ Cache Drive for Patching | Done | 5 | Sprint 21 | 2025-12-22 | 2026-01-02 | Yashwant Thakur | Medium | 1863471 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 20:47 | 2026-01-30 00:31 | 2025-12-18 08:19 | 2026-01-02 11:27 |  | 0 | As Cloud Product manager I would like to use Cache drive for the EC2 servers where Storage is low to proceed with Patching so that we can successfully patch servers without any issue. Acceptance Criteria: * Before Patching is initiated Lamda function first assess if the given EC2 server has sufficient storage available. If the Storage is insufficient then it must attach cache drive to the server and reboot flow must be initiated * Post reboot the storage must be attached successfully * If the Storage is sufficient on the given EC2 instance then the patching should be progressed without any issue |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@66bf1276 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001r | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2026-01-02 06:08 | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Jan/26 8:08 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Update* The *AWS Systems Manager (SSM) document* has been modified to optimize patch installation by leveraging a temporary attached volume. h3. *Technical Details* * The SSM document now: ** Utilizes an *attached temporary volume* mounted with drive letter {{T:}}. ** Downloads and installs patches onto this temporary volume during execution. * Post-installation: ** The system does *not maintain any dependency* on the temporary volume. ** The temporary volume is *manually deleted* after installation is complete (deletion is *not automated* within the document). | [29 empty] | Done | 2026-01-02 11:27
AM20-419 | Assessment on CMS Frontend SMS implementation | Done | 8 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Highest | 1842250 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 14:50 | 2026-01-24 15:23 | 2025-11-28 11:16 | 2025-11-28 14:00 |  | 0 | As a cloud platform application owner I want to perform a detailed assessment for enable SMS notification in the CMS frontend application hosted in AWS so that I can determine best approach, integration method, cost impact, security requirement and technical feasibility before implementation Acceptance Criteria: All use cases for SMS notification are documented SLA, frequency and criticality of SMS delivered and captured User flow diagrams for each SMS scenario prepared Assessment must identify How front will invoke API Required IAM permission documented for access for SMS publishing Consideration for rate limiting and Compliance requirements Risk, Assumption and dependencies |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Understanding alarm implementation and getting AWS frontend access from Leigh.;28/Nov/25 10:33 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on implementing SMS notification on frontend dev account;28/Nov/25 10:33 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | SMS implementation is working, worked on debugging minor issues and updating timeout of Lambda function to enable sending SMS to multiple numbers.;28/Nov/25 10:34 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 |  |  |  | 115200 | 28800 | 86400 | 0.75 | 115200 | 28800 | 86400 | [12 empty] | 28/Nov/25 1:49 PM;17cb9418-1850-4923-932b-7098ec51b6bb;SMS_frontend_alerts.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190540 | 28/Nov/25 10:36 AM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251128-083619.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190436 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67436dd5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5jf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-25 08:56 | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 25/Nov/25 10:56 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created a Whitepage access request to enable access for frontend AWS accounts, reached out to Leigh with ticket details. | 26/Nov/25 8:54 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Access request is approved, awaiting access enabling from Leigh. | 27/Nov/25 8:21 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Got the access from Leigh, worked on provisioning AWS resources (Lambda , eventbridge rule , dynamodb table) for alert implementation, need to get number from Hoosen for sending sms. | 28/Nov/25 10:36 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Hoosen confirmed he got SMS for sample alarm in frontend dev . !image-20251128-083619.png¦width=281,alt="image-20251128-083619.png"! | 28/Nov/25 1:49 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;[^SMS_frontend_alerts.docx] Please find attached document for SMS implementation. | 28/Nov/25 2:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-28 14:00
AM20-420 | Ingesting 500 of lines of inbound and outbound rules from excel to Terraform code for enablement | Done | 6 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1869689 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 15:46 | 2026-01-21 18:07 | 2025-12-14 17:51 | 2025-12-12 14:51 |  | 0 |  |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bae0685 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ocbn: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-05 06:26 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Dec/25 8:26 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script deployment. Currently we are adding the inbound and outbound rule with excel only. | 12/Dec/25 2:51 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approving provided we see workable solution during demo | [28 empty] | Done | 2025-12-12 14:51
AM20-421 | Restrict Admin access to VOIS team by creating dedicated IAM role | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Medium | 1736354 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 20:06 | 2026-01-26 23:25 |  |  |  | 0 | As Product Owner, I want to restrict VOIS team to have Admin role so that all of them cannot be superseded rights and bring more control on AWS management Acceptance criteria: * IAM role to be created for everyone except Sankalp and Aravind from AWS perspective * IAM role for network creation to be created and role assign to Satya * IAM role for rest of team members is of developer |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6edd432e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0c5zn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 06:20 | [13 empty] | 06/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have shared the Excel with the user list to team, upon there confirmation ill start creating custom policy with user groups. | 08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;¦UserID¦IAM user¦UserGroup¦IAM Role¦ ¦raja0001¦Aravind¦VOIS_Admin¦No changes, use existing roles itself¦ ¦rais0003¦Sankalp¦VOIS_Admin¦No changes, use existing roles itself¦ ¦SatyasairamV¦SatyaSairam¦VOIS_Admin¦No changes, use existing roles itself¦ ¦godir001¦Ravinder¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦kiraj001¦Jitender¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Sanjot¦Sanjot¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦nikas001¦Sumit¦VOIS_Admin¦No changes, use existing roles itself¦ ¦FaisalSayed¦Faizal¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SanketKale¦Sanket¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦pathp002¦Pankaj¦VOIS_DBAdmin_Usergroup¦AWS_VOIS_DBAdmin_Role¦ ¦onkar¦Onkar¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦DikshaK¦Diksha¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SatyabrataS¦SatyaBrata¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Shreyash¦Shreyash¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Harsh¦Harsh¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Yashwant¦Yashwant¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Utkarsh¦Utkarsh¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ Â Â Access to User group given as below, ¦VOIS_InfraAdmin_Usergroup¦VOIS_DevOpsAdmin_Usergroup¦VOIS_DBAdmin_Usergroup¦ ¦VPC FullAccess¦CodeBuild FullAccess¦RDS Full Access¦ ¦EC2 FullAccess¦CodePipeline FullAccess¦DMS Full Access¦ ¦S3 FullAccess¦EKS FullAccess¦IAM Full Access¦ ¦CloudWatch FullAccess¦EC2 except delete¦CloudTrail except delete¦ ¦RDS FullAccess¦S3 FullAccess¦KMS except delete¦ ¦IAM FullAccess¦CloudWatch except delete¦CloudWatch except delete¦ ¦CloudTrailFullAccess¦RDS except delete¦Read only¦ ¦MacieFullAccess¦IAM FullAccess¦ ¦ ¦GuardDutyFullAccess¦System managerFullAccess¦ ¦ ¦SecurityHubFullAccess¦LambdaFullAccess¦ ¦ ¦System managerFullAccess¦Event bridgeFullAccess¦ ¦ ¦LambdaFullAccess¦CloudTrail except delete¦ ¦ ¦KMSFullAccess¦Read only¦ ¦ ¦ACMFullAccess¦Secrets managerFullAccess¦ ¦ ¦Aws ConfigFullAccess¦SNSFullAccess¦ ¦ ¦Event bridgeFullAccess¦SESFullAccess¦ ¦ ¦InspectorFullAccess¦ECR FullAccess¦ ¦ ¦SupportFullAccess¦KMS except delete¦ ¦ ¦SNSFullAccess¦Â ¦ ¦ ¦SESFullAccess¦ ¦ ¦ ¦ReadOnly¦ ¦ ¦ ¦Secrets managerFullAccess¦ ¦ ¦ ¦ECRFullAccess¦ ¦ ¦ Â Users have access to the below AWS accounts, Â ¦AWS Account¦Account Name¦ ¦300204747992¦Audit¦ ¦730335236533¦Security¦ ¦080284287007¦LogArchive¦ ¦339712943527¦Network¦ ¦864899875361¦SharedServices¦ ¦585768167545¦SharedVpcDev¦ ¦253490777663¦SharedVpcPreprod¦ ¦820242899278¦SharedVpcProd¦ ¦746669190453¦Backend dev¦ ¦216989128782¦Backend Preprod¦ ¦396608788916¦Backend Prod¦ ¦209479274829¦Tm1¦ ¦345594574792¦AirNAVx¦ ¦536697265099¦NexioAV¦ | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-422 | Backup Server ¦¦ Security compliance implementation | Done | 3 | Sprint 7 | 2025-06-09 | 2025-06-20 | Aravind Raj | Medium | 1681806 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 21:43 | 2026-01-24 00:20 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Backup Server *Acceptance Criteria*: * Renaming of PROS account to Back-Up Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 14400 | 43200 | 1 | 43200 | 14400 | 43200 | [12 empty] | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250612-153959.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1113715 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@48024563 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-09 05:41 | [13 empty] | 09/Jun/25 7:41 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will start working on enabling security frameworks like CIS, NIST, AWS FSBP. | 10/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled controls, will be working on the controls remediation. | 11/Jun/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;controls are implemented waiting for the security score to be update Â· | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CIS, NIST and FSBP controls were enabled and required controls remediated. !image-20250612-153959.png¦width=1279,height=626,alt="image-20250612-153959.png"! | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-12 17:41
AM20-423 | Citrix ¦¦ LLD creation | Done | 6 | Sprint 4 | 2025-04-28 | 2025-05-09 | Sankalp Rai | High | 1619785 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 21:32 | 2026-01-30 01:22 |  |  |  | 0 | As AWS architect, I would create LLD for Citrix application migration *Acceptance Criteria*: * Low level design documentation including proposed architecture completed |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 28800 |  | 0 | 86400 | 28800 | [9 empty] | AM20-23 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b60bc29 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 4 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02775: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-20 08:23 | [13 empty] | 20/May/25 10:22 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;¦Needs discussion with customer on approach to be taken. We can either move with Greenfield Deployment or Migrate the exiting setup to AWS. The call was scheduled for 12th May, however that call did not as Nilesh and Team were not available. Follow-up mail for rescheduling the call has been sent. No Update from customer. We will be able to provide start date and end only after we finalize the approach.Â ¦ ¦ ¦ | 02/Jun/25 8:28 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Need to setup call with Nilesh on Citrix licences on cloud and on the approach for migration to AWS. | 02/Jun/25 8:29 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Moving to Blocked | 13/Jun/25 12:51 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;New business case needed, hence marking this as closed. | [23 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-06-13 12:51
AM20-424 | Implement JSON Message Parsing in AWS sandbox ActiveMQ POC | Done | 4 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811820 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 16:38 | 2026-02-01 17:58 |  | 2025-10-31 17:25 |  | 0 | As part of validating AWS ActiveMQ integration with a Spring Boot application, we will deploy Producerâ€“Consumer.java files to conduct POC to include JSON message parsing capability. The Producer will publish structured JSON messages to ActiveMQ queue, and Consumer will parse and process the JSON payload. This will help validate end-to-end message exchange, parsing logic, and overall integration readiness in AWS sandbox environment. *Acceptance Criteria* * Deploy ActiveMQ in AWS Sandbox environment. * ActiveMQ broker is accessible from Spring Boot application in EC2 windows of AWS sandbox. * Producer publishes a sample JSON message to ActiveMQ queue. * Consumer retrieves the message and successfully parses the JSON payload using a standard parser (e.g., Jackson). * Parsed data fields are printed for verification. * Message transmission and parsing flow verified end-to-end without errors. |  | Sanjot Fotedar | Sumit Nikam | Yashwant Thakur |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;24/Oct/25 10:15 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 57600 | 28800 | 28800 | [12 empty] | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124615.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174186 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124631.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174189 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124648.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174188 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124656.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174187 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5c659eaf | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k74r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-23 13:51 | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 23/Oct/25 3:51 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Following steps are completed: * We have deployed ActiveMQ in AWS sandbox account. * Deploy EC2 windows server manually in same sandbox account align under same network with MQ server. * Tested successfully MQ server connectivity from EC2 windows server. * Installed JDK-17 version , maven to support java spring boot applications. * Developed and deployed java application with pom.xml | 28/Oct/25 2:50 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;* Developed [Producer.java¦http://Producer.java] to publish JSON messages to AWS ActiveMQ queue. * Developed [ConsumerTest.java¦http://Consumer.java] to consume and parse JSON messages. * Verified successful message send/receive flow over SSL connection. * Validated JSON parsing using Jackson and confirmed expected output. * Resolved encoding and dependency issues during build. * End-to-end functionality tested in AWS sandbox account. * MQ server Dashboard shows expected outcome. !image-20251028-124615.png¦width=443,alt="image-20251028-124615.png"! !image-20251028-124631.png¦width=443,alt="image-20251028-124631.png"! !image-20251028-124648.png¦width=443,alt="image-20251028-124648.png"! !image-20251028-124656.png¦width=443,alt="image-20251028-124656.png"! | 31/Oct/25 12:31 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;We have reviewed implementation in sandbox and could see working messaging flow from provider to the consumer via AmazonMQ running with ActiveMQ broker. Next step is to modify the config and test config based on feedback from Amadeus. | 31/Oct/25 5:25 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-10-31 17:25
AM20-425 | Tag Validations for Informatica | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820185 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 18:55 | 2026-02-03 21:49 |  | 2025-11-12 08:22 |  | 0 | As a Cloud governance engineer I want to validate that all resources and workloads related to newly migrated applications have the correct mandatory tags applied so that we can ensure accurate cost allocation, compliance reporting and automation alignment across all Informatica account Acceptance Criteria: * Tags for all applicable application resource type ( EC2, EBS, RDS, S3 lamda, ALB/NLB, Cloudwatch log groups) are successfully captured. * If there are any tags not available then manually updated successfully * Validations runs across all migrated resources and as per agreed format |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:34 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;209400 | [5 empty] | 28800 | 0 | 209400 | 7.27 | 28800 | 0 | 209400 | [12 empty] | 07/Nov/25 9:09 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251107-070856.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1179412 | 07/Nov/25 9:09 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251107-070933.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1179416 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@196a21d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l62b: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 11:53 | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 1:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started verifying the tags are being applied on all resources for both Informatica Dev and Prod environment. | 05/Nov/25 4:19 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have updated all mandatory tags for all Informatica Dev & Prod Environment. | 07/Nov/25 9:09 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251107-070856.png¦width=629,alt="image-20251107-070856.png"! | 07/Nov/25 9:09 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251107-070933.png¦width=629,alt="image-20251107-070933.png"! | 12/Nov/25 8:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-12 08:22
AM20-426 | POC - Create Sustainability dashboards | To Do | 8 | Sprint 10 | 2025-07-21 | 2025-08-01 | Sankalp Rai | High | 1720042 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 16:41 | 2026-02-02 16:54 |  |  |  | 0 | As AWS Expert, I would create sustainability dashboard to access the power consumption, utilization and energy efficiency in alignment with well-architecture Acceptance Criteria * Enable AWS Sustainability Pillar in Well-Architected Reviews, optimize workloads for energy efficiency â€” right-sizing, minimizing network transfer, cold storage, etc. * Leverage S3 Lifecycle Policies & Intelligent Tiering |  | Harsh Chandra | Sankalp Rai |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63121580 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v09 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | Sprint 12 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:13 | [13 empty] | 11/Aug/25 10:12 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 12th August End Date: 21st August | 10/Sep/25 1:15 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Moving this to Backlog from Sprint 13 as suggested by Deepak Sharma, to currently focus on critical migration activities. This will be picked up in later sprints. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | To Do | 2025-10-13 09:27
AM20-427 | Route53 cutover for Airchef | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834911 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 19:55 | 2026-02-05 23:26 | 2025-11-28 10:20 | 2025-11-28 14:01 |  | 0 | As product Onwer I like to perform cutover for Route53 for airchef |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;28/Nov/25 10:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 28/Nov/25 10:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ CHG0068339 for Airchef Route 53 cutover .msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190434 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@c54e709 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mws3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_268391979_*¦*_10041_*:*_2_*:*_1029530025_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_2_*:*_268391979_*¦*_10041_*:*_2_*:*_1029530025_*¦*_13940_*:*_1_*:*_0 | 3_*:*_2_*:*_268391979_*¦*_10041_*:*_2_*:*_1029530025_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_268391979_*¦*_10041_*:*_2_*:*_1029530025_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-25 06:03 | 3_*:*_2_*:*_268391979_*¦*_10041_*:*_2_*:*_1029530025_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 25/Nov/25 8:03 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;[airchefs.co.za¦http://airchefs.co.za] hosted zone has been configured, zone file has been imported. for test point of view i have tried to reach new route53 resolvers from my local laptop and the same able to reach. Share NS resolvers to network team towards adding main domain account. NS resolvers: [ns-1087.awsdns-07.org¦http://ns-1087.awsdns-07.org] [ns-918.awsdns-50.net¦http://ns-918.awsdns-50.net] [ns-1948.awsdns-51.co.uk¦http://ns-1948.awsdns-51.co.uk] [ns-496.awsdns-62.com¦http://ns-496.awsdns-62.com] C:\Users\VaranasiS>nslookup Default Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 {quote}{quote} C:\Users\VaranasiS>nslookup [ns-1087.awsdns-07.org¦http://ns-1087.awsdns-07.org] Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: Name: [ns-1087.awsdns-07.org¦http://ns-1087.awsdns-07.org] Addresses: 2600:9000:5304:3f00::1 205.251.196.63 C:\Users\VaranasiS>nslookup [ns-918.awsdns-50.net¦http://ns-918.awsdns-50.net]. Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: Name: [ns-918.awsdns-50.net¦http://ns-918.awsdns-50.net] Addresses: 2600:9000:5303:9600::1 205.251.195.150 C:\Users\VaranasiS>nslookup [ns-1948.awsdns-51.co.uk¦http://ns-1948.awsdns-51.co.uk]. Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: Name: [ns-1948.awsdns-51.co.uk¦http://ns-1948.awsdns-51.co.uk] Addresses: 2600:9000:5307:9c00::1 205.251.199.156 C:\Users\VaranasiS>nslookup [ns-496.awsdns-62.com¦http://ns-496.awsdns-62.com] Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: Name: [ns-496.awsdns-62.com¦http://ns-496.awsdns-62.com] Addresses: 2600:9000:5301:f000::1 205.251.193.240, | 25/Nov/25 9:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change plan has been shared to customer, customer under process of scheduling the change. | 27/Nov/25 10:28 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;CHG0068339 for [Airchefs.co.za¦http://Airchefs.co.za] is pointing to AWS Route 53 and working fine. | 28/Nov/25 10:34 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change implemented and working smoothly since 36 hours. hence i am closing this story.[^RE_ CHG0068339 for Airchef Route 53 cutover .msg] | 28/Nov/25 2:01 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Implementation done for airchef | [25 empty] | Done | 2025-11-28 14:01
AM20-428 | Miscellaneous Cluster discovery | Done | 6 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1823345 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 12:35 | 2026-02-05 13:19 |  | 2025-11-14 11:13 |  | 0 | As Product and Application Architect I would like to analyse the Cabin crew application so that I can suggest the best possible way to modernize and migrate to AWS. Acceptance Criteria: * Application Overview and business context is captured ( Business criticality, use case, compliance and security needs, Pain point) * Current Architecture assessment ( Front end stack, Backend, integration, dabtabase, storage and compute requirements and assess modernize angles * Security and Governance - IAM and RBAC model, secret and configuration storage, certificate management, logging and audit requirements * Performance and Capacity utilization - CPU, memory and disk usage, scalability needs, Latency and throughput requirements are gathered * Dependency and integration landscape captured * Cost and Licensing requirements clarified (current cost of application, licenses etc.) * Modernization readiness documented * Modernization strategy proposed successfully * Operational readiness documented |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Had workshop with Gayaz and Donald to understand the requirements.;14/Nov/25 8:14 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | Analyzed requirements further.;14/Nov/25 8:15 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Prepared SOW draft;14/Nov/25 8:15 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | Amended SOW as per inputs from internal review and shared with Gayaz.;14/Nov/25 8:16 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 |  |  | 86400 | 7200 | 79200 | 0.91 | 86400 | 7200 | 79200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@27e6cfb4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ljt7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 12:29 | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 2:29 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;# New version of Lounge Tracker application has been under development which consists of a Frontend and a backend microservice component. The backend component will be connecting with 3rd party interfaces like (Discovery Bank, DragonPass etc.) for validations. The ask is to deploy a 'Miscellaneous' cluster which would be capable of hosting diverse set of application microservices with ease. # Focus needs to be on reliability, scalability, and security along with ease of use for this new cluster. # Following two additional projects are in pipeline and business discussions are underway: ## Middleware (Java based microservice which will act as a layer between Amadeus. More clarity is expected by Dec-25) ## Cabin Crew (Project in pipeline) # Â Separate workshops and solutioning will be done for this once business alignment is completed and requirements are finalized. # *Action* â€“ VOIS to share the updated scope of work document for the miscellaneous cluster and related deployments for Gayazâ€™s sign off. | 10/Nov/25 8:16 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Draft SOW document has been prepared. To be reviewed internally. | 13/Nov/25 8:14 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SOW document has been reviewed internally and shared with Gayaz and Vodacom both. | 14/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Followed up with Donald to confirm if there is any new update regarding requirements. There is none. We have already shared an SOW based on current understanding. Activity is completed for now. | 14/Nov/25 11:13 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-14 11:13
AM20-429 | TM1 ¦¦ SSM provisioning and CloudWatch Agent with cutover instance | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1752616 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 16:27 | 2026-02-05 16:56 |  |  |  | 0 | As AWS expert, I would like to provision SSM and Cloudwatch on TM1 cutover instance Acceotance criteria: SSM instance and Cloudwatch instance is successfully provisioned |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Aug/25 8:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Aug/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@777f120 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dnlf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-13 06:17 | [13 empty] | 13/Aug/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cloud watch agent setup is completed, will configure the config.json file to fetch relevant server metrics and application metrics. | 13/Aug/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;after cloud watch configuration will start working on setting up SSM agent. | 14/Aug/25 8:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SSM agent installation is success upon stopping MacAfee and excluding from Trellix service. | 25/Aug/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 06:33
AM20-430 | MQ POC -SbrSplit Parser Testing | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1863568 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 16:36 | 2026-01-21 16:45 | 2026-01-04 09:12 | 2026-01-02 11:05 |  | 0 | I need to test SbrSplit MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [5 empty] | ;17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;18000 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;23/Dec/25 8:26 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18120 | 115200 | 0 | 115320 | 1 | 115200 | 0 | 115320 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2372d0ee | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o64r: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 21 | [97 empty] | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-09 06:22 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 09/Dec/25 8:21 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Testing has been started. Few errors were identified during execution of jar files. Being checked further. | 11/Dec/25 8:17 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Still working on error fixes | 17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Errors have been fixed and initial testing has been completed. | [27 empty] | Done | 2026-01-02 11:05
AM20-431 | SMS Alerting Implementation | Done | 6 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1785825 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 12:30 | 2026-01-17 14:53 |  | 2025-10-31 17:22 |  | 0 | As a cloud product owner I want application and platform alerts to be delivered via SMS from a dedicated long code so that on call engineers and stakeholders receive time critical notifications Acceptance criteria: *E2E SMS on P1/P2* - Given the cloudWatch alarm changes to ALARM with severity ðŸ˜›1 when the alarm event is routed via EventBridge to the SNS topic than all active on-call receipients for the app+env recieve an SMS within 60s and message body includes app, env, alarm name, severity, runbook link and ACK instruction ¦¦*Severity*¦¦*objective signals*¦¦*examples*¦¦ ¦P1 - Critical, user impact¦harsh outage, data loss, security incdences¦API 5xx>10% 5m in production, RDS storage<5% 10m. certificate expiry < 3days, guard duty, unauthrized access¦ ¦P2 - Degradation,Urgent¦performance, throughput, redundancy lost,¦EKS node group<N healthy, ALB healthy, RDS IOPS deviation, CPU utilization, disk innode,¦ ¦P3 - Action soon¦Capacity/Ops issues, repeated flaps¦log patterns,¦ ¦P4 - Informational¦chnages , warnings, failures without user impact¦Daily back ok, lamda changes, deloyment success¦ *Delivery logging and metrics* - Given SMS messages are sent when carriers return delivery statuses then statuses are captured in CloudWatch logs and S3 and dashboards show sends, successes, failures, per country breakdown *Retry and escalations ( in the event of SMS failure)* - Given a send gets a transient failure when the system retries with backoff( up to 3 times in 5 minutes) then on persistent failure an escalation SMS is triggered to secondary contacts and a ticket is created in ServiceNow with failure details *Deduplication and storm control* - Given multiple identical alarms fire within 5 minutes when routing occurs then recipients receive at most one SMS per unique alarm/signature per 5 minute window and a summary SMS is sent after 15 minutes if >5 deduped alerts occurred. |  | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Initially worked on gathering additional information regarding message size limit for SMS in case of long text message sent. Initiated questionaire in AWS community portal to get in depth costing based on message length , worked on restructuring SMS notification to avoid additional costing for SMS. Discussed with Gayaz to get company information to initiate dedicated long code generation (currently using shared pool of origination identities). Worked on updating existing Lambda jobs to support sending SMS alerts and working on fetching amount spent in SMS notification to apply a cost guard rail and send only priority message in case of spent exceeds 80 % limit. ;31/Oct/25 1:17 PM;17cb9418-1850-4923-932b-7098ec51b6bb;115200 | [5 empty] | 86400 | 0 | 115200 | 1.33 | 86400 | 0 | 115200 | [11 empty] | AM20-253 | 31/Oct/25 1:09 PM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251031-110848.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176021 | 31/Oct/25 1:09 PM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251031-110913.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176022 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@78a09d31 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h703: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 |  | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | [65 empty] | YES | YES | 2025-10-03 06:27 | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | [12 empty] | 03/Oct/25 8:26 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Awaiting Go ahead from Husein/Eugene to proceed with this requirement | 14/Oct/25 8:22 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Sign off received to go ahead with SMS alerting requirement | 20/Oct/25 7:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;spill over reason- need company contact details and other relevant information to generate a request for long code on AWS support. | 24/Oct/25 8:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Requested for additional details from Gayaz as asked by AWS support for proceeding with Long code generation request and account spent limit increase. | 30/Oct/25 11:34 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;we have done changes in lambda script to support sending sms for error pattern alerts , test sms was successfully sent to Gayaz. Working on adding similar support for other alarm types as well, also working on implementing other requirements like sending only p1 message if budget is crossed over 80% and opt-in/opt-out functionality. | 31/Oct/25 12:11 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Issue split into: ¦AM20-253¦SMS Alerting implementation- Opt in/Opt out¦ | 31/Oct/25 1:10 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We have configured SMS based alerts for Flysaa Backend Alarms and assigned Priorities to the alerts based on above table. *Error Patterns in Pod logs* : P3 *Api HealthCheck Fail for pod* : P1 *CPU consumption or Memory consumption or Container restart alarm* : P2 For RDS: *When RDS instance is down* : P1 *When RDS cert expiry is < 30 days* : P1 (We check cert expiry daily but SMS notification will only be sent when < 30 days are remaining ) *RDS metrics alarms like CPU utilization, read/write iops* : P2 *RDS metrics when available free space is less than 10 %* : P1 Please find attached screenshots for SMS sent to Gayaz !image-20251031-110848.png¦width=537,alt="image-20251031-110848.png"! !image-20251031-110913.png¦width=463,alt="image-20251031-110913.png"! | 31/Oct/25 5:22 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;SMS sent to Customer and mail confirmation received | [22 empty] | Done | 2025-10-31 17:22
AM20-432 | Tagging Compliance implementation | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834929 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 14:24 | 2026-02-06 17:35 | 2025-11-27 08:26 | 2025-11-28 11:38 |  | 0 | As product owner I would like to setup tagging compliance in centralized Cloudwatch dashboard so that I know how many workloads are not been tagged and take corrective actions accordingly |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;20/Nov/25 8:27 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;21/Nov/25 7:56 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;25/Nov/25 10:41 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;26/Nov/25 3:33 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;27/Nov/25 4:17 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;7200 |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 27/Nov/25 4:17 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251127-141419.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190266 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fa2be84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mwv7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:50 | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:50 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Satya sir is checking with leigh regarding the tag policy enable part after updating the tag policy will start working on the Tag compliance part. | 19/Nov/25 1:33 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have Enabled the Tag Compliance policy for all account. Waiting for security score. | 21/Nov/25 7:55 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Security score is visible for all accounts now next step is we are disabling the ID on with we donâ€™t require this tag compliance policy for all accounts. | 23/Nov/25 2:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have disabled the Tag Compliance policy for all the non required resource IDâ€™s for all 17 mandatory accounts. 746669190453â€ƒâ€ƒFlySAA_CMS_Backend_DevQA 216989128782Â Â Â Â Â Â Â FlySAA_CMS_Backend_PreProd 396608788916â€ƒâ€ƒFlySAA_CMS_Backend_Prod 209479274829â€ƒâ€ƒSAA TM1 345594574792â€ƒâ€ƒSAA AirnavxÂ 536697265099â€ƒâ€ƒSAA_NEXIOAV_PROD 650251698621â€ƒâ€ƒSAA_PROS_PROD 307946680641â€ƒâ€ƒSAA_Informatica_DEV 536697248966â€ƒâ€ƒSAA_Informatica_PROD 195973603339â€ƒâ€ƒvod001_001_payer9 300204747992â€ƒâ€ƒSAA-AuditÂ 730335236533â€ƒâ€ƒAWS_SAA_Security 080284287007â€ƒâ€ƒSAA-LogArchive 339712943527â€ƒâ€ƒAWS_SAA_Network 585768167545Â Â Â Â Â Â Â SharedVPCDevQA() 253490777663Â Â Â Â Â Â Â SharedVPCPreProd() 820242899278Â Â Â Â Â Â Â SharedVPCProd() | 25/Nov/25 10:40 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;For the Untagged one IDâ€™s we are remediating the failed ones as much as we can for all 17 accounts before getting the centralized dashboard enabled for Tag compliance. | 26/Nov/25 9:04 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Tag compliance security score is 95% for all 17 Accounts and to make it 100% we need to Tag IAM Roles for all Accounts and Each account contains more than 60 IAM Roles which is not possible for a Single person to tag them. I need team support to tag those IAM roles as its a manual work no automation will help as they are the existing resources not the new ones. | 26/Nov/25 3:32 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*UPDATE :* With the Help of lambda function we were able to tag all the IAM roles for all 17 accounts. Except the oneâ€™s which are not handled by our team and we are not authorized to tag them. | 27/Nov/25 4:17 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251127-141419.png¦width=629,alt="image-20251127-141419.png"! Tags has been implemented for all resources and in the security account under Security Hub we can see all the tagged resources and the information. | 28/Nov/25 11:38 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. Saw the data presented in review call. satisfied with results | [21 empty] | Done | 2025-11-28 11:38
AM20-433 | Airnavx ¦¦ EC2 Creation using terraform code | Cancelled | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satyabrata Sahoo | Medium | 1760710 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:4b8d8093-596d-4394-a074-4a9a9636f86f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 18:39 | 2026-01-23 22:29 |  |  |  | 0 | As AWS Expert I would like to provision EC2 using terraform so that I can handover to SAA for Airnavx installation Acceptance Criteria: EC2 provisioned successfully using approved AMI Tags applied automatically Instance must have SSM agent installed SSH is enabled only via bastion host Guardduty must detect and monitor instance Instance must publish logs to CloudWatch EC2 must register with org monitoring/alerting |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b9d343f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejt7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | [103 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 06:38 | [13 empty] | 05/Sep/25 8:37 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Closing this as this is a duplicate of [https://vodacom.atlassian.net/browse/AM20-131¦https://vodacom.atlassian.net/browse/AM20-131¦smart-link], hence closing the ticket | [26 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-05 08:38
AM20-434 | AWS_SAA_Security ¦¦ Security Compliance Implementation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642119 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 13:30 | 2026-01-21 17:10 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on *Account no: 30335236533â€ƒâ€ƒAWS_SAA_Security* *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cb06c96 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00tcn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-09 06:21 | [13 empty] | 09/Apr/25 8:21 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled dependencies service like security hub, macie, guard duty for the compliance controls, will start working on the remediation towards other controls. | 14/Apr/25 8:18 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed implementing controls, awaiting for security score update. Will close this story along with score update. | 17/Apr/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed enabling Guard Duty, Macie, Security Hub, followed by this have implemented controls for CIS, NIST, AWS FSBP standards. Still there are few failed controls to be remediated, since the implementation of services done by vodacom, will expect their support in implementing the controls. if the controls cannot be implemented will get a confirmation on the failed control list to close this user story. | 24/Apr/25 5:50 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is not able to enable with the access i have, so requested vodacom team to support. | 28/Apr/25 4:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is enabled after SCP modification, for failed controls vodacom will do the remediation. | 02/May/25 4:58 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-04-28 16:01
AM20-435 | ServiceNow Monitoring ¦¦ Prod Implementation | Done | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1673102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-09 14:51 | 2026-01-09 16:59 |  |  |  | 0 | As AWS solution architect, I would like to implement ServiceNow monitoring in prod environment so that alerts can be generated and reach to ServiceNow in form of Tickets for further actions. Acceptance Criteria: * Setup of ServiceNow integration to pull AWS receive data using EventBridge * Unautherized API calls from GuardDuty and Security Hub * Setup Cloudwatch alarms or rules for all the resources entitled to be monitored and send these to SNS topic * Create SNS topic * Configure SNS HTTPS configuration so that SNS can directly invoke HTTPS endpoints * AWS Lambda function created to forward SNS messages by parsing it and sends REST API requests to ServiceNow. * Attach the Lamda to the SNS topic * Set the credentials in AWS Secret Manager * Lamda function can reach the ServiceNow endpoint through API gateway by using HTTPS and Secure authentication |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;04/Jul/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cfb2e84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04h5f: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-26 06:17 | [13 empty] | 26/May/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 8:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting to get a exact tags to be passed to Ec2 instance to receive at service now. *New HTTPS endpoint will be shared by feroz for the production workloads.* | 25/Jun/25 8:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;From 24th June we had a call with feroz, where we expected to get the production servicenow endpoint by nest week to configure in SNS, hence waiting for same to start this user story. | 02/Jul/25 7:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PRODUCTION ServiceNow Instance: [https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws¦https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws] SNS topic is updated with a new subscription and backend prod integration is completed, unit test yet to start. | 04/Jul/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Right now the production environments like Backend, TM1, AirnavX accounts are integrated with the prod service now endpoint and SNS is configured to get the alerts. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-04 08:15
AM20-436 | Nexio AV ¦¦ Subnet creation | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | Medium | 1650863 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 16:09 | 2026-02-02 19:40 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Nexio AV application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Nexio AV and the configured based on the approved comms matrix |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 14/May/25 7:21 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-05-14 104729-20250514-051730.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100027 | 14/May/25 7:21 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-05-14 105036-20250514-052037.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100026 | 14/May/25 7:24 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052415.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100028 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-072934.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103886 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-073009.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103885 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-073047.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103887 | [12 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@77400985 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:t | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:40 | [13 empty] | 29/Apr/25 7:39 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Relevant subnet has been created, sending for review. | 02/May/25 12:22 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;IP Details ¦¦Nexio AV¦¦Production¦¦10.40.0.176/28¦¦10.40.0.176 - 10.40.0.191¦¦10.40.0.177 - 10.40.0.190¦¦14¦¦AZ1¦¦Â ¦¦ ¦¦Nexio AV (DR)¦Production¦10.40.0.192/28¦10.40.0.192 - 10.40.0.207¦10.40.0.193 - 10.40.0.206¦14¦Â ¦AZ2¦ ¦¦TG ATTACH-Subnet¦Production¦10.40.1.160/28¦10.40.1.160 - 10.40.1.175¦10.40.1.161 - 10.40.1.174¦14¦AZ1¦Â ¦ ¦¦TG ATTACH-Subnet¦Production¦10.40.1.176/28¦10.40.1.176 - 10.40.1.191¦10.40.1.177 - 10.40.1.190¦14¦Â ¦AZ2¦ Route table still need to cleaned up and updated properly. Assigning back the ticket to [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 07/May/25 6:21 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on route table cleanup. | 14/May/25 7:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets already created. IP CIDR Details for prod/DR ¦10.40.0.176/28¦10.40.0.176 - 10.40.0.191¦10.40.0.177 - 10.40.0.190¦14¦/28¦AZ1¦Â ¦ ¦10.40.0.192/28¦10.40.0.192 - 10.40.0.207¦10.40.0.193 - 10.40.0.206¦14¦/28¦Â ¦AZ2¦ Subnet info: !Screenshot 2025-05-14 104729-20250514-051730.png¦width=1117,height=580,alt="Screenshot 2025-05-14 104729-20250514-051730.png"! !Screenshot 2025-05-14 105036-20250514-052037.png¦width=1128,height=586,alt="Screenshot 2025-05-14 105036-20250514-052037.png"! Please review. | 14/May/25 7:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Attached route table screen shots. !image-20250514-052415.png¦width=1130,height=531,alt="image-20250514-052415.png"! | 19/May/25 11:08 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Action Item: Change the Name to Trellix AV from Nexio AV Correct the AZ for DR Route to be tested for correct routing Assigning back to Satya for correction | 19/May/25 6:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sankalp updated me to change NexioAV to Trellix AV. I will update and assign it to Sankalp. | 20/May/25 5:16 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation done and assigned for review, and it has been reassigned for modification and routing validation. Find below reviewer comments. Action Item: Change the Name to Trellix AV from Nexio AV(New requirement according to app name) Correct the AZ for DR (resource name change) Route to be tested for correct routing | 22/May/25 9:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on inputs modification has been done. !image-20250522-072934.png¦width=1103,height=563,alt="image-20250522-072934.png"! !image-20250522-073009.png¦width=1107,height=575,alt="image-20250522-073009.png"! Route Table: !image-20250522-073047.png¦width=1107,height=526,alt="image-20250522-073047.png"! Please check and review the same. | 30/May/25 2:45 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Review done Transitioning to PO Approval | 02/Jun/25 11:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [16 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-02 11:36
AM20-437 | AirNavX ¦¦ DR Setup and Backup | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772205 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 16:24 | 2026-01-15 17:06 |  | 2025-11-15 14:39 |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Informatica-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;14/Nov/25 8:19 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;230400 | ;14/Nov/25 8:20 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;28800 | ;14/Nov/25 3:37 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;57600 |  |  |  | 57600 | 0 | 316800 | 5.5 | 57600 | 0 | 316800 | [12 empty] | 14/Nov/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251114-061617.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1183951 | 14/Nov/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251114-061715.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1183950 | 14/Nov/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251114-061854.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1183952 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3d404a54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 18 | [95 empty] | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 |  | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | [65 empty] | YES | YES | 2025-09-08 07:57 | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | [12 empty] | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 17/Oct/25 11:18 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over reason - Blocked due to ongoing app installation issues, currently worked upon by app owner; post which this story will be progressed in subsequent sprint | 14/Nov/25 8:18 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;AirNavX DR setup completed as well as daily weekly backup has been configured the same working fine. Backup relvent: !image-20251114-061617.png¦width=612,alt="image-20251114-061617.png"! !image-20251114-061715.png¦width=589,alt="image-20251114-061715.png"! DR: !image-20251114-061854.png¦width=597,alt="image-20251114-061854.png"! | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-15 14:39
AM20-438 | PROS ¦¦ setup and validate SG and NACL | Done | 2 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1773949 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 15:22 | 2026-01-17 16:38 |  |  |  | 0 | As AWS network expert I would like to setup the security group and NACL for PROS so that access for Pros allow secure access to allow communication with its services while ensureing access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for PROSor related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1df9f068 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwq3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-25 15:31 | [13 empty] | 25/Sep/25 5:31 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SG and NACL setup has been completed, application ports relevant port need to be configured, this will be ready once test server setup process ready. | 09/Oct/25 4:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SG & NACL has been configured and handed over to customer. | 17/Oct/25 7:14 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-10-17 07:14
AM20-439 | TM1 ¦¦ Integration of AWS IAM roles with TM1 AWS Account Instance using JSON | Done | 10 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642068 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 17:07 | 2026-02-01 19:24 |  |  |  | 0 | As AWS expert, I would be integrating AWS IAM roles with TM1 Instance Acceptance criteria: * IAM roles are created successfully * Integration of defined IAM roles with TM1 instance so that user is able to access the TM1 instance. |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5190a6ea | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-09 07:30 | [13 empty] | 09/Jul/25 9:29 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Following are the details of the role created: role_arn = "arn:aws:iam::209479274829:role/TM1-IAMRole-EC2InstanceProfile" role_name = "TM1-IAMRole-EC2InstanceProfile" Account details: 209479274829 (SAA-TM1) Custom Role Details: The role covers the equivalent of â€œAmazonSSMManagedInstanceCoreâ€, basic CloudWatch Agent permissions, and general S3 access. _*NOTE*: THE FOLLOWING HAS BEEN ACHIEVED USING TERRAFORM._ | 09/Jul/25 9:30 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;.json file of the custom role is as follows: { Â "Version": "2012-10-17", Â "Statement": [ Â Â { Â Â Â "Sid": "SSMManagedInstanceCorePermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssm:DescribeAssociation", Â Â Â Â "ssm:GetDeployablePatchSnapshotForInstance", Â Â Â Â "ssm:GetDocument", Â Â Â Â "ssm:DescribeDocument", Â Â Â Â "ssm:GetManifest", Â Â Â Â "ssm:GetParameter", Â Â Â Â "ssm:GetParameters", Â Â Â Â "ssm:ListAssociations", Â Â Â Â "ssm:ListInstanceAssociations", Â Â Â Â "ssm:PutInventory", Â Â Â Â "ssm:PutComplianceItems", Â Â Â Â "ssm:PutConfigurePackageResult", Â Â Â Â "ssm:UpdateAssociationStatus", Â Â Â Â "ssm:UpdateInstanceAssociationStatus", Â Â Â Â "ssm:UpdateInstanceInformation" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "SSMMessageGatewayPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssmmessages:CreateControlChannel", Â Â Â Â "ssmmessages:CreateDataChannel", Â Â Â Â "ssmmessages:OpenControlChannel", Â Â Â Â "ssmmessages:OpenDataChannel" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "EC2MessagesPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ec2messages:AcknowledgeMessage", Â Â Â Â "ec2messages:DeleteMessage", Â Â Â Â "ec2messages:FailMessage", Â Â Â Â "ec2messages:GetEndpoint", Â Â Â Â "ec2messages:GetMessages", Â Â Â Â "ec2messages:SendReply" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "CloudWatchAgentPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "logs:CreateLogGroup", Â Â Â Â "logs:CreateLogStream", Â Â Â Â "logs:PutLogEvents", Â Â Â Â "logs:DescribeLogGroups", Â Â Â Â "logs:DescribeLogStreams", Â Â Â Â "cloudwatch:PutMetricData" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "S3AccessPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "s3:GetObject", Â Â Â Â "s3:PutObject", Â Â Â Â "s3:ListBucket" Â Â Â ], Â Â Â "Resource": "*" Â Â } Â ] } | 11/Jul/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed IAM roles is having required permissions | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-440 | TM1 ¦¦ Subnet creation using terraform | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Satya Varanasi | Medium | 1620359 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 13:28 | 2026-01-09 16:28 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for TM1 application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for TM1 and the configured based on the approved comms matrix |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-11 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a96537d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnn3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:53 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 04/Apr/25 10:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation got completed Manuel. As terraform not ready. While creating this TM1 subnets. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-07 10:11
AM20-441 | Terraform Development ¦¦ Define CloudWatch Agent config and Automate Agent Start via Terraform | Done | 20 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1661298 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-20 16:02 | 2026-01-20 17:36 |  |  |  | 0 | As Devops Engineer, I would like to define the CloudWatch Agentâ€™s configuration and Automate Cloud Watch Agent start using Terraform so that the metrics and logs it collects are consistent across environments Acceptance Criteria: * Terraform manages the agent config JSON file as a template * The config files includes, CPU, Memory, disk and Network metrics and application/system log files paths. * The file is stored locally or pushed to EC2 during provisioning via user_data * Terraform - provisioned EC2 instances start the CloudWatch agent on boot * The agent fetches the config file and start sending data to CloudWatch * Verification - Metrics and logs appear in CloudWatch console post launch |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7aab33b8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4h: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-11 06:40 | [13 empty] | 11/Jun/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;* The Terraform script for configuring and starting the CloudWatch agent is ready for both Linux and Windows instances. * Linux automation is working as expected. * Faced issues with Windows agent installation during EC2 provisioning. * Initial approach used user data to download and install the CloudWatch agent. * Encountered failure due to network not being ready at the time of user data execution. * Attempted to resolve this with a 60-second sleep delay, but it was unsuccessful. * New approach identified: using SSM documents to automate agent installation post-boot. * Will implement this alternative and move the changes to code review. * A meeting will be scheduled following successful implementation. | 16/Jun/25 10:03 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# *Used SSM Documents to Automate Agent Installation*Â * We leveraged *AWS SSM Run Command* documents instead of manual scripts or hardcoding logic.Â * Specifically, we used:Â * {{AWS-ConfigureAWSPackage}} to *install the CloudWatch Agent*Â * {{AmazonCloudWatch-ManageAgent}} to *configure and start the agent* using a *Parameter Store JSON config* named {{/Windows_Monitor_CW}}.Â Â *ðŸ”¹ 2. Embedded SSM Associations in Terraform*Â * Inside our *main EC2 Terraform project*, we embedded two {{aws_ssm_association}} resources:Â * *install_cwagent_windows* â€“ installs CloudWatch agentÂ * *configure_cwagent_windows* â€“ tells the agent to pull its config from {{/Windows_Monitor_CW}} in SSM Parameter Store and start itÂ * Both associations *target EC2 instances by tag*: {{CWAgent = EnabledÂ }} * The EC2 instances were pre-tagged via Terraform to ensure automatic targetingÂ Â *ðŸ”¹ 3. Created a Third Association to Force Re-fetch Config*Â * In some cases, the agent might need to re-fetch its config after the EC2 instance is up and the services are stable.Â * So we created a *third SSM association*: {{force_fetch_start_agentÂ }} * Uses {{AWS-RunPowerShellScript}} to run:Â {{& "C:\Program Files\Amazon\AmazonCloudWatchAgent\amazon-cloudwatch-agent-ctl.ps1" -a fetch-config -m ec2 -c ssm:/Windows_Monitor_CW -sÂ }} Â * This *manually triggers the fetch* of the config from SSM Parameter Store and starts the agent again if neededÂ Â *ðŸ”¹ 4. Split This Trigger into a Separate Terraform Directory*Â * To keep your deployment clean and *modular*, we:Â * Created a new folder: {{terraform/cwagent-trigger/Â }} * Placed only the {{force_fetch_start_agent}} logic in this moduleÂ * Why?Â * This allows you to *run it manually or conditionally* after core EC2 and SSM setups are completeÂ * Ensures *clean execution ordering* and better control in CI/CDÂ * Prevents early execution before the agent is even installedÂ Â *ðŸ”¹ 5. Designed for Platform-Specific Control*Â * Logic is gated with:Â {{count = var.platform == "windows" && var.enable_windows_ssm_association ? 1 : 0Â }} Â * Ensures this entire operation is *executed only for Windows instances*, as Linux would follow a different path.Â | 24/Jun/25 6:55 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;cloud watch agent installation is done using terraform script, have enabled only memory and disk utilization as of now. | 29/Jun/25 8:14 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:15
AM20-442 | Informatica ¦¦ connectivity with Sales force, SAP Raise and EDW with test server | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1751445 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 20:06 | 2026-01-16 22:36 |  |  |  | 0 | As product Owner I would like to establish seamless connectivity between Informatica server and saleforce/Terradata so that the functinality does not break Acceptance Criteria: Informatica server connectivity established successfully with both Salesforce and Terradata TGW attachments, route tables and propogation allows reachability from Informatica to Salesforce and Terraform CIDR only Pripary path (DX or VPN) with secondary path tested, failover keeps sessions with degraded SLO Path MTU validated without fragmentation affection FTP data channels Passive FTP is enforced in AWS client Each FTP server exposes a fixed passive port range and publish it on the client Security groups: egress from AWS app to on-prem TCP21 the agreed passive range; return traffic allowed on-prem firewall allows the Aws static egress IP for TCP 21 and passive range FTP ALG/instapection behavour documented and validated Server authentication: username/password or TLS client auth are stored in secret manager no reliance on public IP, all traffic stays private via TGW Name resolution works both ways AWS can resolve slaesforce.corp and terradata.corp via resolver outbound rules, negative lookups dont hit public DNS TGW flow logs show accepted flows for TCP 21 and passive port Cloudwatch alarm on tunnel/BGP state, connection failures, repeated 4XX/%XX FTP responses, transfer timeouts Application log capture: server filename, size, checksum, duration, success/fail code, logs centralized Concurrency limited tuned so both servers can be hit in parallel without timeouts SLO defined (ex: sustainable throughput) and documented Checksum validated after transfer VPN/DX failover tested mid-transfer client resumes without manual intervention drift detection enabled |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5cf8baca | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ddx3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 06:25 | [13 empty] | 12/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Relevant flows has been added under application flows. Once implementation done i will work further. | 25/Aug/25 8:55 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Spill over Reason: Still comms under approval and implementation so this need to action after comms implementation. | 08/Sep/25 10:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;EDW side issue got fixed and working, right now SAP raise Sita compass side need to fix. I have scheduled troubleshooting call with relevant stake holder towards fixing. Still connectivity is not resolved, so i am not closed this story and it is moving to current sprint. | 12/Sep/25 8:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SAP Raise side SR has been logged, it will be implemented today. | 19/Sep/25 2:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SAP rise team has been configured NAC,SG and Routing but still connectivity issue persists, while checking traceroute, the request moving out to SAP Rise gateway but not troughing to shared VPC & vice versa. Further validation there is No routes advertised from DX side, engaged SAP team asking how SAP rise will be connected but they are not sure. Finally we have identified SAP rise is connecting via Direct connect, this was analyzed with the help of current working connection. | 19/Sep/25 2:49 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Notified network team to advertise complete shared VPC Prod and Dev vpc ranges to avoid future issues. 10.40.0.0/18 and 10.42.0.0/21. | 19/Sep/25 2:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network team has bee advertise the range to SAP rise direct connect, after advertise the connectivity has been fixed. | 19/Sep/25 2:51 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;ticket information: Ticket ID 1163452562 & 1163792032 AWS Connectivity - FIREWALL RULES REQUIRED FOR CUSTOMER INFORMATICA & RISE COMMUNICATION | 19/Sep/25 2:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;I am resolving the story as connectivity has been fixed. | [21 empty] | Done | 2025-09-22 08:49
AM20-443 | Nexio AV ¦¦ Life Cycle Management ¦¦ Log Retention | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1730232 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 14:10 | 2026-02-01 17:32 |  |  |  | 0 | As Product Owner I would like to establish the life cycle management for log retention specific to Nexio AV account to have defined log retention policies for all critical log sources so that we can meet compliance, enable forensic investigation and optimize storage Acceptance Criteria: log retention policy is defined per account * Production env. - log retention period 90 days Â *Please note* that post retention period, these logs can either be deleted or moved to cold storage, which can be configured based on your confirmation however, data retrieval from cold storage is charged additionally. * All critical log sources are covered - cloudtrail, VPC flow logs, cloudwatch logs and other tools must be retained as per policy * Log retention is automated - log groups are created when they are detected * Logs reaches its retention threshold when the time expires it should either be deleted or moved to archive (cold storage) * Retention policy is editable so that it can be configured accordingly |  | Aravind Raj | Diksha Koul | Onkar Mirajkar | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [27 empty] | 06/Aug/25 9:45 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;Screenshot 2025-08-06 131412.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136044 | 29/Jul/25 9:39 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250729-073927.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1132067 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@410ec9e6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bn77: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-29 07:40 | [13 empty] | 29/Jul/25 9:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;No S3 bucket resource has been created on NEXIO AV as of now for retention period. !image-20250729-073927.png¦width=1545,height=507,alt="image-20250729-073927.png"! | 31/Jul/25 12:53 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Created Log metrics for NEXIO AV | 01/Aug/25 8:14 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created one life cycle rule for the deletion of logs after 90 days need to review it with Aravind. | 01/Aug/25 9:00 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;we will be having an confirmation email from the client and will be then implementing the retention life cycle rule on the centralized account as Logs will store to cold storage and retention days will be 90 days. | 05/Aug/25 11:11 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Retention rule has been created in the Log Archive account on S3 all environment as 90 days and also after 90 days it will get moved to cold storage. | 06/Aug/25 9:45 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!Screenshot 2025-08-06 131412.png¦width=934,height=354,alt="Screenshot 2025-08-06 131412.png"! Attaching the screenshot of the changes we have done in the log archive account. | 08/Aug/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Transition rule in place for centralized cloud trail logs to send to glacier after 90 days. | 11/Aug/25 7:59 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 07:59
AM20-444 | Nexio AV ¦¦ Subnet creation | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | Medium | 1650863 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 14:04 | 2026-01-19 14:45 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Nexio AV application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Nexio AV and the configured based on the approved comms matrix |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 14/May/25 7:21 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-05-14 104729-20250514-051730.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100027 | 14/May/25 7:21 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-05-14 105036-20250514-052037.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100026 | 14/May/25 7:24 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052415.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100028 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-072934.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103886 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-073009.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103885 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-073047.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103887 | [12 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@77400985 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:t | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:40 | [13 empty] | 29/Apr/25 7:39 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Relevant subnet has been created, sending for review. | 02/May/25 12:22 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;IP Details ¦¦Nexio AV¦¦Production¦¦10.40.0.176/28¦¦10.40.0.176 - 10.40.0.191¦¦10.40.0.177 - 10.40.0.190¦¦14¦¦AZ1¦¦Â ¦¦ ¦¦Nexio AV (DR)¦Production¦10.40.0.192/28¦10.40.0.192 - 10.40.0.207¦10.40.0.193 - 10.40.0.206¦14¦Â ¦AZ2¦ ¦¦TG ATTACH-Subnet¦Production¦10.40.1.160/28¦10.40.1.160 - 10.40.1.175¦10.40.1.161 - 10.40.1.174¦14¦AZ1¦Â ¦ ¦¦TG ATTACH-Subnet¦Production¦10.40.1.176/28¦10.40.1.176 - 10.40.1.191¦10.40.1.177 - 10.40.1.190¦14¦Â ¦AZ2¦ Route table still need to cleaned up and updated properly. Assigning back the ticket to [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 07/May/25 6:21 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on route table cleanup. | 14/May/25 7:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets already created. IP CIDR Details for prod/DR ¦10.40.0.176/28¦10.40.0.176 - 10.40.0.191¦10.40.0.177 - 10.40.0.190¦14¦/28¦AZ1¦Â ¦ ¦10.40.0.192/28¦10.40.0.192 - 10.40.0.207¦10.40.0.193 - 10.40.0.206¦14¦/28¦Â ¦AZ2¦ Subnet info: !Screenshot 2025-05-14 104729-20250514-051730.png¦width=1117,height=580,alt="Screenshot 2025-05-14 104729-20250514-051730.png"! !Screenshot 2025-05-14 105036-20250514-052037.png¦width=1128,height=586,alt="Screenshot 2025-05-14 105036-20250514-052037.png"! Please review. | 14/May/25 7:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Attached route table screen shots. !image-20250514-052415.png¦width=1130,height=531,alt="image-20250514-052415.png"! | 19/May/25 11:08 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Action Item: Change the Name to Trellix AV from Nexio AV Correct the AZ for DR Route to be tested for correct routing Assigning back to Satya for correction | 19/May/25 6:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sankalp updated me to change NexioAV to Trellix AV. I will update and assign it to Sankalp. | 20/May/25 5:16 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation done and assigned for review, and it has been reassigned for modification and routing validation. Find below reviewer comments. Action Item: Change the Name to Trellix AV from Nexio AV(New requirement according to app name) Correct the AZ for DR (resource name change) Route to be tested for correct routing | 22/May/25 9:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on inputs modification has been done. !image-20250522-072934.png¦width=1103,height=563,alt="image-20250522-072934.png"! !image-20250522-073009.png¦width=1107,height=575,alt="image-20250522-073009.png"! Route Table: !image-20250522-073047.png¦width=1107,height=526,alt="image-20250522-073047.png"! Please check and review the same. | 30/May/25 2:45 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Review done Transitioning to PO Approval | 02/Jun/25 11:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [16 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-02 11:36
AM20-445 | Comms metrics creation for Informatica server | Done | 6 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642050 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 20:56 | 2026-01-27 22:00 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for Informatica server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability created * Low level design documentation including proposed architecture completed Server names to be provided by [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] |  | Harsh Chandra | Satya Varanasi | Sumit Nikam |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3c3333a4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0r: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-17 15:34 | [13 empty] | 17/Apr/25 5:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Due to other activities i am not able to manage this task in this sprint. it required to move other sprint. | 07/May/25 6:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;VDC side DEV/PROD comms has been created, Working on sita side and the same will be ready on Thursday EOD | 12/May/25 7:52 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;comms has been completed, i will initiate review communication | 16/May/25 8:39 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Comm matrix has been verified as per available information. | 18/May/25 2:37 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:37
AM20-446 | Cost Anomaly Detection | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1719961 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 18:50 | 2026-01-25 21:50 |  |  |  | 0 | As AWS expert I would like to report any sudden spike in the cost against any of the application or accounts so that the concerned team can validate the reasoning and take appropriate action to ascertain reasons and take reactive measures Acceptance Criteria: < pre-req> : * Ensure all accounts are part of AWS Org. with consolidated billing enabled * Use the Payer9 account to see all account cost level Acceptance Criteria * Cost anomaly detection is enabled successfully * Anomaly monitor is is enabled * Anomaly subscription is successfully enabled using SNS * CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage * Use Amazon Athena or quicksight for stakeholder friendly dashboards * Graphical representation of the cost to be captured |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4d6b831e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0attv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-18 06:07 | [13 empty] | 18/Jul/25 8:07 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;* CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm *---Done* * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage *---Done* Cost anomaly detection is enabled successfully *---Done* * Anomaly monitor is is enabled *---Done* * Anomaly subscription is successfully enabled using SNS *---Done* | 23/Jul/25 8:08 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working on Amazon Athena or quicksight for stakeholder friendly dashboards ---*Done* | 24/Jul/25 7:38 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;As discussed with Yashwant, we need to track cost anomalies for specific AWS services and implement it separately for each account. | 24/Jul/25 8:57 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Cost anomalies detction for specific AWS services and implement it separately for each account. *---Done* Updated for Only TM1 account.(As discussed with Yashwant) | 28/Jul/25 9:58 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:58
AM20-447 | Patch Management ¦¦ Dashboard Enhancement | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1746156 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 19:10 | 2026-01-16 22:39 |  |  |  | 0 | As Product manager compliance dashboard needs to be enhance and should covered details of patch file Acceptance Criteria: Compliance dashboard need to patch details and account details |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4159e3f0 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cz63: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 20:35 | [13 empty] | 18/Aug/25 10:34 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Update for Patch Manager Monitoring, in the compliance bucket there are 3 folders created after creating the resource data sync but not for the target acc we need. i have changed certain policies and also added some permissions both in security as well as dev acc. I am waiting for the data to pop up and also i can trigger data collection forcefully via aws cloudshell command but i do not have access i have intimated Aravind for permission addition. and the data that is being collected is basically json and that is the format that we need for it to be visualized in cloudwatch. | 25/Aug/25 8:52 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;spillover: the data sync which has been created in the management acc theoretically should be able to fetch the summaries from target account and sync that data in the s3 bucket in central account. the steps that were tried to force a sync were: {code:json}Check if the Instance is Managed by Systems Manager Check Current Associations Check Current Inventory Data Create the Inventory Association Verify Association Creation Check Association Status Monitor Association Execution Check for Updated Inventory Data{code} All of these were done and created an association manually for it to be populated into s3 bucket yet it did not work. the permission policies are provided yet the target account data is not being synced. the issue was that resource data sync must be created in each of the target account which was earlier thought as not needed. have created ressource data sync and waiting for the data to be populated. | 28/Aug/25 8:34 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Spillover Revised Comment: I was troubleshooting the resource data sync that i created since theoretically, resource data sync in the management account was enough. After rigorous attempts to fix the issue and trying to find out the workarounds they all failed. At the end of the week, close to sprint closure I found the solution and applied it and the solution worked. Hence, the delay and also for the data to populate into the intended bucket it sometime takes 10-12 hrs. | 03/Sep/25 8:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# The Resource Data Sync has been troubleshoot correctly and is working as intended. # Lambda function has been created in backend-dev account so that it can brand all the instances as non-compliant initially. # EventBridge has been configured as such when any new instance is provisioned it shall be flagged as non-compliant using the lambda function mentioned in point no.2. # The data in S3 is being used to project it to CloudWatch and that is being do using a Lambda function which will create metrics from the data in S3. # CloudWatch Dashboard is created such that it will have visual data segregated acc to the Acc Ids. (which was requirement by Bhavish). | 08/Sep/25 6:35 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;need demo | 08/Sep/25 8:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: The story was completed sufficing all the acceptance criteria. Demo was not done due to unavailability, hence scheduling the demo for 9/9/2025 considering everyoneâ€™s availability. | 11/Sep/25 9:12 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Demo was provided. The methodology and implementation was agreed upon and approved. There was an ask to involve another accounts, in order to check the workability. The accounts addition was done successfully and the data is presented on the custom dashboard as well. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:20
AM20-448 | Restrict Admin access to VOIS team by creating dedicated IAM role | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Medium | 1736354 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 21:03 | 2026-01-11 21:35 |  |  |  | 0 | As Product Owner, I want to restrict VOIS team to have Admin role so that all of them cannot be superseded rights and bring more control on AWS management Acceptance criteria: * IAM role to be created for everyone except Sankalp and Aravind from AWS perspective * IAM role for network creation to be created and role assign to Satya * IAM role for rest of team members is of developer |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6edd432e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0c5zn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 06:20 | [13 empty] | 06/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have shared the Excel with the user list to team, upon there confirmation ill start creating custom policy with user groups. | 08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;¦UserID¦IAM user¦UserGroup¦IAM Role¦ ¦raja0001¦Aravind¦VOIS_Admin¦No changes, use existing roles itself¦ ¦rais0003¦Sankalp¦VOIS_Admin¦No changes, use existing roles itself¦ ¦SatyasairamV¦SatyaSairam¦VOIS_Admin¦No changes, use existing roles itself¦ ¦godir001¦Ravinder¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦kiraj001¦Jitender¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Sanjot¦Sanjot¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦nikas001¦Sumit¦VOIS_Admin¦No changes, use existing roles itself¦ ¦FaisalSayed¦Faizal¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SanketKale¦Sanket¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦pathp002¦Pankaj¦VOIS_DBAdmin_Usergroup¦AWS_VOIS_DBAdmin_Role¦ ¦onkar¦Onkar¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦DikshaK¦Diksha¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SatyabrataS¦SatyaBrata¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Shreyash¦Shreyash¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Harsh¦Harsh¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Yashwant¦Yashwant¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Utkarsh¦Utkarsh¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ Â Â Access to User group given as below, ¦VOIS_InfraAdmin_Usergroup¦VOIS_DevOpsAdmin_Usergroup¦VOIS_DBAdmin_Usergroup¦ ¦VPC FullAccess¦CodeBuild FullAccess¦RDS Full Access¦ ¦EC2 FullAccess¦CodePipeline FullAccess¦DMS Full Access¦ ¦S3 FullAccess¦EKS FullAccess¦IAM Full Access¦ ¦CloudWatch FullAccess¦EC2 except delete¦CloudTrail except delete¦ ¦RDS FullAccess¦S3 FullAccess¦KMS except delete¦ ¦IAM FullAccess¦CloudWatch except delete¦CloudWatch except delete¦ ¦CloudTrailFullAccess¦RDS except delete¦Read only¦ ¦MacieFullAccess¦IAM FullAccess¦ ¦ ¦GuardDutyFullAccess¦System managerFullAccess¦ ¦ ¦SecurityHubFullAccess¦LambdaFullAccess¦ ¦ ¦System managerFullAccess¦Event bridgeFullAccess¦ ¦ ¦LambdaFullAccess¦CloudTrail except delete¦ ¦ ¦KMSFullAccess¦Read only¦ ¦ ¦ACMFullAccess¦Secrets managerFullAccess¦ ¦ ¦Aws ConfigFullAccess¦SNSFullAccess¦ ¦ ¦Event bridgeFullAccess¦SESFullAccess¦ ¦ ¦InspectorFullAccess¦ECR FullAccess¦ ¦ ¦SupportFullAccess¦KMS except delete¦ ¦ ¦SNSFullAccess¦Â ¦ ¦ ¦SESFullAccess¦ ¦ ¦ ¦ReadOnly¦ ¦ ¦ ¦Secrets managerFullAccess¦ ¦ ¦ ¦ECRFullAccess¦ ¦ ¦ Â Users have access to the below AWS accounts, Â ¦AWS Account¦Account Name¦ ¦300204747992¦Audit¦ ¦730335236533¦Security¦ ¦080284287007¦LogArchive¦ ¦339712943527¦Network¦ ¦864899875361¦SharedServices¦ ¦585768167545¦SharedVpcDev¦ ¦253490777663¦SharedVpcPreprod¦ ¦820242899278¦SharedVpcProd¦ ¦746669190453¦Backend dev¦ ¦216989128782¦Backend Preprod¦ ¦396608788916¦Backend Prod¦ ¦209479274829¦Tm1¦ ¦345594574792¦AirNAVx¦ ¦536697265099¦NexioAV¦ | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-449 | MQ ¦¦ Application comms metrics preparation and implementation | To Do | 0 | None( Backlog) |  |  | Satya Varanasi | Medium | 1795166 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 20:21 | 2026-01-11 23:42 |  |  |  | 0 | AS Network expertise I want to define, track and baseline and validate network communication metrics including subnets, connectivity with downstream/3rd party applications and network rules so that the applicationcan be migrated to the cloud without connectivity failures, security gaps or performance degradation Acceptance Criteria: Application specific subnets (CIDR range, VPC design, Private/public allocation) documented Overlapping IP ranges validated against downstream and 3rd party integrations subnet utilization % captured E2E connectivity map prepared: application <->DB<->downstream services <->3rd party APIs Latency, Packet loss, throughput baselined from VDC/onprem to cloud traget points DNS resolution | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3842a4ec | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g1 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:35
AM20-450 | TM1 ¦¦ Integration of AWS IAM roles with TM1 AWS Account Instance using JSON | Done | 10 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642068 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 19:42 | 2026-01-09 23:11 |  |  |  | 0 | As AWS expert, I would be integrating AWS IAM roles with TM1 Instance Acceptance criteria: * IAM roles are created successfully * Integration of defined IAM roles with TM1 instance so that user is able to access the TM1 instance. |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5190a6ea | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-09 07:30 | [13 empty] | 09/Jul/25 9:29 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Following are the details of the role created: role_arn = "arn:aws:iam::209479274829:role/TM1-IAMRole-EC2InstanceProfile" role_name = "TM1-IAMRole-EC2InstanceProfile" Account details: 209479274829 (SAA-TM1) Custom Role Details: The role covers the equivalent of â€œAmazonSSMManagedInstanceCoreâ€, basic CloudWatch Agent permissions, and general S3 access. _*NOTE*: THE FOLLOWING HAS BEEN ACHIEVED USING TERRAFORM._ | 09/Jul/25 9:30 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;.json file of the custom role is as follows: { Â "Version": "2012-10-17", Â "Statement": [ Â Â { Â Â Â "Sid": "SSMManagedInstanceCorePermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssm:DescribeAssociation", Â Â Â Â "ssm:GetDeployablePatchSnapshotForInstance", Â Â Â Â "ssm:GetDocument", Â Â Â Â "ssm:DescribeDocument", Â Â Â Â "ssm:GetManifest", Â Â Â Â "ssm:GetParameter", Â Â Â Â "ssm:GetParameters", Â Â Â Â "ssm:ListAssociations", Â Â Â Â "ssm:ListInstanceAssociations", Â Â Â Â "ssm:PutInventory", Â Â Â Â "ssm:PutComplianceItems", Â Â Â Â "ssm:PutConfigurePackageResult", Â Â Â Â "ssm:UpdateAssociationStatus", Â Â Â Â "ssm:UpdateInstanceAssociationStatus", Â Â Â Â "ssm:UpdateInstanceInformation" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "SSMMessageGatewayPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssmmessages:CreateControlChannel", Â Â Â Â "ssmmessages:CreateDataChannel", Â Â Â Â "ssmmessages:OpenControlChannel", Â Â Â Â "ssmmessages:OpenDataChannel" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "EC2MessagesPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ec2messages:AcknowledgeMessage", Â Â Â Â "ec2messages:DeleteMessage", Â Â Â Â "ec2messages:FailMessage", Â Â Â Â "ec2messages:GetEndpoint", Â Â Â Â "ec2messages:GetMessages", Â Â Â Â "ec2messages:SendReply" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "CloudWatchAgentPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "logs:CreateLogGroup", Â Â Â Â "logs:CreateLogStream", Â Â Â Â "logs:PutLogEvents", Â Â Â Â "logs:DescribeLogGroups", Â Â Â Â "logs:DescribeLogStreams", Â Â Â Â "cloudwatch:PutMetricData" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "S3AccessPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "s3:GetObject", Â Â Â Â "s3:PutObject", Â Â Â Â "s3:ListBucket" Â Â Â ], Â Â Â "Resource": "*" Â Â } Â ] } | 11/Jul/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed IAM roles is having required permissions | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-451 | Transit Gateway setup for Dev environment | Done | 6 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1702418 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 12:48 | 2026-02-04 14:13 |  |  |  | 0 | As Network Expert, I would be able to setup Transit network gateway for Dev environment Acceptance Criteria: Transit Gateway is provisioned successfully in Dev environment. |  | Aravind Raj | Satya Varanasi |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [13 empty] | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132834.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121470 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132924.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121472 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133228.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121473 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133337.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121469 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133439.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121471 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67c2563b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i095nv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-01 16:49 | [13 empty] | 01/Jul/25 6:49 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;There is no Preprod env for 20+ app migration list, hence we are not setting up Preprod TG attachment, in case needed near future we will setup according to requirement. In this sprint we will setup TG attach for Dev env. | 03/Jul/25 3:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Common TG Attach has be setup on shared VPC dev Account and tested internet connectivity via informatica DEV subnet. !image-20250703-132834.png¦width=1306,height=662,alt="image-20250703-132834.png"! !image-20250703-132924.png¦width=1204,height=668,alt="image-20250703-132924.png"! TG-Attach subnets: !image-20250703-133228.png¦width=1243,height=475,alt="image-20250703-133228.png"! TG attachment details. !image-20250703-133337.png¦width=1189,height=448,alt="image-20250703-133337.png"! Subnet associations !image-20250703-133439.png¦width=1215,height=611,alt="image-20250703-133439.png"! | 04/Jul/25 12:05 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed, test server is working with internet. | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-04 12:05
AM20-452 | PROS¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773953 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 21:50 | 2026-01-13 23:48 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4ce03565 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:04 | [13 empty] | 24/Sep/25 8:04 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS migration agent comms has been implemented. SAA = REQ0056503 (CHG0067695) CSOC = CHR0027812 | 25/Sep/25 5:24 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still CSOC under approval, also we have identified as some miss match in Agent Comms. I have updated and shared to Wanda for CSOC updation. | 06/Oct/25 8:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over - Comms implementation delayed from SAA, hence will be spilled over and worked upon in subsequent sprint | 09/Oct/25 4:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration agent comms has been implemented and agent has been installed n all 3 PROS servers, Created test instance and handover to customer for testing. | 17/Oct/25 7:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:16
AM20-453 | IAM roles need to created based on LLD. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Satya Varanasi | Medium | 1832050 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Satya Varanasi | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Satya Varanasi | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 2026-01-18 20:03 | 2026-01-18 20:47 |  |  |  | 0 | IAM roles need to be created. Â·Â Â Â Â Â Â Â IAM-based access with predefined roles: oÂ Â *DNSAdmin*Â â€“ Full Route 53 management. oÂ Â *DNSOperator*Â â€“ Modify records, no zone deletions. oÂ Â *DNSViewer*Â â€“ Read-only access. |  | Faisal Sayed | Satya Varanasi |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 |  |  |  |  | ;12/Nov/25 10:19 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fec0f31 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mkiz: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:41 | [13 empty] | 12/Nov/25 6:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Update* * Permission policies for *DNS Admin*, *DNS Operator*, and *DNS Viewer* have been configured. * These will be implemented in the *Management Account (ID: 195973603339)* after approval from *Staya Sir*. h3. *Next Steps* * Schedule a call with *Staya Sir* to review and obtain approval for policy implementation. * Post-approval, apply the policies in the Management Account and validate access controls. | 12/Nov/25 10:19 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Call has been scheduled and IAM roles have been successfully created. Moving the item to *Staya Sirâ€™s review bucket* and updating the status to *In Review*. | 14/Nov/25 8:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Roles has been created according to LLD on main account. | [24 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-14 08:10
AM20-454 | PROS¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773953 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 13:48 | 2026-01-15 14:37 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4ce03565 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:04 | [13 empty] | 24/Sep/25 8:04 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS migration agent comms has been implemented. SAA = REQ0056503 (CHG0067695) CSOC = CHR0027812 | 25/Sep/25 5:24 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still CSOC under approval, also we have identified as some miss match in Agent Comms. I have updated and shared to Wanda for CSOC updation. | 06/Oct/25 8:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over - Comms implementation delayed from SAA, hence will be spilled over and worked upon in subsequent sprint | 09/Oct/25 4:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration agent comms has been implemented and agent has been installed n all 3 PROS servers, Created test instance and handover to customer for testing. | 17/Oct/25 7:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:16
AM20-455 | MQ-PROD ¦¦Setup Subnet, NACL and SG Creation and Validation | Done | 3 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1794109 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 14:50 | 2026-02-03 18:38 |  | 2025-10-31 09:34 |  | 0 | As AWS network expert I would like to setup the security group and NACL for MQ so that access for MQ allow secure access to allow communication with its services while ensuring access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for MQ or related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [13 empty] | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090000.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175254 | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090022.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175253 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@680e7164 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0i6ob: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 17 | [97 empty] | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [65 empty] | YES | YES | 2025-10-17 09:19 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [12 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 27/Oct/25 4:05 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working on it. | 30/Oct/25 11:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to requirement i have done platform setup. Subnets: ¦Subnet address¦Range of addresses¦Useable IPs¦Hosts¦Divide¦Used Status¦App Name¦ ¦10.40.0.224/28¦10.40.0.224 - 10.40.0.239¦10.40.0.225 - 10.40.0.238¦14¦Divide¦Done¦MQ PROD PRIVATE¦ ¦10.40.0.240/28¦10.40.0.240 - 10.40.0.255¦10.40.0.241 - 10.40.0.254¦14¦Divide¦Done¦MQ PROD PUBLIC¦ ¦10.40.1.32/28¦10.40.1.32 - 10.40.1.47¦10.40.1.33 - 10.40.1.46¦14¦Divide¦Done¦MQ PROD DR¦ ¦10.40.1.48/28¦10.40.1.48 - 10.40.1.63¦10.40.1.49 - 10.40.1.62¦14¦Divide¦Done¦MQ PROD DR¦ Subnets screen: !image-20251030-090022.png¦width=597,alt="image-20251030-090022.png"! EC2 connectivity screen: !image-20251030-090000.png¦width=597,alt="image-20251030-090000.png"! | 31/Oct/25 9:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though MQ migration is put on hold however since the objective and acceptance criteria is met, approving the User story to close | [26 empty] | Done | 2025-10-31 09:34
AM20-456 | PROS¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773953 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 13:50 | 2026-01-17 14:56 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4ce03565 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:04 | [13 empty] | 24/Sep/25 8:04 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS migration agent comms has been implemented. SAA = REQ0056503 (CHG0067695) CSOC = CHR0027812 | 25/Sep/25 5:24 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still CSOC under approval, also we have identified as some miss match in Agent Comms. I have updated and shared to Wanda for CSOC updation. | 06/Oct/25 8:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over - Comms implementation delayed from SAA, hence will be spilled over and worked upon in subsequent sprint | 09/Oct/25 4:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration agent comms has been implemented and agent has been installed n all 3 PROS servers, Created test instance and handover to customer for testing. | 17/Oct/25 7:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:16
AM20-457 | Lambda function to observe state in cloudwatch alarms configured for monitoring other lambda | Done | 2 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1812682 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 13:43 | 2026-02-05 15:20 |  | 2025-10-31 17:23 |  | 0 | As Product manager I would like to create Lambda function to observe state in cloudwatch alarms configured for monitoring other lambda function and send Â alert payload to servicenow as per the shared format to servicenow so that any failure of lamda is captured and remediation can be initiated. # Create Eventbridge to monitor the state change in alarm. # Create Lambda function to send alarm notifications to ServiceNow when threshold is breached. # Configure event bridge as the trigger for lambda function |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;31/Oct/25 11:21 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f18c499 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kag3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-27 04:51 | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 27/Oct/25 6:51 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will review the description & configuration needs and will connect with Shreyash for getting more clarity. Once I get the whole picture will move the story to In Progress. | 31/Oct/25 11:20 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Create Eventbridge to monitor the state change in alarm. - Done # Create Lambda function to send alarm notifications to ServiceNow when threshold is breached. - Done # Configure event bridge as the trigger for lambda function - Done Tested it with a test alarm event. [~accountid:712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8] | 31/Oct/25 5:23 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though no demo was provided, based on Faisal comments approving it. | [27 empty] | Done | 2025-10-31 17:23
AM20-458 | Backup Server ¦¦ Security compliance implementation | Done | 3 | Sprint 7 | 2025-06-09 | 2025-06-20 | Aravind Raj | Medium | 1681806 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 20:02 | 2026-01-15 22:01 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Backup Server *Acceptance Criteria*: * Renaming of PROS account to Back-Up Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 14400 | 43200 | 1 | 43200 | 14400 | 43200 | [12 empty] | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250612-153959.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1113715 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@48024563 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-09 05:41 | [13 empty] | 09/Jun/25 7:41 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will start working on enabling security frameworks like CIS, NIST, AWS FSBP. | 10/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled controls, will be working on the controls remediation. | 11/Jun/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;controls are implemented waiting for the security score to be update Â· | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CIS, NIST and FSBP controls were enabled and required controls remediated. !image-20250612-153959.png¦width=1279,height=626,alt="image-20250612-153959.png"! | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-12 17:41
AM20-459 | PROS¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773953 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 12:26 | 2026-01-17 15:36 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4ce03565 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:04 | [13 empty] | 24/Sep/25 8:04 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS migration agent comms has been implemented. SAA = REQ0056503 (CHG0067695) CSOC = CHR0027812 | 25/Sep/25 5:24 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still CSOC under approval, also we have identified as some miss match in Agent Comms. I have updated and shared to Wanda for CSOC updation. | 06/Oct/25 8:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over - Comms implementation delayed from SAA, hence will be spilled over and worked upon in subsequent sprint | 09/Oct/25 4:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration agent comms has been implemented and agent has been installed n all 3 PROS servers, Created test instance and handover to customer for testing. | 17/Oct/25 7:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:16
AM20-460 | Security Hardening Audit and Analysis for FLYSAA Backend | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Sumit Nikam | Medium | 1886488 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 13:16 | 2026-01-16 14:27 | 2026-01-08 08:41 |  |  | 0 | As an Internal Auditor, I want to review EKS control plane security configurations across all production accounts, IAM authentication and Kubernetes RBAC mappings, Audit Node & Worker Security Controls, Audit Network Security & Traffic Controls, Audit Pod & Workload Security Posture, Audit Secrets Management & Data Protection So that gaps against AWS and Kubernetes security benchmarks are identified, Acceptance Criteria * EKS cluster version documented per account * API endpoint exposure (public/private) recorded * Allowed CIDR ranges captured * Control plane logging status verified * Secrets encryption (KMS / default) documented * Evidence stored (CLI output / console screenshots) * Gaps mapped to CIS EKS benchmark controls * IAM users vs roles usage documented * aws-auth ConfigMap reviewed * Cluster-admin bindings identified * Namespace vs cluster scoped access recorded * IRSA adoption status captured * Evidence collected (RBAC YAML, IAM role list) * High-risk access clearly flagged * Node type (Managed / Self-managed / Fargate) documented * AMI patching and update mechanism recorded * Node IAM role permissions reviewed * IMDS version (v1/v2) verified * SSH access presence documented * Evidence retained (Launch Template / ASG config) * NetworkPolicy enforcement status recorded * Default deny posture verified * Ingress exposure documented (public/private) * WAF & TLS configuration reviewed * Egress paths documented * Evidence retained (manifests, ALB config) * Pod Security Standards status documented * Privileged pods identified * Containers running as root recorded * Linux capabilities usage reviewed * Secrets usage method documented * Evidence retained (pod specs, namespace labels) * Image registries used documented * Image scanning availability verified * CVE handling process reviewed * Image tagging strategy recorded * Admission control presence documented * Evidence captured (CI logs, ECR settings) * Secret storage mechanisms documented * Encryption at rest/in transit verified * Secrets rotation capability reviewed * Backup and restore process recorded * Evidence retained (KMS config, secret manifests) * Control plane & workload logs documented * Log centralization status verified * Runtime threat detection presence reviewed * Alerting and escalation paths documented * SIEM integration status captured * Evidence retained (CloudWatch, GuardDuty) * GitOps vs manual change model documented * Policy enforcement tooling identified * Change approval records reviewed * Ownership & RACI clarity assessed * CIS / ISO alignment documented * Findings categorized (High / Medium / Low) * Risk statement defined for each gap * Affected accounts listed * Evidence referenced * Recommendations documented separately * Executive summary prepared |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [11 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@26af9eed | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0px2z: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-08 06:30 | [13 empty] | 08/Jan/26 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Initial discovery has been started post discussion. Working on Kyverno issue first in-order to have necessary violations report. | [29 empty] | In Progress | 2026-01-08 08:28
AM20-461 | Nexio ¦¦ Alarm Solution | Done | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1760700 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 19:51 | 2026-01-20 20:51 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if Nexio server is stopped |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 02/Sep/25 4:23 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;Trellix alarms for CPU,MEMORY,DISK,STATUSFAILEDCHECK.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1146818 | 05/Sep/25 1:00 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image (4).png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148618 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@be8ff55 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejrn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 12:34 | [13 empty] | 25/Aug/25 2:33 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;* CloudWatch metrics are enabled for CPU, memory, disc, network I/O â€“ *Done* * Dashboards are created to monitor key services also alarms have been created â€“ *Done* | 28/Aug/25 2:10 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the update from sinjun regarding the alerts so will be creating the alerts as per finalized naming and severity sheet for Nexio av | 01/Sep/25 4:20 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Created few alarms for FLYSAA CPU & Memory and StatusCheckFailed as per the finalized naming from sinjun & bhavish end. Other alarms will be created after reviewing the created ones. | 02/Sep/25 4:23 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!Trellix alarms for CPU,MEMORY,DISK,STATUSFAILEDCHECK.png¦width=947,height=324,alt="Trellix alarms for CPU,MEMORY,DISK,STATUSFAILEDCHECK.png"! Attached the screenshot of Cloud watch alarms that i created as per the finalized naming ,threshold and datapoints. Also, Dashboard has been created to monitor key services & SNS alert will be triggered if the Nexioav EC2 server status goes down or stopped. | 03/Sep/25 8:44 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Iâ€™m putting the US in review. | 05/Sep/25 8:41 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Awaiting the Review from Aravind side then only the US will get closed. | 05/Sep/25 1:00 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;the Alarms are getting triggering to Service Now properly attaching the screenshot evidence which i got from Priyanka for the reference. !image (4).png¦width=1090,height=573,alt="image (4).png"! | 08/Sep/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-09-08 06:33
AM20-462 | ServiceNow ¦¦ CloudWatch Rule for Error detection | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650995 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 19:54 | 2026-01-10 20:38 |  |  |  | 0 | As a AWS engineer, I want to create CloudWatch alarms to send error-level logs to be notified of infrastructure issues Acceptance criteria: * CloudWatch metric filters to be configured to match specific error patterns or log levels |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fabfe65 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0280b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 06:03 | [13 empty] | 29/Apr/25 8:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will review utkarsh terraform script and will assign this story to him. | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed. | 07/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;We can use utkarsh terraform script for cloud watch alarm creation, but sns topic cant be modified so we need manual update to SNS access policy. | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:39 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [22 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:39
AM20-463 | (Airchef)Terraform code generation for Route 53 Hosted Zone Creation & Record Migration. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Faisal Sayed | Medium | 1827706 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-09 20:33 | 2026-01-09 22:15 |  |  |  | 0 | Hosted Zone Creation Develop infrastructure-as-code to provision a Route 53 hosted zone for the specified domain. The configuration should support tagging, environment-specific naming, and be reusable across deployments. DNS Record Management Implement a declarative script to define and manage DNS records within the hosted zone. This should include support for common record types (A, CNAME, MX, TXT) with configurable TTLs and values. |  | Faisal Sayed | Sanket Kale |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e |  |  |  |  | ;12/Nov/25 10:17 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 |  |  |  |  | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@53b50383 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1v7: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:56 | [13 empty] | 07/Nov/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status: Blocked* Awaiting SAA approval for the updated DNS records associated with the {{airchef}} domain. Terraform provisioning is currently on hold until the DNS configuration is finalized. | 12/Nov/25 6:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status Update:* * Task moved from *Blocked* to *In Progress*. * Terraform code for Route 53 provisioning has been developed and handed over to *Sanket*. * *Next Action:* Sanket to review and execute the code in the *sandbox account* for validation. | 12/Nov/25 6:55 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform code has been successfully reviewed and tested in the sandbox environment, and all validations are positive. Â | 12/Nov/25 10:16 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Code has been reviewed, tested successfully, and validated. Moving the sub-story to *Done*. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-12 10:12
AM20-464 | Nexio AV ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 5 | 2025-05-12 | 2025-05-23 | Satya Varanasi | High | 1650865 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 12:59 | 2026-01-24 13:43 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5c904e9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akl: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 15:23 | [13 empty] | 20/May/25 5:23 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This Story dependency with comms implementation, the same with SAA team. Once SAA team actioned this story will be handled and closed until that this will not possible to address.(Note: it may move next sprint also) | 10/Jun/25 2:08 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0; No longer needed based on recent conversation. * Based on request from Sinjun, the migration approach for Trellix/NexioAV has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. Â | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-10 14:08
AM20-465 | Nexio AV ¦¦ Subnet creation | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | Medium | 1650863 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 18:13 | 2026-01-31 19:48 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Nexio AV application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Nexio AV and the configured based on the approved comms matrix |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 14/May/25 7:21 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-05-14 104729-20250514-051730.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100027 | 14/May/25 7:21 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-05-14 105036-20250514-052037.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100026 | 14/May/25 7:24 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052415.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100028 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-072934.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103886 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-073009.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103885 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-073047.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103887 | [12 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@77400985 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:t | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:40 | [13 empty] | 29/Apr/25 7:39 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Relevant subnet has been created, sending for review. | 02/May/25 12:22 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;IP Details ¦¦Nexio AV¦¦Production¦¦10.40.0.176/28¦¦10.40.0.176 - 10.40.0.191¦¦10.40.0.177 - 10.40.0.190¦¦14¦¦AZ1¦¦Â ¦¦ ¦¦Nexio AV (DR)¦Production¦10.40.0.192/28¦10.40.0.192 - 10.40.0.207¦10.40.0.193 - 10.40.0.206¦14¦Â ¦AZ2¦ ¦¦TG ATTACH-Subnet¦Production¦10.40.1.160/28¦10.40.1.160 - 10.40.1.175¦10.40.1.161 - 10.40.1.174¦14¦AZ1¦Â ¦ ¦¦TG ATTACH-Subnet¦Production¦10.40.1.176/28¦10.40.1.176 - 10.40.1.191¦10.40.1.177 - 10.40.1.190¦14¦Â ¦AZ2¦ Route table still need to cleaned up and updated properly. Assigning back the ticket to [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 07/May/25 6:21 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on route table cleanup. | 14/May/25 7:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets already created. IP CIDR Details for prod/DR ¦10.40.0.176/28¦10.40.0.176 - 10.40.0.191¦10.40.0.177 - 10.40.0.190¦14¦/28¦AZ1¦Â ¦ ¦10.40.0.192/28¦10.40.0.192 - 10.40.0.207¦10.40.0.193 - 10.40.0.206¦14¦/28¦Â ¦AZ2¦ Subnet info: !Screenshot 2025-05-14 104729-20250514-051730.png¦width=1117,height=580,alt="Screenshot 2025-05-14 104729-20250514-051730.png"! !Screenshot 2025-05-14 105036-20250514-052037.png¦width=1128,height=586,alt="Screenshot 2025-05-14 105036-20250514-052037.png"! Please review. | 14/May/25 7:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Attached route table screen shots. !image-20250514-052415.png¦width=1130,height=531,alt="image-20250514-052415.png"! | 19/May/25 11:08 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Action Item: Change the Name to Trellix AV from Nexio AV Correct the AZ for DR Route to be tested for correct routing Assigning back to Satya for correction | 19/May/25 6:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sankalp updated me to change NexioAV to Trellix AV. I will update and assign it to Sankalp. | 20/May/25 5:16 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation done and assigned for review, and it has been reassigned for modification and routing validation. Find below reviewer comments. Action Item: Change the Name to Trellix AV from Nexio AV(New requirement according to app name) Correct the AZ for DR (resource name change) Route to be tested for correct routing | 22/May/25 9:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on inputs modification has been done. !image-20250522-072934.png¦width=1103,height=563,alt="image-20250522-072934.png"! !image-20250522-073009.png¦width=1107,height=575,alt="image-20250522-073009.png"! Route Table: !image-20250522-073047.png¦width=1107,height=526,alt="image-20250522-073047.png"! Please check and review the same. | 30/May/25 2:45 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Review done Transitioning to PO Approval | 02/Jun/25 11:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [16 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-02 11:36
AM20-466 | Informatica ¦¦ Custom application Metrics | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1761210 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 14:00 | 2026-01-31 17:29 |  |  |  | 0 | # Configure & install cw agent. # Refer email for metrics to be monitored. # Create alerts as per approval in the email. |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@407cb340 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0elc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-17 06:01 | [13 empty] | 17/Sep/25 8:01 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Informatica Accounts (Dev & Prod) cutover is yet to be done. Actual workloads are yet to be migrated. Hence, blocked. | 01/Oct/25 8:24 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Configure & install cw agent - Done # Refer email for metrics to be monitored - Done # Create alerts as per approval in the email - Done | [28 empty] | Done | 2025-10-06 07:58
AM20-467 | Nexio ¦¦ Alarm Solution | Done | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1760700 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 13:37 | 2026-02-01 14:14 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if Nexio server is stopped |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 02/Sep/25 4:23 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;Trellix alarms for CPU,MEMORY,DISK,STATUSFAILEDCHECK.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1146818 | 05/Sep/25 1:00 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image (4).png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148618 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@be8ff55 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejrn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 12:34 | [13 empty] | 25/Aug/25 2:33 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;* CloudWatch metrics are enabled for CPU, memory, disc, network I/O â€“ *Done* * Dashboards are created to monitor key services also alarms have been created â€“ *Done* | 28/Aug/25 2:10 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the update from sinjun regarding the alerts so will be creating the alerts as per finalized naming and severity sheet for Nexio av | 01/Sep/25 4:20 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Created few alarms for FLYSAA CPU & Memory and StatusCheckFailed as per the finalized naming from sinjun & bhavish end. Other alarms will be created after reviewing the created ones. | 02/Sep/25 4:23 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!Trellix alarms for CPU,MEMORY,DISK,STATUSFAILEDCHECK.png¦width=947,height=324,alt="Trellix alarms for CPU,MEMORY,DISK,STATUSFAILEDCHECK.png"! Attached the screenshot of Cloud watch alarms that i created as per the finalized naming ,threshold and datapoints. Also, Dashboard has been created to monitor key services & SNS alert will be triggered if the Nexioav EC2 server status goes down or stopped. | 03/Sep/25 8:44 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Iâ€™m putting the US in review. | 05/Sep/25 8:41 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Awaiting the Review from Aravind side then only the US will get closed. | 05/Sep/25 1:00 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;the Alarms are getting triggering to Service Now properly attaching the screenshot evidence which i got from Priyanka for the reference. !image (4).png¦width=1090,height=573,alt="image (4).png"! | 08/Sep/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-09-08 06:33
AM20-468 | (Airchef)Terraform Implementation for Creation of Route 53 Hosted Zones & Records. | In Progress |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Sanket Kale | Medium | 1827709 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-13 21:36 | 2026-01-13 21:46 |  |  |  | 0 | *Acceptance Criteria:* * *Deploy Public Hosted Zone* Use Terraform to provision a *Route 53 public hosted zone* for the domain [*airchef.co.za*¦http://airchef.co.za]. * *Manage DNS Records via Terraform* Implement Terraform configurations to create and manage various DNS record types (A, CNAME, MX, TXT, etc.) within the hosted zone. |  | Faisal Sayed | Sanket Kale | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [20 empty] | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28df5c12 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1vn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-07 05:56 | [13 empty] | 07/Nov/25 7:56 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Code review completed from my side its working. Created and deployed the base and component modules. | 10/Nov/25 9:07 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and tested on Sandbox environment | 14/Nov/25 4:01 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code deployment done sandbox and same tested. | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | In Progress | 2025-11-20 08:59
AM20-469 | Cost Anomaly Detection | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1719961 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 14:59 | 2026-01-11 18:39 |  |  |  | 0 | As AWS expert I would like to report any sudden spike in the cost against any of the application or accounts so that the concerned team can validate the reasoning and take appropriate action to ascertain reasons and take reactive measures Acceptance Criteria: < pre-req> : * Ensure all accounts are part of AWS Org. with consolidated billing enabled * Use the Payer9 account to see all account cost level Acceptance Criteria * Cost anomaly detection is enabled successfully * Anomaly monitor is is enabled * Anomaly subscription is successfully enabled using SNS * CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage * Use Amazon Athena or quicksight for stakeholder friendly dashboards * Graphical representation of the cost to be captured |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4d6b831e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0attv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-18 06:07 | [13 empty] | 18/Jul/25 8:07 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;* CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm *---Done* * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage *---Done* Cost anomaly detection is enabled successfully *---Done* * Anomaly monitor is is enabled *---Done* * Anomaly subscription is successfully enabled using SNS *---Done* | 23/Jul/25 8:08 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working on Amazon Athena or quicksight for stakeholder friendly dashboards ---*Done* | 24/Jul/25 7:38 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;As discussed with Yashwant, we need to track cost anomalies for specific AWS services and implement it separately for each account. | 24/Jul/25 8:57 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Cost anomalies detction for specific AWS services and implement it separately for each account. *---Done* Updated for Only TM1 account.(As discussed with Yashwant) | 28/Jul/25 9:58 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:58
AM20-470 | ServiceNow ¦¦ Lamda function as SNS Subscriber | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651014 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 16:35 | 2026-01-20 19:06 |  |  |  | 0 | As a Cloud engineer, I want a Lamda function subscribed to the SNS topic so that it can process alerts and forward them to ServiceNow Acceptance Criteria: * The Lamda function is triggered on new SNS messages * It parses event data and sends an HTTP POST request to ServiceNow |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 | ;25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@353710af | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0284j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 03:49 | [13 empty] | 24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Working with the lambda function python script, since the function needs to works with cross account for getting the tags. initially the lambda function developed to get the tags from the same account, whereas here the requirement is to get the tag to Audit account to trigger a SNS. | 25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function is created in Audit account -300204747992, and its working fine as expected. | 02/May/25 4:57 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-25 06:34
AM20-471 | Restrict Admin access to VOIS team by creating dedicated IAM role | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Medium | 1736354 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 19:43 | 2026-01-16 21:07 |  |  |  | 0 | As Product Owner, I want to restrict VOIS team to have Admin role so that all of them cannot be superseded rights and bring more control on AWS management Acceptance criteria: * IAM role to be created for everyone except Sankalp and Aravind from AWS perspective * IAM role for network creation to be created and role assign to Satya * IAM role for rest of team members is of developer |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6edd432e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0c5zn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 06:20 | [13 empty] | 06/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have shared the Excel with the user list to team, upon there confirmation ill start creating custom policy with user groups. | 08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;¦UserID¦IAM user¦UserGroup¦IAM Role¦ ¦raja0001¦Aravind¦VOIS_Admin¦No changes, use existing roles itself¦ ¦rais0003¦Sankalp¦VOIS_Admin¦No changes, use existing roles itself¦ ¦SatyasairamV¦SatyaSairam¦VOIS_Admin¦No changes, use existing roles itself¦ ¦godir001¦Ravinder¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦kiraj001¦Jitender¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Sanjot¦Sanjot¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦nikas001¦Sumit¦VOIS_Admin¦No changes, use existing roles itself¦ ¦FaisalSayed¦Faizal¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SanketKale¦Sanket¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦pathp002¦Pankaj¦VOIS_DBAdmin_Usergroup¦AWS_VOIS_DBAdmin_Role¦ ¦onkar¦Onkar¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦DikshaK¦Diksha¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SatyabrataS¦SatyaBrata¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Shreyash¦Shreyash¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Harsh¦Harsh¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Yashwant¦Yashwant¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Utkarsh¦Utkarsh¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ Â Â Access to User group given as below, ¦VOIS_InfraAdmin_Usergroup¦VOIS_DevOpsAdmin_Usergroup¦VOIS_DBAdmin_Usergroup¦ ¦VPC FullAccess¦CodeBuild FullAccess¦RDS Full Access¦ ¦EC2 FullAccess¦CodePipeline FullAccess¦DMS Full Access¦ ¦S3 FullAccess¦EKS FullAccess¦IAM Full Access¦ ¦CloudWatch FullAccess¦EC2 except delete¦CloudTrail except delete¦ ¦RDS FullAccess¦S3 FullAccess¦KMS except delete¦ ¦IAM FullAccess¦CloudWatch except delete¦CloudWatch except delete¦ ¦CloudTrailFullAccess¦RDS except delete¦Read only¦ ¦MacieFullAccess¦IAM FullAccess¦ ¦ ¦GuardDutyFullAccess¦System managerFullAccess¦ ¦ ¦SecurityHubFullAccess¦LambdaFullAccess¦ ¦ ¦System managerFullAccess¦Event bridgeFullAccess¦ ¦ ¦LambdaFullAccess¦CloudTrail except delete¦ ¦ ¦KMSFullAccess¦Read only¦ ¦ ¦ACMFullAccess¦Secrets managerFullAccess¦ ¦ ¦Aws ConfigFullAccess¦SNSFullAccess¦ ¦ ¦Event bridgeFullAccess¦SESFullAccess¦ ¦ ¦InspectorFullAccess¦ECR FullAccess¦ ¦ ¦SupportFullAccess¦KMS except delete¦ ¦ ¦SNSFullAccess¦Â ¦ ¦ ¦SESFullAccess¦ ¦ ¦ ¦ReadOnly¦ ¦ ¦ ¦Secrets managerFullAccess¦ ¦ ¦ ¦ECRFullAccess¦ ¦ ¦ Â Users have access to the below AWS accounts, Â ¦AWS Account¦Account Name¦ ¦300204747992¦Audit¦ ¦730335236533¦Security¦ ¦080284287007¦LogArchive¦ ¦339712943527¦Network¦ ¦864899875361¦SharedServices¦ ¦585768167545¦SharedVpcDev¦ ¦253490777663¦SharedVpcPreprod¦ ¦820242899278¦SharedVpcProd¦ ¦746669190453¦Backend dev¦ ¦216989128782¦Backend Preprod¦ ¦396608788916¦Backend Prod¦ ¦209479274829¦Tm1¦ ¦345594574792¦AirNAVx¦ ¦536697265099¦NexioAV¦ | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-472 | Terraform Development ¦¦ Define CloudWatch Agent config and Automate Agent Start via Terraform | Done | 20 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1661298 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-30 14:23 | 2026-01-30 17:15 |  |  |  | 0 | As Devops Engineer, I would like to define the CloudWatch Agentâ€™s configuration and Automate Cloud Watch Agent start using Terraform so that the metrics and logs it collects are consistent across environments Acceptance Criteria: * Terraform manages the agent config JSON file as a template * The config files includes, CPU, Memory, disk and Network metrics and application/system log files paths. * The file is stored locally or pushed to EC2 during provisioning via user_data * Terraform - provisioned EC2 instances start the CloudWatch agent on boot * The agent fetches the config file and start sending data to CloudWatch * Verification - Metrics and logs appear in CloudWatch console post launch |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7aab33b8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4h: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-11 06:40 | [13 empty] | 11/Jun/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;* The Terraform script for configuring and starting the CloudWatch agent is ready for both Linux and Windows instances. * Linux automation is working as expected. * Faced issues with Windows agent installation during EC2 provisioning. * Initial approach used user data to download and install the CloudWatch agent. * Encountered failure due to network not being ready at the time of user data execution. * Attempted to resolve this with a 60-second sleep delay, but it was unsuccessful. * New approach identified: using SSM documents to automate agent installation post-boot. * Will implement this alternative and move the changes to code review. * A meeting will be scheduled following successful implementation. | 16/Jun/25 10:03 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# *Used SSM Documents to Automate Agent Installation*Â * We leveraged *AWS SSM Run Command* documents instead of manual scripts or hardcoding logic.Â * Specifically, we used:Â * {{AWS-ConfigureAWSPackage}} to *install the CloudWatch Agent*Â * {{AmazonCloudWatch-ManageAgent}} to *configure and start the agent* using a *Parameter Store JSON config* named {{/Windows_Monitor_CW}}.Â Â *ðŸ”¹ 2. Embedded SSM Associations in Terraform*Â * Inside our *main EC2 Terraform project*, we embedded two {{aws_ssm_association}} resources:Â * *install_cwagent_windows* â€“ installs CloudWatch agentÂ * *configure_cwagent_windows* â€“ tells the agent to pull its config from {{/Windows_Monitor_CW}} in SSM Parameter Store and start itÂ * Both associations *target EC2 instances by tag*: {{CWAgent = EnabledÂ }} * The EC2 instances were pre-tagged via Terraform to ensure automatic targetingÂ Â *ðŸ”¹ 3. Created a Third Association to Force Re-fetch Config*Â * In some cases, the agent might need to re-fetch its config after the EC2 instance is up and the services are stable.Â * So we created a *third SSM association*: {{force_fetch_start_agentÂ }} * Uses {{AWS-RunPowerShellScript}} to run:Â {{& "C:\Program Files\Amazon\AmazonCloudWatchAgent\amazon-cloudwatch-agent-ctl.ps1" -a fetch-config -m ec2 -c ssm:/Windows_Monitor_CW -sÂ }} Â * This *manually triggers the fetch* of the config from SSM Parameter Store and starts the agent again if neededÂ Â *ðŸ”¹ 4. Split This Trigger into a Separate Terraform Directory*Â * To keep your deployment clean and *modular*, we:Â * Created a new folder: {{terraform/cwagent-trigger/Â }} * Placed only the {{force_fetch_start_agent}} logic in this moduleÂ * Why?Â * This allows you to *run it manually or conditionally* after core EC2 and SSM setups are completeÂ * Ensures *clean execution ordering* and better control in CI/CDÂ * Prevents early execution before the agent is even installedÂ Â *ðŸ”¹ 5. Designed for Platform-Specific Control*Â * Logic is gated with:Â {{count = var.platform == "windows" && var.enable_windows_ssm_association ? 1 : 0Â }} Â * Ensures this entire operation is *executed only for Windows instances*, as Linux would follow a different path.Â | 24/Jun/25 6:55 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;cloud watch agent installation is done using terraform script, have enabled only memory and disk utilization as of now. | 29/Jun/25 8:14 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:15
AM20-473 | Security and compliance implementation on PROS account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622524 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 17:31 | 2026-02-04 19:07 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on PROS account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in PROS DEV account * NIST policy implementation successfully done in PROS DEV account * AWSFSBP policy implementation successfully done in PROS DEV account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Mar/25 2:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [8 empty] | AM20-19 | AM20-17 |  |  | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250317-060821.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1079558 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a53b25a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxson: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-13 06:02 | [13 empty] | 13/Mar/25 8:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on the controls with the dependency services for the security frameworks. | 14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;The controls were implemented in Pros DEV account, Pros Production account will be picked up in separate user story. | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250317-060821.png¦width=1277,height=642,alt="image-20250317-060821.png"! | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-14 14:22
AM20-474 | Informatica Server ¦¦ NACL and Security group creation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660593 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-11 16:53 | 2026-01-11 18:34 |  |  |  | 0 | As Network expert, I would be creating NACL and Security group along with inbound and outbound rules for Nexio AV Acceptance Criteria: NACL and Security group created successfully with all inbound and outbound rules |  | Aravind Raj | Harsh Chandra | Satya Varanasi | Shreyash Talwekar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 27/Jun/25 3:51 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-134901.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119369 | 27/Jun/25 3:51 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-134948.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119368 | 27/Jun/25 5:54 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155416.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119411 | 27/Jun/25 5:54 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155445.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119410 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4189bc9b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bbn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-16 08:01 | [13 empty] | 16/May/25 10:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Waiting for terraform code towards build this. | 20/May/25 5:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Deepak and team, this need to be addressed with terraform code the same has been prepared by Utkarsh, until core not ready this story may not possible to address. | 10/Jun/25 2:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still â€œShreyashâ€ checking Utkarsh script, this story depending with script testing and execution. | 16/Jun/25 9:06 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Terraform script is under modification by â€œShreyashâ€, as per his update it will be ready this week. Hence this is the reason for spill over Sprint7 to Sprint8. | 18/Jun/25 11:11 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The script is managing by â€œShreyashâ€ so i am assigning this task to him, once his work completes he will reassign to me. | 23/Jun/25 1:59 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We were able to create AWS resources (mentioned in previous mail ) using terraform scripts on sharedvpc-dev account. To address some requirements like adding naming conventions and state file management, we will have to add some changes in terraform scripts. Due to current sprint activities I might not be able to work on the changes in this sprint. | 27/Jun/25 3:46 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Prod NACL/SG has been created, & tested internet access and same working fine. !image-20250627-134901.png¦width=1092,height=400,alt="image-20250627-134901.png"! !image-20250627-134948.png¦width=1308,height=579,alt="image-20250627-134948.png"! sh-5.2$ ping [http://google.com¦http://google.com¦smart-link] PING [http://google.com¦http://google.com¦smart-link] (142.251.47.238) 56(84) bytes of data. 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=1 ttl=108 time=20.5 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=2 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=3 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=4 ttl=108 time=19.7 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=5 ttl=108 time=19.8 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=6 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=7 ttl=108 time=19.7 ms ^C --- [http://google.com¦http://google.com¦smart-link] ping statistics --- 7 packets transmitted, 7 received, 0% packet loss, time 6010ms rtt min/avg/max/mdev = 19.630/19.800/20.473/0.282 ms sh-5.2$ hostname [ip-10-40-0-213.awsflysaa.com¦http://ip-10-40-0-213.awsflysaa.com] sh-5.2$ ifconfig ens5: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 9001 inet 10.40.0.213 netmask 255.255.255.240 broadcast 10.40.0.223 inet6 fe80::4a7:ebff:fe03:c075 prefixlen 64 scopeid 0x20<link> ether 06:a7:eb:03:c0:75 txqueuelen 1000 (Ethernet) RX packets 1653 bytes 293385 (286.5 KiB) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 1809 bytes 265312 (259.0 KiB) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0 lo: flags=73<UP,LOOPBACK,RUNNING> mtu 65536 inet 127.0.0.1 netmask 255.0.0.0 inet6 ::1 prefixlen 128 scopeid 0x10<host> loop txqueuelen 1000 (Local Loopback) RX packets 12 bytes 1020 (1020.0 B) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 12 bytes 1020 (1020.0 B) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0. | 27/Jun/25 5:54 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev: NACL/SG got created. !image-20250627-155416.png¦width=1246,height=457,alt="image-20250627-155416.png"! !image-20250627-155445.png¦width=1155,height=624,alt="image-20250627-155445.png"! | 27/Jun/25 6:13 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;NACL and Route table created for informatica environment, route entry and NACL rules to be created upon network requirement. | 29/Jun/25 8:13 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [17 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-29 20:13
AM20-475 | ServiceNow Integration with FlySAA Back-end servers for error/ reporting | Done | 5 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1685592 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 13:19 | 2026-01-09 14:22 |  |  |  | 0 | As AWS expert, I should be able to integrate ServiceNow API with FlySAA Back-end server so that in case of any error/issues, alerts can be generated and transformed into tickets in ServiceNow. Acceptance Criteria: Tickets are generate in ServiceNow against Alerts that are getting generated for FlySAA Back-End server events successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [13 empty] | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064203.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124194 | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064240.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124193 | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064306.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124195 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@78ab6644 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:06 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-02 05:24 | [13 empty] | 02/Jul/25 7:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Integration have done for backend dev with service now *dev* endpoint. Integration have done for backend prod with service now *prod* endpoint. Preprod yet to configure. | 08/Jul/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will configure the preprod endpoint with service now integration today. | 09/Jul/25 7:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Servicenow preprod integration is completed unit testing will be performed by today. | 09/Jul/25 8:41 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;746669190453 FlySAA_CMS_Backend_DevQA 216989128782 FlySAA_CMS_Backend_PreProd 396608788916 FlySAA_CMS_Backend_Prod These backend environments set with the service now integration and expected to get all the tags of instance with an alarm details. | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250709-064203.png¦width=663,height=458,alt="image-20250709-064203.png"! !image-20250709-064240.png¦width=606,height=397,alt="image-20250709-064240.png"! !image-20250709-064306.png¦width=645,height=440,alt="image-20250709-064306.png"! | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-09 08:43
AM20-476 | AirNavX ¦¦ Monitoring and Alert solution | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772183 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 16:21 | 2026-01-11 17:24 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if AirNavX server is stopped |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 03/Oct/25 9:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251003-073517.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1162022 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c7985 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-09 06:37 | [13 empty] | 09/Sep/25 8:37 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;We will start the US after getting the EC2 instance and application deployed on the AWS environment thatâ€™s why the US is blocked. | 22/Sep/25 10:01 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Spill Over : Due to connectivity issue going on and EC2 instance deployement pending go ahead from customer side. this story goes in spill over in this sprint. | 29/Sep/25 6:54 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Ec2 instances has been created on Friday so from today i will start the to set up the cloud metrics alerts. | 29/Sep/25 3:50 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;CPU utilization alert and dashboard has been created in Audit account. Now will be creating the network I/O and status check failed alerts. | 30/Sep/25 12:41 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The server status check failed alerts has been created and added to dashboard also we have added the network I/O to the dashboard in the Audit account. --*-Done* *Pending* : For disk and memory need to install the cloud watch agent and custom metrics need to be added on all AirnavX servers. Then only will be able to add the alerting for the Memory and disk metrics to dashboard. | 03/Oct/25 9:36 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251003-073517.png¦width=1178,height=647,alt="image-20251003-073517.png"! Created all alerts and dashboard as per the acceptance criteria and also used agreed naming and threshold value by the customer itself. | 03/Oct/25 12:42 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have modified the alarm for disk and memory configuration, other alarm are looking good. | [23 empty] | Done | 2025-10-06 07:58
AM20-477 | AirNavX ¦¦ Subnet creation using terraform | Done | 0 | Sprint 1 | 2025-03-17 | 2025-03-28 | Sankalp Rai | High | 1620392 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 18:54 | 2026-01-13 19:46 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for AirnavX application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for AirNavX and the configured based on the approved comms matrix |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4777a0ee | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnaf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:52 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 09/Apr/25 5:44 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets has been created. Please review | 17/Apr/25 11:10 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Subnet was created manually Subnet > created Route table > Created SG > Created NACL > Created AD Firewall flow > Implemented Send for PO Approval | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-21 09:01
AM20-478 | Trellix integration with MQ | Blocked | 2 | None( Backlog) |  |  | Satya Varanasi | Medium | 1794150 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 19:06 | 2026-01-23 21:59 |  |  |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan MQ workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in MQ server * Trellix is able to access MQ account successfully and perform scanning |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b924c6e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g04 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-27 14:04 | [13 empty] | 27/Oct/25 4:03 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This action need to addressed once server build completes. | [29 empty] | To Do | 2025-09-30 10:19
AM20-479 | Terraform Development ¦¦ Define CloudWatch Agent config and Automate Agent Start via Terraform | Done | 20 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1661298 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-22 17:28 | 2026-01-22 17:45 |  |  |  | 0 | As Devops Engineer, I would like to define the CloudWatch Agentâ€™s configuration and Automate Cloud Watch Agent start using Terraform so that the metrics and logs it collects are consistent across environments Acceptance Criteria: * Terraform manages the agent config JSON file as a template * The config files includes, CPU, Memory, disk and Network metrics and application/system log files paths. * The file is stored locally or pushed to EC2 during provisioning via user_data * Terraform - provisioned EC2 instances start the CloudWatch agent on boot * The agent fetches the config file and start sending data to CloudWatch * Verification - Metrics and logs appear in CloudWatch console post launch |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7aab33b8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4h: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-11 06:40 | [13 empty] | 11/Jun/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;* The Terraform script for configuring and starting the CloudWatch agent is ready for both Linux and Windows instances. * Linux automation is working as expected. * Faced issues with Windows agent installation during EC2 provisioning. * Initial approach used user data to download and install the CloudWatch agent. * Encountered failure due to network not being ready at the time of user data execution. * Attempted to resolve this with a 60-second sleep delay, but it was unsuccessful. * New approach identified: using SSM documents to automate agent installation post-boot. * Will implement this alternative and move the changes to code review. * A meeting will be scheduled following successful implementation. | 16/Jun/25 10:03 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# *Used SSM Documents to Automate Agent Installation*Â * We leveraged *AWS SSM Run Command* documents instead of manual scripts or hardcoding logic.Â * Specifically, we used:Â * {{AWS-ConfigureAWSPackage}} to *install the CloudWatch Agent*Â * {{AmazonCloudWatch-ManageAgent}} to *configure and start the agent* using a *Parameter Store JSON config* named {{/Windows_Monitor_CW}}.Â Â *ðŸ”¹ 2. Embedded SSM Associations in Terraform*Â * Inside our *main EC2 Terraform project*, we embedded two {{aws_ssm_association}} resources:Â * *install_cwagent_windows* â€“ installs CloudWatch agentÂ * *configure_cwagent_windows* â€“ tells the agent to pull its config from {{/Windows_Monitor_CW}} in SSM Parameter Store and start itÂ * Both associations *target EC2 instances by tag*: {{CWAgent = EnabledÂ }} * The EC2 instances were pre-tagged via Terraform to ensure automatic targetingÂ Â *ðŸ”¹ 3. Created a Third Association to Force Re-fetch Config*Â * In some cases, the agent might need to re-fetch its config after the EC2 instance is up and the services are stable.Â * So we created a *third SSM association*: {{force_fetch_start_agentÂ }} * Uses {{AWS-RunPowerShellScript}} to run:Â {{& "C:\Program Files\Amazon\AmazonCloudWatchAgent\amazon-cloudwatch-agent-ctl.ps1" -a fetch-config -m ec2 -c ssm:/Windows_Monitor_CW -sÂ }} Â * This *manually triggers the fetch* of the config from SSM Parameter Store and starts the agent again if neededÂ Â *ðŸ”¹ 4. Split This Trigger into a Separate Terraform Directory*Â * To keep your deployment clean and *modular*, we:Â * Created a new folder: {{terraform/cwagent-trigger/Â }} * Placed only the {{force_fetch_start_agent}} logic in this moduleÂ * Why?Â * This allows you to *run it manually or conditionally* after core EC2 and SSM setups are completeÂ * Ensures *clean execution ordering* and better control in CI/CDÂ * Prevents early execution before the agent is even installedÂ Â *ðŸ”¹ 5. Designed for Platform-Specific Control*Â * Logic is gated with:Â {{count = var.platform == "windows" && var.enable_windows_ssm_association ? 1 : 0Â }} Â * Ensures this entire operation is *executed only for Windows instances*, as Linux would follow a different path.Â | 24/Jun/25 6:55 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;cloud watch agent installation is done using terraform script, have enabled only memory and disk utilization as of now. | 29/Jun/25 8:14 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:15
AM20-480 | ServiceNow ¦¦ LLD preparation | Done | 4 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1610563 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 15:52 | 2026-01-11 17:43 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for ServiceNow application so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed |  | Aravind Raj | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;14/Apr/25 9:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;115200 | [5 empty] | 57600 | 0 | 115200 | 2 | 57600 | 0 | 115200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4842827b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 3/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 3 | 75 | 1 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsnj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 2 | Sprint 3 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-10 14:19 | [13 empty] | 10/Mar/25 4:19 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 12/Mar/25 8:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;ServiceNow LLD is prepared, formatting is in progress, will complete and attach the document here. | 14/Apr/25 9:39 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Completed: 10th April 2025 Presentation to be done on Wednesday 16th April 2025 Review done by: [~accountid:712020:5d317226-2402-463f-bda5-c2cac5f43c13] and Deepak | [24 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-04-21 09:02
AM20-481 | Informatica Server - Dev ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1749537 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 16:14 | 2026-01-09 17:03 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 57600 |  | 0 | 86400 | 57600 | [9 empty] | AM20-145 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b90196e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0datf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 14:28 | [13 empty] | 18/Aug/25 4:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev MGN template has been configured, now we are looking AWS migration agent installation on server for sync, Sinjun going to take care tomorrow for the same i have scheduled the call. | 19/Aug/25 5:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;While checking AWS agent connectivity not working, checking with network team for further troubleshooting/fixing the issue. CSOC request has-been createdâ€CINC0909706â€ | 25/Aug/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network routing not implemented, currently it under approval process. | 26/Aug/25 1:11 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Firewall rules implemented. # Configured MGN agent setup on AWS for dev server migration. # Identified as connectivity not working. # Initiated network troubleshooting call towards fixing. # Identified as routing not configured. # Requested LIFT for approval # LIFT approval took 3days # Monday CSOC request raised and routing has ben implemented. # Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 29/Aug/25 8:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev agent installation and Test instance setup has been complted. | 01/Sep/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The test instance connectivity has been completed. Communicated to Peter for connectivity testing. The ip address is: 10.42.0.46. Sending this request for closing. | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-482 | MQ ¦¦ DR and BackUp | To Do | 0 | None( Backlog) |  |  |  | Medium | 1794158 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 22:03 | 2026-01-13 23:36 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Informatica-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@415fe9df | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v08 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 10:24
AM20-483 | Nexio AV ¦¦ CloudTrail and GuardDuty & AWS config Implementation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | High | 1660681 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-03 13:40 | 2026-02-03 16:45 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across NexioAV account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;07/May/25 8:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@319a088e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bmj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-06 06:25 | [13 empty] | 06/May/25 8:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cloud Trails logs to push S3 bucket were implemented already through SCP, now working with guard duty and AWs config enablement. | 07/May/25 8:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard Duty and AWs config is enabled, along with trail. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-07 08:28
AM20-484 | Informatica Server - Cutover for Prod | Done |  | Sprint 13 | 2025-09-01 | 2025-09-12 | Aravind Raj | Medium | 1768422 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 19:40 | 2026-01-31 22:34 |  |  |  | 0 |  |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;30/Sep/25 6:36 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;43200 | [5 empty] | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [12 empty] | 30/Sep/25 6:35 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250930-163551.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1160875 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7b96ec0c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fb2j: | [167 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 07:23 | [13 empty] | 05/Sep/25 9:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Informatica Test server is launched and trying to fix RDP connectivity issue. Only after the test instance confirmation we will be able to deploy cutover, so this will be a spillover. | 30/Sep/25 6:35 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250930-163551.png¦width=669,height=443,alt="image-20250930-163551.png"! | [25 empty] | 1751440 | AM20-140 | Informatica Server ¦¦ Cutover | Done | 2025-09-30 18:36
AM20-485 | Backup Server ¦¦ Security compliance implementation | Done | 3 | Sprint 7 | 2025-06-09 | 2025-06-20 | Aravind Raj | Medium | 1681806 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 14:08 | 2026-01-22 15:52 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Backup Server *Acceptance Criteria*: * Renaming of PROS account to Back-Up Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 14400 | 43200 | 1 | 43200 | 14400 | 43200 | [12 empty] | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250612-153959.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1113715 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@48024563 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-09 05:41 | [13 empty] | 09/Jun/25 7:41 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will start working on enabling security frameworks like CIS, NIST, AWS FSBP. | 10/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled controls, will be working on the controls remediation. | 11/Jun/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;controls are implemented waiting for the security score to be update Â· | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CIS, NIST and FSBP controls were enabled and required controls remediated. !image-20250612-153959.png¦width=1279,height=626,alt="image-20250612-153959.png"! | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-12 17:41
AM20-486 | TM1 ¦¦ Subnet creation using terraform | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Satya Varanasi | Medium | 1620359 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 19:27 | 2026-01-15 22:42 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for TM1 application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for TM1 and the configured based on the approved comms matrix |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-11 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a96537d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnn3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:53 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 04/Apr/25 10:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation got completed Manuel. As terraform not ready. While creating this TM1 subnets. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-07 10:11
AM20-487 | AirNavX ¦¦ Setup and Validate SG and NACL | Done | 8 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747567 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 17:31 | 2026-02-04 20:10 |  |  |  | 0 | As AWS network expert I would like to setup the security group and NACL for Airnavx so that access for aitnavx allow secure access to allow communication with its services while ensureing access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for AirNavX or related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a70d23c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d30b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:54 | [13 empty] | 25/Aug/25 8:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Spill over Reason: Still comms under review, once reviewed i will start action the same. | 28/Aug/25 8:36 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will be addressed once comms implementation done. | 08/Sep/25 9:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms Implementation request has been submitted, LIFT has been approved SITA side under approval process. This story will not be addressed until Comms implementation. | 19/Sep/25 4:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Bhavish Modified comms with /27 to /28 and the same has been shared to Albert. | 19/Sep/25 4:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Now SITA has been implemented flows and the same need to validated. According to management the validation will be managed with new Story, hence i am resolving this story. | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-22 08:49
AM20-488 | Airnavx ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620850 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 14:03 | 2026-01-17 16:53 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [8 empty] | AM20-10 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4559db6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 8 | Sprint 9 | Sprint 12 | Sprint 13 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-25 06:58 | [13 empty] | 25/Jun/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Harsh and Deepak update, this need to address after TM1 and informatica servers network action, hence i am keeping this as blocked(As per Harsh update) | 28/Jul/25 8:51 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Currently app under LLD review once review done i will initiate comms for the same. SO this will be moved to next sprint. | 04/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on it according to recent LLD call review. | 07/Aug/25 8:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared, with latest subnet details, i will initiate mail communication with customer/app owner for flows review or in case any additional flows needed they should notify further process. | 12/Aug/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Shared comms to app owner for review and add in case needed any additional flows for the same. | 25/Aug/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms under validation by app owner, so this is right story for spill over to this sprint. | 26/Aug/25 1:04 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Initially after follow-up customer prepared and send comms. # During review i identified as comms as not prepared right way and reshared the same comms to customer for validation. # After continuous 3 days follow-up we have received comms from customer as on date 25th Aug 10:00 PM. # There is no sufficient time to manage this story in this sprint due delay with customer. # Note: It has been communicated customer and management regularly but he took longer time to manage. | 29/Aug/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Reviewed and prepared AirNavX comms for VDC/SITA sheets and same sent app owner for LIFT/CSOC request towards implementation. | 03/Sep/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been reviewed and submitted to app owner for further process. | 03/Sep/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Albert has been submitted requested LIFT and CSOC request for ports androuting implementation. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 03/Sep/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The below is the current status: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Routing already in place hance not required any action on this and making this as completed.) | 08/Sep/25 6:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [15 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:36
AM20-489 | PROS ¦¦ LLD Creation | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sankalp Rai | Medium | 1749504 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 18:00 | 2026-01-23 21:12 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1809d79f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0danv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | Sprint 15 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 06:06 | [13 empty] | 06/Oct/25 8:05 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;LLD document created. | 06/Oct/25 8:07 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;[PROS_Low Level Design Document_v1.0.docx¦https://vodafone.sharepoint.com/:w:/r/sites/SouthAfricaAirlines/Shared%20Documents/Technical%20Documents/SAA%20Design%20documents/LLD%20Documents/Wave%202%20apps/PROS%20LLD/PROS_Low%20Level%20Design%20Document_v1.0.docx?d=w4faebf320e0f4c53aedb5b192660de4f&csf=1&web=1&e=jOZXIo] | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-10-06 08:07
AM20-490 | AirNavX ¦¦ Setup and Validate SG and NACL | Done | 8 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747567 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 19:40 | 2026-01-23 19:51 |  |  |  | 0 | As AWS network expert I would like to setup the security group and NACL for Airnavx so that access for aitnavx allow secure access to allow communication with its services while ensureing access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for AirNavX or related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a70d23c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d30b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:54 | [13 empty] | 25/Aug/25 8:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Spill over Reason: Still comms under review, once reviewed i will start action the same. | 28/Aug/25 8:36 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will be addressed once comms implementation done. | 08/Sep/25 9:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms Implementation request has been submitted, LIFT has been approved SITA side under approval process. This story will not be addressed until Comms implementation. | 19/Sep/25 4:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Bhavish Modified comms with /27 to /28 and the same has been shared to Albert. | 19/Sep/25 4:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Now SITA has been implemented flows and the same need to validated. According to management the validation will be managed with new Story, hence i am resolving this story. | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-22 08:49
AM20-491 | Terraform Development ¦¦ CloudWatch Agent deployment across multiple instances | Done | 0 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1661291 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-03 19:52 | 2026-02-03 22:09 |  |  |  | 0 | AS DevOps Engineer, I want to manage CloudWatch Agent deployment across multiple instances using Terraform so that the setup is consistent , Scalable and repeatable Acceptance Criteria: * Terraform module supports deploying CloudWatch agent setup to multiple EC2 instances * Changes to the config or deployment can be applied centrally via Terraform * Terraform State reflects current deployed infrastructure and config |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [45 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cbbbf77 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i06kuv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-16 06:26 | [13 empty] | 16/Jun/25 8:26 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;* The Terraform script for configuring and starting the CloudWatch agent is ready for both Linux and Windows instances. * Linux automation is working as expected. * Faced issues with Windows agent installation during EC2 provisioning. * Initial approach used user data to download and install the CloudWatch agent. * Encountered failure due to network not being ready at the time of user data execution. * Attempted to resolve this with a 60-second sleep delay, but it was unsuccessful. * New approach identified: using SSM documents to automate agent installation post-boot. * Will implement this alternative and move the changes to code review. * A meeting will be scheduled following successful implementation. | 16/Jun/25 10:04 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# *Used SSM Documents to Automate Agent Installation*Â * We leveraged *AWS SSM Run Command* documents instead of manual scripts or hardcoding logic.Â * Specifically, we used:Â * {{AWS-ConfigureAWSPackage}} to *install the CloudWatch Agent*Â * {{AmazonCloudWatch-ManageAgent}} to *configure and start the agent* using a *Parameter Store JSON config* named {{/Windows_Monitor_CW}}.Â Â *ðŸ”¹ 2. Embedded SSM Associations in Terraform*Â * Inside our *main EC2 Terraform project*, we embedded two {{aws_ssm_association}} resources:Â * *install_cwagent_windows* â€“ installs CloudWatch agentÂ * *configure_cwagent_windows* â€“ tells the agent to pull its config from {{/Windows_Monitor_CW}} in SSM Parameter Store and start itÂ * Both associations *target EC2 instances by tag*: {{CWAgent = EnabledÂ }} * The EC2 instances were pre-tagged via Terraform to ensure automatic targetingÂ Â *ðŸ”¹ 3. Created a Third Association to Force Re-fetch Config*Â * In some cases, the agent might need to re-fetch its config after the EC2 instance is up and the services are stable.Â * So we created a *third SSM association*: {{force_fetch_start_agentÂ }} * Uses {{AWS-RunPowerShellScript}} to run:Â {{& "C:\Program Files\Amazon\AmazonCloudWatchAgent\amazon-cloudwatch-agent-ctl.ps1" -a fetch-config -m ec2 -c ssm:/Windows_Monitor_CW -sÂ }} Â * This *manually triggers the fetch* of the config from SSM Parameter Store and starts the agent again if neededÂ Â *ðŸ”¹ 4. Split This Trigger into a Separate Terraform Directory*Â * To keep your deployment clean and *modular*, we:Â * Created a new folder: {{terraform/cwagent-trigger/Â }} * Placed only the {{force_fetch_start_agent}} logic in this moduleÂ * Why?Â * This allows you to *run it manually or conditionally* after core EC2 and SSM setups are completeÂ * Ensures *clean execution ordering* and better control in CI/CDÂ * Prevents early execution before the agent is even installedÂ Â *ðŸ”¹ 5. Designed for Platform-Specific Control*Â * Logic is gated with:Â {{count = var.platform == "windows" && var.enable_windows_ssm_association ? 1 : 0Â }} Â * Ensures this entire operation is *executed only for Windows instances*, as Linux would follow a different path.Â | 24/Jun/25 6:54 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;terraform script is enabled with the SSM agent installation, a server deployed in sandbox and have verified it. | 29/Jun/25 8:15 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:15
AM20-492 | Airnavx ¦¦ EC2 Creation using terraform code | Cancelled | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satyabrata Sahoo | Medium | 1760710 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:4b8d8093-596d-4394-a074-4a9a9636f86f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 17:33 | 2026-01-18 21:32 |  |  |  | 0 | As AWS Expert I would like to provision EC2 using terraform so that I can handover to SAA for Airnavx installation Acceptance Criteria: EC2 provisioned successfully using approved AMI Tags applied automatically Instance must have SSM agent installed SSH is enabled only via bastion host Guardduty must detect and monitor instance Instance must publish logs to CloudWatch EC2 must register with org monitoring/alerting |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b9d343f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejt7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | [103 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 06:38 | [13 empty] | 05/Sep/25 8:37 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Closing this as this is a duplicate of [https://vodacom.atlassian.net/browse/AM20-131¦https://vodacom.atlassian.net/browse/AM20-131¦smart-link], hence closing the ticket | [26 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-05 08:38
AM20-493 | Servicenow Payload severity updates for Lambda alarms | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Shreyash Talwekar | Medium | 1835024 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-05 16:34 | 2026-02-05 17:23 |  |  |  | 0 | Enhance the existing Lambda function that triggers when Lambda alarms enter an alarm state. Currently, the function gathers alarm-related metrics, collects function details, and sends an approved payload to ServiceNow. However, severity information from the alarm is not included in the payload. This story addresses that gap by updating the Lambda function to capture and transmit the correct severity level from the alarm to ServiceNow. *Acceptance Criteria:* * Lambda function must include severity details from the alarm in the payload. * Payload sent to ServiceNow should accurately reflect the alarm severity. |  | Faisal Sayed | Harsh Chandra | Shreyash Talwekar |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  | ;20/Nov/25 8:33 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;14400 | [6 empty] | 0 | 14400 |  |  | 0 | 14400 | [12 empty] | 21/Nov/25 7:04 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251121-050425.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187511 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@560f4ab3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxar: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 05:33 | [13 empty] | 20/Nov/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Requirements have been gathered. Lambda function code will be reconfigured to incorporate changes, followed by payload testing. Ticket will be updated upon successful completion of testing. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Lambda function has been updated per requirements to capture severity. A test event was executed to validate behavior and output; results are attached. Test outcome is successful, and the implementation is complete. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251121-050425.png¦width=555,alt="image-20251121-050425.png"! | 24/Nov/25 8:42 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reviewed output, LGTM. | [23 empty] | 1832856 | AM20-264 | Update ServiceNow Payloads with severity | Done | 2025-11-24 08:41
AM20-494 | PROS ¦¦ Pre-requisite of Network components | Done | 3 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1760705 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 15:11 | 2026-01-21 16:13 |  |  |  | 0 | As AWS expert I would like to create/configuration required network pre-requisite so that later on EC2 instance can be provisioned in PROS account Acceptance criteria: The parent account must share private subnet with PROS account using AWS RAM the sharing also includes route tables The IAM user/role in the child account Security group are created in shared VPC NACL are attached at the subnet level |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [13 empty] | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152123.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153300 | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152137.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153299 | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152151.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153301 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3397a03b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejsb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-28 06:31 | [13 empty] | 28/Aug/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;I am looking final LLD based on that i will created required Subnets against platform ready ness. | 12/Sep/25 8:12 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Pieter, all servers can be migrated under single subnet, and there is no requirement for DB server. I have initiated the Platform readyness. | 15/Sep/25 5:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS application platform/network setup has been completed. ¦PROS¦3¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.192/28¦10.40.1.192 - 10.40.1.207¦10.40.1.193 - 10.40.1.206¦14¦/28¦AZ1¦Â ¦ ¦PROS(DR)¦3¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.224/28¦10.40.1.224 - 10.40.1.239¦10.40.1.225 - 10.40.1.238¦14¦/28¦Â ¦AZ2¦ !image-20250915-152123.png¦width=405,height=211,alt="image-20250915-152123.png"! !image-20250915-152137.png¦width=406,height=166,alt="image-20250915-152137.png"! !image-20250915-152151.png¦width=408,height=117,alt="image-20250915-152151.png"! | 16/Sep/25 4:23 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;validated internet is working with the subnet. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:21
AM20-495 | Monitor health and logs of Lamda connector function to troubleshoot issue , if alerts in not processed | Done | 8 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747507 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 20:26 | 2026-01-27 21:01 |  |  |  | 0 | As Product owner I want to monitor health and logs of Lamda connector function so that I can troubleshoot issues quickly when alerts are not processed and ensure reliability of the alerting pipeline Acceptance Criteria: CloudWatch logs are enabled for the Lamda connector function to capture execution details, input events and error messages Cloudwatch Metrices (invocations, errors, throttles, duration) are available for function and updated in real time cloudwatch alarms are configured for * Errors >0 in last 5 minues * Throttles >0 * Duration exceeds timeout threshold A SNS is configured to capture failed Lamda execution Alerts from cloud watch are sent via SNS to notify ServiceNow CloudWatch Logs insights queries are available to quickly identify error trends and assist RCA Lamda health and alerting processing mertics are visulaized in a CloudWatch dashboard. |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 07/Aug/25 2:30 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1137015 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4db73908 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2qr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-07 12:31 | [13 empty] | 07/Aug/25 2:30 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[^LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx] Have attached the lambda detailed sheet. | 25/Aug/25 2:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;the alarms have been created for lambda functions in flysaa-backend and they are created for â€œerrorâ€, â€œthrottleâ€, â€œdurationâ€ and the thresholds are 1, 1 and 30sec respectively. the alarms notifications are now being sent to respective sns topics created which shall in-turn appear into service now dashboard as soon as the threshold values are met. | 25/Aug/25 6:32 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 06:32
AM20-496 | MQ ¦¦ Monitoring and Alert Solution | Blocked | 4 | None( Backlog) |  |  | Diksha Koul | Medium | 1794147 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 18:00 | 2026-01-15 18:27 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if MQ server is stopped |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c39a10 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-02 17:42 | [13 empty] | 02/Nov/25 7:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over* : After creation of the MQ EC2 instance we can start the creation of MQ monitoring and alerting solution. | [29 empty] | To Do | 2025-09-30 10:17
AM20-497 | Airnavx ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620850 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 21:27 | 2026-01-26 00:21 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [8 empty] | AM20-10 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4559db6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 8 | Sprint 9 | Sprint 12 | Sprint 13 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-25 06:58 | [13 empty] | 25/Jun/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Harsh and Deepak update, this need to address after TM1 and informatica servers network action, hence i am keeping this as blocked(As per Harsh update) | 28/Jul/25 8:51 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Currently app under LLD review once review done i will initiate comms for the same. SO this will be moved to next sprint. | 04/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on it according to recent LLD call review. | 07/Aug/25 8:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared, with latest subnet details, i will initiate mail communication with customer/app owner for flows review or in case any additional flows needed they should notify further process. | 12/Aug/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Shared comms to app owner for review and add in case needed any additional flows for the same. | 25/Aug/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms under validation by app owner, so this is right story for spill over to this sprint. | 26/Aug/25 1:04 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Initially after follow-up customer prepared and send comms. # During review i identified as comms as not prepared right way and reshared the same comms to customer for validation. # After continuous 3 days follow-up we have received comms from customer as on date 25th Aug 10:00 PM. # There is no sufficient time to manage this story in this sprint due delay with customer. # Note: It has been communicated customer and management regularly but he took longer time to manage. | 29/Aug/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Reviewed and prepared AirNavX comms for VDC/SITA sheets and same sent app owner for LIFT/CSOC request towards implementation. | 03/Sep/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been reviewed and submitted to app owner for further process. | 03/Sep/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Albert has been submitted requested LIFT and CSOC request for ports androuting implementation. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 03/Sep/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The below is the current status: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Routing already in place hance not required any action on this and making this as completed.) | 08/Sep/25 6:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [15 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:36
AM20-498 | Informatica Server - Dev ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1749537 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 14:11 | 2026-01-28 16:33 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 57600 |  | 0 | 86400 | 57600 | [9 empty] | AM20-145 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b90196e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0datf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 14:28 | [13 empty] | 18/Aug/25 4:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev MGN template has been configured, now we are looking AWS migration agent installation on server for sync, Sinjun going to take care tomorrow for the same i have scheduled the call. | 19/Aug/25 5:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;While checking AWS agent connectivity not working, checking with network team for further troubleshooting/fixing the issue. CSOC request has-been createdâ€CINC0909706â€ | 25/Aug/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network routing not implemented, currently it under approval process. | 26/Aug/25 1:11 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Firewall rules implemented. # Configured MGN agent setup on AWS for dev server migration. # Identified as connectivity not working. # Initiated network troubleshooting call towards fixing. # Identified as routing not configured. # Requested LIFT for approval # LIFT approval took 3days # Monday CSOC request raised and routing has ben implemented. # Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 29/Aug/25 8:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev agent installation and Test instance setup has been complted. | 01/Sep/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The test instance connectivity has been completed. Communicated to Peter for connectivity testing. The ip address is: 10.42.0.46. Sending this request for closing. | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-499 | PROS ¦¦ Monitoring and Alerting Servers post migration | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773954 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 21:48 | 2026-02-07 00:32 |  | 2025-10-31 17:21 |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if PROS service is stopped |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@37ad6335 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 |  | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [65 empty] | YES | YES | 2025-10-31 12:27 | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [12 empty] | 31/Oct/25 2:26 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Post Migration: I have installed the SSM Agent for all the PROS prod instances. Configured CloudWatch Agent. Created Systems Manager Parameters for the CloudWatch Agent to fetch the config. Custom Metrics part completed. Monitoring done. Alerts generated for the metrics. | 31/Oct/25 5:20 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-10-31 17:21
AM20-500 | Extend Codepipeline modules for bitbucket and custom stages - POC over sandbox | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1824325 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 13:46 | 2026-01-12 15:37 | 2026-01-08 08:39 |  |  | 0 | *Description:* Enhance existing CodePipeline Terraform modules to support Bitbucket as a source and allow configurable custom stages for improved flexibility and reuse. *Acceptance Criteria:* * Bitbucket source integration added and configurable via variables. * Custom pipeline stages supported through module inputs. * Existing Bitbucket pipelines remain unaffected. * Validation done for both GitHub and Bitbucket pipelines. | [19 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6747613f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptvb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | In Progress | 2026-01-06 08:25
AM20-501 | Security Hardening Audit and Analysis for FLYSAA Backend | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Sumit Nikam | Medium | 1886488 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 14:38 | 2026-01-13 17:43 | 2026-01-08 08:41 |  |  | 0 | As an Internal Auditor, I want to review EKS control plane security configurations across all production accounts, IAM authentication and Kubernetes RBAC mappings, Audit Node & Worker Security Controls, Audit Network Security & Traffic Controls, Audit Pod & Workload Security Posture, Audit Secrets Management & Data Protection So that gaps against AWS and Kubernetes security benchmarks are identified, Acceptance Criteria * EKS cluster version documented per account * API endpoint exposure (public/private) recorded * Allowed CIDR ranges captured * Control plane logging status verified * Secrets encryption (KMS / default) documented * Evidence stored (CLI output / console screenshots) * Gaps mapped to CIS EKS benchmark controls * IAM users vs roles usage documented * aws-auth ConfigMap reviewed * Cluster-admin bindings identified * Namespace vs cluster scoped access recorded * IRSA adoption status captured * Evidence collected (RBAC YAML, IAM role list) * High-risk access clearly flagged * Node type (Managed / Self-managed / Fargate) documented * AMI patching and update mechanism recorded * Node IAM role permissions reviewed * IMDS version (v1/v2) verified * SSH access presence documented * Evidence retained (Launch Template / ASG config) * NetworkPolicy enforcement status recorded * Default deny posture verified * Ingress exposure documented (public/private) * WAF & TLS configuration reviewed * Egress paths documented * Evidence retained (manifests, ALB config) * Pod Security Standards status documented * Privileged pods identified * Containers running as root recorded * Linux capabilities usage reviewed * Secrets usage method documented * Evidence retained (pod specs, namespace labels) * Image registries used documented * Image scanning availability verified * CVE handling process reviewed * Image tagging strategy recorded * Admission control presence documented * Evidence captured (CI logs, ECR settings) * Secret storage mechanisms documented * Encryption at rest/in transit verified * Secrets rotation capability reviewed * Backup and restore process recorded * Evidence retained (KMS config, secret manifests) * Control plane & workload logs documented * Log centralization status verified * Runtime threat detection presence reviewed * Alerting and escalation paths documented * SIEM integration status captured * Evidence retained (CloudWatch, GuardDuty) * GitOps vs manual change model documented * Policy enforcement tooling identified * Change approval records reviewed * Ownership & RACI clarity assessed * CIS / ISO alignment documented * Findings categorized (High / Medium / Low) * Risk statement defined for each gap * Affected accounts listed * Evidence referenced * Recommendations documented separately * Executive summary prepared |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [11 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@26af9eed | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0px2z: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-08 06:30 | [13 empty] | 08/Jan/26 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Initial discovery has been started post discussion. Working on Kyverno issue first in-order to have necessary violations report. | [29 empty] | In Progress | 2026-01-08 08:28
AM20-502 | Nexio AV¦¦ Migration tool installation / New Set-up | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620531 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 14:43 | 2026-01-31 17:25 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the Nexio AV SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [6 empty] | AM20-13 | AM20-15 | [5 empty] | 05/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;NexioAV-Replacement.pdf;https://vodacom.atlassian.net/rest/api/3/attachment/content/1110196 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ac52572 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:u | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:25 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked due to [https://vodacom.atlassian.net/browse/AM20-15¦https://vodacom.atlassian.net/browse/AM20-15¦smart-link] network story, upon completion will pick this up. | 21/Mar/25 12:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AirnavX migration discussion is still on-going, post that network setup will be created along with connectivity. After the connectivity established, will be able to pick this migration agent toll installation for AitnavX. | 02/May/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for Network setup with internet access to be in place with all required route entry. | 16/May/25 8:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting on network matrix implementation and confirmation. waiting for centralized subnet on transit gateway creation and confirmation from [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 04/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Story to be dropped, migration is not applicable for this application whereas fresh installation is planned with a new EC2 instance. | 05/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;[^NexioAV-Replacement.pdf] | 05/Jun/25 8:32 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Requirement is changed as part of attached email, hence closing this one. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-05 08:31
AM20-503 | Informatica Server ¦¦ Back up and DR | Done | 5 | Sprint 13 | 2025-09-01 | 2025-09-12 | Aravind Raj | Critical | 1751441 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 15:29 | 2026-01-15 16:12 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Informatica-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM h2. Confluence content |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;30/Sep/25 6:38 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;13/Oct/25 6:32 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;43200 |  |  |  |  | 72000 | 0 | 72000 | 1 | 72000 | 0 | 72000 | [12 empty] | 13/Oct/25 6:32 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251013-163227.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1167346 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@76f244a1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabl: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | Sprint 16 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 07:22 | [13 empty] | 05/Sep/25 9:21 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Informatica Test server is launched and trying to fix connectivity issue. Only after the cutover launch we will be able to configure DR and backup solution for this server, so this will be a spillover. | 22/Sep/25 8:44 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This is a spillover due to the dependent userstory - [[AM20-140] Informatica Server ¦¦ Cutover - Jira¦https://vodacom.atlassian.net/browse/AM20-140], only after cutover we would be able to do backup and DR setup. | 30/Sep/25 6:37 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Since Cutover is completed have started working on setting UP DR, will be completing in sometime. | 03/Oct/25 9:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Backup is completed, DR is in progress, waiting for DR drill to complete. send a mail on asking for slot with app owner to perform DR drill, upon drill completion with complete this US. | 09/Oct/25 6:29 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;DR Drill is planned today with albert at 1:30PM, looking forward to complete the drill. | 13/Oct/25 6:32 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Drill is completed successfully. !image-20251013-163227.png¦width=1278,height=489,alt="image-20251013-163227.png"! | [24 empty] | Done | 2025-10-13 18:32
AM20-504 | Guardy duty and Guardrail implementation on Pegasys account | To Do | 0 | None( Backlog) |  |  |  | Medium | 1835991 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 19:06 | 2026-01-21 21:49 |  |  |  | 0 | [57 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@69378c41 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g000i | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-13 19:35
AM20-505 | Restrict Admin access to VOIS team by creating dedicated IAM role | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Medium | 1736354 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 17:55 | 2026-01-23 19:21 |  |  |  | 0 | As Product Owner, I want to restrict VOIS team to have Admin role so that all of them cannot be superseded rights and bring more control on AWS management Acceptance criteria: * IAM role to be created for everyone except Sankalp and Aravind from AWS perspective * IAM role for network creation to be created and role assign to Satya * IAM role for rest of team members is of developer |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6edd432e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0c5zn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 06:20 | [13 empty] | 06/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have shared the Excel with the user list to team, upon there confirmation ill start creating custom policy with user groups. | 08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;¦UserID¦IAM user¦UserGroup¦IAM Role¦ ¦raja0001¦Aravind¦VOIS_Admin¦No changes, use existing roles itself¦ ¦rais0003¦Sankalp¦VOIS_Admin¦No changes, use existing roles itself¦ ¦SatyasairamV¦SatyaSairam¦VOIS_Admin¦No changes, use existing roles itself¦ ¦godir001¦Ravinder¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦kiraj001¦Jitender¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Sanjot¦Sanjot¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦nikas001¦Sumit¦VOIS_Admin¦No changes, use existing roles itself¦ ¦FaisalSayed¦Faizal¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SanketKale¦Sanket¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦pathp002¦Pankaj¦VOIS_DBAdmin_Usergroup¦AWS_VOIS_DBAdmin_Role¦ ¦onkar¦Onkar¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦DikshaK¦Diksha¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SatyabrataS¦SatyaBrata¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Shreyash¦Shreyash¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Harsh¦Harsh¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Yashwant¦Yashwant¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Utkarsh¦Utkarsh¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ Â Â Access to User group given as below, ¦VOIS_InfraAdmin_Usergroup¦VOIS_DevOpsAdmin_Usergroup¦VOIS_DBAdmin_Usergroup¦ ¦VPC FullAccess¦CodeBuild FullAccess¦RDS Full Access¦ ¦EC2 FullAccess¦CodePipeline FullAccess¦DMS Full Access¦ ¦S3 FullAccess¦EKS FullAccess¦IAM Full Access¦ ¦CloudWatch FullAccess¦EC2 except delete¦CloudTrail except delete¦ ¦RDS FullAccess¦S3 FullAccess¦KMS except delete¦ ¦IAM FullAccess¦CloudWatch except delete¦CloudWatch except delete¦ ¦CloudTrailFullAccess¦RDS except delete¦Read only¦ ¦MacieFullAccess¦IAM FullAccess¦ ¦ ¦GuardDutyFullAccess¦System managerFullAccess¦ ¦ ¦SecurityHubFullAccess¦LambdaFullAccess¦ ¦ ¦System managerFullAccess¦Event bridgeFullAccess¦ ¦ ¦LambdaFullAccess¦CloudTrail except delete¦ ¦ ¦KMSFullAccess¦Read only¦ ¦ ¦ACMFullAccess¦Secrets managerFullAccess¦ ¦ ¦Aws ConfigFullAccess¦SNSFullAccess¦ ¦ ¦Event bridgeFullAccess¦SESFullAccess¦ ¦ ¦InspectorFullAccess¦ECR FullAccess¦ ¦ ¦SupportFullAccess¦KMS except delete¦ ¦ ¦SNSFullAccess¦Â ¦ ¦ ¦SESFullAccess¦ ¦ ¦ ¦ReadOnly¦ ¦ ¦ ¦Secrets managerFullAccess¦ ¦ ¦ ¦ECRFullAccess¦ ¦ ¦ Â Users have access to the below AWS accounts, Â ¦AWS Account¦Account Name¦ ¦300204747992¦Audit¦ ¦730335236533¦Security¦ ¦080284287007¦LogArchive¦ ¦339712943527¦Network¦ ¦864899875361¦SharedServices¦ ¦585768167545¦SharedVpcDev¦ ¦253490777663¦SharedVpcPreprod¦ ¦820242899278¦SharedVpcProd¦ ¦746669190453¦Backend dev¦ ¦216989128782¦Backend Preprod¦ ¦396608788916¦Backend Prod¦ ¦209479274829¦Tm1¦ ¦345594574792¦AirNAVx¦ ¦536697265099¦NexioAV¦ | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-506 | Route53 ¦¦ Alert Configuration | In Progress | 6 | Sprint 22 | 2026-01-05 | 2026-01-16 | Satya Varanasi | Medium | 1881343 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 20:53 | 2026-01-19 22:37 | 2026-01-08 08:39 |  |  | 0 | As a cloud infra platform team I want to implement automated alerting for Route53 DNS health, record changes and DNS health, record changes and DNS failover so that application teams and support teams can proactively detect outages, unauthorized changes and DNS failures across all AWS accounts. Acceptance Criteria: # Route 53 Health Check Alerts * Health checks must be created for all critical endpoints (HTTP, 1. HTTPS, TCP, or CloudWatch metric-based). * Â A CloudWatch alarm must automatically trigger if the health check status = Unhealthy. * Â Alarm must send a notification to an SNS topic configured for the environment (Dev/Pre-Prod/Prod). * Â Health check status must be visible on the central monitoring dashboard. # DNS Failover Alarms * Â Failover configurations (Primary/Secondary records) must be validated after deployment. * Â A CloudWatch alarm must trigger when Route 53 performs an automated failover action. Â Notification must include: * Â hosted zone name * Â record name * Â failover type (PRIMARY â†’ SECONDARY) * Â timestamp Â Application team must receive ServiceNow notification immediately. Â All failover events must be recorded in audit logs (CloudTrail). # Hosted Zone Change & Record Modification Alerts Â CloudTrail must be enabled for all Route 53 API events: * Â CreateHostedZone * Â ChangeResourceRecordSets * Â DeleteHostedZone 4.Â An EventBridge rule must detect record or zone changes and send alerts to SNS. Alert must contain: * user/role who made the change * old value vs new value * timestamp * AWS account ID # Unauthorized changes must automatically raise a ticket in ServiceNow/JIRA (if integrated). * All record changes must be stored for audit (S3/CloudTrail). * DNS Query Volume / Anomaly Alerts * Â CloudWatch metric "DNS Queries" must be monitored for abnormal spikes or drops. * Â CloudWatch Anomaly Detection must be configured with proper thresholds. * Â Alerts must trigger when query volume deviates beyond normal traffic window. * Â Notification must reach platform + application teams. * Â Alerts must indicate possible DDoS, misconfiguration, or routing issue.Â * DNS Latency or Resolver Issue Alerts * Â Route 53 Resolver metric "ResolverQueryError" or "DNS Resolution Failure" must be monitored. * Â Alerts must trigger when error rate exceeds threshold (ex: >5% errors for 5 mins). * Â Alerts must include resolver IP, VPC ID, region. * Â Incident must be auto-created in monitoring tool.Â # Alert Routing & Escalation * Â Alerts from all child accounts must centralize into a single parent-account SNS topic using cross-account permissions. * Â Separate channels must exist for PROD vs NON-PROD. * Â Severity mapping must follow organizational incident guidelines (SEV-1, SEV-2, SEV-3) # Â A centralized CloudWatch dashboard must show: * Â health check status * Â failover events * Â DNS query traffic * Â record change logs * Â Dashboard must be accessible from parent account to all authorized users. * Â Dashboard updated in near real-time (<1 min delay).Â # Security & Governance * Â IAM policies must restrict record modification to authorized roles. * Â All Route 53 API calls must be captured via CloudTrail. * Â Patchable misconfigurations (e.g., TTL mismatch, missing health checks) must be flagged automatically. * Â Alerts must comply with compliance policies (PCI, CIS benchmarks if applicable). # Integration Requirements * Â SNS must integrate with: * Â ServiceNowÂ * Alert payload must follow a standard message template. 10. Testing & Validation * Test failover must generate an alert. * Test manual record change must generate an audit alert. * Test endpoint failure must trigger "Unhealthy" alarm. |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2e5b4dfc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptvd: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-07 14:38 | [13 empty] | 07/Jan/26 4:38 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working on it. | [29 empty] | In Progress | 2026-01-08 08:27
AM20-507 | TM1 ¦¦ Integration of AWS IAM roles with TM1 AWS Account Instance using JSON | Done | 10 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642068 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 13:34 | 2026-02-06 13:40 |  |  |  | 0 | As AWS expert, I would be integrating AWS IAM roles with TM1 Instance Acceptance criteria: * IAM roles are created successfully * Integration of defined IAM roles with TM1 instance so that user is able to access the TM1 instance. |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5190a6ea | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-09 07:30 | [13 empty] | 09/Jul/25 9:29 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Following are the details of the role created: role_arn = "arn:aws:iam::209479274829:role/TM1-IAMRole-EC2InstanceProfile" role_name = "TM1-IAMRole-EC2InstanceProfile" Account details: 209479274829 (SAA-TM1) Custom Role Details: The role covers the equivalent of â€œAmazonSSMManagedInstanceCoreâ€, basic CloudWatch Agent permissions, and general S3 access. _*NOTE*: THE FOLLOWING HAS BEEN ACHIEVED USING TERRAFORM._ | 09/Jul/25 9:30 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;.json file of the custom role is as follows: { Â "Version": "2012-10-17", Â "Statement": [ Â Â { Â Â Â "Sid": "SSMManagedInstanceCorePermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssm:DescribeAssociation", Â Â Â Â "ssm:GetDeployablePatchSnapshotForInstance", Â Â Â Â "ssm:GetDocument", Â Â Â Â "ssm:DescribeDocument", Â Â Â Â "ssm:GetManifest", Â Â Â Â "ssm:GetParameter", Â Â Â Â "ssm:GetParameters", Â Â Â Â "ssm:ListAssociations", Â Â Â Â "ssm:ListInstanceAssociations", Â Â Â Â "ssm:PutInventory", Â Â Â Â "ssm:PutComplianceItems", Â Â Â Â "ssm:PutConfigurePackageResult", Â Â Â Â "ssm:UpdateAssociationStatus", Â Â Â Â "ssm:UpdateInstanceAssociationStatus", Â Â Â Â "ssm:UpdateInstanceInformation" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "SSMMessageGatewayPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssmmessages:CreateControlChannel", Â Â Â Â "ssmmessages:CreateDataChannel", Â Â Â Â "ssmmessages:OpenControlChannel", Â Â Â Â "ssmmessages:OpenDataChannel" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "EC2MessagesPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ec2messages:AcknowledgeMessage", Â Â Â Â "ec2messages:DeleteMessage", Â Â Â Â "ec2messages:FailMessage", Â Â Â Â "ec2messages:GetEndpoint", Â Â Â Â "ec2messages:GetMessages", Â Â Â Â "ec2messages:SendReply" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "CloudWatchAgentPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "logs:CreateLogGroup", Â Â Â Â "logs:CreateLogStream", Â Â Â Â "logs:PutLogEvents", Â Â Â Â "logs:DescribeLogGroups", Â Â Â Â "logs:DescribeLogStreams", Â Â Â Â "cloudwatch:PutMetricData" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "S3AccessPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "s3:GetObject", Â Â Â Â "s3:PutObject", Â Â Â Â "s3:ListBucket" Â Â Â ], Â Â Â "Resource": "*" Â Â } Â ] } | 11/Jul/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed IAM roles is having required permissions | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-508 | MQ ¦¦ Monitoring and Alert Solution | Blocked | 4 | None( Backlog) |  |  | Diksha Koul | Medium | 1794147 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 21:31 | 2026-01-13 01:01 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if MQ server is stopped |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c39a10 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-02 17:42 | [13 empty] | 02/Nov/25 7:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over* : After creation of the MQ EC2 instance we can start the creation of MQ monitoring and alerting solution. | [29 empty] | To Do | 2025-09-30 10:17
AM20-509 | PROS ¦¦ LLD Creation | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sankalp Rai | Medium | 1749504 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 13:18 | 2026-01-21 14:39 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1809d79f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0danv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | Sprint 15 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 06:06 | [13 empty] | 06/Oct/25 8:05 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;LLD document created. | 06/Oct/25 8:07 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;[PROS_Low Level Design Document_v1.0.docx¦https://vodafone.sharepoint.com/:w:/r/sites/SouthAfricaAirlines/Shared%20Documents/Technical%20Documents/SAA%20Design%20documents/LLD%20Documents/Wave%202%20apps/PROS%20LLD/PROS_Low%20Level%20Design%20Document_v1.0.docx?d=w4faebf320e0f4c53aedb5b192660de4f&csf=1&web=1&e=jOZXIo] | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-10-06 08:07
AM20-510 | Alignment of AWS account in Control tower | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | Highest | 1660079 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-15 19:55 | 2026-01-15 23:40 |  |  |  | 0 | As AWS expert, I would like to perform clean-up the account in control tower that is not needed and perform changes in control tower w.r.t changes in optimization of workload utilization *Acceptance Criteria*: * Clean-up account in control tower is successfully completed * Identified workload utilization are optimized successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;19/May/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@44b8caa8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i039nf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-14 06:28 | [13 empty] | 14/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will connect with takura today and initiate a modification to the hierarchy of AWS accounts under AWS organizations. | 19/May/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CMS Front Dev/QA > FLYSAA OU (Workload OU) Backend > FLYSAA OU (Workload OU) 730335236533 AWS_SAA_Security (Check for services) >>Infra OU 339712943527 AWS_SAA_Network (Check for Services) >> > Infra OU Â | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-19 08:09
AM20-511 | MQ ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Blocked | 0 | Sprint 16 | 2025-10-13 | 2025-10-24 | Satya Varanasi | Medium | 1758329 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 15:50 | 2026-02-04 16:06 |  |  |  | 0 |  |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4544ef36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g02 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-17 09:19 | [13 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | [29 empty] | To Do | 2025-08-18 16:44
AM20-512 | Patch Management ¦¦ Dashboard Enhancement | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1746156 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 14:31 | 2026-01-27 15:14 |  |  |  | 0 | As Product manager compliance dashboard needs to be enhance and should covered details of patch file Acceptance Criteria: Compliance dashboard need to patch details and account details |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4159e3f0 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cz63: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 20:35 | [13 empty] | 18/Aug/25 10:34 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Update for Patch Manager Monitoring, in the compliance bucket there are 3 folders created after creating the resource data sync but not for the target acc we need. i have changed certain policies and also added some permissions both in security as well as dev acc. I am waiting for the data to pop up and also i can trigger data collection forcefully via aws cloudshell command but i do not have access i have intimated Aravind for permission addition. and the data that is being collected is basically json and that is the format that we need for it to be visualized in cloudwatch. | 25/Aug/25 8:52 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;spillover: the data sync which has been created in the management acc theoretically should be able to fetch the summaries from target account and sync that data in the s3 bucket in central account. the steps that were tried to force a sync were: {code:json}Check if the Instance is Managed by Systems Manager Check Current Associations Check Current Inventory Data Create the Inventory Association Verify Association Creation Check Association Status Monitor Association Execution Check for Updated Inventory Data{code} All of these were done and created an association manually for it to be populated into s3 bucket yet it did not work. the permission policies are provided yet the target account data is not being synced. the issue was that resource data sync must be created in each of the target account which was earlier thought as not needed. have created ressource data sync and waiting for the data to be populated. | 28/Aug/25 8:34 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Spillover Revised Comment: I was troubleshooting the resource data sync that i created since theoretically, resource data sync in the management account was enough. After rigorous attempts to fix the issue and trying to find out the workarounds they all failed. At the end of the week, close to sprint closure I found the solution and applied it and the solution worked. Hence, the delay and also for the data to populate into the intended bucket it sometime takes 10-12 hrs. | 03/Sep/25 8:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# The Resource Data Sync has been troubleshoot correctly and is working as intended. # Lambda function has been created in backend-dev account so that it can brand all the instances as non-compliant initially. # EventBridge has been configured as such when any new instance is provisioned it shall be flagged as non-compliant using the lambda function mentioned in point no.2. # The data in S3 is being used to project it to CloudWatch and that is being do using a Lambda function which will create metrics from the data in S3. # CloudWatch Dashboard is created such that it will have visual data segregated acc to the Acc Ids. (which was requirement by Bhavish). | 08/Sep/25 6:35 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;need demo | 08/Sep/25 8:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: The story was completed sufficing all the acceptance criteria. Demo was not done due to unavailability, hence scheduling the demo for 9/9/2025 considering everyoneâ€™s availability. | 11/Sep/25 9:12 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Demo was provided. The methodology and implementation was agreed upon and approved. There was an ask to involve another accounts, in order to check the workability. The accounts addition was done successfully and the data is presented on the custom dashboard as well. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:20
AM20-513 | (Airchef)Terraform code generation for Route 53 Hosted Zone Creation & Record Migration. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Faisal Sayed | Medium | 1827706 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-30 13:08 | 2026-01-30 16:26 |  |  |  | 0 | Hosted Zone Creation Develop infrastructure-as-code to provision a Route 53 hosted zone for the specified domain. The configuration should support tagging, environment-specific naming, and be reusable across deployments. DNS Record Management Implement a declarative script to define and manage DNS records within the hosted zone. This should include support for common record types (A, CNAME, MX, TXT) with configurable TTLs and values. |  | Faisal Sayed | Sanket Kale |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e |  |  |  |  | ;12/Nov/25 10:17 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 |  |  |  |  | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@53b50383 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1v7: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:56 | [13 empty] | 07/Nov/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status: Blocked* Awaiting SAA approval for the updated DNS records associated with the {{airchef}} domain. Terraform provisioning is currently on hold until the DNS configuration is finalized. | 12/Nov/25 6:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status Update:* * Task moved from *Blocked* to *In Progress*. * Terraform code for Route 53 provisioning has been developed and handed over to *Sanket*. * *Next Action:* Sanket to review and execute the code in the *sandbox account* for validation. | 12/Nov/25 6:55 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform code has been successfully reviewed and tested in the sandbox environment, and all validations are positive. Â | 12/Nov/25 10:16 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Code has been reviewed, tested successfully, and validated. Moving the sub-story to *Done*. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-12 10:12
AM20-514 | AirNavX ¦¦ Budget Management Configuration | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772224 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 14:16 | 2026-02-05 18:04 |  |  |  | 0 | As AWS expert I would like to configure AirNavX budget management and alerts so that stakeholders gets the frequent notifications on budgets and alerts if the budget crosses threshold Acceptance Criteria: * Budget management for AirNavX is configured successfully * Alerts triggered if the budget crosses 80%, 85% and 90% of Threshold |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [9 empty] | AM20-165 |  |  |  | 18/Sep/25 10:42 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250918-084042.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1155392 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7cf7b049 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq0j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-09 06:42 | [13 empty] | 09/Sep/25 8:42 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created the Budget on management account for Airnavx now will be adding the account and application owner mail idâ€™s in the lambda function. | 09/Sep/25 11:01 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have set the threshold value to 80%, 85% & 90% now will add the account details and application owner mail id in the lambda function. | 15/Sep/25 11:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have added the Account name and application owner email ids in lambda function also tested the budget alerting and we are successfully getting the alerts for budget management. | 18/Sep/25 10:42 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8; !image-20250918-084042.png¦width=860,height=569,alt="image-20250918-084042.png"! Attached is the screenshot as an evidence that we are getting the alert email if the threshold value exceeds more than the utilized budget value. | 18/Sep/25 2:45 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Demo was given to Yashwant today still wants Aravind to review the same. | 22/Sep/25 8:36 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;the threshold of budget should be calculated based on the all the resources involved in the architecture and LLD, though its modifiable, i would suggest to update the value in firsthand itself. | [24 empty] | Done | 2025-09-22 08:50
AM20-515 | Nexio AV ¦¦ E2E Integration testing of ServiceNow monitoring | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1732203 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 15:28 | 2026-01-10 15:45 |  |  |  | 0 | As Product Owner I would like to review e2e testing completed with servicenow team for all wave 1 application so that we can confirm to business that in case of any issue service ticket would be raised Acceptance Criteria: * Tickets/issues are getting raised successfully against the alerts raise via cloudwatch for all Wave1 applications * ServiceNow team signoff received * Showcase (demo) provided to all relevant stakeholders |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 19/Aug/25 10:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141324 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1c3893f7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0brrj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-28 07:41 | [13 empty] | 28/Jul/25 9:41 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[https://vodacom.atlassian.net/browse/AM20-116¦https://vodacom.atlassian.net/browse/AM20-116¦smart-link] Only after completing the above US will start working on this story. | 28/Jul/25 3:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;After completion of Faisal story i will be proceeding with this US. | 11/Aug/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: Since the story was blocked due to configuration of monitoring and alerting on NexioAV ec2 instances (application specific) which was completed on 8th Aug 2025 (evening), Diksha did not get any time to validate end to end solution. Hence, the spillover. | 19/Aug/25 10:17 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have tried to triggered the alert to service now team. Now waiting for them to confirm from there side. | 19/Aug/25 10:33 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation for Priyanka and team the alerts are getting generated and tickets are being created in service now. Attaching the same screenshot for the reference. | 19/Aug/25 10:36 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image.png¦width=881,height=228,alt="image.png"! attaching the screenshot what service now team is getting the alerts for your reference from Priyanka and team. | 21/Aug/25 2:31 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:31
AM20-516 | PROS ¦¦ setup and validate SG and NACL | Done | 2 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1773949 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 14:00 | 2026-01-18 14:50 |  |  |  | 0 | As AWS network expert I would like to setup the security group and NACL for PROS so that access for Pros allow secure access to allow communication with its services while ensureing access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for PROSor related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1df9f068 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwq3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-25 15:31 | [13 empty] | 25/Sep/25 5:31 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SG and NACL setup has been completed, application ports relevant port need to be configured, this will be ready once test server setup process ready. | 09/Oct/25 4:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SG & NACL has been configured and handed over to customer. | 17/Oct/25 7:14 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-10-17 07:14
AM20-517 | Patch Solution cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818696 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-21 18:39 | 2026-01-21 21:18 |  |  |  | 0 |  |  | Aravind Raj | Faisal Sayed |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@698194ac | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzvv: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-31 09:18 | [13 empty] | 31/Oct/25 11:17 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;The Patching instances are still needed, it shall be in stopped state when not in use and terminated once the patching demo is done which has been postponed. [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] [~accountid:712020:54791a09-30fd-4ab7-8a1d-068b13e544d8] | [26 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-11-14 20:26
AM20-518 | PROS¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773953 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 21:05 | 2026-02-02 23:02 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4ce03565 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:04 | [13 empty] | 24/Sep/25 8:04 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS migration agent comms has been implemented. SAA = REQ0056503 (CHG0067695) CSOC = CHR0027812 | 25/Sep/25 5:24 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still CSOC under approval, also we have identified as some miss match in Agent Comms. I have updated and shared to Wanda for CSOC updation. | 06/Oct/25 8:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over - Comms implementation delayed from SAA, hence will be spilled over and worked upon in subsequent sprint | 09/Oct/25 4:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration agent comms has been implemented and agent has been installed n all 3 PROS servers, Created test instance and handover to customer for testing. | 17/Oct/25 7:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:16
AM20-519 | Push to FlySAA backend Alarm related code to the bitbucket in dev and preprod environment | Done | 8 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786761 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 18:25 | 2026-01-29 22:22 |  |  |  | 0 | Add existing terraform code to create CloudWatch alarms and other required AWS resources into the bitbucket. Add alarms for following: # Kubernetes microservice CPU and Memory consumption alarms for Amadeus and Fabric microservices. # Error Patterns observed in microservice logs. # Healthcheck API endpoint return status monitoring. # Configured Alerts to monitor RDS metrics. Also create EventBridges to capture alarm state change (Ok â†’ Alarm and Alarm â†’ Ok). Create Lambda jobs to be triggered by EventBridge which in turn sends notification to ServiceNow using existing SNS topics. |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7d9f3978 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hatj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-29 08:07 | [13 empty] | 29/Sep/25 10:07 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Added alerts for monitor error patterns in microservice logs for dev account . Added alerts for monitor cpu, memory and container restart for dev account for dev account . | [29 empty] | Done | 2025-10-06 07:59
AM20-520 | Nexio AV¦¦ Migration tool installation / New Set-up | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620531 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 17:06 | 2026-01-14 17:27 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the Nexio AV SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [6 empty] | AM20-13 | AM20-15 | [5 empty] | 05/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;NexioAV-Replacement.pdf;https://vodacom.atlassian.net/rest/api/3/attachment/content/1110196 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ac52572 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:u | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:25 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked due to [https://vodacom.atlassian.net/browse/AM20-15¦https://vodacom.atlassian.net/browse/AM20-15¦smart-link] network story, upon completion will pick this up. | 21/Mar/25 12:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AirnavX migration discussion is still on-going, post that network setup will be created along with connectivity. After the connectivity established, will be able to pick this migration agent toll installation for AitnavX. | 02/May/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for Network setup with internet access to be in place with all required route entry. | 16/May/25 8:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting on network matrix implementation and confirmation. waiting for centralized subnet on transit gateway creation and confirmation from [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 04/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Story to be dropped, migration is not applicable for this application whereas fresh installation is planned with a new EC2 instance. | 05/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;[^NexioAV-Replacement.pdf] | 05/Jun/25 8:32 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Requirement is changed as part of attached email, hence closing this one. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-05 08:31
AM20-521 | ServiceNow ¦¦ SNS Topic for Alerts | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650429 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 15:40 | 2026-02-05 17:28 |  |  |  | 0 | AS AWS Expert, I want to create an Amazon SNS topic so that AWS services can be publish alert messages to it. Acceptance Criteria: * AN SNS topic is created * Permissions are set to allow EventBridge and Lamda to publish to it * The topic supports the subscription |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@505787e3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [66 empty] | Unit Tested | [51 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-06 06:23 | [13 empty] | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed, and will modify the required configurations. Â· | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:38
AM20-522 | PROS ¦¦ Monitoring and Alerting Servers post migration | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773954 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 15:40 | 2026-02-05 19:27 |  | 2025-10-31 17:21 |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if PROS service is stopped |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@37ad6335 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 |  | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [65 empty] | YES | YES | 2025-10-31 12:27 | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [12 empty] | 31/Oct/25 2:26 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Post Migration: I have installed the SSM Agent for all the PROS prod instances. Configured CloudWatch Agent. Created Systems Manager Parameters for the CloudWatch Agent to fetch the config. Custom Metrics part completed. Monitoring done. Alerts generated for the metrics. | 31/Oct/25 5:20 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-10-31 17:21
AM20-523 | MQ ¦¦ Monitoring and Alert Solution | Blocked | 4 | None( Backlog) |  |  | Diksha Koul | Medium | 1794147 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 13:58 | 2026-01-20 15:40 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if MQ server is stopped |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c39a10 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-02 17:42 | [13 empty] | 02/Nov/25 7:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over* : After creation of the MQ EC2 instance we can start the creation of MQ monitoring and alerting solution. | [29 empty] | To Do | 2025-09-30 10:17
AM20-524 | Patch Management ¦¦ Life Cycle ¦¦ Implement Retention Policy in S3 busket | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1746117 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 13:26 | 2026-01-20 16:38 |  |  |  | 0 | As Product Owner I want to implement retention policy on S3 server so that download files can be managed Acceptance Criteria: * Retention policy is implemented on S3 * Post retention period file getting deleted successfully |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@401c6aaa | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 07:07 | [13 empty] | 12/Aug/25 9:07 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Retention rule for central patching bucket is as follows: the rule is created for prefix filters like (windows/dev/, windows/preprod/, windows/prod/, linux/dev/, linux/preprod/, linux/prod/) After 60 days objects within the path shall expire. | 20/Aug/25 8:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-20 08:10
AM20-525 | AirNavX ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672697 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-28 13:16 | 2026-01-28 16:32 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across AirNavX account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cdd392e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04fqr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 06:27 | [13 empty] | 20/May/25 8:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on enabling the cloud config and guard duty along with macie. | 22/May/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;below mentioned service were enabled. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-22 08:19
AM20-526 | TM1 ¦¦ Configuring Application specific error in Cloudwatch for alerting | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730283 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 19:08 | 2026-01-19 20:40 |  |  |  | 0 | As a AWS expert I want to detect application specific error patterns in CloudWatch logs so that I can generate alerts for ServiceNow ticket creation and respond to runtime failure Acceptance Criteria: * Error pattern is defined and tested * Given an application output logs to cloudwatch when a known error occurs, then the pattern must correctly match that log * Metric filter is created - when error count exceeds the threshold then cloud watch alarm should trigger * Alert notification is sent, given the alarm is triggered when the condition is met then an alert must be sent to relevant teams |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [25 empty] | AM20-116 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3fa4464b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bnb3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:37 | [13 empty] | 04/Aug/25 6:37 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will start working on this from today. | 08/Aug/25 12:05 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Monitoring for specifically reporting & tm1serv application has been set. Alarm for Total Commit Usage has been created and configured to send those to ServiceNow. | 08/Aug/25 12:06 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Moving to Aravindâ€™s bucket for review. | 08/Aug/25 12:30 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;every cloud watch custom metrics are captured as error metrics and create an alarm for same. | 08/Aug/25 12:30 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;create a memoryutilization and disk utilization alarm and move to review | 08/Aug/25 8:43 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Monitoring metric is created for Overall Committed Memory Bytes and then further classified for each service that was mentioned in the mail. Alert has been created for â€œOverall Committed Memory Bytesâ€, so creating alarms for its further classification would be redundant. And in the email, we have a confirmation to create an alarm for â€œTotal Commit Sizeâ€ hence have created for â€œOverall Committed Memory Bytesâ€ and not for the per service. | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-527 | Alignment of AWS account in Control tower | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | Highest | 1660079 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-03 12:30 | 2026-02-03 14:23 |  |  |  | 0 | As AWS expert, I would like to perform clean-up the account in control tower that is not needed and perform changes in control tower w.r.t changes in optimization of workload utilization *Acceptance Criteria*: * Clean-up account in control tower is successfully completed * Identified workload utilization are optimized successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;19/May/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@44b8caa8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i039nf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-14 06:28 | [13 empty] | 14/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will connect with takura today and initiate a modification to the hierarchy of AWS accounts under AWS organizations. | 19/May/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CMS Front Dev/QA > FLYSAA OU (Workload OU) Backend > FLYSAA OU (Workload OU) 730335236533 AWS_SAA_Security (Check for services) >>Infra OU 339712943527 AWS_SAA_Network (Check for Services) >> > Infra OU Â | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-19 08:09
AM20-528 | Configure respective IAM role for TM1 and Nexio business team for Budget management dashboard | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1729920 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 20:11 | 2026-01-31 22:58 |  |  |  | 0 | As Product owner I want to create IAM role specific for Budget management and add business representatives from TM1 and Nexio so that they can able to view dashboards and receive alerts in case these is an unexpected jump in cost or the threshold is crossed. Acceptance Criteria: * IAM role is created successfully * Nexio and TM1 business representative emails gets added in the foresaid role * Test is concluded to ensure emails are getting triggered successfully * walkthrough provided to the relevant stakeholders |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@53ee738a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bm4j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-05 08:17 | [13 empty] | 05/Aug/25 10:16 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;*Group Name* Naming Conventions is Given as "*TM1-Budget-Users-Group*" and "*NexioAv-Budget-Users-Group*" Â Â *Policy name* given Â as "*TM1-BudgetAccess-Policy*" and "*NexioAV-BudgetAccess-Policy*" *ViewAllBudget-Group* is created for only Viewing All Budgets with *ViewAllBudget-Policy* | 05/Aug/25 10:19 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Groups has been created for TM1 and NexioAV Budgets. Users from Respective Group can edit only respective Budgets | 11/Aug/25 4:27 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:26
AM20-529 | Nexio AV ¦¦ E2E Integration testing of ServiceNow monitoring | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1732203 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 21:19 | 2026-02-05 22:33 |  |  |  | 0 | As Product Owner I would like to review e2e testing completed with servicenow team for all wave 1 application so that we can confirm to business that in case of any issue service ticket would be raised Acceptance Criteria: * Tickets/issues are getting raised successfully against the alerts raise via cloudwatch for all Wave1 applications * ServiceNow team signoff received * Showcase (demo) provided to all relevant stakeholders |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 19/Aug/25 10:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141324 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1c3893f7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0brrj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-28 07:41 | [13 empty] | 28/Jul/25 9:41 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[https://vodacom.atlassian.net/browse/AM20-116¦https://vodacom.atlassian.net/browse/AM20-116¦smart-link] Only after completing the above US will start working on this story. | 28/Jul/25 3:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;After completion of Faisal story i will be proceeding with this US. | 11/Aug/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: Since the story was blocked due to configuration of monitoring and alerting on NexioAV ec2 instances (application specific) which was completed on 8th Aug 2025 (evening), Diksha did not get any time to validate end to end solution. Hence, the spillover. | 19/Aug/25 10:17 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have tried to triggered the alert to service now team. Now waiting for them to confirm from there side. | 19/Aug/25 10:33 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation for Priyanka and team the alerts are getting generated and tickets are being created in service now. Attaching the same screenshot for the reference. | 19/Aug/25 10:36 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image.png¦width=881,height=228,alt="image.png"! attaching the screenshot what service now team is getting the alerts for your reference from Priyanka and team. | 21/Aug/25 2:31 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:31
AM20-530 | Centralized Utilization CloudWatch Dashboard | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820131 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 19:10 | 2026-02-02 22:45 |  | 2025-11-14 10:59 |  | 0 | As a cloud finops engineer I want to view utilization metrics of all workloads across all child accounts in one place so that I can identify performance inefficiencies and optimize cost Acceptance Criteria: CloudWatch cross account observability is enabled between Parent and child accounts CloudWatch Dashboards show metrics from EC2, RDS,EKS,S3 and Lamda for each environment Metrics are visualized per account, environment and service * CPU utilization (EC2) * Disk Performance (EC2) * NetworkIn NetworkOut (EC2) * Memory utilization (RDS) * IO performance (RDS) * Storage usage (S3) * Error Rate (S3) * Invocation health (Lamda) * Traffic (ALB/NLB) * Availability - Helthyhostcount (ALB/NLB) * Account utilization score (Cross Account) * Tag compliance (Cross account) CloudWatch Dashboard auto refreshes daily and supports drill down views |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | create the dashboard for all cross accounts.;14/Nov/25 8:29 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;275400 | [5 empty] | 57600 | 57600 | 275400 | 4.78 | 57600 | 57600 | 275400 | [12 empty] | 12/Nov/25 2:00 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251112-115953.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182044 | 12/Nov/25 2:01 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251112-120058.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182047 | 13/Nov/25 12:11 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-101129.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182802 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5149805 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l5u3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-07 06:59 | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 07/Nov/25 8:59 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start working on this US whatever resources are created we will create and update the custom metric as per accounts and will try to create the Cloudwatch dashboard and alerts accordingly. | 12/Nov/25 1:59 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created the dashboard for all cross accounts on the *SAA_Audit* account. Dashboard Name : *Central Dashboard* This Dashboards show metrics from EC2, RDS,EKS,S3 and Lamda for each environment. | 12/Nov/25 2:00 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251112-115953.png¦width=714,alt="image-20251112-115953.png"! Screenshot has been attached as an evidence that the Dashboard has been created. | 12/Nov/25 2:01 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251112-120058.png¦width=714,alt="image-20251112-120058.png"! | 12/Nov/25 4:09 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Now checking for the tag compliance policy. | 13/Nov/25 12:11 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;For Cross account utilization score we have Dashboard in Payer Account which is out organization management account. We can see all account wise score , costing as well as percentage. !image-20251113-101129.png¦width=714,alt="image-20251113-101129.png"! | 14/Nov/25 8:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Tag Compliance remained pending due to some tag policy disable issue. Will taking this in next sprint. | 14/Nov/25 10:56 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;As discussed in the Sprint review call we will have to get in touch with leigh for his approval for enabling the Tag policy for the Cross account thatâ€™s why this Tag compliance part we are taking in next sprint. | 14/Nov/25 10:59 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | Done | 2025-11-14 10:59
AM20-531 | Backup using lifecycle management by Terraform | Done | 0 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sanket Kale | Medium | 1752552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 20:58 | 2026-01-15 23:40 |  |  |  | 0 |  |  | Sanket Kale | [5 empty] | 712020:91948faf-1676-4820-bf6b-d50a7992943e | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4eaa1670 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dndf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:52 | [13 empty] | 25/Aug/25 8:52 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;As discussed with Yashwant and Sankalp this is no more require to implement. So closing it. | [26 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 08:52
AM20-532 | Citrix ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672695 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-09 16:18 | 2026-01-09 19:41 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across Citrix account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4f5d9411 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04fqj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 06:27 | [13 empty] | 20/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on enabling the cloud config and guard duty along with macie. | 22/May/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;below mentioned service were enabled. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-22 08:19
AM20-533 | Airnavx ¦¦ EC2 Creation using terraform code | Cancelled | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satyabrata Sahoo | Medium | 1760710 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:4b8d8093-596d-4394-a074-4a9a9636f86f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 21:09 | 2026-01-09 22:27 |  |  |  | 0 | As AWS Expert I would like to provision EC2 using terraform so that I can handover to SAA for Airnavx installation Acceptance Criteria: EC2 provisioned successfully using approved AMI Tags applied automatically Instance must have SSM agent installed SSH is enabled only via bastion host Guardduty must detect and monitor instance Instance must publish logs to CloudWatch EC2 must register with org monitoring/alerting |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b9d343f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejt7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | [103 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 06:38 | [13 empty] | 05/Sep/25 8:37 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Closing this as this is a duplicate of [https://vodacom.atlassian.net/browse/AM20-131¦https://vodacom.atlassian.net/browse/AM20-131¦smart-link], hence closing the ticket | [26 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-05 08:38
AM20-534 | MQ POC ¦¦ MQ Parser Execution - Lambda integration testing & Message body validation | Done | 8 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1842282 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 18:11 | 2026-02-02 22:08 |  | 2025-11-28 07:36 |  | 0 | As Application product owner I would like to perform Lamda integration test with MQ parser and validate the messages output |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Nov/25 5:05 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;7200 | ;21/Nov/25 9:21 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;43200 | ;25/Nov/25 4:07 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;64800 |  |  |  | 115200 | 0 | 115200 | 1 | 115200 | 0 | 115200 | [12 empty] | 25/Nov/25 4:07 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251125-140722.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189321 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124739.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189722 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124758.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189723 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124816.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189725 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124826.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189726 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124840.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189721 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124850.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189724 | [11 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@21c31db9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5mz: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 15:05 | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 5:05 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Exploring feasible approaches for Lambda integration with MQ parser, since direct MQ - Lambda integration is not possible. | 21/Nov/25 8:27 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;we have configured lambda and tested workfow funtionality by pushing message to s3 bucket from SQS. Now we go with checking feasibility with pegasys application usecase | 25/Nov/25 4:07 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Another approach, we tried to integrate MQ queue â€œPEGASYS.OUT.UATâ€ directly to Lambda !image-20251125-140722.png¦width=459,alt="image-20251125-140722.png"! | 26/Nov/25 2:49 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Â We tried integrating both S3 and MQ with Lambda directly. Whenever message reaches to MQ queue, it should trigger lambda which doesnâ€™t happen. However we tested then by integrating s3 event type â€œPutâ€, as soon as any object is uploaded to s3 bucket, it triggers Lambda Â !image-20251126-124739.png¦width=443,alt="image-20251126-124739.png"! Â !image-20251126-124758.png¦width=443,alt="image-20251126-124758.png"! Â !image-20251126-124840.png¦width=443,alt="image-20251126-124840.png"! !image-20251126-124850.png¦width=443,alt="image-20251126-124850.png"! !image-20251126-124816.png¦width=443,alt="image-20251126-124816.png"! !image-20251126-124826.png¦width=443,alt="image-20251126-124826.png"! As next step in next sprint , we will raise support ticket with AWS to get more clarity on this approach of direct integration of lambda and MQ | 28/Nov/25 7:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-28 07:36
AM20-535 | Provision and manage Amazon Inspector V2 across AWS account using Terraform with master-member hierarchy | Done | 20 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1718164 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 13:11 | 2026-02-04 16:59 |  |  |  | 0 | As a cloud security engineer, I want to provision Amazon inspector across all accounts in my AWS org using a delegated administrator account so that I can perform centralized automated and continuous vulnerability scanning of EC2, ECR, and Lamda across all member accounts Acceptance Criteria: * Terraform must be enabled in Payer9 account * Terraform must register the Payer9 account for Inspector within AWS organization to allow Payer9 to manage inspector across member accounts * Terraform must enable Inspector in each member account by assuming a role into those accounts for all resource types (EC2,ECR, Lamda function) must be activated * Terraform must ensure that EC2 scanning is enabled, ECR scanning is continuous, Lamda scanning is turned on * Once enabled, findings for all member accounts must be accessible from delegated account via Inspector console * The terraform config must be reusable across multiple accounts and support by parameterized resources types * All terraform created resources must include standard tags for auditability * Integrate Inspector with security hub * Alert on critical CVEs using SNS/EventBridge * Raise alerts on high severity findings |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@35c15470 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aoa3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | Sprint 12 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-18 06:22 | [13 empty] | 18/Jul/25 8:22 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Need to send the email to Ismail about add the amazon inspector in trusted entity. | 22/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Email sent to Ismaail and leigh about Request to Enable Centralized Management for GuardDuty and Amazon Inspector and currently I am working on Terrafrom script to create the base module for resources | 23/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Leigh replied and asked to Ismaail for assisting. | 25/Jul/25 8:33 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;It will be spillover because there was a dependency on Ismail and he has updated on 23 July Only so thatâ€™s why I am not able to complete it on time. | 21/Aug/25 2:33 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. Please delete Amazon Inspector instances as it is POC | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:33
AM20-536 | Handover of Patching solution | Done | 4 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1866136 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 21:31 | 2026-02-03 01:21 | 2025-12-14 17:52 | 2025-12-12 11:19 |  | 0 | As product owner I want Diksha to take handover along with Satya from Faisal so that she can support customer |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [5 empty] | ;09/Dec/25 12:43 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;10/Dec/25 3:38 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 09/Dec/25 12:55 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251209-105350.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1193694 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@58f0f8fd | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7xd: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-09 10:45 | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 09/Dec/25 12:45 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started the Hands on for patching first worked on pre-requisites and AWS cli and cloud watch agent installation on the Sandbox EC2 instance. The Session has been recorded as well. | 09/Dec/25 12:55 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251209-105350.png¦width=641,alt="image-20251209-105350.png"! This server is created as a Test Patching server for the Windows patching activity. As of now this has been kept in stopped state later after the patching will get done we will delete the server moving further. The below pointers has been completed. * *Provisioned Test Environment* ** Deployed a test EC2 instance in the designated sandbox environment. * *Network Configuration* ** Configured VPC endpoints to enable *private connectivity for AWS Systems Manager (SSM)*, ensuring secure management without requiring a public IP. * *Identity and Access Management (IAM)* ** Created IAM roles, policies, and instance profiles for EC2 to support required permissions. ** Implemented a *cross-account IAM role* for Lambda in the security account, enabling patching operations in the sandbox environment. ** Updated trust relationships to align with cross-account access requirements. * *Instance Setup and Agent Installation* ** Downloaded and installed *AWS CLI*, *CloudWatch Agent*, and *SSM Agent* on the EC2 instance. ** Deployed a custom compliance reporting script within the instance. * *Automation and Management* ** Authored and deployed a *custom SSM document* to support patching and compliance workflows. | 10/Dec/25 3:37 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Below pending points are also covered today and the handover of the patching is completed. * *S3 Bucket Configuration* ** Set up an Amazon S3 bucket with the required folder structure. ** Apply appropriate *IAM permissions* and *bucket policies* to ensure secure access. ** Configure *S3 event notifications* to trigger downstream processes as needed. * *Lambda Automation for Patching* ** Develop and deploy a Lambda function to *automate patching activities* within the sandbox account. ** Ensure the Lambda function uses the *cross-account IAM role* created today, granting it the necessary permissions to execute patching tasks in the sandbox environment. ** Validate the Lambda execution policy and trust relationship for compliance and least-privilege access. | 10/Dec/25 3:38 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[Recap: Patch Implementation - Internal Tuesday, December 9 ¦ Meeting ¦ Microsoft Teams¦https://teams.microsoft.com/l/meetingrecap?driveId=b%21d5bfbASx8UyuyN5zJPY_C1jj3vg4dqxGo4vsecE4YZu3kE97HxTiSrSKd-pI-KUx&driveItemId=016NKAQFNQOEZURWCDERFYBPVICI6NDJX2&sitePath=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQCwcTNI2EMkS4C-qBI80ab6Af6L1MuuoLAsP4web0CEjFk&fileUrl=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQCwcTNI2EMkS4C-qBI80ab6Af6L1MuuoLAsP4web0CEjFk&iCalUid=040000008200E00074C5B7101A82E00800000000A47F206EE268DC01000000000000000010000000321233C36A404C46934C1B5B72B7F07A&threadId=19%3Ameeting_ZjBlZDVhMjMtNDI4ZC00NjQ5LThiMzgtM2FiMDhhNTIyZDg2%40thread.v2&organizerId=8f4c76ce-ca6e-44bd-bbde-0eb6186f9df7&tenantId=68283f3b-8487-4c86-adb3-a5228f18b893&callId=76b0f585-b89d-412b-b23f-2527a464dab5&threadType=Meeting&meetingType=Scheduled&subType=RecapSharingLink_RecapChiclet] [Recap: Patch Implementation - Internal Wednesday, December 10 ¦ Meeting ¦ Microsoft Teams¦https://teams.microsoft.com/l/meetingrecap?driveId=b%21d5bfbASx8UyuyN5zJPY_C1jj3vg4dqxGo4vsecE4YZu3kE97HxTiSrSKd-pI-KUx&driveItemId=016NKAQFKGUFQPO2BR7VC3OZIJ4T4BALUJ&sitePath=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQBGoWD3aDH9RbdlCeT4EC6JAf1ANE41qecWYg-ZpI8nWPs&fileUrl=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQBGoWD3aDH9RbdlCeT4EC6JAf1ANE41qecWYg-ZpI8nWPs&iCalUid=040000008200E00074C5B7101A82E00800000000F3F48BFDF868DC01000000000000000010000000D320B3E36531F44C8156C61B7DCD0871&threadId=19%3Ameeting_YTQ3OGI1ODMtM2JjMy00YTkzLTlhNjQtYWUwMGY4OTFlZDAz%40thread.v2&organizerId=8f4c76ce-ca6e-44bd-bbde-0eb6186f9df7&tenantId=68283f3b-8487-4c86-adb3-a5228f18b893&callId=3fb32e76-7aa1-40f8-a245-6ac6fdac8f6c&threadType=Meeting&meetingType=Scheduled&subType=RecapSharingLink_RecapChiclet] Both recording links has been attached above. | [26 empty] | Done | 2025-12-12 11:19
AM20-537 | CSA assessment | Done | 8 | Sprint 2 | 2025-03-31 | 2025-04-11 | Sumit Nikam | Medium | 1627466 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 13:43 | 2026-01-28 14:50 |  |  |  | 0 | As application architect I would assess current CSA application architecture, functional complexity, ease of migration, current and future scalability requirements, dependencies between different components and data consistency across services. Acceptance Criteria: Document consisting of current and to-be architecture, proposed microservices,, dependencies and data consistency approach is successfully completed |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;02/Apr/25 6:36 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 |  |  | 115200 | 21600 | 93600 | 0.81 | 115200 | 21600 | 93600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@11a4dc28 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 4 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxso7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-26 06:12 | [13 empty] | 26/Mar/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;High level plan for CSA Modernization has been prepared, reviewed internally and shared with Vodacom. Next step is to prepare for SOW document. | 01/Apr/25 7:11 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Working along with Yashwant for SOW document preparation and review | 02/Apr/25 6:36 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Reviewing functional details shared by Sampi | 04/Apr/25 3:26 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Follow-up discussion completed with Sampi. | 04/Apr/25 8:08 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. SOW completed | [22 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-04-04 20:08
AM20-538 | EKS Cluster and other services required IAM role | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741147 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-21 13:38 | 2026-01-21 16:18 |  |  |  | 0 |  |  | Aravind Raj | Ravinder Godiyal Godiyal |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:7535df8d-3051-4556-b1c1-6a7195121b35 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1546fba | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cker: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:08 | [13 empty] | 11/Aug/25 10:07 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;Request [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] to update the spill over reason in the main user story being the assignee, i had to go on an emergency leave due to family exigency where we did not get a chance to formulate these details around. | 13/Aug/25 9:30 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;¦NAME¦Description¦ ¦flysaa-backend-dev-eks-deployer¦IAM Role to deploy EKS Cluster via Terraform¦ ¦eks-flysaa-dev-531cab81-argocd-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-aws-alb-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-aws-ebs-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-controlplane-role-34708c3e¦IAM Role for EKS Control Plane dynamically created by system with EKS Cluster creation¦ ¦eks-flysaa-dev-531cab81-ingress-nginx-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-karpenter-profile-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-KarpenterRole¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-sonarqube-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-workernode-role¦IAM Role for EKS Data Plane nodes managed by Karpenter¦ ¦eksctl-eks-flysaa-dev-531cab81-addon-iamservi-Role1-Wu60GGlLdLGi¦IAM Roles for EKS Cluster Add-ons¦ ¦eksctl-eks-flysaa-dev-531cab81-addon-iamservi-Role1-Y6EbqpTYxUCn¦IAM Roles for EKS Cluster Add-ons¦ ¦bitbucket-oidc-flysaa-role¦IAM Role for bitbucket replication to S3 bucket for CI/CD¦ ¦flysaa-backend-dev-codebuild-service-role¦IAM Service Role for codebuild projects¦ ¦ekstf-pipeline-codepipeline-role-4e353e4a¦IAM Service Role used by codepipeline which is dynamically created during runtime¦ ¦flysaa-backend-dev-ssminstancerole¦IAM Role to be used by bastion-hosts/jumpbox EC2 MachinesÂ ¦ As Discussed in our DS Call, Here are IAM Role details from Dev Environment, [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] request you to kindly make use of this information and fetch the same from all environments along with the respective permissions incorporated. | 13/Aug/25 10:06 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;Moving the subtask for review with [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] | 18/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have received dev env role, need to get the roles from preprod and prod along with policy. | [23 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-21 18:09
AM20-539 | Terraform code to automate the Route 53 cutover | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Satya Varanasi | Medium | 1835056 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-17 16:34 | 2026-01-17 17:38 | 2025-11-25 08:21 |  |  | 0 | [airchefs.co.za¦http://airchefs.co.za] need to be setup on network account. |  | Harsh Chandra | Sanket Kale |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:91948faf-1676-4820-bf6b-d50a7992943e | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@279e63c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxgj: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 07:08 | [13 empty] | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | 25/Nov/25 8:17 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Validated with the internal team and assign it to Satyasairam for the review | [25 empty] | 1834911 | AM20-267 | Route53 cutover for Airchef | Done | 2025-11-25 09:23
AM20-540 | AWS_SAA_Network ¦¦ Security Compliance Implementation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642120 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 13:12 | 2026-01-11 14:35 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on *Account no: 339712943527â€ƒâ€ƒAWS_SAA_Network* *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/Apr/25 9:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Network-Acccount-FailedControls.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1092887 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@749b116f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00tcp: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-15 06:22 | [13 empty] | 15/Apr/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on implementing dependency services for CIS, NIST and FSBP | 17/Apr/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed enabling Guard Duty, Macie, Security Hub, followed by this have implemented controls for CIS, NIST, AWS FSBP standards. Still there are few failed controls to be remediated, since the implementation of services done by vodacom, will expect their support in implementing the controls. if the controls cannot be implemented will get a confirmation on the failed control list to close this user story. | 22/Apr/25 9:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;[^Network-Acccount-FailedControls.csv] Failed controls list to work with vodacom team, hence marking this story to done status. | 02/May/25 4:58 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-04-22 09:53
AM20-541 | MQ Modernization POC ¦¦ Parser testing based on sample pegasys parser | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832848 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 14:26 | 2026-01-15 18:12 | 2025-11-28 11:15 | 2025-11-28 12:00 |  | 0 | As DevOps Engineer, I need to test few existing MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6bedb0f1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo0r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:26 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:26 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;CPP to Java: Parser to be re-written with line to line conversion to retain logic. | 20/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Java Parser Covering Following High-level Algorithm- # Input * Receive a raw text message body (rawMessage) from AmazonMQ PEGASYS.OUT.UAT. # Pre-check * If rawMessage is null or empty â†’ return ParseResult with error = true (this is defensive; in normal operation this should not happen). # stripId() â€“ remove ID block if present 3.1. Let msg = rawMessage. 3.2. If msg contains "\nM42": * Call stripId(msg): * Find index of " /ID ". * From there, find "ACARS\r\n". * Return: msg_before_ID + msg_from_ACARS_onwards. 3.3. Else: keep msg unchanged. . # Construct buff and newbuff 4.1. buff = msg (the stripped or original message). 4.2. Append control chars: * CR = 13, NL = 10, ETX = 3. * newbuff = buff + CR + NL + ETX. # Split into lines & find .JNB 5.1. Split newbuff by '\n' into lines[]. 5.2. Search for first line where lines[i].startsWith(".JNB"). 5.3. If found, set counter = i + 1 (line after .JNB). 5.4. If not found or counter >= lines.length: * Default: create OutboundMessage(qMng, newbuff) â†’ MNG only. * Return this as ParseResult with error = false. # Extract relevant lines safely * line0 = lines[counter] (or "" if out of range). * line1 = lines[counter + 1] * line2 = lines[counter + 2] * line3 = lines[counter + 3] Using helpers: * safeLine(lines, index) â€“ returns "" if index out of range. # Extract tokens (T1, T2, etc.) safely Using safeSub(s, begin, endExclusive) to avoid index errors. 7.1. T1 = line0[0..3) â†’ message type (MVT, DIV, ASM, SSM, CGO, etc.). 7.2. T2 = line1[1..5) â†’ secondary code (CIRQ, CICX, etc.). 7.3. line1_0_2 = line1[0..2) â†’ used to check "SA". 7.4. line2_0_2 = line2[0..2) â†’ used to check "ED". 7.5. line3_0_3 = line3[0..3) â†’ used to check "TIM". # Prepare result container * outputs = new ArrayList<OutboundMessage>(); # Rule 1 (SSM/CGO â†’ ICARGO) * If T1 is "SSM" or "CGO": * outputs.add(new OutboundMessage(qIcargo, buff)); 10. Rule 2 (CIRQ/CICX â†’ SIP) * If T2 is "CIRQ" or "CICX": * Add OutboundMessage(qSip, buff) to outputs. * Return ParseResult(outputs, false, null) immediately 11. Rule 3 (MVT / DIV / ASM) 11.1. If T1 in { "MVT", "DIV", "ASM" }: 11.1.1 ASM + TIM * If T1 == "ASM" and line3_0_3 == "TIM": * Add OutboundMessage(qCimp, buff) (CIMP). * Add OutboundMessage(qIcargo, buff) (ICARGO). * Then continue. 11.1.2 MVT-specific * If T1 == "MVT": * If line1_0_2 == "SA" (SA flight): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG with CR/LF/ETX). * Add OutboundMessage(qIcargo, buff) (ICARGO). * If line2_0_2 == "ED": * Add OutboundMessage(qCimp, buff) (CIMP). * Add another OutboundMessage(qIcargo, buff) (ICARGO again â€“ same as C++ double-write). * Else (non-SA): * Add OutboundMessage(qMng, newbuff) (MNG only). 11.1.3 DIV/ASM (fallback) * Else (T1 is DIV or ASM without TIM rule): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG). 12. Rule 4 (other message types) * Else (T1 is not MVT, DIV, ASM, and not CIRQ/CICX): * Add OutboundMessage(qMng, newbuff) (MNG only). 13. Return final result * return new ParseResult(outputs, false, null); | 24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Additional parser related to Pegasys called SbrSplit has been shared by Sampi. Analysis has been started for the same. | 28/Nov/25 11:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SbrSplit parser - CPP has been converted into java based code. Repo structure has also been transformed to adopt microservice alike design. [https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git¦https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git] Parser to be tested in next sprint. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [25 empty] | Done | 2025-11-28 12:00
AM20-542 | MQ - Parser trigger based on incoming message | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1863569 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 15:59 | 2026-01-14 16:40 | 2025-12-14 17:52 | 2025-12-12 14:49 |  | 0 | As Product Owner I like to ensure that each relevant incoming message triggers the respective parser and process the message successfully |  | Sanjot Fotedar | [5 empty] | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [5 empty] | ;11/Dec/25 4:51 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;86400 | ;12/Dec/25 1:19 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;28800 |  |  |  |  | 115200 | 0 | 115200 | 1 | 115200 | 0 | 115200 | [12 empty] | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111735.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194825 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111750.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194828 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111758.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194830 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111812.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194831 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111822.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194826 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111832.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194829 | 12/Dec/25 1:18 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251212-111843.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194827 | [11 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4937ec21 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o64z: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_104373748_*¦*_10041_*:*_1_*:*_1274929064_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_104373748_*¦*_10041_*:*_1_*:*_1274929064_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_104373748_*¦*_10041_*:*_1_*:*_1274929064_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_104373748_*¦*_10041_*:*_1_*:*_1274929064_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-11 14:53 | 3_*:*_1_*:*_104373748_*¦*_10041_*:*_1_*:*_1274929064_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 11/Dec/25 4:53 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Working on lambda integration setup to trigger as soon as message arrives to specific queue in AWS Active MQ broker. | 12/Dec/25 1:18 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;* Integrated AWS lambda with Active MQ so that any message on queue automatically triggers processing * Added secure integration with aws secrets manager for fetching MQ broker credentials * Implemented java 17 lambda to decode base64 messages, run ParserLogic, and generate outputs. * added logging to track message received, parsed output, and any errors. * End-to end flow: Message arrives in MQ â†’ Lambda Triggers â†’ Credentials fetched securely â†’ Message Decoded â†’ Parsed â†’ Logged successfully. !image-20251212-111735.png¦width=455,alt="image-20251212-111735.png"! !image-20251212-111750.png¦width=455,alt="image-20251212-111750.png"! !image-20251212-111758.png¦width=455,alt="image-20251212-111758.png"! !image-20251212-111812.png¦width=455,alt="image-20251212-111812.png"! !image-20251212-111822.png¦width=455,alt="image-20251212-111822.png"! !image-20251212-111832.png¦width=455,alt="image-20251212-111832.png"! !image-20251212-111843.png¦width=455,alt="image-20251212-111843.png"! | [28 empty] | Done | 2025-12-12 14:49
AM20-543 | ServiceNow ¦¦ Secure Integration with Cloud ServiceNow | Done | 8 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650451 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 16:24 | 2026-01-16 20:09 |  |  |  | 0 | As a AWS Cloud architect, I want the Amazon SNS to securely connect to the on-prem ServiceNow instance so that error alerts can be logged as incidents. Acceptance Criteria: * ServiceNow API credentials are stored securely in AWS Secrets manager * Network connectivity is verified via NAT gateway/VPN * HTTP request to ServiceNow are authenticated and secure |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;13/May/25 11:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;24/Jun/25 1:30 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;10/Jul/25 9:30 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;57600 |  |  |  | 115200 | 0 | 115200 | 1 | 115200 | 0 | 115200 | [12 empty] | 15/May/25 11:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;Ashton response on delay for SNow endpoint.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100994 | 22/May/25 9:56 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103907 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5538b454 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 08:59 | [13 empty] | 02/May/25 10:58 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Current State: AWS Level configuration of ServiceNow with Lambda Function and SNS is complete. Next Steps: # Setup a call with ServiceNow Cloud team to do the POC # Setup SNS to Push notifications to ServiceNow # Setup required matrices # Validate the functionality. # Get Sign-off on successful Setup | 15/May/25 11:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Delay from ServiceNow app owner ( Ashton) in providing the ServiceNow API endpoint, conversations comms screenshot attached. Potential spill over [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] | 20/May/25 10:18 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;¦Setup on AWS in complete. API endpoint is to be provided by Ashton Steyn. Once the end point is added to SNS, we would be able to test if the notification is received correctly in ServiceNow Cloud. Next Step would be to showcase this entire setup to Denise and Bhavesh and get Sign off. Action Points API EndPoint pending on Ashton Steyn. Need Availability of Denise and Bhavesh to showcase the POC and get SignOff on the POC¦ | 22/May/25 9:57 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 02/Jun/25 8:22 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;API Provided by Ashton, could not be configured in SNS Topic. We are getting error â€œURL is not valid, INVALIDâ€ We are waiting for an update from Ashton on how to resolve this error. | 19/Jun/25 7:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Call planned with ServiceNow team on 19th June to provide walkthrough and clarify open queries, needed to proceed with next steps [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] | 24/Jun/25 1:30 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Setup Completed POC Completed End Point for Prod to be provided by service now team (Feroz). | 10/Jul/25 9:30 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Setup >> Completed POC >> Completed End Point for Prod to be provided by service now team (Feroz) >> Completed Moving to review for closure | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-544 | MQ ¦¦ DR and BackUp | To Do | 0 | None( Backlog) |  |  |  | Medium | 1794158 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 13:21 | 2026-02-04 13:47 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Informatica-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@415fe9df | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v08 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 10:24
AM20-545 | PROS ¦¦ LLD Creation | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sankalp Rai | Medium | 1749504 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 18:15 | 2026-01-17 21:35 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1809d79f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0danv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | Sprint 15 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 06:06 | [13 empty] | 06/Oct/25 8:05 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;LLD document created. | 06/Oct/25 8:07 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;[PROS_Low Level Design Document_v1.0.docx¦https://vodafone.sharepoint.com/:w:/r/sites/SouthAfricaAirlines/Shared%20Documents/Technical%20Documents/SAA%20Design%20documents/LLD%20Documents/Wave%202%20apps/PROS%20LLD/PROS_Low%20Level%20Design%20Document_v1.0.docx?d=w4faebf320e0f4c53aedb5b192660de4f&csf=1&web=1&e=jOZXIo] | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-10-06 08:07
AM20-546 | Front End (SMS notification)- Business Level Improvements | To Do | 4 | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1885790 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 14:12 | 2026-01-13 16:44 | 2026-01-06 08:25 |  |  | 0 | As Product Owner I would like to take business input and configure the SMS accordingly so that informative SMS notification reached out to operation and support group. *Acceptance Criteria*: * SMS notification configured successfully as Business input |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@55581f2c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptv7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-08 09:34 | [13 empty] | 08/Jan/26 11:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reached out to Hoosen and Javier to enquire their availability for resuming the discussions, awaiting their response. | [29 empty] | To Do | 2025-12-30 08:45
AM20-547 | RDS Upgrade in Flysaa backend Dev environment | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1842266 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 13:13 | 2026-01-09 14:53 | 2025-11-26 08:48 | 2025-11-27 09:18 |  | 0 | h2. User story * When the RDS instance is upgraded, I want to ensure compatibility with MySQL 8.4 so that our application runs smoothly without issues. h2. Context The development RDS instance will be upgraded from MySQL version 5.7 to 8.4. This upgrade may affect the functionality and performance of the application. h2. Acceptance criteria * The RDS instance must be successfully upgraded to MySQL 8.4. * All application features should function correctly after the upgrade. * Performance benchmarks should be met post-upgrade. h2. Other information N/A |  | Pankaj Pathak | Yashwant Thakur |  |  |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7e1de089 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5lf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [65 empty] | YES | YES | 2025-11-20 06:25 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [12 empty] | 20/Nov/25 8:24 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;The upgrade from MySQL version 5.7.44 to 8.0.42 was successful. The DB instance is running smoothly. We asked the application team (Donald and Gavin) to confirm everything is functioning well on their end. We are awaiting their response to close this story. | 25/Nov/25 2:00 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Ticket moved to In review. As we have completed internal review. | 27/Nov/25 9:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Post upgrade, Business confirmed that BAU is working as expected hence approving | [27 empty] | Done | 2025-11-27 09:18
AM20-548 | AirNavX Account ¦¦ Security Compliance Implementation | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672716 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-27 21:58 | 2026-01-28 01:50 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of AirNavX account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250528-092239.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1106065 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@33a69e54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04ft7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-28 09:24 | [13 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Account - 345594574792 Controls were implemented and security score is updated is for all the three security standard frameworks- CIS, NIST and AWS FSBP !image-20250528-092239.png¦width=1279,height=589,alt="image-20250528-092239.png"! | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-28 11:24
AM20-549 | Pegasys LLD Creation | To Do | 0 | None( Backlog) |  |  |  | Medium | 1832851 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 18:02 | 2026-01-18 19:14 |  |  |  | 0 |  |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@ab71d36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g002 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-11 14:48
AM20-550 | Cloud watch and secrets manager | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Shreyash Talwekar | Medium | 1869414 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-20 12:51 | 2026-01-20 16:34 | 2025-12-12 08:25 |  |  | 0 | Remediate or provide justification comments for failed security controls. |  | Aravind Raj | Shreyash Talwekar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [29 empty] | 10/Dec/25 12:10 PM;17cb9418-1850-4923-932b-7098ec51b6bb;CloudWatch.15 2025-12-10T15_37_22+05_30.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194024 | 10/Dec/25 12:10 PM;17cb9418-1850-4923-932b-7098ec51b6bb;CloudWatch.17 2025-12-10T15_33_10+05_30.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194025 | 10/Dec/25 12:17 PM;17cb9418-1850-4923-932b-7098ec51b6bb;SecretsManager.1 2025-12-10T15_41_47+05_30.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194029 | 10/Dec/25 12:17 PM;17cb9418-1850-4923-932b-7098ec51b6bb;SecretsManager.4 2025-12-10T15_45_31+05_30.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194028 | 12/Dec/25 10:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251212-083216.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1194759 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@275f2c9e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obrv: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-10 10:10 | [13 empty] | 10/Dec/25 12:10 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Backend Prod [^CloudWatch.17 2025-12-10T15_33_10+05_30.csv] [^CloudWatch.15 2025-12-10T15_37_22+05_30.csv] I have provided comment for CloudWatch 17 and Cloudwatch 15 Security Control. The actions specified in those cannot be enabled because As per decided implementation approach, we are using Lambda to send notifications hence alarm actions are not needed. ¦As per decided implementation approach, we are using Lambda to send notifications hence alarm actions are not needed¦ | 10/Dec/25 12:11 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Backend Prod: We have updated log group retention period for log group with no retention period prior. This is for CloudWatch 16 rule, but the rule is showing failed because the rule expects retention period to be more than 365 days but it will cause increase in CloudWatch costs. | 10/Dec/25 12:17 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;[^SecretsManager.1 2025-12-10T15_41_47+05_30.csv] [^SecretsManager.4 2025-12-10T15_45_31+05_30.csv] Backend Prod Automatic rotation cannot be enabled because we store application specific confidential parameters used by deployment, auto rotate will change value in secret and that will cause issue in running application since incorrect parameter value will be fetched from AWS secret manager. | 10/Dec/25 12:53 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Backend Preprod: CloudWatch 17 and CloudWatch 15 rules cannot be enforced due to same reason as Prod environment. | 12/Dec/25 10:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;upon the requirement control state can be suppressed, so mark the control status to suppressed. cloudwatch15 and cloudwatch17 !image-20251212-083216.png¦width=435,alt="image-20251212-083216.png"! | 12/Dec/25 2:38 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Updated security controls to suppress for CloudWatch 15 and CloudWatch 17. | [21 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2025-12-13 14:33
AM20-551 | Cost Anomaly Detection | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1719961 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 16:42 | 2026-02-01 19:58 |  |  |  | 0 | As AWS expert I would like to report any sudden spike in the cost against any of the application or accounts so that the concerned team can validate the reasoning and take appropriate action to ascertain reasons and take reactive measures Acceptance Criteria: < pre-req> : * Ensure all accounts are part of AWS Org. with consolidated billing enabled * Use the Payer9 account to see all account cost level Acceptance Criteria * Cost anomaly detection is enabled successfully * Anomaly monitor is is enabled * Anomaly subscription is successfully enabled using SNS * CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage * Use Amazon Athena or quicksight for stakeholder friendly dashboards * Graphical representation of the cost to be captured |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4d6b831e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0attv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-18 06:07 | [13 empty] | 18/Jul/25 8:07 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;* CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm *---Done* * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage *---Done* Cost anomaly detection is enabled successfully *---Done* * Anomaly monitor is is enabled *---Done* * Anomaly subscription is successfully enabled using SNS *---Done* | 23/Jul/25 8:08 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working on Amazon Athena or quicksight for stakeholder friendly dashboards ---*Done* | 24/Jul/25 7:38 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;As discussed with Yashwant, we need to track cost anomalies for specific AWS services and implement it separately for each account. | 24/Jul/25 8:57 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Cost anomalies detction for specific AWS services and implement it separately for each account. *---Done* Updated for Only TM1 account.(As discussed with Yashwant) | 28/Jul/25 9:58 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:58
AM20-552 | ServiceNow ¦¦ CloudWatch Rule for Error detection | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650995 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 12:33 | 2026-01-23 12:54 |  |  |  | 0 | As a AWS engineer, I want to create CloudWatch alarms to send error-level logs to be notified of infrastructure issues Acceptance criteria: * CloudWatch metric filters to be configured to match specific error patterns or log levels |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fabfe65 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0280b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 06:03 | [13 empty] | 29/Apr/25 8:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will review utkarsh terraform script and will assign this story to him. | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed. | 07/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;We can use utkarsh terraform script for cloud watch alarm creation, but sns topic cant be modified so we need manual update to SNS access policy. | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:39 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [22 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:39
AM20-553 | EKS Cluster and other services required IAM role | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741147 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-04 16:38 | 2026-02-04 16:54 |  |  |  | 0 |  |  | Aravind Raj | Ravinder Godiyal Godiyal |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:7535df8d-3051-4556-b1c1-6a7195121b35 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1546fba | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cker: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:08 | [13 empty] | 11/Aug/25 10:07 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;Request [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] to update the spill over reason in the main user story being the assignee, i had to go on an emergency leave due to family exigency where we did not get a chance to formulate these details around. | 13/Aug/25 9:30 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;¦NAME¦Description¦ ¦flysaa-backend-dev-eks-deployer¦IAM Role to deploy EKS Cluster via Terraform¦ ¦eks-flysaa-dev-531cab81-argocd-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-aws-alb-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-aws-ebs-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-controlplane-role-34708c3e¦IAM Role for EKS Control Plane dynamically created by system with EKS Cluster creation¦ ¦eks-flysaa-dev-531cab81-ingress-nginx-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-karpenter-profile-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-KarpenterRole¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-sonarqube-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-workernode-role¦IAM Role for EKS Data Plane nodes managed by Karpenter¦ ¦eksctl-eks-flysaa-dev-531cab81-addon-iamservi-Role1-Wu60GGlLdLGi¦IAM Roles for EKS Cluster Add-ons¦ ¦eksctl-eks-flysaa-dev-531cab81-addon-iamservi-Role1-Y6EbqpTYxUCn¦IAM Roles for EKS Cluster Add-ons¦ ¦bitbucket-oidc-flysaa-role¦IAM Role for bitbucket replication to S3 bucket for CI/CD¦ ¦flysaa-backend-dev-codebuild-service-role¦IAM Service Role for codebuild projects¦ ¦ekstf-pipeline-codepipeline-role-4e353e4a¦IAM Service Role used by codepipeline which is dynamically created during runtime¦ ¦flysaa-backend-dev-ssminstancerole¦IAM Role to be used by bastion-hosts/jumpbox EC2 MachinesÂ ¦ As Discussed in our DS Call, Here are IAM Role details from Dev Environment, [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] request you to kindly make use of this information and fetch the same from all environments along with the respective permissions incorporated. | 13/Aug/25 10:06 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;Moving the subtask for review with [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] | 18/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have received dev env role, need to get the roles from preprod and prod along with policy. | [23 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-21 18:09
AM20-554 | AMOS Follow-up Assessment | Blocked | 4 | None( Backlog) |  |  | Sumit Nikam | Medium | 1833693 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 17:28 | 2026-01-30 20:02 | 2025-11-28 11:14 |  |  | 0 | As Product owner I would like to reinitiate assessment for AMOS application so that we can finalize approach to modernize it |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7ed8f0ed | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0009 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-24 06:09 | [13 empty] | 24/Nov/25 8:09 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Still awaiting approval from SAA\Tumelo for migration to AWS. Moving this to blocked state since the assessment canâ€™t be resumed until then. | [29 empty] | To Do | 2025-11-12 10:56
AM20-555 | Budget management - AWS Cost Control on application | In Progress | 6 | Sprint 22 | 2026-01-05 | 2026-01-16 | Diksha Koul | Medium | 1885694 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 13:21 | 2026-02-01 15:50 | 2026-01-08 08:32 |  |  | 0 | As Product Owner, I would like to address frequent spikes on budget of AWS accounts so that we can manage cost within the forecasted cost. Acceptance Criteria: * Identify the root cost of cost spiked in EKS cluster, Audit account, SAA_Airnavx and CMS backend(Prod) * resolve the root cause to reduce the associated cost |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [5 empty] | ;08/Jan/26 7:38 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | [5 empty] | 86400 | 57600 | 28800 | 0.33 | 86400 | 57600 | 28800 | [12 empty] | 08/Jan/26 10:57 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-085716.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197716 | 08/Jan/26 11:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-093536.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197744 | 08/Jan/26 12:15 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-101131.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197769 | 08/Jan/26 12:15 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-101412.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197770 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3731daff | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptcb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-06 11:56 | [13 empty] | 06/Jan/26 1:55 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started working on the root cause and cost spike for AirnavX | 08/Jan/26 7:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have checked the costing spike for all accounts its showing that EC2 instances are consuming more cost. Now checking the cloud watch logs for them. | 08/Jan/26 10:57 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I checked in the *AirnavX Account* there are snapshots which has been created for all EC2 instances including the DR instance and also the backup is enabled. Attaching the screenshot below: !image-20260108-085716.png¦width=641,alt="image-20260108-085716.png"! This is also one reason that the costing is spiking. For *Audit Account* also i checked that the SNS and Cloudwatch is consuming lot of cost spike due to which the budget costing is spiked. Attaching the screenshot: !image-20260108-093536.png¦width=613,alt="image-20260108-093536.png"! For *CMS_Backend_Prod* the t3.xlarge instances that is EKS nodes is cost consuming as you can see below Attached Screenshot below showing nodes spike for 4 months. !image-20260108-101131.png¦width=496,alt="image-20260108-101131.png"! Also, below screenshot showing instance type size for EC2 and EKS nodes and there costing for 4 months. !image-20260108-101412.png¦width=583,alt="image-20260108-101412.png"! | [27 empty] | In Progress | 2026-01-06 12:51
AM20-556 | MQ ¦¦ Monitoring and Alert Solution | Blocked | 4 | None( Backlog) |  |  | Diksha Koul | Medium | 1794147 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 21:11 | 2026-01-17 23:33 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if MQ server is stopped |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c39a10 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-02 17:42 | [13 empty] | 02/Nov/25 7:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over* : After creation of the MQ EC2 instance we can start the creation of MQ monitoring and alerting solution. | [29 empty] | To Do | 2025-09-30 10:17
AM20-557 | TM1 ¦¦ Integration of AWS IAM roles with TM1 AWS Account Instance using JSON | Done | 10 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642068 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 20:19 | 2026-01-28 22:21 |  |  |  | 0 | As AWS expert, I would be integrating AWS IAM roles with TM1 Instance Acceptance criteria: * IAM roles are created successfully * Integration of defined IAM roles with TM1 instance so that user is able to access the TM1 instance. |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5190a6ea | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-09 07:30 | [13 empty] | 09/Jul/25 9:29 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Following are the details of the role created: role_arn = "arn:aws:iam::209479274829:role/TM1-IAMRole-EC2InstanceProfile" role_name = "TM1-IAMRole-EC2InstanceProfile" Account details: 209479274829 (SAA-TM1) Custom Role Details: The role covers the equivalent of â€œAmazonSSMManagedInstanceCoreâ€, basic CloudWatch Agent permissions, and general S3 access. _*NOTE*: THE FOLLOWING HAS BEEN ACHIEVED USING TERRAFORM._ | 09/Jul/25 9:30 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;.json file of the custom role is as follows: { Â "Version": "2012-10-17", Â "Statement": [ Â Â { Â Â Â "Sid": "SSMManagedInstanceCorePermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssm:DescribeAssociation", Â Â Â Â "ssm:GetDeployablePatchSnapshotForInstance", Â Â Â Â "ssm:GetDocument", Â Â Â Â "ssm:DescribeDocument", Â Â Â Â "ssm:GetManifest", Â Â Â Â "ssm:GetParameter", Â Â Â Â "ssm:GetParameters", Â Â Â Â "ssm:ListAssociations", Â Â Â Â "ssm:ListInstanceAssociations", Â Â Â Â "ssm:PutInventory", Â Â Â Â "ssm:PutComplianceItems", Â Â Â Â "ssm:PutConfigurePackageResult", Â Â Â Â "ssm:UpdateAssociationStatus", Â Â Â Â "ssm:UpdateInstanceAssociationStatus", Â Â Â Â "ssm:UpdateInstanceInformation" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "SSMMessageGatewayPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssmmessages:CreateControlChannel", Â Â Â Â "ssmmessages:CreateDataChannel", Â Â Â Â "ssmmessages:OpenControlChannel", Â Â Â Â "ssmmessages:OpenDataChannel" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "EC2MessagesPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ec2messages:AcknowledgeMessage", Â Â Â Â "ec2messages:DeleteMessage", Â Â Â Â "ec2messages:FailMessage", Â Â Â Â "ec2messages:GetEndpoint", Â Â Â Â "ec2messages:GetMessages", Â Â Â Â "ec2messages:SendReply" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "CloudWatchAgentPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "logs:CreateLogGroup", Â Â Â Â "logs:CreateLogStream", Â Â Â Â "logs:PutLogEvents", Â Â Â Â "logs:DescribeLogGroups", Â Â Â Â "logs:DescribeLogStreams", Â Â Â Â "cloudwatch:PutMetricData" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "S3AccessPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "s3:GetObject", Â Â Â Â "s3:PutObject", Â Â Â Â "s3:ListBucket" Â Â Â ], Â Â Â "Resource": "*" Â Â } Â ] } | 11/Jul/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed IAM roles is having required permissions | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-558 | Guardy duty and Guardrail implementation on Pegasys account | To Do | 0 | None( Backlog) |  |  |  | Medium | 1835991 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 12:53 | 2026-01-25 16:10 |  |  |  | 0 | [57 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@69378c41 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g000i | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-13 19:35
AM20-559 | NexioAV (Trellix) ¦¦ DR | Done | 5 | Sprint 9 | 2025-07-07 | 2025-07-18 | Yashwant Thakur | High | 1699562 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 13:43 | 2026-01-25 14:09 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Trellix-application.awsflysaa.com¦http://TM1-application.awsflysaa.com] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [13 empty] | 24/Jul/25 11:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250724-091921.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1130283 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4121fe0a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i08p7v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 10 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-08 06:08 | [13 empty] | 08/Jul/25 8:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Setting up Trellix server with AWS DR service is in progress, upon successful installation of software will initiate a replication and complete the setup. | 09/Jul/25 7:32 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;DR setup is completed followed by initial replication, upon software installation we will start replication again and perform failover and failback upon requirement. | 09/Jul/25 7:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Moving to blocked as sinjun yet to install the software. | 17/Jul/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Agent installation is completed, TM1 and frontend prod server are added for testing. | 17/Jul/25 8:09 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;will coordinate with the application owner and initiate a replication back. | 21/Jul/25 7:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Failover and Failback will be performed after getting formal approval from the application owner. | 21/Jul/25 7:04 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;replication is initialized upon bhavish confirmation. | 24/Jul/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have scheduled a call with sinjun today 1.30PM, will perform DR drill and close this userstory. | 24/Jul/25 11:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250724-091921.png¦width=682,height=443,alt="image-20250724-091921.png"! | 25/Jul/25 7:48 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [17 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-07-25 19:48
AM20-560 | POC for replacing IBM MQ with AWS MQ | To Do | 0 | None( Backlog) |  |  |  | Medium | 1795168 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 16:01 | 2026-02-03 19:43 |  |  |  | 0 | [57 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63afd04c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akq: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:36
AM20-561 | MQ ¦¦ Monitoring and Alert Solution | Blocked | 4 | None( Backlog) |  |  | Diksha Koul | Medium | 1794147 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 18:51 | 2026-01-28 20:55 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if MQ server is stopped |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c39a10 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-02 17:42 | [13 empty] | 02/Nov/25 7:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over* : After creation of the MQ EC2 instance we can start the creation of MQ monitoring and alerting solution. | [29 empty] | To Do | 2025-09-30 10:17
AM20-562 | Informatica Server ¦¦ CloudTrail and Guard Rail implementation | Done | 2 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | Medium | 1681743 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 18:30 | 2026-01-20 22:04 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across informatica server (PROS) account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1eb85c02 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05trf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-05 06:17 | [13 empty] | 05/Jun/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Config and guard Duty is enabled and configured. Cloud Trails logging is enabled already. | 06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard rail implementation is applied for the S3 block public access | 13/Jun/25 2:36 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:36
AM20-563 | PROS ¦¦ setup and validate SG and NACL | Done | 2 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1773949 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 21:11 | 2026-01-15 22:05 |  |  |  | 0 | As AWS network expert I would like to setup the security group and NACL for PROS so that access for Pros allow secure access to allow communication with its services while ensureing access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for PROSor related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1df9f068 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwq3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-25 15:31 | [13 empty] | 25/Sep/25 5:31 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SG and NACL setup has been completed, application ports relevant port need to be configured, this will be ready once test server setup process ready. | 09/Oct/25 4:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SG & NACL has been configured and handed over to customer. | 17/Oct/25 7:14 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-10-17 07:14
AM20-564 | MQ ¦¦ POC customer Demo | Blocked | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Sumit Nikam | High | 1672939 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-10 17:37 | 2026-01-10 17:55 | 2026-01-08 08:41 |  |  | 0 | As AWS architect, I would align with SAA stakeholders to give a demo on MQ PoC. *Acceptance Criteria*: * Demo given and next steps discussed with SAA. |  | Harsh Chandra | Sankalp Rai | Sumit Nikam |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67032dc2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pttb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 15 | Sprint 16 | Sprint 22 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 08:24 | [13 empty] | 20/May/25 10:23 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 26th May 2025 End Date: 30th May 2025 | 02/Jun/25 8:26 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;MQ has two option on AWS # Migrate existing MQ Servers to AWS # Use AWS Native MQ service We need a confirmation on approach from Sampi after which we will start working on LLD Document Moving to Blocked | 24/Sep/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Will be taken up once POC is completed in Sandbox | 17/Oct/25 11:21 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 30/Oct/25 9:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;LLD no longer needed To be considered for Modernization as per feedback from Gayaz. Next steps: # Analyze Amadeus response Perform PoC as per Amadeus requirements # Agreement with SAA based on PoC # SoW sigoff # Design Document # AmazonMQ Implementation # Queue by Queue migration | 08/Jan/26 8:48 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Awaiting for a go-ahead to setup a demo call with SAA. | [21 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | To Do | 2026-01-08 08:41
AM20-565 | TM1 ¦¦ Migration tool installation | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620533 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 12:32 | 2026-01-11 15:48 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the TM1 SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | Working with nexio team on troubleshooting the replication issue and configuring required services to get the agent installation successful followed by replication.;07/Apr/25 10:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [5 empty] | AM20-14 | AM20-4 | [23 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@106887e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnnb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:26 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This user story is blocked due to [https://vodacom.atlassian.net/browse/AM20-14¦https://vodacom.atlassian.net/browse/AM20-14¦smart-link] the network setup, upon completion of network will pick this one up. | 21/Mar/25 12:19 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet is shared, requested [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] to create a connectivity between on-premises to cloud. After the connectivity established, will be able to pick this migration agent toll installation for TM1. | 25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created a replication template and post launch template, waiting for the connectivity to be established between on-premises and TM1 AWS account. | 27/Mar/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Shared Agent and access details to vodacom team, have raised CRQ request for agent installation. 28th is planned for agent installation followed by replication will be initiated. | 04/Apr/25 11:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;On-prem to AWS Connectivity is established, Agent installation is getting failed due to multiple time of attempt, now waiting for restart of server from the logs. will try to install again and update the proceeding's here, | 07/Apr/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Replication is in progress, waiting for initial snapshot to be created. | 07/Apr/25 10:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Though agent installation completed, marking this story to done. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-07 10:45
AM20-566 | Nexio AV ¦¦ E2E Integration testing of ServiceNow monitoring | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1732203 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 12:28 | 2026-01-25 15:27 |  |  |  | 0 | As Product Owner I would like to review e2e testing completed with servicenow team for all wave 1 application so that we can confirm to business that in case of any issue service ticket would be raised Acceptance Criteria: * Tickets/issues are getting raised successfully against the alerts raise via cloudwatch for all Wave1 applications * ServiceNow team signoff received * Showcase (demo) provided to all relevant stakeholders |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 19/Aug/25 10:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141324 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1c3893f7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0brrj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-28 07:41 | [13 empty] | 28/Jul/25 9:41 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[https://vodacom.atlassian.net/browse/AM20-116¦https://vodacom.atlassian.net/browse/AM20-116¦smart-link] Only after completing the above US will start working on this story. | 28/Jul/25 3:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;After completion of Faisal story i will be proceeding with this US. | 11/Aug/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: Since the story was blocked due to configuration of monitoring and alerting on NexioAV ec2 instances (application specific) which was completed on 8th Aug 2025 (evening), Diksha did not get any time to validate end to end solution. Hence, the spillover. | 19/Aug/25 10:17 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have tried to triggered the alert to service now team. Now waiting for them to confirm from there side. | 19/Aug/25 10:33 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation for Priyanka and team the alerts are getting generated and tickets are being created in service now. Attaching the same screenshot for the reference. | 19/Aug/25 10:36 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image.png¦width=881,height=228,alt="image.png"! attaching the screenshot what service now team is getting the alerts for your reference from Priyanka and team. | 21/Aug/25 2:31 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:31
AM20-567 | Teammate ¦¦ subnet creation using terraform | Done | 2 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620382 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 18:28 | 2026-01-13 19:01 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Teammate application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Teammate and the configured based on the approved comms matrix |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@776c05e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 3 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-04 08:58 | [13 empty] | 04/Apr/25 10:58 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets has been created | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-14 09:39
AM20-568 | Airnavx ¦¦ EC2 Creation using terraform code | Cancelled | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satyabrata Sahoo | Medium | 1760710 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:4b8d8093-596d-4394-a074-4a9a9636f86f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 20:53 | 2026-01-26 00:21 |  |  |  | 0 | As AWS Expert I would like to provision EC2 using terraform so that I can handover to SAA for Airnavx installation Acceptance Criteria: EC2 provisioned successfully using approved AMI Tags applied automatically Instance must have SSM agent installed SSH is enabled only via bastion host Guardduty must detect and monitor instance Instance must publish logs to CloudWatch EC2 must register with org monitoring/alerting |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b9d343f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejt7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | [103 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 06:38 | [13 empty] | 05/Sep/25 8:37 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Closing this as this is a duplicate of [https://vodacom.atlassian.net/browse/AM20-131¦https://vodacom.atlassian.net/browse/AM20-131¦smart-link], hence closing the ticket | [26 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-05 08:38
AM20-569 | S3, KMS Failed Controls | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Aravind Raj | Medium | 1869412 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-01 16:59 | 2026-02-01 19:47 | 2025-12-11 08:18 |  |  | 0 | With a different compliances and standard framework will remediate the failed controls for S3 and KMS |  | Aravind Raj | Sanjot Fotedar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 |  |  |  |  | ;08/Dec/25 7:28 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18000 | ;11/Dec/25 8:25 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;39720 |  |  |  |  | 57600 | 0 | 57720 | 1 | 57600 | 0 | 57720 | [12 empty] | 10/Dec/25 10:36 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;Assessment_sheet_s3KMS.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1193964 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b7df5b0 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obrn: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-08 17:27 | [13 empty] | 08/Dec/25 7:27 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Have started working with fixing Failed Compliance s3 and KMS resources. | 10/Dec/25 10:36 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Compliance gaps identified and resolved failed controllers for S3 and KMS in backend accounts by implementing required configurations. Excel sheet is attached for fixed controllers.[^Assessment_sheet_s3KMS.xlsx] | 12/Dec/25 10:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed all controls are in passed state hence closing. | [24 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2025-12-12 10:35
AM20-570 | Nexio AV ¦¦ establish internet connectivity via TGW | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650868 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 20:51 | 2026-01-26 00:42 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Harsh Chandra | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  | ;02/May/25 12:35 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;14400 | [5 empty] | 14400 | 0 | 14400 | 1 | 14400 | 0 | 14400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1e57c316 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:x | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:43 | [13 empty] | 29/Apr/25 7:43 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;internet connectivity has ben setup, sending for review | 02/May/25 12:37 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Tested through SSM {quote}Ping to 8.8.8.8 working Tracert to 8.8.8.8 working{quote} Forwarding for PO Approval | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:38
AM20-571 | (Airchef)Terraform code generation for Route 53 Hosted Zone Creation & Record Migration. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Faisal Sayed | Medium | 1827706 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-02-04 12:40 | 2026-02-04 15:44 |  |  |  | 0 | Hosted Zone Creation Develop infrastructure-as-code to provision a Route 53 hosted zone for the specified domain. The configuration should support tagging, environment-specific naming, and be reusable across deployments. DNS Record Management Implement a declarative script to define and manage DNS records within the hosted zone. This should include support for common record types (A, CNAME, MX, TXT) with configurable TTLs and values. |  | Faisal Sayed | Sanket Kale |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e |  |  |  |  | ;12/Nov/25 10:17 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 |  |  |  |  | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@53b50383 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1v7: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:56 | [13 empty] | 07/Nov/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status: Blocked* Awaiting SAA approval for the updated DNS records associated with the {{airchef}} domain. Terraform provisioning is currently on hold until the DNS configuration is finalized. | 12/Nov/25 6:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status Update:* * Task moved from *Blocked* to *In Progress*. * Terraform code for Route 53 provisioning has been developed and handed over to *Sanket*. * *Next Action:* Sanket to review and execute the code in the *sandbox account* for validation. | 12/Nov/25 6:55 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform code has been successfully reviewed and tested in the sandbox environment, and all validations are positive. Â | 12/Nov/25 10:16 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Code has been reviewed, tested successfully, and validated. Moving the sub-story to *Done*. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-12 10:12
AM20-572 | SMS Alerting implementation- Opt in/Opt out | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-25 15:37 | 2026-01-25 17:46 |  | 2025-11-15 14:38 |  | 0 | As a cloud product owner I want application and platform alerts to be delivered via SMS from a dedicated long code so that on call engineers and stakeholders receive time critical notifications Acceptance criteria: *Long code configured and verified* - given the approved long code when I set SNS and SMS preferences then the long code is used as the origination identity for the supported countries and unsupported routes use the configured Sender ID feedback *E2E SMS on P1/P2* - Given the cloudWatch alarm changes to ALARM with severity ðŸ˜›1 when the alarm event is routed via EventBridge to the SNS topic than all active on-call receipients for the app+env recieve an SMS within 60s and message body includes app, env, alarm name, severity, runbook link and ACK instruction ¦¦*Severity*¦¦*objective signals*¦¦*examples*¦¦ ¦P1 - Critical, user impact¦harsh outage, data loss, security incdences¦API 5xx>10% 5m in production, RDS storage<5% 10m. certificate expiry < 3days, guard duty, unauthrized access¦ ¦P2 - Degradation,Urgent¦performance, throughput, redundancy lost,¦EKS node group<N healthy, ALB healthy, RDS IOPS deviation, CPU utilization, disk innode,¦ ¦P3 - Action soon¦Capacity/Ops issues, repeated flaps¦log patterns,¦ ¦P4 - Informational¦chnages , warnings, failures without user impact¦Daily back ok, lamda changes, deloyment success¦ *Delivery logging and metrics* - Given SMS messages are sent when carriers return delivery statuses then statuses are captured in CloudWatch logs and S3 and dashboards show sends, successes, failures, per country breakdown *Retry and escalations ( in the event of SMS failure)* - Given a send gets a transient failure when the system retries with backoff( up to 3 times in 5 minutes) then on persistent failure an escalation SMS is triggered to secondary contacts and a ticket is created in ServiceNow with failure details *Deduplication and storm control* - Given multiple identical alarms fire within 5 minutes when routing occurs then recipients receive at most one SMS per unique alarm/signature per 5 minute window and a summary SMS is sent after 15 minutes if >5 deduped alerts occurred. *Opt-out/Opt-in* - Given a recipient replied STOP when routing future SMS to that number then messages are surpassed and audit shows timestamp and actor and START re-enables *Cost Guardrails* - Given a monthly SMS budget when SNS spend reaches 80% then P2 alert is sent to Ops and at 100% sends are rate limited to P1 only until an override flag is set *Cross account publish* - Given alarms originate in child accounts when Event Bridge forwards to central account Then publishing to the central SNS topic succeeds via resources based and IAM roles |  | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Working on exploring the ways to implement cost guardrail for lambda. Exploring enabling cloudwatch metric to track the money spent on SMS sent through the account.;10/Nov/25 8:37 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on understanding how cost is shown in billing in case of SMS sent through SNS or SMS sent using End User Messaging.;11/Nov/25 3:39 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on updating lambda to get cross account cost metric to implement 80% cost guardrail to send notification only in case of P1 and P2 alarms when 80% threshold is breached.;11/Nov/25 3:40 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). Trying the opt-out mechanism for SA number(carrier blocking was cited as one of the issues behind blocking) and parallely raised a request to understand the issue.;13/Nov/25 8:04 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Deployed changes on production cluster.;14/Nov/25 8:18 AM;17cb9418-1850-4923-932b-7098ec51b6bb;14400 |  | 57600 | 0 | 129600 | 2.25 | 57600 | 0 | 129600 | [10 empty] | AM20-176 | [19 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3955b400 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h707: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:34 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Working on implementing cost guardrails to restrict sms sending to only P1 and P2 messages when 80% limit is utilised. | 11/Nov/25 8:25 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Will be testing using cost explorer API to fetch billing cost of SNS during Lambda execution. As per AWS docs, if we are using SNS for sending SMS then the metrics wonâ€™t get reflected on CloudWatch metrics. For opt-in/opt-out as per docs, user can send the STOP message to stop getting message. Need to try this part on our end. | 12/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Updated lambda to fetch amount spent on SMS sent using cost explorer API, currently able to fetch cross account. Working on updating Lambda to avoid duplication using DynamoDB. Testing in progress. | 13/Nov/25 8:02 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Able to fetch cost of sending SMS using API, able to avoid deduplication of alarms with the help of DynamoDB table. Currently Working on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). | 14/Nov/25 8:19 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed changes on production account. | 15/Nov/25 2:38 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-15 14:38
AM20-573 | ServiceNow Integration with Wave 1 application accounts for migration | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1718215 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 20:30 | 2026-01-10 23:58 |  |  |  | 0 | As AWS expert I would like to setup ServiceNow monitoring with all the application accounts so that in case of any alerts generated via CloudWatch agents, it can be cascaded to ServiceNow to form an incident tickets Below applications are considered TM1, Patch managment, NexioAV, Informatica server Acceptance Criteria: * ServiceNow monitoring is setup successfully in all the accounts targeted to be used for respective application migration * API for serviceNow is successfully configured for non-prod as well as prod accounts respectively * ServiceNow team confirmation is received that API is transferring the information successfully * E2E validation is completed ( App account-->cloudwatch-->SNS topic-->alerts-->Servicenow monitoring-->ServiceNow |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [13 empty] | 17/Jul/25 5:53 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250717-155331.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1127871 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7ecd77e5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aoff: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-17 06:11 | [13 empty] | 17/Jul/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 and Nexio AV service now integration is completed, unit testing will be completed. | 17/Jul/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Only after the demo and approval patching server will be added to the service now integration | 17/Jul/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will add informatica server integration today. | 17/Jul/25 5:53 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Informatica aws account integration is completed, test with a test server working fine as expected. !image-20250717-155331.png¦width=647,height=465,alt="image-20250717-155331.png"! | 21/Jul/25 7:05 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;patch management server is expected to setup in security account, so ill be doing security account integration with service now by today. | 21/Jul/25 6:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Security account service now integration is completed unit test yet to be performed. | 25/Jul/25 7:48 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-25 19:48
AM20-574 | PROS ¦¦ Cutover | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773952 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 12:53 | 2026-01-10 13:04 |  | 2025-10-31 18:04 |  | 0 | As AWS expert I would be performing the cutover for PROS application. Acceptance Criteria: * Replication from on-prem is successfully stopped using API calls * Back up of PROS VDC Server * Monitoring disable - VDC Server * Shutting down Informatica application in VDC * Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining PROS Server to the AD * MAT Testing completed successfully by SAA * Deploy the Test instance with the network components * Deploy cutover actual instance * Wait for the launch instance check the status checks * configure required SSM and CW agent |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 31/Oct/25 11:09 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;RE_ PROS Server Cutover - Migratiom.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175913 | 28/Oct/25 11:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251028-095312.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174005 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4900724c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwr7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 |  | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | [65 empty] | YES | YES | 2025-10-03 07:24 | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | [12 empty] | 03/Oct/25 9:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Only after the server migration we would be able to do cutover so this US will be blocked. | 17/Oct/25 11:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cut over is planned on 27th Oct as per client request, since this will be spillover. | 28/Oct/25 11:52 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SSM agent installation and cloud watch installation is completed followed by domain join. | 28/Oct/25 11:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have sent a mail to application owner on the confirmation for closing cutover, upon receiving same will close this US. !image-20251028-095312.png¦width=423,alt="image-20251028-095312.png"! | 28/Oct/25 5:31 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;client facing some FTP issue, after it resolved this US can be closed | 31/Oct/25 11:08 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Cutover completed as per the email from Pieter Scheepers ( app owner)- email attached | 31/Oct/25 6:04 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [23 empty] | Done | 2025-10-31 18:04
AM20-575 | Monitor health and logs of Lamda connector function to troubleshoot issue , if alerts in not processed | Done | 8 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747507 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 13:04 | 2026-02-05 13:37 |  |  |  | 0 | As Product owner I want to monitor health and logs of Lamda connector function so that I can troubleshoot issues quickly when alerts are not processed and ensure reliability of the alerting pipeline Acceptance Criteria: CloudWatch logs are enabled for the Lamda connector function to capture execution details, input events and error messages Cloudwatch Metrices (invocations, errors, throttles, duration) are available for function and updated in real time cloudwatch alarms are configured for * Errors >0 in last 5 minues * Throttles >0 * Duration exceeds timeout threshold A SNS is configured to capture failed Lamda execution Alerts from cloud watch are sent via SNS to notify ServiceNow CloudWatch Logs insights queries are available to quickly identify error trends and assist RCA Lamda health and alerting processing mertics are visulaized in a CloudWatch dashboard. |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 07/Aug/25 2:30 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1137015 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4db73908 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2qr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-07 12:31 | [13 empty] | 07/Aug/25 2:30 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[^LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx] Have attached the lambda detailed sheet. | 25/Aug/25 2:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;the alarms have been created for lambda functions in flysaa-backend and they are created for â€œerrorâ€, â€œthrottleâ€, â€œdurationâ€ and the thresholds are 1, 1 and 30sec respectively. the alarms notifications are now being sent to respective sns topics created which shall in-turn appear into service now dashboard as soon as the threshold values are met. | 25/Aug/25 6:32 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 06:32
AM20-576 | Airnavx ¦¦ Lift Request creation | Done | 1 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | Medium | 1761196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 16:58 | 2026-01-30 19:21 |  |  |  | 0 | As Network expert I have to raise Lift request so that Network Firewall implementation CSOC request for port, routing connectivity can be established with VDC Acceptance criteria: Post Lift request, firewall, port and routing connectivity is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@70851109 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0el9v: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 08:42 | [13 empty] | 05/Sep/25 10:41 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;AirNavX Lift request has been created and completed. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Network team confirmed as routing in place hence no routing required. CSOC and under implementation process from VDC/SITA side. | 08/Sep/25 6:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-09-08 06:34
AM20-577 | IAM role used for Patch Solutions | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741163 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-31 16:16 | 2026-01-31 16:53 |  |  |  | 0 |  |  | Aravind Raj | Faisal Sayed |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@35ee02d7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckgj: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:32 | [13 empty] | 04/Aug/25 6:31 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*In Security Acc* # [saa-security-central-patch-bucket-windows-lambda-roleÂ ¦https://730335236533-kttygmoz.af-south-1.console.aws.amazon.com/go/view?arn=arn%3Aaws%3Aiam%3A%3A730335236533%3Arole%2Fsaa-security-central-patch-bucket-windows-lambda-role&source=lambda] # [ComplianceSyncLambdaRole¦https://730335236533-kttygmoz.af-south-1.console.aws.amazon.com/go/view?arn=arn%3Aaws%3Aiam%3A%3A730335236533%3Arole%2FComplianceSyncLambdaRole&source=lambda] # SAA_Security_WSUS_Central_Server_EC2_Role *In FlySAA-Backend-Dev Acc* # ssm-flysaa-backend-dev-spoke-windows-instance-role # [sm-flysaa-backend-dev-spoke-crossaccount-lambda-role-1¦https://746669190453-quvjamav.us-east-1.console.aws.amazon.com/iam/home?region=af-south-1#/roles/details/sm-flysaa-backend-dev-spoke-crossaccount-lambda-role-1] # [ssm-flysaa-backend-dev-spoke-crossaccount-lambda-role¦https://746669190453-quvjamav.us-east-1.console.aws.amazon.com/iam/home?region=af-south-1#/roles/details/ssm-flysaa-backend-dev-spoke-crossaccount-lambda-role] | 04/Aug/25 6:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;User Permissions: # EC2 Full Access. # Lambda Full Access # SSM Full Access # S3 Full Access # IAM Write Access | 12/Aug/25 10:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Provide me the policy list with the roles you have used. | 12/Aug/25 11:28 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;{adf:display=block} {"type":"table","attrs":{"isNumberColumnEnabled":false,"layout":"center","localId":"29cd7e76-bf6f-40fa-9142-c6fb8bb33df1"},"content":[{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Name Of Role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Account"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Permission Policies"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Permission Policy"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":4},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-flysaa-backend-dev-spoke-windows-instance-role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonS3FullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMManagedInstanceCore"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"KMSFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-flysaa-backend-dev-spoke-windows-instance-s3-policy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":4},"content":[{"type":"paragraph","content":[{"type":"text","text":"sm-flysaa-backend-dev-spoke-crossaccount-lambda-role-1"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AllowSSMExecution"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CloudWatchLogsFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Trust RealtionshipÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":3},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-flysaa-backend-dev-spoke-crossaccount-lambda-role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CloudWatchLogsFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-ec2-read-access"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]}]} {adf} | 12/Aug/25 11:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;{adf:display=block} {"type":"table","attrs":{"isNumberColumnEnabled":false,"layout":"center","localId":"4bd8311d-ebb8-4ed2-b8da-1e130a493dfb"},"content":[{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":5},"content":[{"type":"paragraph","content":[{"type":"text","text":"saa-security-central-patch-bucket-windows-lambda-role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWSLambdaBasicExecutionRole"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWSLambdaRole"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CrossAccountLambdaExecutionPolicy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"lambda-access-to-s3"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"StartAutomationRole-Linux"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"ComplianceSyncLambdaRole"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"lambda-permission-policy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":3},"content":[{"type":"paragraph","content":[{"type":"text","text":"SAA_Security_WSUS_Central_Server_EC2_Role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AllowPutToCentralPatchBucket"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMManagedInstanceCore"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CloudWatchAgentServerPolicy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]}]} {adf} | [22 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-21 18:09
AM20-578 | Push to FlySAA backend Alarm related code to the bitbucket in dev and preprod environment | Done | 8 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786761 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 13:51 | 2026-01-13 16:09 |  |  |  | 0 | Add existing terraform code to create CloudWatch alarms and other required AWS resources into the bitbucket. Add alarms for following: # Kubernetes microservice CPU and Memory consumption alarms for Amadeus and Fabric microservices. # Error Patterns observed in microservice logs. # Healthcheck API endpoint return status monitoring. # Configured Alerts to monitor RDS metrics. Also create EventBridges to capture alarm state change (Ok â†’ Alarm and Alarm â†’ Ok). Create Lambda jobs to be triggered by EventBridge which in turn sends notification to ServiceNow using existing SNS topics. |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7d9f3978 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hatj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-29 08:07 | [13 empty] | 29/Sep/25 10:07 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Added alerts for monitor error patterns in microservice logs for dev account . Added alerts for monitor cpu, memory and container restart for dev account for dev account . | [29 empty] | Done | 2025-10-06 07:59
AM20-579 | Security and compliance implementation on PEGASYS account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622536 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 20:19 | 2026-01-09 22:14 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on Pegasys account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in TM1, Teammate account * NIST policy implementation successfully done in TM1, Teammate account * AWSFSBP policy implementation successfully done in TM1, Teammate account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [10 empty] | AM20-18 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@792d09b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxstj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-21 10:14 | [13 empty] | 21/Mar/25 12:14 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Marking as Done, as pegasys account migration still on discussion. | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-21 12:14
AM20-580 | Provision and manage Amazon Inspector V2 across AWS account using Terraform with master-member hierarchy | Done | 20 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1718164 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 14:31 | 2026-01-09 15:54 |  |  |  | 0 | As a cloud security engineer, I want to provision Amazon inspector across all accounts in my AWS org using a delegated administrator account so that I can perform centralized automated and continuous vulnerability scanning of EC2, ECR, and Lamda across all member accounts Acceptance Criteria: * Terraform must be enabled in Payer9 account * Terraform must register the Payer9 account for Inspector within AWS organization to allow Payer9 to manage inspector across member accounts * Terraform must enable Inspector in each member account by assuming a role into those accounts for all resource types (EC2,ECR, Lamda function) must be activated * Terraform must ensure that EC2 scanning is enabled, ECR scanning is continuous, Lamda scanning is turned on * Once enabled, findings for all member accounts must be accessible from delegated account via Inspector console * The terraform config must be reusable across multiple accounts and support by parameterized resources types * All terraform created resources must include standard tags for auditability * Integrate Inspector with security hub * Alert on critical CVEs using SNS/EventBridge * Raise alerts on high severity findings |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@35c15470 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aoa3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | Sprint 12 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-18 06:22 | [13 empty] | 18/Jul/25 8:22 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Need to send the email to Ismail about add the amazon inspector in trusted entity. | 22/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Email sent to Ismaail and leigh about Request to Enable Centralized Management for GuardDuty and Amazon Inspector and currently I am working on Terrafrom script to create the base module for resources | 23/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Leigh replied and asked to Ismaail for assisting. | 25/Jul/25 8:33 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;It will be spillover because there was a dependency on Ismail and he has updated on 23 July Only so thatâ€™s why I am not able to complete it on time. | 21/Aug/25 2:33 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. Please delete Amazon Inspector instances as it is POC | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:33
AM20-581 | Servicenow Payload severity updates for Lambda alarms | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Shreyash Talwekar | Medium | 1835024 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-27 21:22 | 2026-01-28 00:06 |  |  |  | 0 | Enhance the existing Lambda function that triggers when Lambda alarms enter an alarm state. Currently, the function gathers alarm-related metrics, collects function details, and sends an approved payload to ServiceNow. However, severity information from the alarm is not included in the payload. This story addresses that gap by updating the Lambda function to capture and transmit the correct severity level from the alarm to ServiceNow. *Acceptance Criteria:* * Lambda function must include severity details from the alarm in the payload. * Payload sent to ServiceNow should accurately reflect the alarm severity. |  | Faisal Sayed | Harsh Chandra | Shreyash Talwekar |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  | ;20/Nov/25 8:33 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;14400 | [6 empty] | 0 | 14400 |  |  | 0 | 14400 | [12 empty] | 21/Nov/25 7:04 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251121-050425.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187511 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@560f4ab3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxar: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 05:33 | [13 empty] | 20/Nov/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Requirements have been gathered. Lambda function code will be reconfigured to incorporate changes, followed by payload testing. Ticket will be updated upon successful completion of testing. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Lambda function has been updated per requirements to capture severity. A test event was executed to validate behavior and output; results are attached. Test outcome is successful, and the implementation is complete. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251121-050425.png¦width=555,alt="image-20251121-050425.png"! | 24/Nov/25 8:42 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reviewed output, LGTM. | [23 empty] | 1832856 | AM20-264 | Update ServiceNow Payloads with severity | Done | 2025-11-24 08:41
AM20-582 | POC - Create Sustainability dashboards | To Do | 8 | Sprint 10 | 2025-07-21 | 2025-08-01 | Sankalp Rai | High | 1720042 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 14:50 | 2026-01-10 17:53 |  |  |  | 0 | As AWS Expert, I would create sustainability dashboard to access the power consumption, utilization and energy efficiency in alignment with well-architecture Acceptance Criteria * Enable AWS Sustainability Pillar in Well-Architected Reviews, optimize workloads for energy efficiency â€” right-sizing, minimizing network transfer, cold storage, etc. * Leverage S3 Lifecycle Policies & Intelligent Tiering |  | Harsh Chandra | Sankalp Rai |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63121580 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v09 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | Sprint 12 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:13 | [13 empty] | 11/Aug/25 10:12 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 12th August End Date: 21st August | 10/Sep/25 1:15 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Moving this to Backlog from Sprint 13 as suggested by Deepak Sharma, to currently focus on critical migration activities. This will be picked up in later sprints. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | To Do | 2025-10-13 09:27
AM20-583 | Security and compliance implementation on PROS account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622524 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 21:10 | 2026-01-30 00:37 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on PROS account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in PROS DEV account * NIST policy implementation successfully done in PROS DEV account * AWSFSBP policy implementation successfully done in PROS DEV account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Mar/25 2:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [8 empty] | AM20-19 | AM20-17 |  |  | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250317-060821.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1079558 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a53b25a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxson: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-13 06:02 | [13 empty] | 13/Mar/25 8:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on the controls with the dependency services for the security frameworks. | 14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;The controls were implemented in Pros DEV account, Pros Production account will be picked up in separate user story. | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250317-060821.png¦width=1277,height=642,alt="image-20250317-060821.png"! | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-14 14:22
AM20-584 | Route53 cutover for FlySAA.com | Done | 2 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865867 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 15:57 | 2026-01-20 16:59 | 2025-12-14 18:49 | 2025-12-12 11:18 |  | 0 | As product Ownwer I like to perform cutover for Route53 for [FlySAA.com¦http://FlySAA.com] Acceptance Criteria: The [flysaa.com¦http://flysaa.com] application must be highly available and resilient to single-region outages (e.g., 99.99% uptime). *Route 53 Implementation:* Configure *Failover Routing* policies. A primary record is associated with an active endpoint. A secondary, passive record is configured as a backup. Route 53 health checks automatically switch traffic to the secondary region if the primary endpoint is deemed unhealthy. |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;04/Dec/25 8:30 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;43200 | [5 empty] | 28800 | 0 | 43200 | 1.5 | 28800 | 0 | 43200 | [12 empty] | 04/Dec/25 8:30 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251204-063001.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1192161 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@769d9d3b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7mz: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-02 16:21 | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Dec/25 6:20 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Latest zone file has been imported under public hosted zone route53 AWS.. Earlier 313 after upload 318 records has-been created. | 04/Dec/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;DNS pointer has been modified to route53. C:\Users\VaranasiS>nslookup -query=NS [flysaa.com¦http://flysaa.com] Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: [flysaa.com¦http://flysaa.com] nameserver = [ns-1419.awsdns-49.org¦http://ns-1419.awsdns-49.org] [flysaa.com¦http://flysaa.com] nameserver = [ns-308.awsdns-38.com¦http://ns-308.awsdns-38.com] [flysaa.com¦http://flysaa.com] nameserver = [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] [flysaa.com¦http://flysaa.com] nameserver = [ns-1777.awsdns-30.co.uk¦http://ns-1777.awsdns-30.co.uk] [ns-1419.awsdns-49.org¦http://ns-1419.awsdns-49.org] internet address = 205.251.197.139 [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] internet address = 205.251.194.93 [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] AAAA IPv6 address = 2600:9000:5302:5d00::1 [ns-1777.awsdns-30.co.uk¦http://ns-1777.awsdns-30.co.uk] internet address = 205.251.198.241 C:\Users\VaranasiS> | 04/Dec/25 8:23 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Customer requested to add new alias zone for ALB. ¦[flysaa.com¦http://flysaa.com]¦A¦Simple¦-¦Yes¦[flysaa-cms-alb-402247724.af-south-1.elb.amazonaws.com¦http://flysaa-cms-alb-402247724.af-south-1.elb.amazonaws.com].¦ ¦ Zone has been created and validated after DNS cutover and same working fine. !image-20251204-063001.png¦width=591,alt="image-20251204-063001.png"! | 05/Dec/25 8:29 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SAA SSL DNS has been modified according to request. the change requested under â€œCHG0068431/ CHR0031920â€ has been successfully implemented. Below you will find the latest and updated record for your reference. Â Â C:\Users\VaranasiS>nslookup [upwards.flysaa.com¦http://upwards.flysaa.com] Server:Â UnKnown Address:Â 2401:4900:50:9::7d5 Â Non-authoritative answer: Name:Â Â Â [upwards.flysaa.com¦http://upwards.flysaa.com] Address:Â [102.130.96.4¦https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2F102.130.96.4%2F&data=05%7C02%7Csatyasairam.varanasi%40vodafone.com%7C3d58714d9d324c04956d08de33430e8a%7C68283f3b84874c86adb3a5228f18b893%7C0%7C0%7C639004560572522291%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=w7K%2F%2Fjsk9kHTi00XQSJKC3mq2iHGjbBvw1316zlJjyk%3D&reserved=0] Â Â C:\Users\VaranasiS> Â | 12/Dec/25 11:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-12-12 11:18
AM20-585 | Ingesting 500 of lines of inbound and outbound rules from excel to Terraform code for enablement | Done | 6 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1869689 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 12:50 | 2026-02-03 16:29 | 2025-12-14 17:51 | 2025-12-12 14:51 |  | 0 |  |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bae0685 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ocbn: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-05 06:26 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Dec/25 8:26 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script deployment. Currently we are adding the inbound and outbound rule with excel only. | 12/Dec/25 2:51 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approving provided we see workable solution during demo | [28 empty] | Done | 2025-12-12 14:51
AM20-586 | Assessment on CMS Frontend SMS implementation | Done | 8 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Highest | 1842250 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 22:05 | 2026-01-14 22:35 | 2025-11-28 11:16 | 2025-11-28 14:00 |  | 0 | As a cloud platform application owner I want to perform a detailed assessment for enable SMS notification in the CMS frontend application hosted in AWS so that I can determine best approach, integration method, cost impact, security requirement and technical feasibility before implementation Acceptance Criteria: All use cases for SMS notification are documented SLA, frequency and criticality of SMS delivered and captured User flow diagrams for each SMS scenario prepared Assessment must identify How front will invoke API Required IAM permission documented for access for SMS publishing Consideration for rate limiting and Compliance requirements Risk, Assumption and dependencies |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Understanding alarm implementation and getting AWS frontend access from Leigh.;28/Nov/25 10:33 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on implementing SMS notification on frontend dev account;28/Nov/25 10:33 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | SMS implementation is working, worked on debugging minor issues and updating timeout of Lambda function to enable sending SMS to multiple numbers.;28/Nov/25 10:34 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 |  |  |  | 115200 | 28800 | 86400 | 0.75 | 115200 | 28800 | 86400 | [12 empty] | 28/Nov/25 1:49 PM;17cb9418-1850-4923-932b-7098ec51b6bb;SMS_frontend_alerts.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190540 | 28/Nov/25 10:36 AM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251128-083619.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190436 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67436dd5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5jf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-25 08:56 | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 25/Nov/25 10:56 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created a Whitepage access request to enable access for frontend AWS accounts, reached out to Leigh with ticket details. | 26/Nov/25 8:54 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Access request is approved, awaiting access enabling from Leigh. | 27/Nov/25 8:21 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Got the access from Leigh, worked on provisioning AWS resources (Lambda , eventbridge rule , dynamodb table) for alert implementation, need to get number from Hoosen for sending sms. | 28/Nov/25 10:36 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Hoosen confirmed he got SMS for sample alarm in frontend dev . !image-20251128-083619.png¦width=281,alt="image-20251128-083619.png"! | 28/Nov/25 1:49 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;[^SMS_frontend_alerts.docx] Please find attached document for SMS implementation. | 28/Nov/25 2:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-28 14:00
AM20-587 | AWS Centralized dashboard CloudWatch Dashboard for Nexio AV to monitor Performance, cost optimization and security Metrics | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718753 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 18:59 | 2026-01-31 22:49 |  |  |  | 0 | As AWS expert, I would like to create centralized CloudWatch to capture Performance, Security and Cost metrics from across accounts. Acceptance Criteria: * CloudWatch dashboards can be created in one account (Payer9 account) anf pull metrics from other accounts * User cross account IAM roles to allow Payer9 account to read cloudwatch from other accounts * Add Widgets sourcing metrics from each account * Setup AWS config aggregator in the Payer9 account to collect configuration and compliance data across all members accounts * Performance metrics - Use below Cloudwatch metrics * EC2 : CPU, Network, Disk I/O * RDS: CPU, READ/Write IOPS * Lambda: Duration, Error Rate * and source these into widgets in the centralized dashboard * Security Metrics: Centralized Security Hub is already enabled, which can pull in findings from GuardDuty, Config, Macie, Cloudtrail, Inspector etc. |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60b85e0b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aofj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-23 14:43 | [13 empty] | 23/Jul/25 4:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Created Trellix Dash board with CPU, Memory and Disk usage. | 25/Jul/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dash board prepared for CPU, Disk, Network and memory for Trellix application. | 25/Jul/25 8:09 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sent for review | 27/Jul/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Could see the metrics for trellix server, moving to PO approval, | 28/Jul/25 9:57 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:57
AM20-588 | CloudWatch Metrics configuration in all AWS account | To Do | 0 | None( Backlog) |  |  | Faisal Sayed | Medium | 1868810 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 13:32 | 2026-01-12 16:30 | 2026-01-06 08:22 |  |  | 0 | As Cloud Product Owner I wish to configure below metrices in Cloudwatch for all the AWS accounts so that we can monitor the memory and Disk availability for each applications residing over the AWS accounts. * Memory Available MBytes * LogicalDisk % Free Space * LogicalDisk Free Megabytes Acceptance Criteria * CloudWatch dashboard must consist of all the above mentioned metrics for all application so that we can view the memory and disk available space * Only specific IAM role must give permission to the CloudWatch agent to collect metrics from server * The above metrics view is restricted with relevant IAM role * The dashboard must be configured in centralized audit account ¦ ¦ | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@32f363c4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0002 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-28 08:08
AM20-589 | Code Pipeline creation using Terraform in Sandbox | Done | 8 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1749627 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 16:18 | 2026-01-31 20:08 |  | 2025-10-31 17:19 |  | 0 | As Platform owner I want to create code pipeline POC in sandbox so that we can achieve a base module for centralizing CI/CD pipeline. *Acceptance Criteria*: * Code build and S3 and IAM role replica is created which is needed in code pipeline integration * Code pipeline base module is ready |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;30/Oct/25 6:52 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;86400 | ;30/Oct/25 6:52 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;10800 | ;31/Oct/25 10:55 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18120 |  |  |  | 115200 | 0 | 115320 | 1 | 115200 | 0 | 115320 | [12 empty] | 31/Oct/25 11:10 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251031-091042.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175916 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@648c36cb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v05i | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-28 06:19 | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 28/Oct/25 8:19 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Started work on codepipeline module for Github base repository. Feature branch â€œfeat/codepipeline2â€ is created for this. | 30/Oct/25 6:51 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Modules have been created in feature branch of base and component repositories [https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa/tree/feat/codepipeline2¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa/tree/feat/codepipeline2¦smart-link] [https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/tree/feat/codepipeline2¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/tree/feat/codepipeline2¦smart-link] These modules have been tested as well in sandbox aws account. Now in next sprint, we will focus on to have dependency of required modules like s3, iam roles, kms (if needed), codebuild to be integrated with codepipeline in Bitbucket repository alongwith modules creation in BB repo. | 31/Oct/25 11:10 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Following successful validation with â€œterraform planâ€, modules have now been pushed to remote feature branches of both base and component repositories. !image-20251031-091042.png¦width=459,alt="image-20251031-091042.png"! | 31/Oct/25 5:19 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-10-31 17:19
AM20-590 | Tagging validations for AWS workloads across environments | Done | 0 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1749567 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 14:14 | 2026-01-19 14:47 |  |  |  | 0 | As AWS expert, Tagging of all resources must be completed and verified |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@24bea93e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0daxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:59 | [13 empty] | 25/Aug/25 8:59 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill over :* I will be reviewing & Attaching the sheet here in US as on friday EOD sanjot & shreyash updated the tags and added them on sheet thatâ€™s why this story got spilled over. | 25/Aug/25 10:03 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have reviewed the sheet all tags are updated for all resources. [Validation sheet for Naming and tagging for FLYSAA_CMS_BACKEND DEV PREPROD & PROD.xlsx¦https://vodafone.sharepoint.com/:x:/r/sites/SouthAfricaAirlines/_layouts/15/Doc.aspx?sourcedoc=%7BD95F49D1-A6B2-4430-A48E-1925ADA79A0D%7D&file=Validation%20sheet%20for%20Naming%20and%20tagging%20for%20FLYSAA_CMS_BACKEND%20DEV%20PREPROD%20%26%20PROD.xlsx&action=default&mobileredirect=true] | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:56
AM20-591 | Informatica ¦¦ Alerting and Monitoring Solution | Done | 4 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1800159 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-01 14:51 | 2026-02-01 14:59 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment. Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O. * Dashboards are created to monitor key services. * SNS Alert should be generated if Informatica server is stopped. |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 09/Oct/25 9:21 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251009-071913.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1165179 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3ac6b815 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ivor: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 09:08 | [13 empty] | 06/Oct/25 11:07 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start creating the dashboard and alerting for Informatica Dev and Prod environment. | 06/Oct/25 12:13 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I enabled the CloudWatch metrics for Informatica Dev and Prod for CPU, memory, disc, network I/O. Dashboards are also created to monitor key services. --- *DONE.* Now Alerting and monitoring needs to be created with proper naming and threshold values â€“ *PENDING*. | 07/Oct/25 12:19 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Created alarms and monitoring for informatica prod and dev for CPU and Status Check failed â€“ *DONE.* | 08/Oct/25 12:38 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;All alerts including the Disk and memory utilization for Informatica Prod and Dev has been created with proper naming and threshold value. --- *DONE.* | 09/Oct/25 9:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251009-071913.png¦width=1575,height=673,alt="image-20251009-071913.png"! Have created the Informatica prod and dev alerting rules setup the threshold value for them. | 09/Oct/25 10:46 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Moving this US to in review to Aravind. If require any modification. | 13/Oct/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have reviewed has some query will discuss with diksha and close. | 15/Oct/25 11:58 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Aravind reviewed the changes and gave his approval now we can move it to PO approval. | 17/Oct/25 7:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | Done | 2025-10-17 07:17
AM20-592 | Terraform Development ¦¦ Creation of Outbound and inbound rules in NACL | Done | 8 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1651313 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 14:16 | 2026-02-04 17:49 | 2025-11-27 08:27 | 2025-11-28 12:00 |  | 0 | As Terraform expert, I want to be creating a network ACL with inbound and outbound rules using terraform code, so that I can apply stateless packet filtering at the subnet level Acceptance Criteria: * Define variable for CIDRs, ports and subnets * NACL resources is created and associated with target subnets * Application relevant flows needs to be populated * Application inbound rule and comms metric needs to populated for NACL * Outbound rules allow return traffic on the same ports. * Each rule has a unique number and direction * Rules are parameterized for environment flexibility * add rule description and tags. * Provision to add or deny additional rules with max of 20 rules to be allowed for NACL |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@442b4964 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mrnr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 19 | [96 empty] | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-20 07:06 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 20/Nov/25 9:06 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Working on base module code of terraform script. It will be completed by this Friday EOD. | 27/Nov/25 8:24 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform script completed and NACL resource created in sandbox environment. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-11-28 12:00
AM20-593 | MQ Modernization POC ¦¦ Parser testing based on sample pegasys parser | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832848 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 16:13 | 2026-01-25 17:56 | 2025-11-28 11:15 | 2025-11-28 12:00 |  | 0 | As DevOps Engineer, I need to test few existing MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6bedb0f1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo0r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:26 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:26 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;CPP to Java: Parser to be re-written with line to line conversion to retain logic. | 20/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Java Parser Covering Following High-level Algorithm- # Input * Receive a raw text message body (rawMessage) from AmazonMQ PEGASYS.OUT.UAT. # Pre-check * If rawMessage is null or empty â†’ return ParseResult with error = true (this is defensive; in normal operation this should not happen). # stripId() â€“ remove ID block if present 3.1. Let msg = rawMessage. 3.2. If msg contains "\nM42": * Call stripId(msg): * Find index of " /ID ". * From there, find "ACARS\r\n". * Return: msg_before_ID + msg_from_ACARS_onwards. 3.3. Else: keep msg unchanged. . # Construct buff and newbuff 4.1. buff = msg (the stripped or original message). 4.2. Append control chars: * CR = 13, NL = 10, ETX = 3. * newbuff = buff + CR + NL + ETX. # Split into lines & find .JNB 5.1. Split newbuff by '\n' into lines[]. 5.2. Search for first line where lines[i].startsWith(".JNB"). 5.3. If found, set counter = i + 1 (line after .JNB). 5.4. If not found or counter >= lines.length: * Default: create OutboundMessage(qMng, newbuff) â†’ MNG only. * Return this as ParseResult with error = false. # Extract relevant lines safely * line0 = lines[counter] (or "" if out of range). * line1 = lines[counter + 1] * line2 = lines[counter + 2] * line3 = lines[counter + 3] Using helpers: * safeLine(lines, index) â€“ returns "" if index out of range. # Extract tokens (T1, T2, etc.) safely Using safeSub(s, begin, endExclusive) to avoid index errors. 7.1. T1 = line0[0..3) â†’ message type (MVT, DIV, ASM, SSM, CGO, etc.). 7.2. T2 = line1[1..5) â†’ secondary code (CIRQ, CICX, etc.). 7.3. line1_0_2 = line1[0..2) â†’ used to check "SA". 7.4. line2_0_2 = line2[0..2) â†’ used to check "ED". 7.5. line3_0_3 = line3[0..3) â†’ used to check "TIM". # Prepare result container * outputs = new ArrayList<OutboundMessage>(); # Rule 1 (SSM/CGO â†’ ICARGO) * If T1 is "SSM" or "CGO": * outputs.add(new OutboundMessage(qIcargo, buff)); 10. Rule 2 (CIRQ/CICX â†’ SIP) * If T2 is "CIRQ" or "CICX": * Add OutboundMessage(qSip, buff) to outputs. * Return ParseResult(outputs, false, null) immediately 11. Rule 3 (MVT / DIV / ASM) 11.1. If T1 in { "MVT", "DIV", "ASM" }: 11.1.1 ASM + TIM * If T1 == "ASM" and line3_0_3 == "TIM": * Add OutboundMessage(qCimp, buff) (CIMP). * Add OutboundMessage(qIcargo, buff) (ICARGO). * Then continue. 11.1.2 MVT-specific * If T1 == "MVT": * If line1_0_2 == "SA" (SA flight): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG with CR/LF/ETX). * Add OutboundMessage(qIcargo, buff) (ICARGO). * If line2_0_2 == "ED": * Add OutboundMessage(qCimp, buff) (CIMP). * Add another OutboundMessage(qIcargo, buff) (ICARGO again â€“ same as C++ double-write). * Else (non-SA): * Add OutboundMessage(qMng, newbuff) (MNG only). 11.1.3 DIV/ASM (fallback) * Else (T1 is DIV or ASM without TIM rule): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG). 12. Rule 4 (other message types) * Else (T1 is not MVT, DIV, ASM, and not CIRQ/CICX): * Add OutboundMessage(qMng, newbuff) (MNG only). 13. Return final result * return new ParseResult(outputs, false, null); | 24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Additional parser related to Pegasys called SbrSplit has been shared by Sampi. Analysis has been started for the same. | 28/Nov/25 11:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SbrSplit parser - CPP has been converted into java based code. Repo structure has also been transformed to adopt microservice alike design. [https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git¦https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git] Parser to be tested in next sprint. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [25 empty] | Done | 2025-11-28 12:00
AM20-594 | Patch Management ¦¦ Life Cycle ¦¦ Implement Retention Policy in S3 busket | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1746117 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 14:16 | 2026-01-14 16:41 |  |  |  | 0 | As Product Owner I want to implement retention policy on S3 server so that download files can be managed Acceptance Criteria: * Retention policy is implemented on S3 * Post retention period file getting deleted successfully |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@401c6aaa | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 07:07 | [13 empty] | 12/Aug/25 9:07 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Retention rule for central patching bucket is as follows: the rule is created for prefix filters like (windows/dev/, windows/preprod/, windows/prod/, linux/dev/, linux/preprod/, linux/prod/) After 60 days objects within the path shall expire. | 20/Aug/25 8:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-20 08:10
AM20-595 | BackUP Server ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | Medium | 1681815 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 20:15 | 2026-02-02 00:12 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across BackUP server account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43003ef3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4f: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-05 06:17 | [13 empty] | 05/Jun/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Config and guard Duty is enabled and configured. Cloud Trails logging is enabled already. | 06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard rail implementation is applied for the S3 block public access | 13/Jun/25 2:36 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:36
AM20-596 | Migration of FLYSAA DNS Zones to AWS Route53 | To Do | 6 | None( Backlog) |  |  | Satya Varanasi | Medium | 1822276 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 12:59 | 2026-01-13 13:42 |  |  |  | 0 | As a cloud infrastructure Architect I want to migrate existing DNS zones from FLYSAA to AWS Route 53 so thar DNS management can be centralized with AWS, ensuring stability, availability and integration with other AWS services Acceptance Criteria: DNS Zone Discovery and Assessment * Existing FLYSAA DNS zones are inventoried and validated for record types (A, AAAA, CNAME, MA,TXT, SRV, NS, SOA, PTR etc.) * Dependencies on on-prem or third party systems are identified * Zone delegation hierarchy and authoritative name servers are documented * TTL Values and routing policies (simple, Weighted, latency, failover etc.) are reviewed for compatibility with Route53 Route 53 hosted Zone creation * Corresponding public/private hosted zones are created in Route 53 with identical zone names * Correct VPC associations are configured for private zones in the appropriate AWS accounts (dev, pre-prod and prod) * Hosted zones are tagged appropriately * Record Migration and Validation Record Migration and Validation * All DNS record from FLYSAA are migrated to Route 53 with matching values * Route 53 health checks and routing policies are configured as per existing logic * Random sample validation (at least 10%) of DNS resolution from client endpoints confirm accuracy * Validations confirm parity between source and target DNS records Cutover and Delegations * NS records in parent zones are updated to point to Route53 name servers * Change propagation and DNS TTL impact are communicated and managed * Post-cutover validation confirms DNS resolutions is working correctly from internal and external networks * A rollback plan is documented and tested before cutover Security, Audit and logging * Route53 DNS query logging is enabled to CloudWatch or S3 * Access to hosted zones is restricted using IAM roles and policies * GuardDuty and config rules validate DNS configuration integrity * Audit report is generated post migration with DNS record counts and comparison results Monitoring and Alerting * CloudWatch alarms are configured for health checks and DNS failure * SNS topics notify the platform operations team on failure or health check degradation * Dashboards display query metrics and latency per hosted zone Document * Update DNS architecture diagram reflects Route53 integration * SOPs for future DNS change requests are published in the knowledge base * Migration validation report is approved by the business |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [11 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5a13873 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g004 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-10-29 10:50
AM20-597 | ServiceNow Monitoring ¦¦ Prod Implementation | Done | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1673102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-28 18:34 | 2026-01-28 18:53 |  |  |  | 0 | As AWS solution architect, I would like to implement ServiceNow monitoring in prod environment so that alerts can be generated and reach to ServiceNow in form of Tickets for further actions. Acceptance Criteria: * Setup of ServiceNow integration to pull AWS receive data using EventBridge * Unautherized API calls from GuardDuty and Security Hub * Setup Cloudwatch alarms or rules for all the resources entitled to be monitored and send these to SNS topic * Create SNS topic * Configure SNS HTTPS configuration so that SNS can directly invoke HTTPS endpoints * AWS Lambda function created to forward SNS messages by parsing it and sends REST API requests to ServiceNow. * Attach the Lamda to the SNS topic * Set the credentials in AWS Secret Manager * Lamda function can reach the ServiceNow endpoint through API gateway by using HTTPS and Secure authentication |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;04/Jul/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cfb2e84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04h5f: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-26 06:17 | [13 empty] | 26/May/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 8:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting to get a exact tags to be passed to Ec2 instance to receive at service now. *New HTTPS endpoint will be shared by feroz for the production workloads.* | 25/Jun/25 8:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;From 24th June we had a call with feroz, where we expected to get the production servicenow endpoint by nest week to configure in SNS, hence waiting for same to start this user story. | 02/Jul/25 7:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PRODUCTION ServiceNow Instance: [https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws¦https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws] SNS topic is updated with a new subscription and backend prod integration is completed, unit test yet to start. | 04/Jul/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Right now the production environments like Backend, TM1, AirnavX accounts are integrated with the prod service now endpoint and SNS is configured to get the alerts. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-04 08:15
AM20-598 | Informatica Server - Cutover for Dev | Done |  | Sprint 13 | 2025-09-01 | 2025-09-12 | Satya Varanasi | Medium | 1768419 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 21:39 | 2026-01-10 23:42 |  |  |  | 0 |  |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4db6c5dd | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fb23: | [167 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-08 07:54 | [13 empty] | 08/Sep/25 9:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to be action after connectivity test, still connectivity having some issues from SITA compass and SAP raise side. | 30/Sep/25 7:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change has been approved, scheduled change today on 11:00 AM SAST. | 01/Oct/25 8:13 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica DEV server cutover has been completed and app owner and Wanda has been tested initial connectivity. Hence i am closing this Story. | [24 empty] | 1751440 | AM20-140 | Informatica Server ¦¦ Cutover | Done | 2025-10-01 08:24
AM20-599 | Documentation on Budget Management | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747516 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 19:30 | 2026-01-14 20:03 |  |  |  | 0 | As Product Owner, I would like to create a detailed documentation on Budget management solution Acceptance Criteria: Document should consist of below sections with detailed description. * IAM roles /groups and policy created for it * Details of any Lamda functions are configured * process to add users to the group to allow edit/view/remove privileges * Dashboard and configurations details * Process to change, update budget allocated, notification iteration etc. * Details of naming convention and tagging as applicable * Architectural diagram as applicable |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/Aug/25 12:23 PM;9e4636e8-9dfc-4a33-901b-fcd75015926a;AWS_Budget_Management.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1143135 | 14/Aug/25 7:01 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;Budget Documentation (24287a92-0ff3-4da3-9f2c-3378740b4c97).docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139610 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@58ed7f61 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2rv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-14 05:03 | [13 empty] | 14/Aug/25 7:02 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Document has been attached. Please verify [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] | 22/Aug/25 12:23 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;[^AWS_Budget_Management.docx] AWS Budget Document attached | 25/Aug/25 6:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 06:34
AM20-600 | SMS Alerting implementation- Opt in/Opt out | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-30 21:03 | 2026-01-30 23:44 |  | 2025-11-15 14:38 |  | 0 | As a cloud product owner I want application and platform alerts to be delivered via SMS from a dedicated long code so that on call engineers and stakeholders receive time critical notifications Acceptance criteria: *Long code configured and verified* - given the approved long code when I set SNS and SMS preferences then the long code is used as the origination identity for the supported countries and unsupported routes use the configured Sender ID feedback *E2E SMS on P1/P2* - Given the cloudWatch alarm changes to ALARM with severity ðŸ˜›1 when the alarm event is routed via EventBridge to the SNS topic than all active on-call receipients for the app+env recieve an SMS within 60s and message body includes app, env, alarm name, severity, runbook link and ACK instruction ¦¦*Severity*¦¦*objective signals*¦¦*examples*¦¦ ¦P1 - Critical, user impact¦harsh outage, data loss, security incdences¦API 5xx>10% 5m in production, RDS storage<5% 10m. certificate expiry < 3days, guard duty, unauthrized access¦ ¦P2 - Degradation,Urgent¦performance, throughput, redundancy lost,¦EKS node group<N healthy, ALB healthy, RDS IOPS deviation, CPU utilization, disk innode,¦ ¦P3 - Action soon¦Capacity/Ops issues, repeated flaps¦log patterns,¦ ¦P4 - Informational¦chnages , warnings, failures without user impact¦Daily back ok, lamda changes, deloyment success¦ *Delivery logging and metrics* - Given SMS messages are sent when carriers return delivery statuses then statuses are captured in CloudWatch logs and S3 and dashboards show sends, successes, failures, per country breakdown *Retry and escalations ( in the event of SMS failure)* - Given a send gets a transient failure when the system retries with backoff( up to 3 times in 5 minutes) then on persistent failure an escalation SMS is triggered to secondary contacts and a ticket is created in ServiceNow with failure details *Deduplication and storm control* - Given multiple identical alarms fire within 5 minutes when routing occurs then recipients receive at most one SMS per unique alarm/signature per 5 minute window and a summary SMS is sent after 15 minutes if >5 deduped alerts occurred. *Opt-out/Opt-in* - Given a recipient replied STOP when routing future SMS to that number then messages are surpassed and audit shows timestamp and actor and START re-enables *Cost Guardrails* - Given a monthly SMS budget when SNS spend reaches 80% then P2 alert is sent to Ops and at 100% sends are rate limited to P1 only until an override flag is set *Cross account publish* - Given alarms originate in child accounts when Event Bridge forwards to central account Then publishing to the central SNS topic succeeds via resources based and IAM roles |  | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Working on exploring the ways to implement cost guardrail for lambda. Exploring enabling cloudwatch metric to track the money spent on SMS sent through the account.;10/Nov/25 8:37 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on understanding how cost is shown in billing in case of SMS sent through SNS or SMS sent using End User Messaging.;11/Nov/25 3:39 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on updating lambda to get cross account cost metric to implement 80% cost guardrail to send notification only in case of P1 and P2 alarms when 80% threshold is breached.;11/Nov/25 3:40 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). Trying the opt-out mechanism for SA number(carrier blocking was cited as one of the issues behind blocking) and parallely raised a request to understand the issue.;13/Nov/25 8:04 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Deployed changes on production cluster.;14/Nov/25 8:18 AM;17cb9418-1850-4923-932b-7098ec51b6bb;14400 |  | 57600 | 0 | 129600 | 2.25 | 57600 | 0 | 129600 | [10 empty] | AM20-176 | [19 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3955b400 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h707: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:34 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Working on implementing cost guardrails to restrict sms sending to only P1 and P2 messages when 80% limit is utilised. | 11/Nov/25 8:25 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Will be testing using cost explorer API to fetch billing cost of SNS during Lambda execution. As per AWS docs, if we are using SNS for sending SMS then the metrics wonâ€™t get reflected on CloudWatch metrics. For opt-in/opt-out as per docs, user can send the STOP message to stop getting message. Need to try this part on our end. | 12/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Updated lambda to fetch amount spent on SMS sent using cost explorer API, currently able to fetch cross account. Working on updating Lambda to avoid duplication using DynamoDB. Testing in progress. | 13/Nov/25 8:02 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Able to fetch cost of sending SMS using API, able to avoid deduplication of alarms with the help of DynamoDB table. Currently Working on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). | 14/Nov/25 8:19 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed changes on production account. | 15/Nov/25 2:38 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-15 14:38
AM20-601 | Transit Gateway setup for Dev environment | Done | 6 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1702418 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 17:07 | 2026-01-19 18:26 |  |  |  | 0 | As Network Expert, I would be able to setup Transit network gateway for Dev environment Acceptance Criteria: Transit Gateway is provisioned successfully in Dev environment. |  | Aravind Raj | Satya Varanasi |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [13 empty] | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132834.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121470 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132924.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121472 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133228.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121473 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133337.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121469 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133439.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121471 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67c2563b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i095nv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-01 16:49 | [13 empty] | 01/Jul/25 6:49 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;There is no Preprod env for 20+ app migration list, hence we are not setting up Preprod TG attachment, in case needed near future we will setup according to requirement. In this sprint we will setup TG attach for Dev env. | 03/Jul/25 3:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Common TG Attach has be setup on shared VPC dev Account and tested internet connectivity via informatica DEV subnet. !image-20250703-132834.png¦width=1306,height=662,alt="image-20250703-132834.png"! !image-20250703-132924.png¦width=1204,height=668,alt="image-20250703-132924.png"! TG-Attach subnets: !image-20250703-133228.png¦width=1243,height=475,alt="image-20250703-133228.png"! TG attachment details. !image-20250703-133337.png¦width=1189,height=448,alt="image-20250703-133337.png"! Subnet associations !image-20250703-133439.png¦width=1215,height=611,alt="image-20250703-133439.png"! | 04/Jul/25 12:05 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed, test server is working with internet. | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-04 12:05
AM20-602 | POC - Create Sustainability dashboards | To Do | 8 | Sprint 10 | 2025-07-21 | 2025-08-01 | Sankalp Rai | High | 1720042 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 17:45 | 2026-01-24 19:45 |  |  |  | 0 | As AWS Expert, I would create sustainability dashboard to access the power consumption, utilization and energy efficiency in alignment with well-architecture Acceptance Criteria * Enable AWS Sustainability Pillar in Well-Architected Reviews, optimize workloads for energy efficiency â€” right-sizing, minimizing network transfer, cold storage, etc. * Leverage S3 Lifecycle Policies & Intelligent Tiering |  | Harsh Chandra | Sankalp Rai |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63121580 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v09 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | Sprint 12 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:13 | [13 empty] | 11/Aug/25 10:12 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 12th August End Date: 21st August | 10/Sep/25 1:15 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Moving this to Backlog from Sprint 13 as suggested by Deepak Sharma, to currently focus on critical migration activities. This will be picked up in later sprints. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | To Do | 2025-10-13 09:27
AM20-603 | (Airchef)Terraform code generation for Route 53 Hosted Zone Creation & Record Migration. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Faisal Sayed | Medium | 1827706 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-24 19:48 | 2026-01-24 20:24 |  |  |  | 0 | Hosted Zone Creation Develop infrastructure-as-code to provision a Route 53 hosted zone for the specified domain. The configuration should support tagging, environment-specific naming, and be reusable across deployments. DNS Record Management Implement a declarative script to define and manage DNS records within the hosted zone. This should include support for common record types (A, CNAME, MX, TXT) with configurable TTLs and values. |  | Faisal Sayed | Sanket Kale |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e |  |  |  |  | ;12/Nov/25 10:17 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 |  |  |  |  | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@53b50383 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1v7: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:56 | [13 empty] | 07/Nov/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status: Blocked* Awaiting SAA approval for the updated DNS records associated with the {{airchef}} domain. Terraform provisioning is currently on hold until the DNS configuration is finalized. | 12/Nov/25 6:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status Update:* * Task moved from *Blocked* to *In Progress*. * Terraform code for Route 53 provisioning has been developed and handed over to *Sanket*. * *Next Action:* Sanket to review and execute the code in the *sandbox account* for validation. | 12/Nov/25 6:55 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform code has been successfully reviewed and tested in the sandbox environment, and all validations are positive. Â | 12/Nov/25 10:16 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Code has been reviewed, tested successfully, and validated. Moving the sub-story to *Done*. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-12 10:12
AM20-604 | MQ-PROD ¦¦Setup Subnet, NACL and SG Creation and Validation | Done | 3 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1794109 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 17:40 | 2026-01-09 19:54 |  | 2025-10-31 09:34 |  | 0 | As AWS network expert I would like to setup the security group and NACL for MQ so that access for MQ allow secure access to allow communication with its services while ensuring access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for MQ or related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [13 empty] | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090000.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175254 | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090022.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175253 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@680e7164 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0i6ob: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 17 | [97 empty] | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [65 empty] | YES | YES | 2025-10-17 09:19 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [12 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 27/Oct/25 4:05 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working on it. | 30/Oct/25 11:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to requirement i have done platform setup. Subnets: ¦Subnet address¦Range of addresses¦Useable IPs¦Hosts¦Divide¦Used Status¦App Name¦ ¦10.40.0.224/28¦10.40.0.224 - 10.40.0.239¦10.40.0.225 - 10.40.0.238¦14¦Divide¦Done¦MQ PROD PRIVATE¦ ¦10.40.0.240/28¦10.40.0.240 - 10.40.0.255¦10.40.0.241 - 10.40.0.254¦14¦Divide¦Done¦MQ PROD PUBLIC¦ ¦10.40.1.32/28¦10.40.1.32 - 10.40.1.47¦10.40.1.33 - 10.40.1.46¦14¦Divide¦Done¦MQ PROD DR¦ ¦10.40.1.48/28¦10.40.1.48 - 10.40.1.63¦10.40.1.49 - 10.40.1.62¦14¦Divide¦Done¦MQ PROD DR¦ Subnets screen: !image-20251030-090022.png¦width=597,alt="image-20251030-090022.png"! EC2 connectivity screen: !image-20251030-090000.png¦width=597,alt="image-20251030-090000.png"! | 31/Oct/25 9:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though MQ migration is put on hold however since the objective and acceptance criteria is met, approving the User story to close | [26 empty] | Done | 2025-10-31 09:34
AM20-605 | (Airchef)Terraform Implementation for Creation of Route 53 Hosted Zones & Records. | In Progress |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Sanket Kale | Medium | 1827709 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-17 18:42 | 2026-01-17 21:41 |  |  |  | 0 | *Acceptance Criteria:* * *Deploy Public Hosted Zone* Use Terraform to provision a *Route 53 public hosted zone* for the domain [*airchef.co.za*¦http://airchef.co.za]. * *Manage DNS Records via Terraform* Implement Terraform configurations to create and manage various DNS record types (A, CNAME, MX, TXT, etc.) within the hosted zone. |  | Faisal Sayed | Sanket Kale | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [20 empty] | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28df5c12 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1vn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-07 05:56 | [13 empty] | 07/Nov/25 7:56 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Code review completed from my side its working. Created and deployed the base and component modules. | 10/Nov/25 9:07 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and tested on Sandbox environment | 14/Nov/25 4:01 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code deployment done sandbox and same tested. | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | In Progress | 2025-11-20 08:59
AM20-606 | Extend Codepipeline modules for bitbucket and custom stages - POC over sandbox | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1824325 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 17:14 | 2026-02-05 20:44 | 2026-01-08 08:39 |  |  | 0 | *Description:* Enhance existing CodePipeline Terraform modules to support Bitbucket as a source and allow configurable custom stages for improved flexibility and reuse. *Acceptance Criteria:* * Bitbucket source integration added and configurable via variables. * Custom pipeline stages supported through module inputs. * Existing Bitbucket pipelines remain unaffected. * Validation done for both GitHub and Bitbucket pipelines. | [19 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6747613f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptvb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | In Progress | 2026-01-06 08:25
AM20-607 | SMS Alerting Implementation | Done | 6 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1785825 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 19:42 | 2026-02-04 21:10 |  | 2025-10-31 17:22 |  | 0 | As a cloud product owner I want application and platform alerts to be delivered via SMS from a dedicated long code so that on call engineers and stakeholders receive time critical notifications Acceptance criteria: *E2E SMS on P1/P2* - Given the cloudWatch alarm changes to ALARM with severity ðŸ˜›1 when the alarm event is routed via EventBridge to the SNS topic than all active on-call receipients for the app+env recieve an SMS within 60s and message body includes app, env, alarm name, severity, runbook link and ACK instruction ¦¦*Severity*¦¦*objective signals*¦¦*examples*¦¦ ¦P1 - Critical, user impact¦harsh outage, data loss, security incdences¦API 5xx>10% 5m in production, RDS storage<5% 10m. certificate expiry < 3days, guard duty, unauthrized access¦ ¦P2 - Degradation,Urgent¦performance, throughput, redundancy lost,¦EKS node group<N healthy, ALB healthy, RDS IOPS deviation, CPU utilization, disk innode,¦ ¦P3 - Action soon¦Capacity/Ops issues, repeated flaps¦log patterns,¦ ¦P4 - Informational¦chnages , warnings, failures without user impact¦Daily back ok, lamda changes, deloyment success¦ *Delivery logging and metrics* - Given SMS messages are sent when carriers return delivery statuses then statuses are captured in CloudWatch logs and S3 and dashboards show sends, successes, failures, per country breakdown *Retry and escalations ( in the event of SMS failure)* - Given a send gets a transient failure when the system retries with backoff( up to 3 times in 5 minutes) then on persistent failure an escalation SMS is triggered to secondary contacts and a ticket is created in ServiceNow with failure details *Deduplication and storm control* - Given multiple identical alarms fire within 5 minutes when routing occurs then recipients receive at most one SMS per unique alarm/signature per 5 minute window and a summary SMS is sent after 15 minutes if >5 deduped alerts occurred. |  | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Initially worked on gathering additional information regarding message size limit for SMS in case of long text message sent. Initiated questionaire in AWS community portal to get in depth costing based on message length , worked on restructuring SMS notification to avoid additional costing for SMS. Discussed with Gayaz to get company information to initiate dedicated long code generation (currently using shared pool of origination identities). Worked on updating existing Lambda jobs to support sending SMS alerts and working on fetching amount spent in SMS notification to apply a cost guard rail and send only priority message in case of spent exceeds 80 % limit. ;31/Oct/25 1:17 PM;17cb9418-1850-4923-932b-7098ec51b6bb;115200 | [5 empty] | 86400 | 0 | 115200 | 1.33 | 86400 | 0 | 115200 | [11 empty] | AM20-253 | 31/Oct/25 1:09 PM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251031-110848.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176021 | 31/Oct/25 1:09 PM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251031-110913.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176022 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@78a09d31 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h703: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 |  | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | [65 empty] | YES | YES | 2025-10-03 06:27 | 3_*:*_1_*:*_1487503847_*¦*_10041_*:*_1_*:*_502605019_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1727584741 | [12 empty] | 03/Oct/25 8:26 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Awaiting Go ahead from Husein/Eugene to proceed with this requirement | 14/Oct/25 8:22 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Sign off received to go ahead with SMS alerting requirement | 20/Oct/25 7:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;spill over reason- need company contact details and other relevant information to generate a request for long code on AWS support. | 24/Oct/25 8:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Requested for additional details from Gayaz as asked by AWS support for proceeding with Long code generation request and account spent limit increase. | 30/Oct/25 11:34 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;we have done changes in lambda script to support sending sms for error pattern alerts , test sms was successfully sent to Gayaz. Working on adding similar support for other alarm types as well, also working on implementing other requirements like sending only p1 message if budget is crossed over 80% and opt-in/opt-out functionality. | 31/Oct/25 12:11 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Issue split into: ¦AM20-253¦SMS Alerting implementation- Opt in/Opt out¦ | 31/Oct/25 1:10 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We have configured SMS based alerts for Flysaa Backend Alarms and assigned Priorities to the alerts based on above table. *Error Patterns in Pod logs* : P3 *Api HealthCheck Fail for pod* : P1 *CPU consumption or Memory consumption or Container restart alarm* : P2 For RDS: *When RDS instance is down* : P1 *When RDS cert expiry is < 30 days* : P1 (We check cert expiry daily but SMS notification will only be sent when < 30 days are remaining ) *RDS metrics alarms like CPU utilization, read/write iops* : P2 *RDS metrics when available free space is less than 10 %* : P1 Please find attached screenshots for SMS sent to Gayaz !image-20251031-110848.png¦width=537,alt="image-20251031-110848.png"! !image-20251031-110913.png¦width=463,alt="image-20251031-110913.png"! | 31/Oct/25 5:22 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;SMS sent to Customer and mail confirmation received | [22 empty] | Done | 2025-10-31 17:22
AM20-608 | Centralized Cluster Creation Strategy | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Sanjot Fotedar | Medium | 1885775 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 17:02 | 2026-01-14 17:28 | 2026-01-08 08:38 |  |  | 0 | As A platform Owner I want to create a detailed design document for centralized management of EKS cluster across multiple AWS child accounts from a central account so that the solution is secure, scalable, compliant and operationally ready before implementation Acceptance Criteria: *Architecture and Account structure* - * Parent, central management and child application accounts * hub and spoke model connectivity model * shared vs isolation responsibilities *EKS management Strategy* - * Centralized model * Namespace isolation strategy * Cluster ownership and lifecycle boundaries *IAM and Security design* - * Cross account IAM roles and trust relationship * K8s RBAC mapping * Least privileges access model * SCP usage and guardrails *Network and Connectivity design* - * VPC architecture per account * Connectivity via TGW /VPC peering * Control plane and data plane traffic flow * DNS resolution strategy *Governance and Policy Enforcement* - * Kubernetes admission controls (Kyverno) * naming, tagging and quota standards * Policy exception handling process *Observability and Logging* - * Centralized logging and metrics flow * Alerting and escalation paths *Security and Compliance* - * EKS security monitoring * Image scanning approach * Compliance reporting and audit readiness *Operation model* - * RACI matrix (L1/L2/L3) * Incident and change management process * upgrade and patching strategy * Backup and DR approach |  | Sanjot Fotedar | [5 empty] | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [5 empty] | ;07/Jan/26 7:23 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;7200 | [5 empty] | 115200 | 108000 | 7200 | 0.06 | 115200 | 108000 | 7200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43715548 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptve: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-07 17:24 | [13 empty] | 07/Jan/26 7:23 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Started work on this. Currently evaluating the framework for assessing multi-tenancy readiness of existing eks cluster. Identifying key focus areas for hardening -Â namespace isolation, RBAC scope, network segmentation, resource governance, policy enforcement. | [29 empty] | In Progress | 2026-01-07 19:21
AM20-609 | PROS ¦¦ Migration agent installation | Done | 0 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786910 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 22:07 | 2026-01-25 01:34 |  |  |  | 0 | AS AWS Product owner I want to install migration agents in both source and target accounts so that workloads can be discovered replicated and migrated securly and reliable into AWS, capture disk, network activity and replicate workloads in AWS Acceptance Criteria: *Replication receiver* - Given the target AWS account is selected when the migration service creates replication servers or staging area subnets then the target account provisions EC2 instances and storage for replication *IAM trust policies* - The migration hub service role is created in the target account when the source account publishes replication traffic, then cross account IAM trust allows replication without manual credential handling *Networking and Security* - The replication server is deployed in a VPC when traffic flows from source to target then it uses encrypted channels and passes through SG/NACLrules validated against compliance baselines *Resources readiness* - Migrated workloads are created in the target when cutover happens the EC2, RDS and AWS service provision successfully in the correct subnet, AZ and security group *Monitoring and rollback* - Agents are sending replication data when a failure occurs then alerts are generated in CoudWatch/SNS and rollback to the last stable snapshot is possible |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5de8572e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hc4b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:15 | [13 empty] | 24/Sep/25 8:14 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Need to check with Sinjun/Wanda for change request initiation for agent installation. | 25/Sep/25 5:25 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change has been submitted â€œCHG0067735â€ and approved, we required Sinjun support for Agent installation. | 26/Sep/25 12:19 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still Migration agent comms not implemented and it is under approval process. | 09/Oct/25 4:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Agent has been installed on all 3 PROS servers and test instance has been created and handed over to customer for connectivity testing. Hence i am closing this story. | 17/Oct/25 7:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:17
AM20-610 | AirNavX ¦¦ Comms Matrix modification | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Yashwant Thakur | High | 1672499 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-06 20:48 | 2026-02-06 21:19 |  |  |  | 0 | As Network expert, I would be modifying the comms Metrices for AirNavX as the number of servers reduced to 3 servers instead of earlier scope of 5 servers. Acceptance Criteria: * Comms Metrics are successfully created * Sent for reviews to SITA team and agreement received |  | Harsh Chandra | Satya Varanasi | Sumit Nikam | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@40de4872 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04f2j: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-23 11:33 | [13 empty] | 23/May/25 1:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working it will be ready next week. | 27/May/25 8:12 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started and will be closed today or tomorrow. | 28/May/25 5:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;I have prepared 3 servers AirNavx comms and sending for review. | 16/Jun/25 8:32 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;This was checked and reviewed. | 16/Jun/25 8:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-16 08:34
AM20-611 | CMS Backend RDS instance (Pre-prod/Prod) analysis | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1833687 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 21:01 | 2026-01-12 00:20 |  | 2025-11-27 09:21 |  | 0 | As Product owner I like to analyse RDS for rightsizing based on utlization to reduce cost |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Nov/25 5:10 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;21600 | ;25/Nov/25 4:08 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;64800 |  |  |  |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 18/Nov/25 5:09 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251118-150648.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1185982 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6460780 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo2n: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 15:10 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 5:09 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;RDS cost analysis is started. Today, we have reduced backup retention period of preprod rds to 7 days from 35 days. Also, storage limit threshold for dev rds is updated to 200 GiB from 110GiB because it was generating alerts â€œ*_Storage size 100 GiB is approaching the maximum storage threshold 110 GiB. Increase the maximum storage threshold_*â€ !image-20251118-150648.png¦width=459,alt="image-20251118-150648.png"! Next we will monitor cpu, memory consumption across three environments | 25/Nov/25 4:15 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;h3. Next Steps for CMS Backend RDS Cost Optimization With discussion with Pankaj, we have identified the following points as next steps for CMS Backend RDS cost optimization: * Turn off non-prod RDS instances when not in use or during off-business hours and turn them back on when required. * Further reduce backup retention period for non-prod RDS instances (currently 7 days) to explore additional cost savings. These actions will be implemented post confirmation from FlySAA team. | 27/Nov/25 9:21 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:21
AM20-612 | Informatica Server - Dev ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1749537 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 18:15 | 2026-01-28 19:40 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 57600 |  | 0 | 86400 | 57600 | [9 empty] | AM20-145 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b90196e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0datf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 14:28 | [13 empty] | 18/Aug/25 4:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev MGN template has been configured, now we are looking AWS migration agent installation on server for sync, Sinjun going to take care tomorrow for the same i have scheduled the call. | 19/Aug/25 5:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;While checking AWS agent connectivity not working, checking with network team for further troubleshooting/fixing the issue. CSOC request has-been createdâ€CINC0909706â€ | 25/Aug/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network routing not implemented, currently it under approval process. | 26/Aug/25 1:11 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Firewall rules implemented. # Configured MGN agent setup on AWS for dev server migration. # Identified as connectivity not working. # Initiated network troubleshooting call towards fixing. # Identified as routing not configured. # Requested LIFT for approval # LIFT approval took 3days # Monday CSOC request raised and routing has ben implemented. # Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 29/Aug/25 8:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev agent installation and Test instance setup has been complted. | 01/Sep/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The test instance connectivity has been completed. Communicated to Peter for connectivity testing. The ip address is: 10.42.0.46. Sending this request for closing. | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-613 | Informatica Server - Cutover for Prod | Done |  | Sprint 13 | 2025-09-01 | 2025-09-12 | Aravind Raj | Medium | 1768422 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 19:51 | 2026-02-05 22:01 |  |  |  | 0 |  |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;30/Sep/25 6:36 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;43200 | [5 empty] | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [12 empty] | 30/Sep/25 6:35 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250930-163551.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1160875 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7b96ec0c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fb2j: | [167 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 07:23 | [13 empty] | 05/Sep/25 9:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Informatica Test server is launched and trying to fix RDP connectivity issue. Only after the test instance confirmation we will be able to deploy cutover, so this will be a spillover. | 30/Sep/25 6:35 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250930-163551.png¦width=669,height=443,alt="image-20250930-163551.png"! | [25 empty] | 1751440 | AM20-140 | Informatica Server ¦¦ Cutover | Done | 2025-09-30 18:36
AM20-614 | AirNavX ¦¦ Validation for SG and NACL | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Satya Varanasi | Medium | 1786688 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 18:15 | 2026-02-04 21:23 |  |  |  | 0 | As Product owner I would like to validate SG and NACL in AirnavX account so that to ensure that is correctly configured as required and netwrok access is restricted to least privilege, compliant with security standards and traceable to the right owners *Acceptance Criteria*: Ingress Rule: * Validate only required ports are open * Check if the rules are restricted to known source IPs or SGs * Avoid overly permissive rules like ALL Traffic/ All Ports Egress Rule: * Confirm outbound rules are limited to required destinations/services * Avoid all traffic / 0.0.0.0/0 * Remove duplicate or unused rules * Check if multiple rules overlap unnecessarily * Validate SGs have proper tags (name, environment, owner) for traceability * Confirm unused SGs are not attached to ENIs NACL: * Check both inbound and outbound rules match expected traffic flow * validate rule numbers and ensure no conflicts/overlaps * Ensure the implicit DENY is preserved and only necessary allow rules are added * Avoid overly permissive entries * Since NACL are stateless, confirm return traffic rules exist for each allowed inbound connection * Validate that the correct subnets are associated with the right NACL * Avoid leaving critical subnets with the default NACL explicitly required * Confirm VPC flow logs are enabled for subnets tied to NACLs to validate actual traffic patterns against intended rules |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@f3dd427 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hatf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-25 15:29 | [13 empty] | 25/Sep/25 5:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Airnavx Comms has been implemented and the need to configure respective account and initiate testing. Currently team working on server deployment process, once done we will configure rules and will initiate testing. | 06/Oct/25 8:41 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Comms has been implemented, NACL and SG is setup. App owner is able to access and install the application. Hence closing the story | [28 empty] | Done | 2025-10-06 08:41
AM20-615 | EKS Cluster and other services required IAM role | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741147 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-12 14:42 | 2026-01-12 16:18 |  |  |  | 0 |  |  | Aravind Raj | Ravinder Godiyal Godiyal |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:7535df8d-3051-4556-b1c1-6a7195121b35 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1546fba | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cker: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:08 | [13 empty] | 11/Aug/25 10:07 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;Request [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] to update the spill over reason in the main user story being the assignee, i had to go on an emergency leave due to family exigency where we did not get a chance to formulate these details around. | 13/Aug/25 9:30 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;¦NAME¦Description¦ ¦flysaa-backend-dev-eks-deployer¦IAM Role to deploy EKS Cluster via Terraform¦ ¦eks-flysaa-dev-531cab81-argocd-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-aws-alb-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-aws-ebs-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-controlplane-role-34708c3e¦IAM Role for EKS Control Plane dynamically created by system with EKS Cluster creation¦ ¦eks-flysaa-dev-531cab81-ingress-nginx-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-karpenter-profile-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-KarpenterRole¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-sonarqube-role¦Infra Component being used as IRSA for platform workloads¦ ¦eks-flysaa-dev-531cab81-workernode-role¦IAM Role for EKS Data Plane nodes managed by Karpenter¦ ¦eksctl-eks-flysaa-dev-531cab81-addon-iamservi-Role1-Wu60GGlLdLGi¦IAM Roles for EKS Cluster Add-ons¦ ¦eksctl-eks-flysaa-dev-531cab81-addon-iamservi-Role1-Y6EbqpTYxUCn¦IAM Roles for EKS Cluster Add-ons¦ ¦bitbucket-oidc-flysaa-role¦IAM Role for bitbucket replication to S3 bucket for CI/CD¦ ¦flysaa-backend-dev-codebuild-service-role¦IAM Service Role for codebuild projects¦ ¦ekstf-pipeline-codepipeline-role-4e353e4a¦IAM Service Role used by codepipeline which is dynamically created during runtime¦ ¦flysaa-backend-dev-ssminstancerole¦IAM Role to be used by bastion-hosts/jumpbox EC2 MachinesÂ ¦ As Discussed in our DS Call, Here are IAM Role details from Dev Environment, [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] request you to kindly make use of this information and fetch the same from all environments along with the respective permissions incorporated. | 13/Aug/25 10:06 AM;712020:7535df8d-3051-4556-b1c1-6a7195121b35;Moving the subtask for review with [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] | 18/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have received dev env role, need to get the roles from preprod and prod along with policy. | [23 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-21 18:09
AM20-616 | PROS ¦¦ LLD Creation | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sankalp Rai | Medium | 1749504 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 16:28 | 2026-01-27 20:13 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1809d79f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0danv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | Sprint 15 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 06:06 | [13 empty] | 06/Oct/25 8:05 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;LLD document created. | 06/Oct/25 8:07 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;[PROS_Low Level Design Document_v1.0.docx¦https://vodafone.sharepoint.com/:w:/r/sites/SouthAfricaAirlines/Shared%20Documents/Technical%20Documents/SAA%20Design%20documents/LLD%20Documents/Wave%202%20apps/PROS%20LLD/PROS_Low%20Level%20Design%20Document_v1.0.docx?d=w4faebf320e0f4c53aedb5b192660de4f&csf=1&web=1&e=jOZXIo] | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-10-06 08:07
AM20-617 | Rename Citrix account with informatica Prod: Re-establish Informatica ¦¦ Subnet Configuration and Setup platform | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1749511 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 21:28 | 2026-02-03 21:53 |  |  |  | 0 | As Network expert, I would like to provision subnet configuration for PROS application Acceptance criteria: * Subnet configuration completed successfully * Tagging of all network elements associated done succesfully * Traffic flow testing and validation is concluded |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153624.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141700 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153747.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141702 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-154222.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141701 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@e805dba | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dap7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 06:22 | [13 empty] | 12/Aug/25 8:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;We are looking account id rename or new id creation process accordingly i will proceed for next steps. | 19/Aug/25 5:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Citrix Account ID has been renamed with Informatica Prod â€œ536697248966 â€ƒâ€ƒ SAA_Informatica_PRODâ€ | 19/Aug/25 5:42 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet, NACL, RAM ,SG and connectivity has been established. !image-20250819-153624.png¦width=1417,height=750,alt="image-20250819-153624.png"! Connectivity has been tested and working fine. !image-20250819-153747.png¦width=1417,height=750,alt="image-20250819-153747.png"! ¦Informatica Prod-Public¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.0.208/28¦10.40.0.208 - 10.40.0.223¦10.40.0.209 - 10.40.0.222¦14¦/28¦ ¦Informatica Prod-Public(DR)¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.128/28¦10.40.1.128 - 10.40.1.143¦10.40.1.129 - 10.40.1.142¦14¦/28¦Â ¦AZ2¦ !image-20250819-154222.png¦width=1417,height=750,alt="image-20250819-154222.png"! | 19/Aug/25 5:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Assigning for review. | 21/Aug/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed with internet acess. | 25/Aug/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 06:33
AM20-618 | AirNavX ¦¦ Budget Management Configuration | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772224 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 13:05 | 2026-01-11 13:56 |  |  |  | 0 | As AWS expert I would like to configure AirNavX budget management and alerts so that stakeholders gets the frequent notifications on budgets and alerts if the budget crosses threshold Acceptance Criteria: * Budget management for AirNavX is configured successfully * Alerts triggered if the budget crosses 80%, 85% and 90% of Threshold |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [9 empty] | AM20-165 |  |  |  | 18/Sep/25 10:42 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250918-084042.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1155392 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7cf7b049 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq0j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-09 06:42 | [13 empty] | 09/Sep/25 8:42 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created the Budget on management account for Airnavx now will be adding the account and application owner mail idâ€™s in the lambda function. | 09/Sep/25 11:01 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have set the threshold value to 80%, 85% & 90% now will add the account details and application owner mail id in the lambda function. | 15/Sep/25 11:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have added the Account name and application owner email ids in lambda function also tested the budget alerting and we are successfully getting the alerts for budget management. | 18/Sep/25 10:42 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8; !image-20250918-084042.png¦width=860,height=569,alt="image-20250918-084042.png"! Attached is the screenshot as an evidence that we are getting the alert email if the threshold value exceeds more than the utilized budget value. | 18/Sep/25 2:45 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Demo was given to Yashwant today still wants Aravind to review the same. | 22/Sep/25 8:36 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;the threshold of budget should be calculated based on the all the resources involved in the architecture and LLD, though its modifiable, i would suggest to update the value in firsthand itself. | [24 empty] | Done | 2025-09-22 08:50
AM20-619 | Informatica ¦¦ Alerting and Monitoring Solution | Done | 4 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1800159 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-27 16:14 | 2026-01-27 19:46 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment. Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O. * Dashboards are created to monitor key services. * SNS Alert should be generated if Informatica server is stopped. |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 09/Oct/25 9:21 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251009-071913.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1165179 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3ac6b815 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ivor: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 09:08 | [13 empty] | 06/Oct/25 11:07 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start creating the dashboard and alerting for Informatica Dev and Prod environment. | 06/Oct/25 12:13 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I enabled the CloudWatch metrics for Informatica Dev and Prod for CPU, memory, disc, network I/O. Dashboards are also created to monitor key services. --- *DONE.* Now Alerting and monitoring needs to be created with proper naming and threshold values â€“ *PENDING*. | 07/Oct/25 12:19 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Created alarms and monitoring for informatica prod and dev for CPU and Status Check failed â€“ *DONE.* | 08/Oct/25 12:38 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;All alerts including the Disk and memory utilization for Informatica Prod and Dev has been created with proper naming and threshold value. --- *DONE.* | 09/Oct/25 9:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251009-071913.png¦width=1575,height=673,alt="image-20251009-071913.png"! Have created the Informatica prod and dev alerting rules setup the threshold value for them. | 09/Oct/25 10:46 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Moving this US to in review to Aravind. If require any modification. | 13/Oct/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have reviewed has some query will discuss with diksha and close. | 15/Oct/25 11:58 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Aravind reviewed the changes and gave his approval now we can move it to PO approval. | 17/Oct/25 7:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | Done | 2025-10-17 07:17
AM20-620 | SMS Alerting implementation- Opt in/Opt out | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-28 21:33 | 2026-01-28 23:18 |  | 2025-11-15 14:38 |  | 0 | As a cloud product owner I want application and platform alerts to be delivered via SMS from a dedicated long code so that on call engineers and stakeholders receive time critical notifications Acceptance criteria: *Long code configured and verified* - given the approved long code when I set SNS and SMS preferences then the long code is used as the origination identity for the supported countries and unsupported routes use the configured Sender ID feedback *E2E SMS on P1/P2* - Given the cloudWatch alarm changes to ALARM with severity ðŸ˜›1 when the alarm event is routed via EventBridge to the SNS topic than all active on-call receipients for the app+env recieve an SMS within 60s and message body includes app, env, alarm name, severity, runbook link and ACK instruction ¦¦*Severity*¦¦*objective signals*¦¦*examples*¦¦ ¦P1 - Critical, user impact¦harsh outage, data loss, security incdences¦API 5xx>10% 5m in production, RDS storage<5% 10m. certificate expiry < 3days, guard duty, unauthrized access¦ ¦P2 - Degradation,Urgent¦performance, throughput, redundancy lost,¦EKS node group<N healthy, ALB healthy, RDS IOPS deviation, CPU utilization, disk innode,¦ ¦P3 - Action soon¦Capacity/Ops issues, repeated flaps¦log patterns,¦ ¦P4 - Informational¦chnages , warnings, failures without user impact¦Daily back ok, lamda changes, deloyment success¦ *Delivery logging and metrics* - Given SMS messages are sent when carriers return delivery statuses then statuses are captured in CloudWatch logs and S3 and dashboards show sends, successes, failures, per country breakdown *Retry and escalations ( in the event of SMS failure)* - Given a send gets a transient failure when the system retries with backoff( up to 3 times in 5 minutes) then on persistent failure an escalation SMS is triggered to secondary contacts and a ticket is created in ServiceNow with failure details *Deduplication and storm control* - Given multiple identical alarms fire within 5 minutes when routing occurs then recipients receive at most one SMS per unique alarm/signature per 5 minute window and a summary SMS is sent after 15 minutes if >5 deduped alerts occurred. *Opt-out/Opt-in* - Given a recipient replied STOP when routing future SMS to that number then messages are surpassed and audit shows timestamp and actor and START re-enables *Cost Guardrails* - Given a monthly SMS budget when SNS spend reaches 80% then P2 alert is sent to Ops and at 100% sends are rate limited to P1 only until an override flag is set *Cross account publish* - Given alarms originate in child accounts when Event Bridge forwards to central account Then publishing to the central SNS topic succeeds via resources based and IAM roles |  | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Working on exploring the ways to implement cost guardrail for lambda. Exploring enabling cloudwatch metric to track the money spent on SMS sent through the account.;10/Nov/25 8:37 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on understanding how cost is shown in billing in case of SMS sent through SNS or SMS sent using End User Messaging.;11/Nov/25 3:39 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on updating lambda to get cross account cost metric to implement 80% cost guardrail to send notification only in case of P1 and P2 alarms when 80% threshold is breached.;11/Nov/25 3:40 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). Trying the opt-out mechanism for SA number(carrier blocking was cited as one of the issues behind blocking) and parallely raised a request to understand the issue.;13/Nov/25 8:04 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Deployed changes on production cluster.;14/Nov/25 8:18 AM;17cb9418-1850-4923-932b-7098ec51b6bb;14400 |  | 57600 | 0 | 129600 | 2.25 | 57600 | 0 | 129600 | [10 empty] | AM20-176 | [19 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3955b400 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h707: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:34 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Working on implementing cost guardrails to restrict sms sending to only P1 and P2 messages when 80% limit is utilised. | 11/Nov/25 8:25 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Will be testing using cost explorer API to fetch billing cost of SNS during Lambda execution. As per AWS docs, if we are using SNS for sending SMS then the metrics wonâ€™t get reflected on CloudWatch metrics. For opt-in/opt-out as per docs, user can send the STOP message to stop getting message. Need to try this part on our end. | 12/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Updated lambda to fetch amount spent on SMS sent using cost explorer API, currently able to fetch cross account. Working on updating Lambda to avoid duplication using DynamoDB. Testing in progress. | 13/Nov/25 8:02 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Able to fetch cost of sending SMS using API, able to avoid deduplication of alarms with the help of DynamoDB table. Currently Working on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). | 14/Nov/25 8:19 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed changes on production account. | 15/Nov/25 2:38 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-15 14:38
AM20-621 | TM1 ¦¦ Firewall Rule creation | Done | 2 | Sprint 3 | 2025-04-14 | 2025-04-25 | Sankalp Rai | Medium | 1644189 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 16:08 | 2026-01-15 19:19 |  |  |  | 0 | As AWS expert I will be creating firewall rules for TM1 application so that security compliance can be met Acceptance Criteria: * Firewall rules are created and sent to Vodacom implementation |  | Sankalp Rai | [5 empty] | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [5 empty] | ;17/Apr/25 11:05 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b493d0d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-14 07:44 | [13 empty] | 14/Apr/25 9:44 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Call Pending on Firewall placement. Call scheduled for 15th April 2025 Vodacom: Leigh to manage the Firewall and create Rules on Firewall VOIS: Raise request for Firewall Rule in the provided Format | 17/Apr/25 11:06 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;AWS Network Firewall is for monitoring internet traffic coming into AWS and going out of AWS. TM1 does not require any connectivity over internet. Connectivity to TerraData is being done internally Some of the VMs under TerraData right now are being moved to Shared VPC. SAP Rise connectivity is not required. Since TM1 does not require internet connectivity, there is no need to create AWS Network Firewall rules for TM1 Moving to in review for closure | [25 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-21 09:03
AM20-622 | PROS ¦¦ Establish connectivity port opening and firewall connectivity | Done | 3 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1773948 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 12:31 | 2026-01-28 13:59 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2f2b180d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwpv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-12 06:14 | [13 empty] | 12/Sep/25 8:14 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;On 11th the app owner Pieter has confirmed as we can go with single subnet for all 3 servers, Now i have initiated comms preparation. | 19/Sep/25 3:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been sent (16th Sep) and validated by Pieter on on 17th Sep 2025, again send mail to Pieter asking about any additional SITA side flows required or not. | 19/Sep/25 4:12 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Received feedback from Pieter and prepared final comms for SITA/VDC. Sent for LIFT and CSOC submiss towards for implementation. | 19/Sep/25 4:14 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Hence the action with SAA side, hence i am closing this Story. | [26 empty] | Done | 2025-09-22 08:50
AM20-623 | Airnavx ¦¦ Lift Request creation | Done | 1 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | Medium | 1761196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 17:47 | 2026-01-17 17:57 |  |  |  | 0 | As Network expert I have to raise Lift request so that Network Firewall implementation CSOC request for port, routing connectivity can be established with VDC Acceptance criteria: Post Lift request, firewall, port and routing connectivity is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@70851109 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0el9v: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 08:42 | [13 empty] | 05/Sep/25 10:41 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;AirNavX Lift request has been created and completed. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Network team confirmed as routing in place hence no routing required. CSOC and under implementation process from VDC/SITA side. | 08/Sep/25 6:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-09-08 06:34
AM20-624 | PROS ¦¦ Pre-requisite of Network components | Done | 3 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1760705 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 20:13 | 2026-01-09 22:44 |  |  |  | 0 | As AWS expert I would like to create/configuration required network pre-requisite so that later on EC2 instance can be provisioned in PROS account Acceptance criteria: The parent account must share private subnet with PROS account using AWS RAM the sharing also includes route tables The IAM user/role in the child account Security group are created in shared VPC NACL are attached at the subnet level |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [13 empty] | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152123.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153300 | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152137.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153299 | 15/Sep/25 5:22 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250915-152151.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1153301 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3397a03b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ejsb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-28 06:31 | [13 empty] | 28/Aug/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;I am looking final LLD based on that i will created required Subnets against platform ready ness. | 12/Sep/25 8:12 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Pieter, all servers can be migrated under single subnet, and there is no requirement for DB server. I have initiated the Platform readyness. | 15/Sep/25 5:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS application platform/network setup has been completed. ¦PROS¦3¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.192/28¦10.40.1.192 - 10.40.1.207¦10.40.1.193 - 10.40.1.206¦14¦/28¦AZ1¦Â ¦ ¦PROS(DR)¦3¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.224/28¦10.40.1.224 - 10.40.1.239¦10.40.1.225 - 10.40.1.238¦14¦/28¦Â ¦AZ2¦ !image-20250915-152123.png¦width=405,height=211,alt="image-20250915-152123.png"! !image-20250915-152137.png¦width=406,height=166,alt="image-20250915-152137.png"! !image-20250915-152151.png¦width=408,height=117,alt="image-20250915-152151.png"! | 16/Sep/25 4:23 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;validated internet is working with the subnet. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:21
AM20-625 | SMS Alerting implementation- Opt in/Opt out | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-16 13:40 | 2026-01-16 16:49 |  | 2025-11-15 14:38 |  | 0 | As a cloud product owner I want application and platform alerts to be delivered via SMS from a dedicated long code so that on call engineers and stakeholders receive time critical notifications Acceptance criteria: *Long code configured and verified* - given the approved long code when I set SNS and SMS preferences then the long code is used as the origination identity for the supported countries and unsupported routes use the configured Sender ID feedback *E2E SMS on P1/P2* - Given the cloudWatch alarm changes to ALARM with severity ðŸ˜›1 when the alarm event is routed via EventBridge to the SNS topic than all active on-call receipients for the app+env recieve an SMS within 60s and message body includes app, env, alarm name, severity, runbook link and ACK instruction ¦¦*Severity*¦¦*objective signals*¦¦*examples*¦¦ ¦P1 - Critical, user impact¦harsh outage, data loss, security incdences¦API 5xx>10% 5m in production, RDS storage<5% 10m. certificate expiry < 3days, guard duty, unauthrized access¦ ¦P2 - Degradation,Urgent¦performance, throughput, redundancy lost,¦EKS node group<N healthy, ALB healthy, RDS IOPS deviation, CPU utilization, disk innode,¦ ¦P3 - Action soon¦Capacity/Ops issues, repeated flaps¦log patterns,¦ ¦P4 - Informational¦chnages , warnings, failures without user impact¦Daily back ok, lamda changes, deloyment success¦ *Delivery logging and metrics* - Given SMS messages are sent when carriers return delivery statuses then statuses are captured in CloudWatch logs and S3 and dashboards show sends, successes, failures, per country breakdown *Retry and escalations ( in the event of SMS failure)* - Given a send gets a transient failure when the system retries with backoff( up to 3 times in 5 minutes) then on persistent failure an escalation SMS is triggered to secondary contacts and a ticket is created in ServiceNow with failure details *Deduplication and storm control* - Given multiple identical alarms fire within 5 minutes when routing occurs then recipients receive at most one SMS per unique alarm/signature per 5 minute window and a summary SMS is sent after 15 minutes if >5 deduped alerts occurred. *Opt-out/Opt-in* - Given a recipient replied STOP when routing future SMS to that number then messages are surpassed and audit shows timestamp and actor and START re-enables *Cost Guardrails* - Given a monthly SMS budget when SNS spend reaches 80% then P2 alert is sent to Ops and at 100% sends are rate limited to P1 only until an override flag is set *Cross account publish* - Given alarms originate in child accounts when Event Bridge forwards to central account Then publishing to the central SNS topic succeeds via resources based and IAM roles |  | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Working on exploring the ways to implement cost guardrail for lambda. Exploring enabling cloudwatch metric to track the money spent on SMS sent through the account.;10/Nov/25 8:37 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on understanding how cost is shown in billing in case of SMS sent through SNS or SMS sent using End User Messaging.;11/Nov/25 3:39 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on updating lambda to get cross account cost metric to implement 80% cost guardrail to send notification only in case of P1 and P2 alarms when 80% threshold is breached.;11/Nov/25 3:40 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). Trying the opt-out mechanism for SA number(carrier blocking was cited as one of the issues behind blocking) and parallely raised a request to understand the issue.;13/Nov/25 8:04 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Deployed changes on production cluster.;14/Nov/25 8:18 AM;17cb9418-1850-4923-932b-7098ec51b6bb;14400 |  | 57600 | 0 | 129600 | 2.25 | 57600 | 0 | 129600 | [10 empty] | AM20-176 | [19 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3955b400 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h707: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:34 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Working on implementing cost guardrails to restrict sms sending to only P1 and P2 messages when 80% limit is utilised. | 11/Nov/25 8:25 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Will be testing using cost explorer API to fetch billing cost of SNS during Lambda execution. As per AWS docs, if we are using SNS for sending SMS then the metrics wonâ€™t get reflected on CloudWatch metrics. For opt-in/opt-out as per docs, user can send the STOP message to stop getting message. Need to try this part on our end. | 12/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Updated lambda to fetch amount spent on SMS sent using cost explorer API, currently able to fetch cross account. Working on updating Lambda to avoid duplication using DynamoDB. Testing in progress. | 13/Nov/25 8:02 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Able to fetch cost of sending SMS using API, able to avoid deduplication of alarms with the help of DynamoDB table. Currently Working on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). | 14/Nov/25 8:19 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed changes on production account. | 15/Nov/25 2:38 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-15 14:38
AM20-626 | Trellix integration with AirnavX | Done | 1 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 12:29 | 2026-01-15 15:50 |  | 2025-11-12 08:22 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan AirNavX workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in AirNavX server * Trellix is able to access AirnavX account successfully and perform scanning |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 05/Nov/25 3:41 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ Trellix scanning status for New AWS AirNavV servers.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1178115 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f4c84b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 18 | [95 empty] | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [65 empty] | YES | YES | 2025-09-08 07:56 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [12 empty] | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 30/Sep/25 7:40 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working with Sinjun for trellix installation on these 2 servers. | 06/Oct/25 8:39 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Working with Sinjun for Trellix installation, hence will be spilled over | 09/Oct/25 4:29 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Sinjun Albert is going to install Trellix and he will confirm once integration done. | 17/Oct/25 11:17 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over reason - Blocked due to ongoing app installation issues, currently worked upon by app owner; post which this story will be progressed in subsequent sprint | 05/Nov/25 3:41 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Trellix software installed on New AWS AirNavX servers. All AirNavX servers able to discover from Trellix admin server and same has been confirmed by Sinjun. Attaching reference for support. [^RE_ Trellix scanning status for New AWS AirNavV servers.msg] | 12/Nov/25 8:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | Done | 2025-11-12 08:22
AM20-627 | Cynet ¦¦ Server Installation | To Do |  | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1887432 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 14:23 | 2026-01-26 16:38 | 2026-01-07 08:19 |  |  | 0 | As Product owner I want to install Cynet agent on Linux/Windows EC2 instance so that threat detechtion and response coverage is enabled Acceptance Criteria. *Linux*: * Installation package hosted/accessible securely (S3 with KMS, repo, or Cynet direct download). * SSM document / automation executes successfully on a pilot group and then on all in-scope instances. * Agent registers to correct Cynet tenant and shows â€œonline/healthyâ€ in console within defined SLA (e.g., 15 minutes). * Installation is idempotent (re-run does not break existing installation). * Logging captured: instance ID, hostname, timestamp, status, version, and failure reason if any. *Windows*: * Silent install works (msi/exe unattended flags), including token/tenant configuration. * Service is running after installation and agent appears healthy in console. * Windows Event Logs / install logs are retained for troubleshooting. * | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@19d1d99d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0q0i3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2026-01-06 13:12
AM20-628 | Informatica Server ¦¦ LLD preparation | Done | 6 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1610565 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 20:49 | 2026-01-16 20:54 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Sankalp Rai | Yashwant Thakur |  |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;24/Jun/25 1:32 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;11/Aug/25 10:10 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7d2f4e8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a2v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | [104 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-10 14:18 | [13 empty] | 10/Mar/25 4:18 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 10/Mar/25 4:24 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder >> Call to Scheduled on or before 12th* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 20/May/25 10:24 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;1st Draft Complete. Need to review internally revised Start Date: 19th May 2025 End date: 23rd May 2025 | 24/Jun/25 1:32 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Review with customer is completed Awaiting information requested from Application Owner | 11/Aug/25 5:04 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-10-13 09:23
AM20-629 | MQ ¦¦ Application comms metrics preparation and implementation | To Do | 0 | None( Backlog) |  |  | Satya Varanasi | Medium | 1795166 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 21:59 | 2026-01-09 23:01 |  |  |  | 0 | AS Network expertise I want to define, track and baseline and validate network communication metrics including subnets, connectivity with downstream/3rd party applications and network rules so that the applicationcan be migrated to the cloud without connectivity failures, security gaps or performance degradation Acceptance Criteria: Application specific subnets (CIDR range, VPC design, Private/public allocation) documented Overlapping IP ranges validated against downstream and 3rd party integrations subnet utilization % captured E2E connectivity map prepared: application <->DB<->downstream services <->3rd party APIs Latency, Packet loss, throughput baselined from VDC/onprem to cloud traget points DNS resolution | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3842a4ec | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g1 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:35
AM20-630 | Informatica ¦¦ Custom application Metrics | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1761210 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 19:46 | 2026-01-19 21:54 |  |  |  | 0 | # Configure & install cw agent. # Refer email for metrics to be monitored. # Create alerts as per approval in the email. |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@407cb340 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0elc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-17 06:01 | [13 empty] | 17/Sep/25 8:01 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Informatica Accounts (Dev & Prod) cutover is yet to be done. Actual workloads are yet to be migrated. Hence, blocked. | 01/Oct/25 8:24 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Configure & install cw agent - Done # Refer email for metrics to be monitored - Done # Create alerts as per approval in the email - Done | [28 empty] | Done | 2025-10-06 07:58
AM20-631 | AirNavX ¦¦ Port opening, NACL and SG group Whitelisting | Done | 5 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772278 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 15:39 | 2026-02-05 18:29 |  |  |  | 0 | As a cloud infrastructure engineer I want to provision NACL, Security groups and port whitelisting with validated connectivity so that the new application can be securly deployed in AWS with controlled access, compliance to security standards and verified communication paths Acceptance Criteria: * Security groups are created per application tier * required inbound and outbound rules are defined for each tier ( HTTPS: 443 inbound from ALB to web, DB port 3306 from App SG) * no overly permissive rules (0.0.0.0/0) NACL config: * Network ACL applied at subnet level with stateless allow/deny rules for required application port * Both inbound and outbound NACL rules are explicitly documented * Default NACLs are not used Whitelisting: * External IP range for trusted users/ partners are whitelisted * Whitelisting rules are implemented at the SG/NACL level based on environment needs * Documentation include source IPs, purpose and without expiry date Connectivity validations: * E2E connectivity test performed APP--DBflow, External user ---Application endpoint (via ALB/API Gateway) * Connectivity validated using tools like telnet, nc and AWS connectivity tests * Validated evidence captured in the deployment checklist Security and compliance: * All configurations follow least privilege principle * Changes are auditable in CloudTrail with tagging (App, Env, Owner, ChangeID) Deliverable: * SG & NACL rule tables (port, protocol, source/destination) * Whitelist IP registry with owners and validity * Validation test results signed off by infra + security team |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4a97e1ad | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq8r: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-19 14:18 | [13 empty] | 19/Sep/25 4:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared and implemented. with the help of LIFT and CSOC. VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 19/Sep/25 4:19 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Bhavesh we have changed subnet from /27 to /28 and updated comms and shared Sita for implementation. | 19/Sep/25 4:21 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on Albert SITA has been implemented comms via subnet level. according to management i am closing this request and i will working on validation part with new request. | 19/Sep/25 4:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on Albert SITA has been implemented comms via subnet level. according to management i am closing this request and i will working on validation part with new request. | [26 empty] | Done | 2025-09-22 08:50
AM20-632 | Update ServiceNow Payloads with severity | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832856 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 18:57 | 2026-02-02 19:16 | 2025-11-25 08:24 | 2025-11-27 09:16 |  | 0 | As Product owner I would like to send severity to ServiceNow as well in the payload so that alerts can be classified based on Critical, High, Medium, Low and the incident can be generated accordingly. Acceptance Criteria: Lamda function to be updated with Severity SNS should be able to send mandatory parameters along with severity to ServiceNow successfully |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 115200 | 57600 | 72000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ed98b6b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo2j: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-19 10:36 | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 19/Nov/25 12:35 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Discussed with Aravind regarding adding severity to payload and tested execution for infra alarms in dev env. | 24/Nov/25 4:42 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Alarms payloads are now configured with severity field, working on updating list of alarms to be sent to ServiceNow. | 27/Nov/25 9:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:16
AM20-633 | PROS ¦ Cut-Over Instance | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | Medium | 1801097 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-02 12:51 | 2026-02-02 15:37 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [30 empty] | 28/Oct/25 11:51 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251028-095148.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174003 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6de063c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0izhv: | [167 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 11:51 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PROS cutover is carried out successfully, have archived the servers in application migration service. !image-20251028-095148.png¦width=423,alt="image-20251028-095148.png"! | [26 empty] | 1773952 | AM20-170 | PROS ¦¦ Cutover | Done | 2025-10-28 11:52
AM20-634 | POC -AWS Patch Manager ¦¦ Create a patch baseline for installing Windows/RHEL Service Packs | Done | 8 | Sprint 3 | 2025-04-14 | 2025-04-25 | Faisal Sayed | High | 1642024 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 19:40 | 2026-01-26 22:53 |  |  |  | 0 | As AWS architect I would be creating patch baselines for windows Server. Acceptance Criteria: Patch Manager has been created successfully |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Onkar Mirajkar | Sankalp Rai | Yashwant Thakur | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [6 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 23/May/25 8:09 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;Re_ Centralized Multi-Account Patching with AWS System Manger Patch Manger.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1104373 | 09/May/25 12:00 PM;9e4636e8-9dfc-4a33-901b-fcd75015926a;System Patch Manger.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1098376 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@b983d7e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/1 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 1 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00svf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | [108 empty] | 1 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-05 06:16 | [13 empty] | 05/May/25 8:15 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Able to install patches on multi-account ec2 instance using Systems Manager Automation. | 05/May/25 8:16 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working on patch policy | 08/May/25 8:12 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working with Lambda and amazon bridge event to automate the patching process for patch policy to run specific dates | 08/May/25 3:29 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Created lambda function and event bridge to automate patch multi-account setup | 09/May/25 8:01 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Need to update document | 09/May/25 12:02 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Document attached in the Jira sent for review to Arvind | 12/May/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Document is reviewed, automation with lambda is captured. | 18/May/25 2:37 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Since the desired solution objective could not be achieved, rejecting this ticket to in progress. As agreed, onkar needs to rework based on agreement. Solution provided by Aravind needs to be developed as POC. as communicated and mentioned by Yashwant. Rejecting on behalf of Yashwant as he has login issues in Jira | 20/May/25 1:24 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Spoke to Venkat on the issue we are facing with centralized patch management and the limitation to use it in multi-account setup in AWS. Quick Setup as work around for Multi-Account Setup, however this service is not available in CapeTown (SA) region. Venkat has agreed to raise this with AWS. As next Step: # compose email stating the solution we are trying to achieve for patching, the limitations we have come across and all the solution we have and what limitations these solutions have. # Venkat will forward this AWS and work on setting up a call to discuss this issue. # Align with AWS on best possible solution/workaround to achieve the desired state | 21/May/25 10:34 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Email has been sent to Venkat, stating what we are trying to achieve, Limitations identified and workarounds tried.Â | 09/Jun/25 8:22 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;As per call, We have tried to download the packages from server which is having Internet connectivity and tried to update on Private Ec2 instances which is working successfully | 13/Jun/25 12:55 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Centralized EC2 Patch Management (Cross-Account)*{{ â€” AchievedÂ }} Â {{Â }}*Key Outcomes*{{:Â }} # Â *Central Patch Repository in Shared Services Account*{{Â }} * Â {{Created `saa-central-patch-bucket` in }}*af-south-1*{{, configured securely.Â }} * {{Uploaded Linux `.rpm` and Windows `.msu` patches to S3 manually & via scripts.Â }} Â # *SSM-Compatible EC2 Instances in Target Accounts*{{Â }} Â {{Launched both Linux & Windows instances without public IPs.Â }} {{Attached custom IAM roles that:Â }} * Â {{Allow full SSM and `s3:GetObject` access to central bucket.Â }} * {{Assume trust with `ec2.amazonaws.com`.Â }} Â # *Patch Acquisition*{{Â }} * Â {{Downloaded Linux patches using SSM Run Command (manual S3 sync).Â }} * {{Downloaded Windows patches (KB5058392) using RDP, installed AWS CLI manually, then uploaded to S3.Â }} Â # *AWS CLI Installed on Windows EC2 (No Internet)*{{Â }} * Â {{Used temporary public IP â†’ installed AWS CLI â†’ removed IP.Â }} Â # *Tested SSM Agent Connectivity*{{Â }} Â {{Verified instances registered to SSM without public IP using:Â }} * Â {{ VPC endpoints (`ssm`, `ssmmessages`, `ec2messages`, `s3`)Â }} * {{ IAM and SGs allowing HTTPS (`tcp/443`)Â }} Â # *Enabled Patch Deployment via SSM Run Command*{{Â }} Â {{Used SSM to:Â }} * Â {{Copy patches from EC2 to central S3Â }} * {{Test patch install commands (`wusa` for `.msu`, `yum` for `.rpm`)}} | 13/Jun/25 2:35 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [14 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:35
AM20-635 | Informatica Server ¦¦ Security compliance implementation | Done | 3 | Sprint 7 | 2025-06-09 | 2025-06-20 | Aravind Raj | Medium | 1681739 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 15:18 | 2026-01-31 18:05 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of PROS account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;10/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;10/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 43200 | 0 | 57600 | 1.33 | 43200 | 0 | 57600 | [12 empty] | 10/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250610-061229.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1112272 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2572cbfb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05tqj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-06 06:15 | [13 empty] | 06/Jun/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will be start working on enabling the frameworks, followed by that will work controls implementation and remediation | 09/Jun/25 7:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CIS NIST and AWS FSBP security frameworks are enabled, in parallel controls were implemented and have completed remediation. Awaiting for the security score to update in security hub, | 10/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Updated security hub for the different controls; !image-20250610-061229.png¦width=1279,height=587,alt="image-20250610-061229.png"! | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-10 08:12
AM20-636 | AirNavX Account ¦¦ Security Compliance Implementation | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672716 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-18 17:25 | 2026-01-18 18:33 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of AirNavX account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250528-092239.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1106065 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@33a69e54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04ft7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-28 09:24 | [13 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Account - 345594574792 Controls were implemented and security score is updated is for all the three security standard frameworks- CIS, NIST and AWS FSBP !image-20250528-092239.png¦width=1279,height=589,alt="image-20250528-092239.png"! | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-28 11:24
AM20-637 | flysaa Backend - Application alerting | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820107 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 17:51 | 2026-01-11 18:20 |  | 2025-11-14 11:07 |  | 0 | As devops expert I would like to configure application error from workloads running on our EKS cluster to be collected, classified and alerted via cloudwatch so that appropriate alert is passed to Servicenow via SNS/lamda function or Event bridge. Acceptance Criteria: * All the application specific errors are captured for alerting successfully * The alerts are being sent to ServiceNow with agreed format |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Deployed error Alarms to backend production account for fabric and amadeus.;14/Nov/25 8:17 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fd7ba2e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07d | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:39 | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Had a Discussion with Yashwant, will be reaching out to Hoosen for creating a request to deploy alarms to production. | 11/Nov/25 8:26 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Hoosen has created a change request for deploying the alarms, will be working on it when we get the timeslot allocated to deploy in production since we are not deploying alarms on backend dev and preprod. | 14/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed alarms on Production EKS Cluster. | 14/Nov/25 11:07 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-14 11:07
AM20-638 | Security and compliance implementation on PROS account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622524 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 19:15 | 2026-01-15 19:43 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on PROS account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in PROS DEV account * NIST policy implementation successfully done in PROS DEV account * AWSFSBP policy implementation successfully done in PROS DEV account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Mar/25 2:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [8 empty] | AM20-19 | AM20-17 |  |  | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250317-060821.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1079558 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a53b25a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxson: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-13 06:02 | [13 empty] | 13/Mar/25 8:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on the controls with the dependency services for the security frameworks. | 14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;The controls were implemented in Pros DEV account, Pros Production account will be picked up in separate user story. | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250317-060821.png¦width=1277,height=642,alt="image-20250317-060821.png"! | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-14 14:22
AM20-639 | Ec2 Cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818694 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-05 14:23 | 2026-02-05 14:39 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4bebd3dc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzvn: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 2:28 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Sanjot has cleaned up 2 ec2 instance from backend dev. | [26 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-10-28 14:27
AM20-640 | Billing and other solution required roles | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741166 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-24 16:10 | 2026-01-24 16:32 |  |  |  | 0 |  |  | Aravind Raj | Onkar Mirajkar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | [29 empty] | 06/Aug/25 10:30 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;IAM Role Documention.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136095 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f932959 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckgr: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 08:31 | [13 empty] | 06/Aug/25 10:30 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;[^IAM Role Documention.docx] Please Review and Verify | [26 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-11 09:19
AM20-641 | Informatica Server - Dev ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1749537 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 21:17 | 2026-02-03 21:36 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 57600 |  | 0 | 86400 | 57600 | [9 empty] | AM20-145 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b90196e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0datf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 14:28 | [13 empty] | 18/Aug/25 4:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev MGN template has been configured, now we are looking AWS migration agent installation on server for sync, Sinjun going to take care tomorrow for the same i have scheduled the call. | 19/Aug/25 5:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;While checking AWS agent connectivity not working, checking with network team for further troubleshooting/fixing the issue. CSOC request has-been createdâ€CINC0909706â€ | 25/Aug/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network routing not implemented, currently it under approval process. | 26/Aug/25 1:11 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Firewall rules implemented. # Configured MGN agent setup on AWS for dev server migration. # Identified as connectivity not working. # Initiated network troubleshooting call towards fixing. # Identified as routing not configured. # Requested LIFT for approval # LIFT approval took 3days # Monday CSOC request raised and routing has ben implemented. # Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 29/Aug/25 8:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev agent installation and Test instance setup has been complted. | 01/Sep/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The test instance connectivity has been completed. Communicated to Peter for connectivity testing. The ip address is: 10.42.0.46. Sending this request for closing. | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-642 | Implement JSON Message Parsing in AWS sandbox ActiveMQ POC | Done | 4 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811820 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 14:18 | 2026-01-24 17:50 |  | 2025-10-31 17:25 |  | 0 | As part of validating AWS ActiveMQ integration with a Spring Boot application, we will deploy Producerâ€“Consumer.java files to conduct POC to include JSON message parsing capability. The Producer will publish structured JSON messages to ActiveMQ queue, and Consumer will parse and process the JSON payload. This will help validate end-to-end message exchange, parsing logic, and overall integration readiness in AWS sandbox environment. *Acceptance Criteria* * Deploy ActiveMQ in AWS Sandbox environment. * ActiveMQ broker is accessible from Spring Boot application in EC2 windows of AWS sandbox. * Producer publishes a sample JSON message to ActiveMQ queue. * Consumer retrieves the message and successfully parses the JSON payload using a standard parser (e.g., Jackson). * Parsed data fields are printed for verification. * Message transmission and parsing flow verified end-to-end without errors. |  | Sanjot Fotedar | Sumit Nikam | Yashwant Thakur |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;24/Oct/25 10:15 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 57600 | 28800 | 28800 | [12 empty] | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124615.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174186 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124631.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174189 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124648.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174188 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124656.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174187 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5c659eaf | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k74r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-23 13:51 | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 23/Oct/25 3:51 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Following steps are completed: * We have deployed ActiveMQ in AWS sandbox account. * Deploy EC2 windows server manually in same sandbox account align under same network with MQ server. * Tested successfully MQ server connectivity from EC2 windows server. * Installed JDK-17 version , maven to support java spring boot applications. * Developed and deployed java application with pom.xml | 28/Oct/25 2:50 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;* Developed [Producer.java¦http://Producer.java] to publish JSON messages to AWS ActiveMQ queue. * Developed [ConsumerTest.java¦http://Consumer.java] to consume and parse JSON messages. * Verified successful message send/receive flow over SSL connection. * Validated JSON parsing using Jackson and confirmed expected output. * Resolved encoding and dependency issues during build. * End-to-end functionality tested in AWS sandbox account. * MQ server Dashboard shows expected outcome. !image-20251028-124615.png¦width=443,alt="image-20251028-124615.png"! !image-20251028-124631.png¦width=443,alt="image-20251028-124631.png"! !image-20251028-124648.png¦width=443,alt="image-20251028-124648.png"! !image-20251028-124656.png¦width=443,alt="image-20251028-124656.png"! | 31/Oct/25 12:31 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;We have reviewed implementation in sandbox and could see working messaging flow from provider to the consumer via AmazonMQ running with ActiveMQ broker. Next step is to modify the config and test config based on feedback from Amadeus. | 31/Oct/25 5:25 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-10-31 17:25
AM20-643 | POC for ServiceNow Integration with TM1 servers for error/ reporting | Done | 2 | Sprint 8 | 2025-06-23 | 2025-07-04 | Aravind Raj | High | 1685590 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 14:45 | 2026-02-02 15:16 |  |  |  | 0 | As AWS expert, I should be able to integrate ServiceNow API with TM1 server so that in case of any error/issues, alerts can be generated and transformed into tickets in ServiceNow. Acceptance Criteria: Tickets are generate in ServiceNow against Alerts that are getting generated for TM1 server events successfully |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6de32f87 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i06g9v: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-20 05:58 | [13 empty] | 20/Jun/25 7:57 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Yesterday have configured SNS topic with the new subscription which has endpoint of HTTPs protocol, have verified a service now dashboard where we were getting the alert as expected. | [26 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-20 08:56
AM20-644 | ServiceNow ¦¦ CloudWatch Rule for Error detection | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650995 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 21:44 | 2026-01-28 23:00 |  |  |  | 0 | As a AWS engineer, I want to create CloudWatch alarms to send error-level logs to be notified of infrastructure issues Acceptance criteria: * CloudWatch metric filters to be configured to match specific error patterns or log levels |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fabfe65 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0280b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 06:03 | [13 empty] | 29/Apr/25 8:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will review utkarsh terraform script and will assign this story to him. | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed. | 07/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;We can use utkarsh terraform script for cloud watch alarm creation, but sns topic cant be modified so we need manual update to SNS access policy. | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:39 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [22 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:39
AM20-645 | flysaa Backend - Application alerting | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820107 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 12:26 | 2026-02-05 13:30 |  | 2025-11-14 11:07 |  | 0 | As devops expert I would like to configure application error from workloads running on our EKS cluster to be collected, classified and alerted via cloudwatch so that appropriate alert is passed to Servicenow via SNS/lamda function or Event bridge. Acceptance Criteria: * All the application specific errors are captured for alerting successfully * The alerts are being sent to ServiceNow with agreed format |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Deployed error Alarms to backend production account for fabric and amadeus.;14/Nov/25 8:17 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fd7ba2e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07d | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:39 | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Had a Discussion with Yashwant, will be reaching out to Hoosen for creating a request to deploy alarms to production. | 11/Nov/25 8:26 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Hoosen has created a change request for deploying the alarms, will be working on it when we get the timeslot allocated to deploy in production since we are not deploying alarms on backend dev and preprod. | 14/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed alarms on Production EKS Cluster. | 14/Nov/25 11:07 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-14 11:07
AM20-646 | CMS Backend RDS instance (Pre-prod/Prod) analysis | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1833687 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 13:55 | 2026-01-25 16:53 |  | 2025-11-27 09:21 |  | 0 | As Product owner I like to analyse RDS for rightsizing based on utlization to reduce cost |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Nov/25 5:10 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;21600 | ;25/Nov/25 4:08 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;64800 |  |  |  |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 18/Nov/25 5:09 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251118-150648.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1185982 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6460780 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo2n: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 15:10 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 5:09 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;RDS cost analysis is started. Today, we have reduced backup retention period of preprod rds to 7 days from 35 days. Also, storage limit threshold for dev rds is updated to 200 GiB from 110GiB because it was generating alerts â€œ*_Storage size 100 GiB is approaching the maximum storage threshold 110 GiB. Increase the maximum storage threshold_*â€ !image-20251118-150648.png¦width=459,alt="image-20251118-150648.png"! Next we will monitor cpu, memory consumption across three environments | 25/Nov/25 4:15 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;h3. Next Steps for CMS Backend RDS Cost Optimization With discussion with Pankaj, we have identified the following points as next steps for CMS Backend RDS cost optimization: * Turn off non-prod RDS instances when not in use or during off-business hours and turn them back on when required. * Further reduce backup retention period for non-prod RDS instances (currently 7 days) to explore additional cost savings. These actions will be implemented post confirmation from FlySAA team. | 27/Nov/25 9:21 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:21
AM20-647 | Adding Lambda for generating sonar scan reports | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Shreyash Talwekar | Medium | 1799079 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2026-01-10 17:45 | 2026-01-10 21:26 |  |  |  | 0 | Adding terraform code to create Lambda and API Gateway for generating sonar scan reports. |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@62438a0e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ir8b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 03/Oct/25 10:45 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Added lambda module and api gateway module and updated the api gateway url in sonar server webhook. | [26 empty] | 1786761 | AM20-182 | Push to FlySAA backend Alarm related code to the bitbucket in dev and preprod environment | Done | 2025-10-03 10:44
AM20-648 | CSA assessment | Done | 8 | Sprint 2 | 2025-03-31 | 2025-04-11 | Sumit Nikam | Medium | 1627466 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 21:35 | 2026-01-10 00:04 |  |  |  | 0 | As application architect I would assess current CSA application architecture, functional complexity, ease of migration, current and future scalability requirements, dependencies between different components and data consistency across services. Acceptance Criteria: Document consisting of current and to-be architecture, proposed microservices,, dependencies and data consistency approach is successfully completed |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;02/Apr/25 6:36 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 |  |  | 115200 | 21600 | 93600 | 0.81 | 115200 | 21600 | 93600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@11a4dc28 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 4 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxso7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-26 06:12 | [13 empty] | 26/Mar/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;High level plan for CSA Modernization has been prepared, reviewed internally and shared with Vodacom. Next step is to prepare for SOW document. | 01/Apr/25 7:11 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Working along with Yashwant for SOW document preparation and review | 02/Apr/25 6:36 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Reviewing functional details shared by Sampi | 04/Apr/25 3:26 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Follow-up discussion completed with Sampi. | 04/Apr/25 8:08 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. SOW completed | [22 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-04-04 20:08
AM20-649 | Informatica Server account (Formerly PROS) ¦¦ Security compliance Implementation | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | High | 1660212 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-24 14:44 | 2026-01-24 16:21 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of PROS account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;13/May/25 7:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;13/May/25 7:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 13/May/25 7:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250513-054135.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1099412 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1dbe4a84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a3f: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-09 06:12 | [13 empty] | 09/May/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on the CIS, NIST and AWS FSBP controls enablement followed by remediation. | 13/May/25 7:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Pros Production account controls were implemented and score got updated successfully. !image-20250513-054135.png¦width=1272,height=587,alt="image-20250513-054135.png"! | 13/May/25 7:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Dev account of PROS yet to implemented. | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-13 07:42
AM20-650 | ServiceNow ¦¦ Lamda function as SNS Subscriber | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651014 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 20:56 | 2026-01-20 21:53 |  |  |  | 0 | As a Cloud engineer, I want a Lamda function subscribed to the SNS topic so that it can process alerts and forward them to ServiceNow Acceptance Criteria: * The Lamda function is triggered on new SNS messages * It parses event data and sends an HTTP POST request to ServiceNow |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 | ;25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@353710af | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0284j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 03:49 | [13 empty] | 24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Working with the lambda function python script, since the function needs to works with cross account for getting the tags. initially the lambda function developed to get the tags from the same account, whereas here the requirement is to get the tag to Audit account to trigger a SNS. | 25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function is created in Audit account -300204747992, and its working fine as expected. | 02/May/25 4:57 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-25 06:34
AM20-651 | Servicenow Payload severity updates for Lambda alarms | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Shreyash Talwekar | Medium | 1835024 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-13 16:44 | 2026-01-13 16:56 |  |  |  | 0 | Enhance the existing Lambda function that triggers when Lambda alarms enter an alarm state. Currently, the function gathers alarm-related metrics, collects function details, and sends an approved payload to ServiceNow. However, severity information from the alarm is not included in the payload. This story addresses that gap by updating the Lambda function to capture and transmit the correct severity level from the alarm to ServiceNow. *Acceptance Criteria:* * Lambda function must include severity details from the alarm in the payload. * Payload sent to ServiceNow should accurately reflect the alarm severity. |  | Faisal Sayed | Harsh Chandra | Shreyash Talwekar |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  | ;20/Nov/25 8:33 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;14400 | [6 empty] | 0 | 14400 |  |  | 0 | 14400 | [12 empty] | 21/Nov/25 7:04 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251121-050425.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187511 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@560f4ab3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxar: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 05:33 | [13 empty] | 20/Nov/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Requirements have been gathered. Lambda function code will be reconfigured to incorporate changes, followed by payload testing. Ticket will be updated upon successful completion of testing. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Lambda function has been updated per requirements to capture severity. A test event was executed to validate behavior and output; results are attached. Test outcome is successful, and the implementation is complete. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251121-050425.png¦width=555,alt="image-20251121-050425.png"! | 24/Nov/25 8:42 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reviewed output, LGTM. | [23 empty] | 1832856 | AM20-264 | Update ServiceNow Payloads with severity | Done | 2025-11-24 08:41
AM20-652 | MQ¦¦ Migration Agent comms Metrics implementation | Blocked | 2 | Sprint 16 | 2025-10-13 | 2025-10-24 | Satya Varanasi | Medium | 1794120 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 12:35 | 2026-01-13 13:58 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@692cf397 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g9 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-17 09:19 | [13 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | [29 empty] | To Do | 2025-09-30 10:14
AM20-653 | Nexio AV¦¦ Migration tool installation / New Set-up | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620531 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 16:46 | 2026-02-04 17:17 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the Nexio AV SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [6 empty] | AM20-13 | AM20-15 | [5 empty] | 05/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;NexioAV-Replacement.pdf;https://vodacom.atlassian.net/rest/api/3/attachment/content/1110196 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ac52572 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:u | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:25 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked due to [https://vodacom.atlassian.net/browse/AM20-15¦https://vodacom.atlassian.net/browse/AM20-15¦smart-link] network story, upon completion will pick this up. | 21/Mar/25 12:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AirnavX migration discussion is still on-going, post that network setup will be created along with connectivity. After the connectivity established, will be able to pick this migration agent toll installation for AitnavX. | 02/May/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for Network setup with internet access to be in place with all required route entry. | 16/May/25 8:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting on network matrix implementation and confirmation. waiting for centralized subnet on transit gateway creation and confirmation from [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 04/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Story to be dropped, migration is not applicable for this application whereas fresh installation is planned with a new EC2 instance. | 05/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;[^NexioAV-Replacement.pdf] | 05/Jun/25 8:32 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Requirement is changed as part of attached email, hence closing this one. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-05 08:31
AM20-654 | Nexio AV ¦¦ Firewall Rule creation | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Satya Varanasi | Medium | 1650869 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 15:17 | 2026-01-31 18:15 |  |  |  | 0 | As AWS expert I will be creating firewall rules for Nexio AV application so that security compliance can be met Acceptance Criteria: * Firewall rules are created and sent to Vodacom implementation |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@76b1f9b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:y | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:45 | [13 empty] | 29/Apr/25 7:44 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;FW rules will be implemented after comms implementation. This may need to move next sprint. | 20/May/25 5:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This Story dependency with comms implementation, the same with SAA team. Once SAA team actioned this story will be handled and closed until that this will not possible to address.(Note: it may move next sprint also) | 10/Jun/25 2:09 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;No longer needed based on recent conversation. * Based on request from Sinjun, the migration approach for Trellix/NexioAV has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-10 14:09
AM20-655 | CMS Frontend SMS PROD implementation | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865997 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 12:38 | 2026-01-17 13:32 | 2025-12-14 17:52 | 2025-12-12 14:50 |  | 0 | As a cloud platform application owner I want to perform a detailed assessment for enable SMS notification in the CMS frontend application hosted in AWS Acceptance Criteria Dedicated SNS topic created successfully for CMS frontend specific Subscribe long code to SNS topic successfully Complete Configuration of CloudWatch alarms for application error through custom metrics CloudWatch Alarms are created successfully AWS Lamda function is created with all the required error details in compliant with ServiceNow format including Severity Validation of Setup is completed successfully post implementation |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Worked on understanding the alarm list and discussing their priorities.;03/Dec/25 12:11 PM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on adding support for sms notification for critical alerts like ALB getting 400, 500 errors;09/Dec/25 8:00 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Re-deployed sms notification infrastructure on preprod env to mimic instance down scenario.;09/Dec/25 8:01 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on testing number of liferay instances running metric and updating lambda to make sure sms notification indicates which node is not working.;09/Dec/25 8:02 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on replicating logic for similar alarms.;09/Dec/25 8:04 AM;17cb9418-1850-4923-932b-7098ec51b6bb;14400 |  | 115200 | 7200 | 108000 | 0.93 | 115200 | 7200 | 108000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4211dfc7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7x7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-03 10:14 | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 03/Dec/25 12:13 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Discussed with Hoosen regarding the list of alarms to enable SMS notification for and priorities to be assigned to them. Started working on configuring P1 alerts. | 09/Dec/25 8:08 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Status till now: # Worked on configuring sms notifications for critical alerts like ALB, number of liferay running and CPU utilization of instances ,RDS , alarms for metrics like procstat_num_fds, procstat_num_threads. # Replicated sms implementation on saa frontend preprod to test alarms involving stopping instances, alarms are sending correct info regarding which instances are down. # Working on adding sms support for metrics like homepage availability, fabric availability etc. | 10/Dec/25 8:19 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created and tested few alarms for monitoring metric like HomePage availability , Fabric Availability etc in prod. | 12/Dec/25 2:31 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created and Tested alarms in Prod and Preprod. | 12/Dec/25 2:50 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-12-12 14:50
AM20-656 | Airnavx ¦¦ establish internet connectivity via NAT Gateway and TGW | In Review | 0 | Sprint 1 | 2025-03-17 | 2025-03-28 | Sankalp Rai | High | 1620884 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 15:13 | 2026-01-17 18:36 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-10 | AM20-16 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@13dfa190 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akp: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-21 07:32 | [13 empty] | 21/Apr/25 9:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Please review | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | In Progress | 2025-04-08 08:20
AM20-657 | Convert Alarms description into simple user understandable format | Done | 4 | Sprint 21 | 2025-12-22 | 2026-01-02 | Yashwant Thakur | Medium | 1881266 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 17:46 | 2026-01-11 20:01 | 2026-01-04 09:12 | 2026-01-02 11:04 |  | 0 | As Product owner I like to convert alarm description into simple understandable language so that user or resolver group are able to understand what is causing the error for flysaa backend , Front end and airnavx. Acceptance Criteria: alarm description send to Service Now via SNS and Lamda function must be user understable and successfully cascaded to ServiceNow using API. |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;02/Jan/26 9:49 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 72000 | 28800 | 43200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@18246054 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pcib: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2026-01-02 07:49 | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Jan/26 9:48 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Description was added for infrastructure , Lambda function and Flysaa Frontend account alerts. Example payload of frontend account alert: {"Name": "FlySaaCms_ALB_HTTPCode_Target_4XX_Count","IP Address": "NA","Fully Qualified Domain Name": "[api.flysaa.com¦http://api.flysaa.com]","Company": "VFSA","Hostname": "app/FlySaaCmsWebALB/968b1f7492941705","Department": "App DevOps Team","Operating System": "Amazon Linux","DNS Domain": "[api-frontdev-flysaa.com¦http://api-frontdev-flysaa.com]","Disk Space (GB)": "NA","RAM (MB)": "NA","CPU Count": "2","CPU core count": "2","Alarm Time": "2026-01-01 19:42:30 UTC","Account ID": "261365109009","Environment": "prod","Cluster Name": "NA","MetricName": "HTTPCode_Target_4XX_Count","Current State": "ALARM","Reason": "Threshold Crossed: 3 out of the last 3 datapoints [6534.0 (01/01/26 19:35:00), 6206.0 (01/01/26 19:30:00), 3164.0 (01/01/26 19:25:00)] were greater than or equal to the threshold (3000.0) (minimum 3 datapoints for OK -> ALARM transition).","Severity": "Warning","Description": "Error Count for http request exceeded threshold for metric: HTTPCode_Target_4XX_Count ,Loadbalancer affected: app/FlySaaCmsWebALB/968b1f7492941705"} | 02/Jan/26 11:04 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2026-01-02 11:04
AM20-658 | Security and compliance implementation on PEGASYS account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622536 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 17:44 | 2026-01-27 19:21 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on Pegasys account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in TM1, Teammate account * NIST policy implementation successfully done in TM1, Teammate account * AWSFSBP policy implementation successfully done in TM1, Teammate account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [10 empty] | AM20-18 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@792d09b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxstj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-21 10:14 | [13 empty] | 21/Mar/25 12:14 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Marking as Done, as pegasys account migration still on discussion. | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-21 12:14
AM20-659 | MQ¦¦ Migration Agent comms Metrics implementation | Blocked | 2 | Sprint 16 | 2025-10-13 | 2025-10-24 | Satya Varanasi | Medium | 1794120 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 17:54 | 2026-01-24 21:10 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@692cf397 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g9 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-17 09:19 | [13 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | [29 empty] | To Do | 2025-09-30 10:14
AM20-660 | Transit Gateway setup for Dev environment | Done | 6 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1702418 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 21:35 | 2026-01-25 00:31 |  |  |  | 0 | As Network Expert, I would be able to setup Transit network gateway for Dev environment Acceptance Criteria: Transit Gateway is provisioned successfully in Dev environment. |  | Aravind Raj | Satya Varanasi |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [13 empty] | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132834.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121470 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132924.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121472 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133228.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121473 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133337.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121469 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133439.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121471 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67c2563b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i095nv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-01 16:49 | [13 empty] | 01/Jul/25 6:49 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;There is no Preprod env for 20+ app migration list, hence we are not setting up Preprod TG attachment, in case needed near future we will setup according to requirement. In this sprint we will setup TG attach for Dev env. | 03/Jul/25 3:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Common TG Attach has be setup on shared VPC dev Account and tested internet connectivity via informatica DEV subnet. !image-20250703-132834.png¦width=1306,height=662,alt="image-20250703-132834.png"! !image-20250703-132924.png¦width=1204,height=668,alt="image-20250703-132924.png"! TG-Attach subnets: !image-20250703-133228.png¦width=1243,height=475,alt="image-20250703-133228.png"! TG attachment details. !image-20250703-133337.png¦width=1189,height=448,alt="image-20250703-133337.png"! Subnet associations !image-20250703-133439.png¦width=1215,height=611,alt="image-20250703-133439.png"! | 04/Jul/25 12:05 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed, test server is working with internet. | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-04 12:05
AM20-661 | Nexio AV ¦¦ establish internet connectivity via TGW | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650868 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 19:24 | 2026-01-11 22:29 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Harsh Chandra | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  | ;02/May/25 12:35 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;14400 | [5 empty] | 14400 | 0 | 14400 | 1 | 14400 | 0 | 14400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1e57c316 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:x | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:43 | [13 empty] | 29/Apr/25 7:43 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;internet connectivity has ben setup, sending for review | 02/May/25 12:37 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Tested through SSM {quote}Ping to 8.8.8.8 working Tracert to 8.8.8.8 working{quote} Forwarding for PO Approval | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:38
AM20-662 | Airnavx ¦¦ establish internet connectivity via NAT Gateway and TGW | In Review | 0 | Sprint 1 | 2025-03-17 | 2025-03-28 | Sankalp Rai | High | 1620884 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 14:00 | 2026-01-28 14:28 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-10 | AM20-16 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@13dfa190 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akp: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-21 07:32 | [13 empty] | 21/Apr/25 9:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Please review | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | In Progress | 2025-04-08 08:20
AM20-663 | PROS ¦¦ LLD Creation | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sankalp Rai | Medium | 1749504 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 22:06 | 2026-02-01 23:10 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1809d79f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0danv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | Sprint 15 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 06:06 | [13 empty] | 06/Oct/25 8:05 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;LLD document created. | 06/Oct/25 8:07 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;[PROS_Low Level Design Document_v1.0.docx¦https://vodafone.sharepoint.com/:w:/r/sites/SouthAfricaAirlines/Shared%20Documents/Technical%20Documents/SAA%20Design%20documents/LLD%20Documents/Wave%202%20apps/PROS%20LLD/PROS_Low%20Level%20Design%20Document_v1.0.docx?d=w4faebf320e0f4c53aedb5b192660de4f&csf=1&web=1&e=jOZXIo] | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-10-06 08:07
AM20-664 | MQ ¦¦ Application comms metrics preparation and implementation | To Do | 0 | None( Backlog) |  |  | Satya Varanasi | Medium | 1795166 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 17:43 | 2026-01-30 19:49 |  |  |  | 0 | AS Network expertise I want to define, track and baseline and validate network communication metrics including subnets, connectivity with downstream/3rd party applications and network rules so that the applicationcan be migrated to the cloud without connectivity failures, security gaps or performance degradation Acceptance Criteria: Application specific subnets (CIDR range, VPC design, Private/public allocation) documented Overlapping IP ranges validated against downstream and 3rd party integrations subnet utilization % captured E2E connectivity map prepared: application <->DB<->downstream services <->3rd party APIs Latency, Packet loss, throughput baselined from VDC/onprem to cloud traget points DNS resolution | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3842a4ec | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g1 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:35
AM20-665 | AWS Infra Readiness for Migration | To Do |  | None( Epic) |  |  |  | High | 1620376 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 16:21 | 2026-02-01 18:36 |  |  |  | 0 | AWS Platform for all 20+ application must be ready which includes provisioning of AWS workloads in respective application account, Security & Industry standard compliance implementation, connectivity, RBAC and resource tagging in place | [23 empty] | 3398400 | 2736000 | 748920 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6680bbd | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-13 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | dark_green | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxn7b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-03-04 11:47
AM20-666 | Front End (SMS notification)- Business Level Improvements | To Do | 4 | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1885790 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 17:59 | 2026-01-09 20:31 | 2026-01-06 08:25 |  |  | 0 | As Product Owner I would like to take business input and configure the SMS accordingly so that informative SMS notification reached out to operation and support group. *Acceptance Criteria*: * SMS notification configured successfully as Business input |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@55581f2c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptv7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-08 09:34 | [13 empty] | 08/Jan/26 11:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reached out to Hoosen and Javier to enquire their availability for resuming the discussions, awaiting their response. | [29 empty] | To Do | 2025-12-30 08:45
AM20-667 | SSM Documents and cloudtrail - pipeline cleanup | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Aravind Raj | Medium | 1869416 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-01 18:41 | 2026-02-01 19:31 | 2025-12-11 08:16 |  |  | 0 |  |  | Aravind Raj | Faisal Sayed |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb |  |  |  |  | ;11/Dec/25 5:41 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [6 empty] | 0 | 28800 |  |  | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@148fb93 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obs3: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-11 14:59 | [13 empty] | 11/Dec/25 4:58 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;---- h3. *Account: Backend-Prod* *Control:* {{SSM.7 â€“ SSM documents should have the block public sharing setting enabled}} *Status:* *Remediated* *Action Taken:* * Disabled public access for all Systems Manager (SSM) documents to enforce the *Block Public Sharing* setting. ---- h3. *Account: Backend-PreProd* *Control:* {{CloudTrail.2 â€“ CloudTrail should have encryption at rest enabled}} *Status:* *Suppressed* *Justification:* The presence of {{"Values": []}} (empty array) in the event selector configuration is conclusive evidence of the following sequence: # *Pipeline Creation:* An AWS CodePipeline with an S3 source was initially created. This action automatically provisioned a dedicated CloudTrail trail to capture S3 object-level events for event-driven triggers. # *Pipeline Deletion:* The pipeline was subsequently deleted. # *Orphaned Resources:* During deletion, the pipeline removed the S3 bucket ARN from the CloudTrail event selectors, resulting in an empty {{Values}} array. However, the CloudTrail trail itself and its placeholder bucket were not removed, leaving orphaned resources in the account. # *EventBridge Rules Cleanup:* The absence of EventBridge rules ({{aws events list-rules}} returned empty) confirms that these rules were cleaned up as part of the pipeline deletion process. # *Orphaned CloudTrail trail*: {{codepipeline-source-trail}} with empty event selectors (not logging anything) # *Orphaned placeholder bucket*: {{codepipeline-cloudtrail-placeholder-bucket-af-south-1}} ---- h3. *Account: Backend-Dev* *Status:* *No Action Required* | 12/Dec/25 10:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed the status is in passed state hence marking for PO approval. | 12/Dec/25 10:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;marking to done. | [24 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2025-12-12 10:26
AM20-668 | Security and compliance implementation on PROS account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622524 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 20:04 | 2026-01-28 20:23 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on PROS account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in PROS DEV account * NIST policy implementation successfully done in PROS DEV account * AWSFSBP policy implementation successfully done in PROS DEV account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Mar/25 2:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [8 empty] | AM20-19 | AM20-17 |  |  | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250317-060821.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1079558 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a53b25a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxson: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-13 06:02 | [13 empty] | 13/Mar/25 8:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on the controls with the dependency services for the security frameworks. | 14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;The controls were implemented in Pros DEV account, Pros Production account will be picked up in separate user story. | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250317-060821.png¦width=1277,height=642,alt="image-20250317-060821.png"! | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-14 14:22
AM20-669 | Rehosting & Replatforming of applications from on-Prem to AWS | To Do |  | None( Epic) |  |  |  | High | 1620369 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 14:42 | 2026-01-19 17:19 |  |  |  | 0 | Application migration (re-hosting or re-platforming of on-prem applications to AWS cloud. The activities includes, deployment of DMS tool in SAA servers, migration related activities, configuration, 3rd party application connectivity's, setting up of issue resolution, backup and restore validations, DR, DNS change, UAT, Delta migration, issue fixes and final handover activities | [23 empty] | 1713600 | 864000 | 835200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6d20c765 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-6 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | green | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxn5r: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-03-04 11:46
AM20-670 | Restrict Admin access to VOIS team by creating dedicated IAM role | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Medium | 1736354 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 22:13 | 2026-01-26 01:59 |  |  |  | 0 | As Product Owner, I want to restrict VOIS team to have Admin role so that all of them cannot be superseded rights and bring more control on AWS management Acceptance criteria: * IAM role to be created for everyone except Sankalp and Aravind from AWS perspective * IAM role for network creation to be created and role assign to Satya * IAM role for rest of team members is of developer |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6edd432e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0c5zn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 06:20 | [13 empty] | 06/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have shared the Excel with the user list to team, upon there confirmation ill start creating custom policy with user groups. | 08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;¦UserID¦IAM user¦UserGroup¦IAM Role¦ ¦raja0001¦Aravind¦VOIS_Admin¦No changes, use existing roles itself¦ ¦rais0003¦Sankalp¦VOIS_Admin¦No changes, use existing roles itself¦ ¦SatyasairamV¦SatyaSairam¦VOIS_Admin¦No changes, use existing roles itself¦ ¦godir001¦Ravinder¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦kiraj001¦Jitender¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Sanjot¦Sanjot¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦nikas001¦Sumit¦VOIS_Admin¦No changes, use existing roles itself¦ ¦FaisalSayed¦Faizal¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SanketKale¦Sanket¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦pathp002¦Pankaj¦VOIS_DBAdmin_Usergroup¦AWS_VOIS_DBAdmin_Role¦ ¦onkar¦Onkar¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦DikshaK¦Diksha¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SatyabrataS¦SatyaBrata¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Shreyash¦Shreyash¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Harsh¦Harsh¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Yashwant¦Yashwant¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Utkarsh¦Utkarsh¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ Â Â Access to User group given as below, ¦VOIS_InfraAdmin_Usergroup¦VOIS_DevOpsAdmin_Usergroup¦VOIS_DBAdmin_Usergroup¦ ¦VPC FullAccess¦CodeBuild FullAccess¦RDS Full Access¦ ¦EC2 FullAccess¦CodePipeline FullAccess¦DMS Full Access¦ ¦S3 FullAccess¦EKS FullAccess¦IAM Full Access¦ ¦CloudWatch FullAccess¦EC2 except delete¦CloudTrail except delete¦ ¦RDS FullAccess¦S3 FullAccess¦KMS except delete¦ ¦IAM FullAccess¦CloudWatch except delete¦CloudWatch except delete¦ ¦CloudTrailFullAccess¦RDS except delete¦Read only¦ ¦MacieFullAccess¦IAM FullAccess¦ ¦ ¦GuardDutyFullAccess¦System managerFullAccess¦ ¦ ¦SecurityHubFullAccess¦LambdaFullAccess¦ ¦ ¦System managerFullAccess¦Event bridgeFullAccess¦ ¦ ¦LambdaFullAccess¦CloudTrail except delete¦ ¦ ¦KMSFullAccess¦Read only¦ ¦ ¦ACMFullAccess¦Secrets managerFullAccess¦ ¦ ¦Aws ConfigFullAccess¦SNSFullAccess¦ ¦ ¦Event bridgeFullAccess¦SESFullAccess¦ ¦ ¦InspectorFullAccess¦ECR FullAccess¦ ¦ ¦SupportFullAccess¦KMS except delete¦ ¦ ¦SNSFullAccess¦Â ¦ ¦ ¦SESFullAccess¦ ¦ ¦ ¦ReadOnly¦ ¦ ¦ ¦Secrets managerFullAccess¦ ¦ ¦ ¦ECRFullAccess¦ ¦ ¦ Â Users have access to the below AWS accounts, Â ¦AWS Account¦Account Name¦ ¦300204747992¦Audit¦ ¦730335236533¦Security¦ ¦080284287007¦LogArchive¦ ¦339712943527¦Network¦ ¦864899875361¦SharedServices¦ ¦585768167545¦SharedVpcDev¦ ¦253490777663¦SharedVpcPreprod¦ ¦820242899278¦SharedVpcProd¦ ¦746669190453¦Backend dev¦ ¦216989128782¦Backend Preprod¦ ¦396608788916¦Backend Prod¦ ¦209479274829¦Tm1¦ ¦345594574792¦AirNAVx¦ ¦536697265099¦NexioAV¦ | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-671 | Patch Management ¦¦ Dashboard Enhancement | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1746156 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 21:32 | 2026-01-17 01:02 |  |  |  | 0 | As Product manager compliance dashboard needs to be enhance and should covered details of patch file Acceptance Criteria: Compliance dashboard need to patch details and account details |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4159e3f0 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cz63: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 20:35 | [13 empty] | 18/Aug/25 10:34 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Update for Patch Manager Monitoring, in the compliance bucket there are 3 folders created after creating the resource data sync but not for the target acc we need. i have changed certain policies and also added some permissions both in security as well as dev acc. I am waiting for the data to pop up and also i can trigger data collection forcefully via aws cloudshell command but i do not have access i have intimated Aravind for permission addition. and the data that is being collected is basically json and that is the format that we need for it to be visualized in cloudwatch. | 25/Aug/25 8:52 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;spillover: the data sync which has been created in the management acc theoretically should be able to fetch the summaries from target account and sync that data in the s3 bucket in central account. the steps that were tried to force a sync were: {code:json}Check if the Instance is Managed by Systems Manager Check Current Associations Check Current Inventory Data Create the Inventory Association Verify Association Creation Check Association Status Monitor Association Execution Check for Updated Inventory Data{code} All of these were done and created an association manually for it to be populated into s3 bucket yet it did not work. the permission policies are provided yet the target account data is not being synced. the issue was that resource data sync must be created in each of the target account which was earlier thought as not needed. have created ressource data sync and waiting for the data to be populated. | 28/Aug/25 8:34 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Spillover Revised Comment: I was troubleshooting the resource data sync that i created since theoretically, resource data sync in the management account was enough. After rigorous attempts to fix the issue and trying to find out the workarounds they all failed. At the end of the week, close to sprint closure I found the solution and applied it and the solution worked. Hence, the delay and also for the data to populate into the intended bucket it sometime takes 10-12 hrs. | 03/Sep/25 8:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# The Resource Data Sync has been troubleshoot correctly and is working as intended. # Lambda function has been created in backend-dev account so that it can brand all the instances as non-compliant initially. # EventBridge has been configured as such when any new instance is provisioned it shall be flagged as non-compliant using the lambda function mentioned in point no.2. # The data in S3 is being used to project it to CloudWatch and that is being do using a Lambda function which will create metrics from the data in S3. # CloudWatch Dashboard is created such that it will have visual data segregated acc to the Acc Ids. (which was requirement by Bhavish). | 08/Sep/25 6:35 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;need demo | 08/Sep/25 8:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: The story was completed sufficing all the acceptance criteria. Demo was not done due to unavailability, hence scheduling the demo for 9/9/2025 considering everyoneâ€™s availability. | 11/Sep/25 9:12 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Demo was provided. The methodology and implementation was agreed upon and approved. There was an ask to involve another accounts, in order to check the workability. The accounts addition was done successfully and the data is presented on the custom dashboard as well. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:20
AM20-672 | Disaster Recovery and Backup | In Progress |  | None( Epic) |  |  | Yashwant Thakur | Critical | 1717990 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 20:58 | 2026-01-13 00:21 |  |  |  | 0 | Automated Backup and Disaster Recovery Infrastructure via Terraform or manual |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [15 empty] | 432000 | 374400 | 86400 | [12 empty] | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133603.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175536 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133705.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175534 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175537 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133947.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175535 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2309b367 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-9 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | orange | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0anuj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-30 13:41 | [13 empty] | 30/Oct/25 3:40 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Validated PROS & Informatica backups, all are configure fine. Pros back up status: !image-20251030-133603.png¦width=612,alt="image-20251030-133603.png"! Policy: !image-20251030-133705.png¦width=597,alt="image-20251030-133705.png"! Informatica Prod Backup: !image-20251030-133909.png¦width=597,alt="image-20251030-133909.png"! Status: !image-20251030-133947.png¦width=597,alt="image-20251030-133947.png"! | 13/Nov/25 8:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Backup has been configured and working fine. DR step-up is done still sync in progress. Once sync completed we can initiate call for testing. | [28 empty] | In Progress | 2025-10-30 15:30
AM20-673 | TM1 ¦¦ Configuring Application specific error in Cloudwatch for alerting | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730283 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 17:21 | 2026-01-14 17:42 |  |  |  | 0 | As a AWS expert I want to detect application specific error patterns in CloudWatch logs so that I can generate alerts for ServiceNow ticket creation and respond to runtime failure Acceptance Criteria: * Error pattern is defined and tested * Given an application output logs to cloudwatch when a known error occurs, then the pattern must correctly match that log * Metric filter is created - when error count exceeds the threshold then cloud watch alarm should trigger * Alert notification is sent, given the alarm is triggered when the condition is met then an alert must be sent to relevant teams |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [25 empty] | AM20-116 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3fa4464b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bnb3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:37 | [13 empty] | 04/Aug/25 6:37 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will start working on this from today. | 08/Aug/25 12:05 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Monitoring for specifically reporting & tm1serv application has been set. Alarm for Total Commit Usage has been created and configured to send those to ServiceNow. | 08/Aug/25 12:06 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Moving to Aravindâ€™s bucket for review. | 08/Aug/25 12:30 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;every cloud watch custom metrics are captured as error metrics and create an alarm for same. | 08/Aug/25 12:30 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;create a memoryutilization and disk utilization alarm and move to review | 08/Aug/25 8:43 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Monitoring metric is created for Overall Committed Memory Bytes and then further classified for each service that was mentioned in the mail. Alert has been created for â€œOverall Committed Memory Bytesâ€, so creating alarms for its further classification would be redundant. And in the email, we have a confirmation to create an alarm for â€œTotal Commit Sizeâ€ hence have created for â€œOverall Committed Memory Bytesâ€ and not for the per service. | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-674 | MQ POC ¦¦ MQ Parser Execution - Lambda integration testing & Message body validation | Done | 8 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1842282 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 17:45 | 2026-01-16 19:55 |  | 2025-11-28 07:36 |  | 0 | As Application product owner I would like to perform Lamda integration test with MQ parser and validate the messages output |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Nov/25 5:05 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;7200 | ;21/Nov/25 9:21 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;43200 | ;25/Nov/25 4:07 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;64800 |  |  |  | 115200 | 0 | 115200 | 1 | 115200 | 0 | 115200 | [12 empty] | 25/Nov/25 4:07 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251125-140722.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189321 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124739.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189722 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124758.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189723 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124816.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189725 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124826.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189726 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124840.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189721 | 26/Nov/25 2:49 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251126-124850.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1189724 | [11 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@21c31db9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5mz: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 15:05 | 3_*:*_1_*:*_713651403_*¦*_10041_*:*_1_*:*_86384139_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 5:05 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Exploring feasible approaches for Lambda integration with MQ parser, since direct MQ - Lambda integration is not possible. | 21/Nov/25 8:27 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;we have configured lambda and tested workfow funtionality by pushing message to s3 bucket from SQS. Now we go with checking feasibility with pegasys application usecase | 25/Nov/25 4:07 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Another approach, we tried to integrate MQ queue â€œPEGASYS.OUT.UATâ€ directly to Lambda !image-20251125-140722.png¦width=459,alt="image-20251125-140722.png"! | 26/Nov/25 2:49 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Â We tried integrating both S3 and MQ with Lambda directly. Whenever message reaches to MQ queue, it should trigger lambda which doesnâ€™t happen. However we tested then by integrating s3 event type â€œPutâ€, as soon as any object is uploaded to s3 bucket, it triggers Lambda Â !image-20251126-124739.png¦width=443,alt="image-20251126-124739.png"! Â !image-20251126-124758.png¦width=443,alt="image-20251126-124758.png"! Â !image-20251126-124840.png¦width=443,alt="image-20251126-124840.png"! !image-20251126-124850.png¦width=443,alt="image-20251126-124850.png"! !image-20251126-124816.png¦width=443,alt="image-20251126-124816.png"! !image-20251126-124826.png¦width=443,alt="image-20251126-124826.png"! As next step in next sprint , we will raise support ticket with AWS to get more clarity on this approach of direct integration of lambda and MQ | 28/Nov/25 7:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-28 07:36
AM20-675 | PROS ¦¦ DR | Done | 3 | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | High | 1717973 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 21:57 | 2026-01-28 23:25 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [TM1-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [11 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@49626307 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-03 07:24 | [13 empty] | 03/Oct/25 9:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Only after the server migration we would be able to do DR so this US will be blocked. | 17/Oct/25 11:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;27th Oct planned for cutover, upon server availability we will initiate DR followed by drill. since this will be spillover | [25 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-17 11:08
AM20-676 | MQ-PROD ¦¦Setup Subnet, NACL and SG Creation and Validation | Done | 3 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1794109 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 18:14 | 2026-01-11 22:06 |  | 2025-10-31 09:34 |  | 0 | As AWS network expert I would like to setup the security group and NACL for MQ so that access for MQ allow secure access to allow communication with its services while ensuring access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for MQ or related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [13 empty] | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090000.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175254 | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090022.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175253 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@680e7164 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0i6ob: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 17 | [97 empty] | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [65 empty] | YES | YES | 2025-10-17 09:19 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [12 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 27/Oct/25 4:05 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working on it. | 30/Oct/25 11:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to requirement i have done platform setup. Subnets: ¦Subnet address¦Range of addresses¦Useable IPs¦Hosts¦Divide¦Used Status¦App Name¦ ¦10.40.0.224/28¦10.40.0.224 - 10.40.0.239¦10.40.0.225 - 10.40.0.238¦14¦Divide¦Done¦MQ PROD PRIVATE¦ ¦10.40.0.240/28¦10.40.0.240 - 10.40.0.255¦10.40.0.241 - 10.40.0.254¦14¦Divide¦Done¦MQ PROD PUBLIC¦ ¦10.40.1.32/28¦10.40.1.32 - 10.40.1.47¦10.40.1.33 - 10.40.1.46¦14¦Divide¦Done¦MQ PROD DR¦ ¦10.40.1.48/28¦10.40.1.48 - 10.40.1.63¦10.40.1.49 - 10.40.1.62¦14¦Divide¦Done¦MQ PROD DR¦ Subnets screen: !image-20251030-090022.png¦width=597,alt="image-20251030-090022.png"! EC2 connectivity screen: !image-20251030-090000.png¦width=597,alt="image-20251030-090000.png"! | 31/Oct/25 9:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though MQ migration is put on hold however since the objective and acceptance criteria is met, approving the User story to close | [26 empty] | Done | 2025-10-31 09:34
AM20-677 | Tag Validations for AirNavX | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820186 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 16:14 | 2026-01-24 16:27 |  | 2025-11-14 10:58 |  | 0 | As a Cloud governance engineer I want to validate that all resources and workloads related to newly migrated applications have the correct mandatory tags applied so that we can ensure accurate cost allocation, compliance reporting and automation alignment across all AirNavX account Acceptance Criteria: * Tags for all applicable application resource type ( EC2, EBS, RDS, S3 lamda, ALB/NLB, Cloudwatch log groups) are successfully captured. * If there are any tags not available then manually updated successfully * Validations runs across all migrated resources and as per agreed format |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:33 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;246000 | [5 empty] | 28800 | 0 | 246000 | 8.54 | 28800 | 0 | 246000 | [12 empty] | 13/Nov/25 9:26 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-072628.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182486 | 13/Nov/25 12:08 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-100724.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182794 | 13/Nov/25 12:08 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-100827.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182795 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ffcb69e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l62j: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-06 06:25 | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 06/Nov/25 8:25 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will Start checking all the tags are in place for AirnavX environment and will update them. | 06/Nov/25 9:35 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;AirnavX code build & code piplines & s3 proper taggings are missing. | 12/Nov/25 2:23 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Followed up with satyabrata he is occupied with some tasks and will connect with me tomorrow for this US. | 13/Nov/25 9:26 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251113-072628.png¦width=631,alt="image-20251113-072628.png"! S3 tagging has been updated by AWS CLI command. Now checking for code build and pipline. | 13/Nov/25 12:08 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251113-100724.png¦width=714,alt="image-20251113-100724.png"! Evidence for code pipline and code build updated tags. !image-20251113-100827.png¦width=695,alt="image-20251113-100827.png"! | 14/Nov/25 10:58 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-14 10:58
AM20-678 | TM1 ¦¦ E2E Integration testing of ServiceNow monitoring | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1729976 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 16:55 | 2026-02-02 19:45 |  |  |  | 0 | As Product Owner I would like to review e2e testing completed with servicenow team for all wave 1 application so that we can confirm to business that in case of any issue service ticket would be raised Acceptance Criteria: * Tickets/issues are getting raised successfully against the alerts raise via cloudwatch for all Wave1 applications * ServiceNow team signoff received * Showcase (demo) provided to all relevant stakeholders |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 19/Aug/25 1:26 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image (3).png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141522 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@98c0df5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bmab: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-28 07:32 | [13 empty] | 28/Jul/25 9:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Once after the TM1 cutover is completed we can proceed with this activity. | 11/Aug/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: Since the story was blocked due to configuration of monitoring and alerting on TM1 ec2 instances (application specific) which was completed on 8th Aug 2025 (evening), Diksha did not get any time to validate end to end solution. Hence, the spillover. | 19/Aug/25 10:40 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start working on this US from today. | 19/Aug/25 12:27 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Alerts are being generated and triggered now waiting for confirmation from Service now team to share the screenshot. | 19/Aug/25 1:26 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image (3).png¦width=1146,height=305,alt="image (3).png"! Attaching the screenshot which I got from service now team that they are getting the alerts generated by our side. | 21/Aug/25 2:33 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:33
AM20-679 | CloudWatch log analysis for Cost optimization | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834933 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 17:16 | 2026-01-11 20:16 | 2025-11-28 13:47 | 2025-11-28 13:59 |  | 0 | As Product owner I like to analyse the Cloudwatch logs and eliminate any duplicate logs to ensure that cost is being charged fairly and take action to reduce the current cost, which is very high at this point of time |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Worked on analysis CloudWatch cost spent on backend dev account to see the detailed spend and identify the sectors with most spent. ;18/Nov/25 8:19 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on identifying cloudwatch components contributing majorly to the CloudWatch costs.;19/Nov/25 8:21 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | ;24/Nov/25 4:49 PM;17cb9418-1850-4923-932b-7098ec51b6bb;7200 | Worked on identifying ingestion in log group to control putLogevents cost;24/Nov/25 4:50 PM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on disabling enhanced monitoring , this will disable scraping pod level metrics to save cost on ObservationUsage.;24/Nov/25 4:51 PM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 |  | 86400 | 0 | 93600 | 1.08 | 86400 | 0 | 93600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cb03268 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mww3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:20 | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:20 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Worked on analysis CloudWatch cost spent on backend dev account to see the detailed spend and identify the sectors with most spent. | 19/Nov/25 8:30 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Enabled CloudTrail to monitor CloudWatch Data Events so that we can track which API is getting used and interacting with CloudWatch. | 24/Nov/25 4:49 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Worked on creating dashboard to identify log ingestion in each log group , updated fluent bit config to send logs only for flysaa backend amadeus and fabric microservices only to CloudWatch, also disabled sending logs to these log groups: # /aws/containerinsights/<eks-dev-cluster>/dataplane # /aws/containerinsights/<eks-dev-cluster>/host # /flysaa/dev/eks Disabled enhanced monitoring for eks cluster to save on ObservationUsage costs. | 28/Nov/25 1:59 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-28 13:59
AM20-680 | Tagging Compliance implementation | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834929 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 15:10 | 2026-02-02 18:22 | 2025-11-27 08:26 | 2025-11-28 11:38 |  | 0 | As product owner I would like to setup tagging compliance in centralized Cloudwatch dashboard so that I know how many workloads are not been tagged and take corrective actions accordingly |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;20/Nov/25 8:27 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;21/Nov/25 7:56 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;25/Nov/25 10:41 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;26/Nov/25 3:33 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;27/Nov/25 4:17 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;7200 |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 27/Nov/25 4:17 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251127-141419.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190266 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fa2be84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mwv7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:50 | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:50 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Satya sir is checking with leigh regarding the tag policy enable part after updating the tag policy will start working on the Tag compliance part. | 19/Nov/25 1:33 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have Enabled the Tag Compliance policy for all account. Waiting for security score. | 21/Nov/25 7:55 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Security score is visible for all accounts now next step is we are disabling the ID on with we donâ€™t require this tag compliance policy for all accounts. | 23/Nov/25 2:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have disabled the Tag Compliance policy for all the non required resource IDâ€™s for all 17 mandatory accounts. 746669190453â€ƒâ€ƒFlySAA_CMS_Backend_DevQA 216989128782Â Â Â Â Â Â Â FlySAA_CMS_Backend_PreProd 396608788916â€ƒâ€ƒFlySAA_CMS_Backend_Prod 209479274829â€ƒâ€ƒSAA TM1 345594574792â€ƒâ€ƒSAA AirnavxÂ 536697265099â€ƒâ€ƒSAA_NEXIOAV_PROD 650251698621â€ƒâ€ƒSAA_PROS_PROD 307946680641â€ƒâ€ƒSAA_Informatica_DEV 536697248966â€ƒâ€ƒSAA_Informatica_PROD 195973603339â€ƒâ€ƒvod001_001_payer9 300204747992â€ƒâ€ƒSAA-AuditÂ 730335236533â€ƒâ€ƒAWS_SAA_Security 080284287007â€ƒâ€ƒSAA-LogArchive 339712943527â€ƒâ€ƒAWS_SAA_Network 585768167545Â Â Â Â Â Â Â SharedVPCDevQA() 253490777663Â Â Â Â Â Â Â SharedVPCPreProd() 820242899278Â Â Â Â Â Â Â SharedVPCProd() | 25/Nov/25 10:40 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;For the Untagged one IDâ€™s we are remediating the failed ones as much as we can for all 17 accounts before getting the centralized dashboard enabled for Tag compliance. | 26/Nov/25 9:04 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Tag compliance security score is 95% for all 17 Accounts and to make it 100% we need to Tag IAM Roles for all Accounts and Each account contains more than 60 IAM Roles which is not possible for a Single person to tag them. I need team support to tag those IAM roles as its a manual work no automation will help as they are the existing resources not the new ones. | 26/Nov/25 3:32 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*UPDATE :* With the Help of lambda function we were able to tag all the IAM roles for all 17 accounts. Except the oneâ€™s which are not handled by our team and we are not authorized to tag them. | 27/Nov/25 4:17 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251127-141419.png¦width=629,alt="image-20251127-141419.png"! Tags has been implemented for all resources and in the security account under Security Hub we can see all the tagged resources and the information. | 28/Nov/25 11:38 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. Saw the data presented in review call. satisfied with results | [21 empty] | Done | 2025-11-28 11:38
AM20-681 | Voager connectivity | Done | 2 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1872880 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 12:30 | 2026-02-06 13:37 | 2025-12-14 19:04 | 2025-12-12 11:20 |  | 0 | Static Routes need to be setup. Advertise Subnets DX. Establish Routing |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;04/Dec/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [12 empty] | 02/Dec/25 5:02 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251202-150140.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1191675 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a461fc5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0oflf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-02 15:02 | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Dec/25 5:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Static routes has been implemented. Notified customer to submit CSOC for routing implementation.(CHR0031699) !image-20251202-150140.png¦width=612,alt="image-20251202-150140.png"! | 02/Dec/25 5:10 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Routing has been implemented and connectivity has been implemented. | 04/Dec/25 8:19 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Customer validated connectivity and working fine, hence resolving this story. | 12/Dec/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-12-12 11:20
AM20-682 | POC for replacing IBM MQ with AWS MQ | To Do | 0 | None( Backlog) |  |  |  | Medium | 1795168 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 18:44 | 2026-01-26 22:22 |  |  |  | 0 | [57 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63afd04c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akq: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:36
AM20-683 | TM1 ¦¦ Migration tool installation | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620533 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 13:43 | 2026-01-22 15:44 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the TM1 SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | Working with nexio team on troubleshooting the replication issue and configuring required services to get the agent installation successful followed by replication.;07/Apr/25 10:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [5 empty] | AM20-14 | AM20-4 | [23 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@106887e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnnb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:26 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This user story is blocked due to [https://vodacom.atlassian.net/browse/AM20-14¦https://vodacom.atlassian.net/browse/AM20-14¦smart-link] the network setup, upon completion of network will pick this one up. | 21/Mar/25 12:19 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet is shared, requested [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] to create a connectivity between on-premises to cloud. After the connectivity established, will be able to pick this migration agent toll installation for TM1. | 25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created a replication template and post launch template, waiting for the connectivity to be established between on-premises and TM1 AWS account. | 27/Mar/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Shared Agent and access details to vodacom team, have raised CRQ request for agent installation. 28th is planned for agent installation followed by replication will be initiated. | 04/Apr/25 11:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;On-prem to AWS Connectivity is established, Agent installation is getting failed due to multiple time of attempt, now waiting for restart of server from the logs. will try to install again and update the proceeding's here, | 07/Apr/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Replication is in progress, waiting for initial snapshot to be created. | 07/Apr/25 10:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Though agent installation completed, marking this story to done. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-07 10:45
AM20-684 | Nexio AV ¦¦ LLD creation | Done | 2 | Sprint 2 | 2025-03-31 | 2025-04-11 | Yashwant Thakur | High | 1619786 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 19:15 | 2026-01-26 21:29 |  |  |  | 0 | As AWS architect, I would create LLD for Nexio AV application migration *Acceptance Criteria*: * Low level design documentation including proposed architecture completed |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;13/May/25 11:21 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [9 empty] | AM20-22 |  |  | 13/May/25 11:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;TrellixAV_DesignDocument_v1.1.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1099634 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28a7c8e2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsmv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 3 | Sprint 4 | Sprint 5 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-13 09:38 | [13 empty] | 13/May/25 11:38 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Document has been prepared for Trellix AV ePO server migration to AWS ¦Backup PolicyÂ ¦To be discussed with customer and finalized¦ ¦DR Policy¦To be discussed with customer and finalized¦ [^TrellixAV_DesignDocument_v1.1.docx] First Draft of LLD is attached Moving to In Review until we can share it with customer and Finalize the Document | 18/May/25 2:41 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [25 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-05-18 14:41
AM20-685 | RDS Upgrade in Flysaa backend Dev environment | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1842266 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 21:59 | 2026-01-10 23:31 | 2025-11-26 08:48 | 2025-11-27 09:18 |  | 0 | h2. User story * When the RDS instance is upgraded, I want to ensure compatibility with MySQL 8.4 so that our application runs smoothly without issues. h2. Context The development RDS instance will be upgraded from MySQL version 5.7 to 8.4. This upgrade may affect the functionality and performance of the application. h2. Acceptance criteria * The RDS instance must be successfully upgraded to MySQL 8.4. * All application features should function correctly after the upgrade. * Performance benchmarks should be met post-upgrade. h2. Other information N/A |  | Pankaj Pathak | Yashwant Thakur |  |  |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7e1de089 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5lf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [65 empty] | YES | YES | 2025-11-20 06:25 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [12 empty] | 20/Nov/25 8:24 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;The upgrade from MySQL version 5.7.44 to 8.0.42 was successful. The DB instance is running smoothly. We asked the application team (Donald and Gavin) to confirm everything is functioning well on their end. We are awaiting their response to close this story. | 25/Nov/25 2:00 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Ticket moved to In review. As we have completed internal review. | 27/Nov/25 9:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Post upgrade, Business confirmed that BAU is working as expected hence approving | [27 empty] | Done | 2025-11-27 09:18
AM20-686 | Terraform Development ¦¦ Creation of Outbound and inbound rules in NACL | Done | 8 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1651313 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 14:37 | 2026-01-30 15:53 | 2025-11-27 08:27 | 2025-11-28 12:00 |  | 0 | As Terraform expert, I want to be creating a network ACL with inbound and outbound rules using terraform code, so that I can apply stateless packet filtering at the subnet level Acceptance Criteria: * Define variable for CIDRs, ports and subnets * NACL resources is created and associated with target subnets * Application relevant flows needs to be populated * Application inbound rule and comms metric needs to populated for NACL * Outbound rules allow return traffic on the same ports. * Each rule has a unique number and direction * Rules are parameterized for environment flexibility * add rule description and tags. * Provision to add or deny additional rules with max of 20 rules to be allowed for NACL |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@442b4964 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mrnr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 19 | [96 empty] | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-20 07:06 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 20/Nov/25 9:06 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Working on base module code of terraform script. It will be completed by this Friday EOD. | 27/Nov/25 8:24 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform script completed and NACL resource created in sandbox environment. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-11-28 12:00
AM20-687 | PROS ¦ Test-Over Instance | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | Medium | 1801095 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-11 13:07 | 2026-01-11 15:30 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@32a969b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0izhn: | [167 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 07/Oct/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Server replication is still on-going after completion of initial sync will start launching test instance. have updated the launch templet based on the LLD document. | 09/Oct/25 6:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test launch instance hand over is completed, awaiting for the response back from the application owner. | 17/Oct/25 11:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;connectivity issue is resolved, have received date to perform cutover. | [24 empty] | 1773952 | AM20-170 | PROS ¦¦ Cutover | Done | 2025-10-17 11:08
AM20-688 | Adding alarms for AWS account config changes. | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Shreyash Talwekar | Medium | 1799088 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2026-01-24 13:54 | 2026-01-24 15:02 |  |  |  | 0 | Add terraform code to configure below mentioned alarms for observing the cloudwatch logs regarding any changes done on AWS account. {noformat}AWSConfigChanges = { metric = "AWSConfigChanges", pattern = "{($.eventName = \"PutBucketPolicy\") ¦¦ ($.eventName = \"RunInstances\") ¦¦ ($.eventName = \"ModifyDBInstance\") ¦¦ ($.eventName = \"PutRolePolicy\")}" }, SecurityGroupChanges = { metric = "SecurityGroupChanges", pattern = "{($.eventName = \"CreateSecurityGroup\") ¦¦ ($.eventName = \"DeleteSecurityGroup\") ¦¦ ($.eventName = \"AuthorizeSecurityGroupIngress\") ¦¦ ($.eventName = \"AuthorizeSecurityGroupEgress\") ¦¦ ($.eventName = \"RevokeSecurityGroupIngress\") ¦¦ ($.eventName = \"RevokeSecurityGroupEgress\") ¦¦ ($.eventName = \"ModifySecurityGroupRules\")}" }, CMKDisablingOrDeletion = { metric = "CMKDisablingOrDeletion", pattern = "{($.eventName = \"DisableKey\") ¦¦ ($.eventName = \"ScheduleKeyDeletion\")}" }, CloudTrailConfigurationChanges = { metric = "CloudTrailConfigurationChanges", pattern = "{($.eventName = \"CreateTrail\") ¦¦ ($.eventName = \"UpdateTrail\") ¦¦ ($.eventName = \"DeleteTrail\") ¦¦ ($.eventName = \"StartLogging\") ¦¦ ($.eventName = \"StopLogging\") ¦¦ ($.eventName = \"PutEventSelectors\")}" }, ConsoleAuthenticationFailures = { metric = "ConsoleAuthenticationFailures", pattern = "{($.eventName = \"ConsoleLogin\") && ($.responseElements.ConsoleLogin = \"Failure\")}" }, ConsoleSignInWithoutMFA = { metric = "ConsoleSignInWithoutMFA", pattern = "{($.eventName = \"ConsoleLogin\") && ($.responseElements.ConsoleLogin = \"Success\") && ($.requestParameters.mfaAuthenticated = \"false\")}" }, IAMPolicyChanges = { metric = "IAMPolicyChanges", pattern = "{($.eventName = \"CreatePolicy\") ¦¦ ($.eventName = \"DeletePolicy\") ¦¦ ($.eventName = \"PutPolicy\") ¦¦ ($.eventName = \"AttachRolePolicy\") ¦¦ ($.eventName = \"DetachRolePolicy\") ¦¦ ($.eventName = \"AttachUserPolicy\") ¦¦ ($.eventName = \"DetachUserPolicy\")}" }, NACLChanges = { metric = "NACLChanges", pattern = "{($.eventName = \"CreateNetworkAcl\") ¦¦ ($.eventName = \"DeleteNetworkAcl\") ¦¦ ($.eventName = \"CreateNetworkAclEntry\") ¦¦ ($.eventName = \"DeleteNetworkAclEntry\") ¦¦ ($.eventName = \"ReplaceNetworkAclEntry\") ¦¦ ($.eventName = \"ModifyNetworkAcl\")}" }, NetworkGatewayChanges = { metric = "NetworkGatewayChanges", pattern = "{($.eventName = \"CreateVpnGateway\") ¦¦ ($.eventName = \"DeleteVpnGateway\") ¦¦ ($.eventName = \"AttachVpnGateway\") ¦¦ ($.eventName = \"DetachVpnGateway\") ¦¦ ($.eventName = \"ModifyVpnGateway\") ¦¦ ($.eventName = \"CreateTransitGateway\") ¦¦ ($.eventName = \"DeleteTransitGateway\") ¦¦ ($.eventName = \"ModifyTransitGateway\") ¦¦ ($.eventName = \"CreateTransitGatewayAttachment\") ¦¦ ($.eventName = \"DeleteTransitGatewayAttachment\") ¦¦ ($.eventName = \"ModifyTransitGatewayVpcAttachment\")}" }, RootAccountUsage = { metric = "RootAccountUsage", pattern = "{($.userIdentity.type = \"Root\")}" }, RouteTableChanges = { metric = "RouteTableChanges", pattern = "{($.eventName = \"CreateRouteTable\") ¦¦ ($.eventName = \"DeleteRouteTable\") ¦¦ ($.eventName = \"CreateRoute\") ¦¦ ($.eventName = \"DeleteRoute\") ¦¦ ($.eventName = \"AssociateRouteTable\") ¦¦ ($.eventName = \"DisassociateRouteTable\") ¦¦ ($.eventName = \"ReplaceRouteTableAssociation\")}" }, S3BucketPolicyChanges = { metric = "S3BucketPolicyChanges", pattern = "{($.eventName = \"PutBucketPolicy\") ¦¦ ($.eventName = \"DeleteBucketPolicy\")}" }, UnauthorizedAPICalls = { metric = "UnauthorizedAPICalls", pattern = "{($.errorCode = \"AccessDenied\") ¦¦ ($.errorCode = \"UnauthorizedOperation\")}" }, VPCChanges = { metric = "VPCChanges", pattern = "{($.eventName = \"CreateVpc\") ¦¦ ($.eventName = \"DeleteVpc\") ¦¦ ($.eventName = \"ModifyVpcAttribute\") ¦¦ ($.eventName = \"CreateSubnet\") ¦¦ ($.eventName = \"DeleteSubnet\") ¦¦ ($.eventName = \"ModifySubnetAttribute\") ¦¦ ($.eventName = \"AssociateRouteTable\") ¦¦ ($.eventName = \"DisassociateRouteTable\") ¦¦ ($.eventName = \"CreateInternetGateway\") ¦¦ ($.eventName = \"DeleteInternetGateway\") ¦¦ ($.eventName = \"AttachInternetGateway\") ¦¦ ($.eventName = \"DetachInternetGateway\") ¦¦ ($.eventName = \"CreateNatGateway\") ¦¦ ($.eventName = \"DeleteNatGateway\")}" }{noformat} |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43895d15 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ir97: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [41 empty] | 1786761 | AM20-182 | Push to FlySAA backend Alarm related code to the bitbucket in dev and preprod environment | Done | 2025-10-03 10:48
AM20-689 | PROS ¦ Test-Over Instance | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | Medium | 1801095 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-06 19:07 | 2026-02-06 22:36 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@32a969b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0izhn: | [167 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 07/Oct/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Server replication is still on-going after completion of initial sync will start launching test instance. have updated the launch templet based on the LLD document. | 09/Oct/25 6:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test launch instance hand over is completed, awaiting for the response back from the application owner. | 17/Oct/25 11:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;connectivity issue is resolved, have received date to perform cutover. | [24 empty] | 1773952 | AM20-170 | PROS ¦¦ Cutover | Done | 2025-10-17 11:08
AM20-690 | PROS ¦¦ database restoration | Done | 0 | Sprint 14 | 2025-09-15 | 2025-09-26 | Fahim Mulla | Medium | 1773951 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:b2e2abba-5056-4f1e-a865-78841b29ab10 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 17:21 | 2026-01-17 20:54 |  |  |  | 0 | As a DBA I want to restore a MYSQL database hosted on AWS from a backup so that I can recover from failures, refresh lower environments or validate DR readiness Acceptance Criteria: * DBA can restore MYSQL from snapshot or PITE in same region * Restore DB uses correct subnet group,SG, Parameter groups * KMS encryption applied to restored DB * PITR restores to chosen timestamp with +-1 minaccuracy * Post restore DBA validates - schema exists, table count match, last transaction ID mateched source (if PITR) * Monitoring enabled (CPUUtilization, FreeStorageSpace, DatabaseConnections) * Access restricted by IAM and SG rules * All restore actions are logged in CloudTrail |  | Fahim Mulla | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:b2e2abba-5056-4f1e-a865-78841b29ab10 | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 17/Sep/25 7:53 AM;7f828717-d8f6-4eae-b82a-b6ba0cff270e;RE minutes SAA II Alignment on PROS connectivity pre-requisites.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1154264 | 19/Sep/25 9:49 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;minutes_ SAA II Alignment on PROS connectivity pre-requisites.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1156090 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2ac02e42 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-16 11:36 | [13 empty] | 16/Sep/25 1:36 PM;712020:b2e2abba-5056-4f1e-a865-78841b29ab10;As per the discussion Final Backup Done and stored in S3 via NetBackup in VDC. To be kept as is. This database will remain in VDC | 19/Sep/25 9:49 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Closing this ticket as PROS DB will now stay on prem. Refer attached email | [25 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-09-19 09:50
AM20-691 | TM1 ¦¦ Alerts renaming & Configuration | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786760 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 17:20 | 2026-01-12 18:36 |  |  |  | 0 | As Product owner I would like to rename alerts and configuration based on agreement with ServiceNow team *Acceptance Criteria*: TM1 alarm renaming completed successfully and configurations updated |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 24/Sep/25 1:56 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250924-115610.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1158311 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@26e51892 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-23 08:55 | [13 empty] | 23/Sep/25 10:54 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I have started creating the alarms with correct naming & threshold value which were agreed with the customer and service now team previously. | 24/Sep/25 1:56 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20250924-115610.png¦width=1580,height=467,alt="image-20250924-115610.png"! Have created alarms as per correct naming and configuration updated. | 29/Sep/25 6:53 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Moving this to In review to Aravind to check the configuration. | 03/Oct/25 12:42 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have modified the alarm for disk and memory configuration, other alarm are looking good. | [26 empty] | Done | 2025-10-06 07:59
AM20-692 | AirNavX ¦¦ Comms Matrix modification | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Yashwant Thakur | High | 1672499 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-09 21:11 | 2026-01-09 21:36 |  |  |  | 0 | As Network expert, I would be modifying the comms Metrices for AirNavX as the number of servers reduced to 3 servers instead of earlier scope of 5 servers. Acceptance Criteria: * Comms Metrics are successfully created * Sent for reviews to SITA team and agreement received |  | Harsh Chandra | Satya Varanasi | Sumit Nikam | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@40de4872 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04f2j: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-23 11:33 | [13 empty] | 23/May/25 1:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working it will be ready next week. | 27/May/25 8:12 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started and will be closed today or tomorrow. | 28/May/25 5:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;I have prepared 3 servers AirNavx comms and sending for review. | 16/Jun/25 8:32 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;This was checked and reviewed. | 16/Jun/25 8:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-16 08:34
AM20-693 | PROS ¦¦ Cutover | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773952 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 19:27 | 2026-01-12 19:49 |  | 2025-10-31 18:04 |  | 0 | As AWS expert I would be performing the cutover for PROS application. Acceptance Criteria: * Replication from on-prem is successfully stopped using API calls * Back up of PROS VDC Server * Monitoring disable - VDC Server * Shutting down Informatica application in VDC * Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining PROS Server to the AD * MAT Testing completed successfully by SAA * Deploy the Test instance with the network components * Deploy cutover actual instance * Wait for the launch instance check the status checks * configure required SSM and CW agent |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 31/Oct/25 11:09 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;RE_ PROS Server Cutover - Migratiom.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175913 | 28/Oct/25 11:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251028-095312.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174005 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4900724c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwr7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 |  | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | [65 empty] | YES | YES | 2025-10-03 07:24 | 3_*:*_1_*:*_2082638391_*¦*_10041_*:*_1_*:*_2427096509_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_346747383 | [12 empty] | 03/Oct/25 9:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Only after the server migration we would be able to do cutover so this US will be blocked. | 17/Oct/25 11:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cut over is planned on 27th Oct as per client request, since this will be spillover. | 28/Oct/25 11:52 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SSM agent installation and cloud watch installation is completed followed by domain join. | 28/Oct/25 11:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have sent a mail to application owner on the confirmation for closing cutover, upon receiving same will close this US. !image-20251028-095312.png¦width=423,alt="image-20251028-095312.png"! | 28/Oct/25 5:31 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;client facing some FTP issue, after it resolved this US can be closed | 31/Oct/25 11:08 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Cutover completed as per the email from Pieter Scheepers ( app owner)- email attached | 31/Oct/25 6:04 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [23 empty] | Done | 2025-10-31 18:04
AM20-694 | Patch Solution cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818696 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-09 12:48 | 2026-01-09 16:34 |  |  |  | 0 |  |  | Aravind Raj | Faisal Sayed |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@698194ac | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzvv: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-31 09:18 | [13 empty] | 31/Oct/25 11:17 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;The Patching instances are still needed, it shall be in stopped state when not in use and terminated once the patching demo is done which has been postponed. [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] [~accountid:712020:54791a09-30fd-4ab7-8a1d-068b13e544d8] | [26 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-11-14 20:26
AM20-695 | ServiceNow ¦¦ Logging and Monitoring | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651021 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 22:00 | 2026-01-22 23:08 |  |  |  | 0 | As an AWS expert, I want to monitor the health and logs of the Lamda connector function so that I can troubleshoot issues when alerts arenâ€™t processed properly Acceptance Criteria: * CloudWatch logs are enabled for Lambda * Metrics and dashboards are available for monitoring invocations, failures and response times. |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/May/25 9:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103910 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60acf139 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0285v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | [108 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 05:45 | [13 empty] | 02/May/25 7:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function to invoke the cloud watch is created and working as expected, Cloud watch dashboard for metrics will be created only after the workloads moved to cloud. service now monitoring can be in place only after successful integration with connector and service now PAAS endpoint. | 16/May/25 9:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have given demo with the email endpoints, waiting for the https endpoint to be received from SAA team to work with full functionality, | 22/May/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have received a endpoint today, yet to update SNS topic endpoint. https://sonicboom_em_saa_7161:wusEwo>G*Xmw@?XOA74\!pm0cx2.[4N;oFz<\!7vSE@liftdev.service-now.com/api/sn_em_connector/em/inbound_event?source=aws&sys_id=870cc1dfc3a5a6d04022f9777a013157 | 22/May/25 9:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 26/May/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 26/May/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;With respect to the endpoint have sent a mail to ashton, but there was response yet. awaiting on same. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. Â· | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 7:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Service now integration is completed with a new subscription HTTPS endpoint, have created a Cloud watch alarm for testing purpose which triggers a SNS as result service now dashboard receives a alert. | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-20 08:17
AM20-696 | TM1 ¦¦ establish internet connectivity via TGW | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620885 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 14:48 | 2026-01-29 16:14 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [26 empty] | AM20-15 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@232fa3c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxslz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-01 17:41 | [13 empty] | 01/Apr/25 7:40 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Internet connectivity has-been established and tested. | 04/Apr/25 10:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Internet setup has been completed and tested working fine. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-14 09:39
AM20-697 | Nexio AV ¦¦ Configuring Application specific error in Cloudwatch for alerting | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730277 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 14:50 | 2026-01-24 16:44 |  |  |  | 0 | As a AWS expert I want to detect application specific error patterns in CloudWatch logs so that I can generate alerts for ServiceNow ticket creation and respond to runtime failure Acceptance Criteria: * Error pattern is defined and tested * Given an application output logs to cloudwatch when a known error occurs, then the pattern must correctly match that log * Metric filter is created - when error count exceeds the threshold then cloud watch alarm should trigger * Alert notification is sent, given the alarm is triggered when the condition is met then an alert must be sent to relevant teams |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [25 empty] | AM20-117 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a72bd8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bnaz: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:37 | [13 empty] | 04/Aug/25 6:36 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will start working on this from today. | 08/Aug/25 9:01 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Used â€œGet-Servicesâ€ command with flags like running and contains trellix to analyse services to be monitored. 8 services identified. Created script for monitoring commit size of each service and in the â€œ*NexioAV/ServiceMemory*â€ namespace and the Overall commit size of EC2 is being monitored in â€œ*System/Memory*â€ namespace. Created alarm for Overall Commit Size threshold is 20GB for now since there is no communication on what should the threshold unlike TM1. | 11/Aug/25 4:27 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-698 | AirNavX Account ¦¦ Security Compliance Implementation | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672716 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-28 16:10 | 2026-01-28 17:49 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of AirNavX account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250528-092239.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1106065 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@33a69e54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04ft7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-28 09:24 | [13 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Account - 345594574792 Controls were implemented and security score is updated is for all the three security standard frameworks- CIS, NIST and AWS FSBP !image-20250528-092239.png¦width=1279,height=589,alt="image-20250528-092239.png"! | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-28 11:24
AM20-699 | ServiceNow ¦¦ SNS Topic for Alerts | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650429 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 20:48 | 2026-02-01 23:38 |  |  |  | 0 | AS AWS Expert, I want to create an Amazon SNS topic so that AWS services can be publish alert messages to it. Acceptance Criteria: * AN SNS topic is created * Permissions are set to allow EventBridge and Lamda to publish to it * The topic supports the subscription |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@505787e3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [66 empty] | Unit Tested | [51 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-06 06:23 | [13 empty] | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed, and will modify the required configurations. Â· | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:38
AM20-700 | Provision AWS GuardDuty using Terraform | Done | 10 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718154 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 14:09 | 2026-01-16 14:45 |  |  |  | 0 | As a cloud security engineer I want to provision and configure AWS GuardDuty using Terraform so that I can automatically detect and respond to potential threats in my AWS environment in a consistent and repeatable manner Acceptance Criteria: * Terraform must create a GuardDuty Detector in the primary AWS region. the detector must be enabled * for multiple AWS accounts Terraform must support creating a GuardDuty master-member relationship * Members must be invited and accepted automatically * GuardDuty should automatically published findings to the console API and this must not be disabled * Terraform must be modular to support enabling GuardDuty in any account and region * inputs like region, accountid, and enable flag must be configurable * All resources created via Terraform must include project defined tags * Forward GuardDuty findings to AWS security Hub or EventBridge |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@50808e38 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ansn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-22 06:28 | [13 empty] | 22/Jul/25 8:28 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Email sent to Ismaail and leigh about Request to Enable Centralized Management for GuardDuty and Amazon Inspector and currently I am working on Terrafrom script to create the base module for resources. | 23/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Leigh replied and asked to Ismaail for assisting. | 25/Jul/25 8:33 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;It will be spillover because there was a dependency on Ismail and he has updated on 23 July Only so thatâ€™s why I am not able to complete it on time. | 30/Jul/25 8:26 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script. Ready for the demo. | 11/Aug/25 4:30 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:30
AM20-701 | MQ ¦¦ Monitoring and Alert Solution | Blocked | 4 | None( Backlog) |  |  | Diksha Koul | Medium | 1794147 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 13:04 | 2026-01-15 13:19 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if MQ server is stopped |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c39a10 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-02 17:42 | [13 empty] | 02/Nov/25 7:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over* : After creation of the MQ EC2 instance we can start the creation of MQ monitoring and alerting solution. | [29 empty] | To Do | 2025-09-30 10:17
AM20-702 | Assessment on CMS Frontend SMS implementation | Done | 8 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Highest | 1842250 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 15:43 | 2026-01-11 16:32 | 2025-11-28 11:16 | 2025-11-28 14:00 |  | 0 | As a cloud platform application owner I want to perform a detailed assessment for enable SMS notification in the CMS frontend application hosted in AWS so that I can determine best approach, integration method, cost impact, security requirement and technical feasibility before implementation Acceptance Criteria: All use cases for SMS notification are documented SLA, frequency and criticality of SMS delivered and captured User flow diagrams for each SMS scenario prepared Assessment must identify How front will invoke API Required IAM permission documented for access for SMS publishing Consideration for rate limiting and Compliance requirements Risk, Assumption and dependencies |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Understanding alarm implementation and getting AWS frontend access from Leigh.;28/Nov/25 10:33 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on implementing SMS notification on frontend dev account;28/Nov/25 10:33 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | SMS implementation is working, worked on debugging minor issues and updating timeout of Lambda function to enable sending SMS to multiple numbers.;28/Nov/25 10:34 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 |  |  |  | 115200 | 28800 | 86400 | 0.75 | 115200 | 28800 | 86400 | [12 empty] | 28/Nov/25 1:49 PM;17cb9418-1850-4923-932b-7098ec51b6bb;SMS_frontend_alerts.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190540 | 28/Nov/25 10:36 AM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251128-083619.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190436 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67436dd5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5jf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-25 08:56 | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 25/Nov/25 10:56 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created a Whitepage access request to enable access for frontend AWS accounts, reached out to Leigh with ticket details. | 26/Nov/25 8:54 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Access request is approved, awaiting access enabling from Leigh. | 27/Nov/25 8:21 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Got the access from Leigh, worked on provisioning AWS resources (Lambda , eventbridge rule , dynamodb table) for alert implementation, need to get number from Hoosen for sending sms. | 28/Nov/25 10:36 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Hoosen confirmed he got SMS for sample alarm in frontend dev . !image-20251128-083619.png¦width=281,alt="image-20251128-083619.png"! | 28/Nov/25 1:49 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;[^SMS_frontend_alerts.docx] Please find attached document for SMS implementation. | 28/Nov/25 2:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-28 14:00
AM20-703 | MQ ¦¦ Application comms metrics preparation and implementation | To Do | 0 | None( Backlog) |  |  | Satya Varanasi | Medium | 1795166 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 22:04 | 2026-01-26 01:45 |  |  |  | 0 | AS Network expertise I want to define, track and baseline and validate network communication metrics including subnets, connectivity with downstream/3rd party applications and network rules so that the applicationcan be migrated to the cloud without connectivity failures, security gaps or performance degradation Acceptance Criteria: Application specific subnets (CIDR range, VPC design, Private/public allocation) documented Overlapping IP ranges validated against downstream and 3rd party integrations subnet utilization % captured E2E connectivity map prepared: application <->DB<->downstream services <->3rd party APIs Latency, Packet loss, throughput baselined from VDC/onprem to cloud traget points DNS resolution | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3842a4ec | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g1 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:35
AM20-704 | Patch Management ¦¦ Dashboard Enhancement | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1746156 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 18:56 | 2026-01-09 19:33 |  |  |  | 0 | As Product manager compliance dashboard needs to be enhance and should covered details of patch file Acceptance Criteria: Compliance dashboard need to patch details and account details |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4159e3f0 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cz63: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 20:35 | [13 empty] | 18/Aug/25 10:34 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Update for Patch Manager Monitoring, in the compliance bucket there are 3 folders created after creating the resource data sync but not for the target acc we need. i have changed certain policies and also added some permissions both in security as well as dev acc. I am waiting for the data to pop up and also i can trigger data collection forcefully via aws cloudshell command but i do not have access i have intimated Aravind for permission addition. and the data that is being collected is basically json and that is the format that we need for it to be visualized in cloudwatch. | 25/Aug/25 8:52 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;spillover: the data sync which has been created in the management acc theoretically should be able to fetch the summaries from target account and sync that data in the s3 bucket in central account. the steps that were tried to force a sync were: {code:json}Check if the Instance is Managed by Systems Manager Check Current Associations Check Current Inventory Data Create the Inventory Association Verify Association Creation Check Association Status Monitor Association Execution Check for Updated Inventory Data{code} All of these were done and created an association manually for it to be populated into s3 bucket yet it did not work. the permission policies are provided yet the target account data is not being synced. the issue was that resource data sync must be created in each of the target account which was earlier thought as not needed. have created ressource data sync and waiting for the data to be populated. | 28/Aug/25 8:34 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Spillover Revised Comment: I was troubleshooting the resource data sync that i created since theoretically, resource data sync in the management account was enough. After rigorous attempts to fix the issue and trying to find out the workarounds they all failed. At the end of the week, close to sprint closure I found the solution and applied it and the solution worked. Hence, the delay and also for the data to populate into the intended bucket it sometime takes 10-12 hrs. | 03/Sep/25 8:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# The Resource Data Sync has been troubleshoot correctly and is working as intended. # Lambda function has been created in backend-dev account so that it can brand all the instances as non-compliant initially. # EventBridge has been configured as such when any new instance is provisioned it shall be flagged as non-compliant using the lambda function mentioned in point no.2. # The data in S3 is being used to project it to CloudWatch and that is being do using a Lambda function which will create metrics from the data in S3. # CloudWatch Dashboard is created such that it will have visual data segregated acc to the Acc Ids. (which was requirement by Bhavish). | 08/Sep/25 6:35 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;need demo | 08/Sep/25 8:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: The story was completed sufficing all the acceptance criteria. Demo was not done due to unavailability, hence scheduling the demo for 9/9/2025 considering everyoneâ€™s availability. | 11/Sep/25 9:12 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Demo was provided. The methodology and implementation was agreed upon and approved. There was an ask to involve another accounts, in order to check the workability. The accounts addition was done successfully and the data is presented on the custom dashboard as well. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:20
AM20-705 | Monitor health and logs of Lamda connector function to troubleshoot issue , if alerts in not processed | Done | 8 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747507 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 15:24 | 2026-01-24 17:10 |  |  |  | 0 | As Product owner I want to monitor health and logs of Lamda connector function so that I can troubleshoot issues quickly when alerts are not processed and ensure reliability of the alerting pipeline Acceptance Criteria: CloudWatch logs are enabled for the Lamda connector function to capture execution details, input events and error messages Cloudwatch Metrices (invocations, errors, throttles, duration) are available for function and updated in real time cloudwatch alarms are configured for * Errors >0 in last 5 minues * Throttles >0 * Duration exceeds timeout threshold A SNS is configured to capture failed Lamda execution Alerts from cloud watch are sent via SNS to notify ServiceNow CloudWatch Logs insights queries are available to quickly identify error trends and assist RCA Lamda health and alerting processing mertics are visulaized in a CloudWatch dashboard. |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 07/Aug/25 2:30 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1137015 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4db73908 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2qr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-07 12:31 | [13 empty] | 07/Aug/25 2:30 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[^LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx] Have attached the lambda detailed sheet. | 25/Aug/25 2:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;the alarms have been created for lambda functions in flysaa-backend and they are created for â€œerrorâ€, â€œthrottleâ€, â€œdurationâ€ and the thresholds are 1, 1 and 30sec respectively. the alarms notifications are now being sent to respective sns topics created which shall in-turn appear into service now dashboard as soon as the threshold values are met. | 25/Aug/25 6:32 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 06:32
AM20-706 | ServiceNow Monitoring ¦¦ Prod Implementation | Done | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1673102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-20 21:39 | 2026-01-21 00:32 |  |  |  | 0 | As AWS solution architect, I would like to implement ServiceNow monitoring in prod environment so that alerts can be generated and reach to ServiceNow in form of Tickets for further actions. Acceptance Criteria: * Setup of ServiceNow integration to pull AWS receive data using EventBridge * Unautherized API calls from GuardDuty and Security Hub * Setup Cloudwatch alarms or rules for all the resources entitled to be monitored and send these to SNS topic * Create SNS topic * Configure SNS HTTPS configuration so that SNS can directly invoke HTTPS endpoints * AWS Lambda function created to forward SNS messages by parsing it and sends REST API requests to ServiceNow. * Attach the Lamda to the SNS topic * Set the credentials in AWS Secret Manager * Lamda function can reach the ServiceNow endpoint through API gateway by using HTTPS and Secure authentication |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;04/Jul/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cfb2e84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04h5f: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-26 06:17 | [13 empty] | 26/May/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 8:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting to get a exact tags to be passed to Ec2 instance to receive at service now. *New HTTPS endpoint will be shared by feroz for the production workloads.* | 25/Jun/25 8:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;From 24th June we had a call with feroz, where we expected to get the production servicenow endpoint by nest week to configure in SNS, hence waiting for same to start this user story. | 02/Jul/25 7:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PRODUCTION ServiceNow Instance: [https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws¦https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws] SNS topic is updated with a new subscription and backend prod integration is completed, unit test yet to start. | 04/Jul/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Right now the production environments like Backend, TM1, AirnavX accounts are integrated with the prod service now endpoint and SNS is configured to get the alerts. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-04 08:15
AM20-707 | Nexio AV ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 5 | 2025-05-12 | 2025-05-23 | Satya Varanasi | High | 1650865 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 19:53 | 2026-02-04 22:13 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5c904e9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akl: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 15:23 | [13 empty] | 20/May/25 5:23 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This Story dependency with comms implementation, the same with SAA team. Once SAA team actioned this story will be handled and closed until that this will not possible to address.(Note: it may move next sprint also) | 10/Jun/25 2:08 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0; No longer needed based on recent conversation. * Based on request from Sinjun, the migration approach for Trellix/NexioAV has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. Â | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-10 14:08
AM20-708 | Guardy duty and Guardrail implementation on Pegasys account | To Do | 0 | None( Backlog) |  |  |  | Medium | 1835991 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 20:45 | 2026-01-27 21:00 |  |  |  | 0 | [57 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@69378c41 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g000i | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-13 19:35
AM20-709 | Provisioning of EC2 via Terraform in Nexio AV account | Done | 4 | Sprint 9 | 2025-07-07 | 2025-07-18 | Yashwant Thakur | High | 1686366 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 12:40 | 2026-01-30 16:18 |  |  |  | 0 | As a AWS expert, I would expert, I would be able to provision EC2 instance in Nexio AV account using terraform code so that the AV can be installed by the respective application Admins Acceptance Criteria: * EC2 successfully gets provisioned in Nexio AV account by terraform code |  | Faisal Sayed | Satya Varanasi |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 08/Jul/25 8:55 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250708-065045.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1123568 | 08/Jul/25 8:55 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250708-065120.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1123569 | 08/Jul/25 8:55 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250708-065236.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1123567 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@621b3d4b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-03 13:53 | [13 empty] | 03/Jul/25 3:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Cloud watch agent installation is not automated via terraform, as we can see from the metrics. This action handled by Faisal so i am assigning this story to Faisal. | 04/Jul/25 12:19 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Implemented EC2 provisioning using Terraform with support for both Linux and Windows modules. Each module includes: * EC2 instance creation with the option for multiple encrypted EBS volumes. * Separate modules for Linux and Windows OS to allow tailored configurations. * Automated installation and configuration of SSM Agent and CloudWatch Agent. * Support for tagging across all provisioned resources. * IAM handling: ability to use an existing IAM instance profile or create a new one as needed, with optional support for custom IAM roles. The implementation ensures modularity, flexibility, and security compliance across environments. | 08/Jul/25 8:55 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to story things has been configured via terraform script. Tested instance storge and configured as encrypted volumes. !image-20250708-065236.png¦width=1309,height=628,alt="image-20250708-065236.png"! Cloud watch agent configured with memory and disk monitoring. !image-20250708-065045.png¦width=1300,height=608,alt="image-20250708-065045.png"! !image-20250708-065120.png¦width=1295,height=624,alt="image-20250708-065120.png"! | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-11 13:46
AM20-710 | Ingesting 500 of lines of inbound and outbound rules from excel to Terraform code for enablement | Done | 6 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1869689 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 17:14 | 2026-01-31 20:17 | 2025-12-14 17:51 | 2025-12-12 14:51 |  | 0 |  |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bae0685 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ocbn: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-05 06:26 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Dec/25 8:26 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script deployment. Currently we are adding the inbound and outbound rule with excel only. | 12/Dec/25 2:51 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approving provided we see workable solution during demo | [28 empty] | Done | 2025-12-12 14:51
AM20-711 | ServiceNow ¦¦ Logging and Monitoring | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651021 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 20:23 | 2026-01-30 21:55 |  |  |  | 0 | As an AWS expert, I want to monitor the health and logs of the Lamda connector function so that I can troubleshoot issues when alerts arenâ€™t processed properly Acceptance Criteria: * CloudWatch logs are enabled for Lambda * Metrics and dashboards are available for monitoring invocations, failures and response times. |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/May/25 9:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103910 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60acf139 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0285v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | [108 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 05:45 | [13 empty] | 02/May/25 7:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function to invoke the cloud watch is created and working as expected, Cloud watch dashboard for metrics will be created only after the workloads moved to cloud. service now monitoring can be in place only after successful integration with connector and service now PAAS endpoint. | 16/May/25 9:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have given demo with the email endpoints, waiting for the https endpoint to be received from SAA team to work with full functionality, | 22/May/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have received a endpoint today, yet to update SNS topic endpoint. https://sonicboom_em_saa_7161:wusEwo>G*Xmw@?XOA74\!pm0cx2.[4N;oFz<\!7vSE@liftdev.service-now.com/api/sn_em_connector/em/inbound_event?source=aws&sys_id=870cc1dfc3a5a6d04022f9777a013157 | 22/May/25 9:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 26/May/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 26/May/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;With respect to the endpoint have sent a mail to ashton, but there was response yet. awaiting on same. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. Â· | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 7:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Service now integration is completed with a new subscription HTTPS endpoint, have created a Cloud watch alarm for testing purpose which triggers a SNS as result service now dashboard receives a alert. | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-20 08:17
AM20-712 | Miscellaneous Cluster discovery | Done | 6 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1823345 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 16:16 | 2026-01-22 17:01 |  | 2025-11-14 11:13 |  | 0 | As Product and Application Architect I would like to analyse the Cabin crew application so that I can suggest the best possible way to modernize and migrate to AWS. Acceptance Criteria: * Application Overview and business context is captured ( Business criticality, use case, compliance and security needs, Pain point) * Current Architecture assessment ( Front end stack, Backend, integration, dabtabase, storage and compute requirements and assess modernize angles * Security and Governance - IAM and RBAC model, secret and configuration storage, certificate management, logging and audit requirements * Performance and Capacity utilization - CPU, memory and disk usage, scalability needs, Latency and throughput requirements are gathered * Dependency and integration landscape captured * Cost and Licensing requirements clarified (current cost of application, licenses etc.) * Modernization readiness documented * Modernization strategy proposed successfully * Operational readiness documented |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Had workshop with Gayaz and Donald to understand the requirements.;14/Nov/25 8:14 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | Analyzed requirements further.;14/Nov/25 8:15 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Prepared SOW draft;14/Nov/25 8:15 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | Amended SOW as per inputs from internal review and shared with Gayaz.;14/Nov/25 8:16 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 |  |  | 86400 | 7200 | 79200 | 0.91 | 86400 | 7200 | 79200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@27e6cfb4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ljt7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 12:29 | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 2:29 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;# New version of Lounge Tracker application has been under development which consists of a Frontend and a backend microservice component. The backend component will be connecting with 3rd party interfaces like (Discovery Bank, DragonPass etc.) for validations. The ask is to deploy a 'Miscellaneous' cluster which would be capable of hosting diverse set of application microservices with ease. # Focus needs to be on reliability, scalability, and security along with ease of use for this new cluster. # Following two additional projects are in pipeline and business discussions are underway: ## Middleware (Java based microservice which will act as a layer between Amadeus. More clarity is expected by Dec-25) ## Cabin Crew (Project in pipeline) # Â Separate workshops and solutioning will be done for this once business alignment is completed and requirements are finalized. # *Action* â€“ VOIS to share the updated scope of work document for the miscellaneous cluster and related deployments for Gayazâ€™s sign off. | 10/Nov/25 8:16 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Draft SOW document has been prepared. To be reviewed internally. | 13/Nov/25 8:14 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SOW document has been reviewed internally and shared with Gayaz and Vodacom both. | 14/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Followed up with Donald to confirm if there is any new update regarding requirements. There is none. We have already shared an SOW based on current understanding. Activity is completed for now. | 14/Nov/25 11:13 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-14 11:13
AM20-713 | PROS ¦¦ Application monitoring and Alerting | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1811843 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 19:25 | 2026-01-14 21:54 |  | 2025-11-12 08:24 |  | 0 | AS Product owner I would like to configure alerting and monitoring for application specific alerts. Acceptance Criteria: Health/ready endpoints: health (basic)/ ready (deps checked) *Alerts*: non-2XX or latency > P95 target for 3-5 mins Startup time and failures: boot duration count of failed boots *Alerts*: boot>5sec or > 1 failed start in 15 mins Unhandled exceptions: total and by class module *Alerts*: error rate > 2% of requests for 5 mins Log anomaly rate: ERROR/WARN per minute vs baseline *Alert*: Spike above learned baseline Critical transaction success rate ( e.g login) *Alert*: Success<98% of 10 mins |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;31/Oct/25 11:27 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [9 empty] | AM20-208 |  |  | 31/Oct/25 11:27 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;RE_ Informatica & PROS __ Application monitoring.eml;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175947 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4d798cc9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v079 | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_72739_*¦*_10041_*:*_1_*:*_1297682389_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_72739_*¦*_10041_*:*_1_*:*_1297682389_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_72739_*¦*_10041_*:*_1_*:*_1297682389_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_72739_*¦*_10041_*:*_1_*:*_1297682389_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-31 09:27 | 3_*:*_1_*:*_72739_*¦*_10041_*:*_1_*:*_1297682389_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 31/Oct/25 11:27 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Attaching email where we have got email confirmation, that the alarms and monitoring is not needed since the client already have it in place. Hence, closing the story with this comment and also attaching the email for reference. | 31/Oct/25 11:27 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^RE_ Informatica & PROS __ Application monitoring.eml] | 12/Nov/25 8:24 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-12 08:24
AM20-714 | ServiceNow ¦¦ Logging and Monitoring | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651021 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 15:02 | 2026-01-14 16:22 |  |  |  | 0 | As an AWS expert, I want to monitor the health and logs of the Lamda connector function so that I can troubleshoot issues when alerts arenâ€™t processed properly Acceptance Criteria: * CloudWatch logs are enabled for Lambda * Metrics and dashboards are available for monitoring invocations, failures and response times. |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/May/25 9:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103910 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60acf139 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0285v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | [108 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 05:45 | [13 empty] | 02/May/25 7:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function to invoke the cloud watch is created and working as expected, Cloud watch dashboard for metrics will be created only after the workloads moved to cloud. service now monitoring can be in place only after successful integration with connector and service now PAAS endpoint. | 16/May/25 9:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have given demo with the email endpoints, waiting for the https endpoint to be received from SAA team to work with full functionality, | 22/May/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have received a endpoint today, yet to update SNS topic endpoint. https://sonicboom_em_saa_7161:wusEwo>G*Xmw@?XOA74\!pm0cx2.[4N;oFz<\!7vSE@liftdev.service-now.com/api/sn_em_connector/em/inbound_event?source=aws&sys_id=870cc1dfc3a5a6d04022f9777a013157 | 22/May/25 9:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 26/May/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 26/May/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;With respect to the endpoint have sent a mail to ashton, but there was response yet. awaiting on same. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. Â· | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 7:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Service now integration is completed with a new subscription HTTPS endpoint, have created a Cloud watch alarm for testing purpose which triggers a SNS as result service now dashboard receives a alert. | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-20 08:17
AM20-715 | Backup Server ¦¦ Security compliance implementation | Done | 3 | Sprint 7 | 2025-06-09 | 2025-06-20 | Aravind Raj | Medium | 1681806 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 21:35 | 2026-01-21 23:40 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Backup Server *Acceptance Criteria*: * Renaming of PROS account to Back-Up Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 14400 | 43200 | 1 | 43200 | 14400 | 43200 | [12 empty] | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250612-153959.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1113715 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@48024563 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-09 05:41 | [13 empty] | 09/Jun/25 7:41 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will start working on enabling security frameworks like CIS, NIST, AWS FSBP. | 10/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled controls, will be working on the controls remediation. | 11/Jun/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;controls are implemented waiting for the security score to be update Â· | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CIS, NIST and FSBP controls were enabled and required controls remediated. !image-20250612-153959.png¦width=1279,height=626,alt="image-20250612-153959.png"! | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-12 17:41
AM20-716 | Security compliance actionpoint | To Do | 0 | None( Backlog) |  |  | Aravind Raj | Medium | 1868968 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 19:46 | 2026-01-27 20:36 | 2025-12-12 08:19 |  |  | 0 | As Product owner for Cloud Platform I would like to ensure that we are compliant with 98% from Infra Security perspective | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ee9de6f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001v | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-28 08:52
AM20-717 | Provision AWS GuardDuty using Terraform | Done | 10 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718154 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 14:02 | 2026-01-30 16:46 |  |  |  | 0 | As a cloud security engineer I want to provision and configure AWS GuardDuty using Terraform so that I can automatically detect and respond to potential threats in my AWS environment in a consistent and repeatable manner Acceptance Criteria: * Terraform must create a GuardDuty Detector in the primary AWS region. the detector must be enabled * for multiple AWS accounts Terraform must support creating a GuardDuty master-member relationship * Members must be invited and accepted automatically * GuardDuty should automatically published findings to the console API and this must not be disabled * Terraform must be modular to support enabling GuardDuty in any account and region * inputs like region, accountid, and enable flag must be configurable * All resources created via Terraform must include project defined tags * Forward GuardDuty findings to AWS security Hub or EventBridge |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@50808e38 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ansn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-22 06:28 | [13 empty] | 22/Jul/25 8:28 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Email sent to Ismaail and leigh about Request to Enable Centralized Management for GuardDuty and Amazon Inspector and currently I am working on Terrafrom script to create the base module for resources. | 23/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Leigh replied and asked to Ismaail for assisting. | 25/Jul/25 8:33 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;It will be spillover because there was a dependency on Ismail and he has updated on 23 July Only so thatâ€™s why I am not able to complete it on time. | 30/Jul/25 8:26 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script. Ready for the demo. | 11/Aug/25 4:30 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:30
AM20-718 | MQ¦¦ Migration Agent comms Metrics implementation | Blocked | 2 | Sprint 16 | 2025-10-13 | 2025-10-24 | Satya Varanasi | Medium | 1794120 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 19:16 | 2026-01-16 22:47 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@692cf397 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g9 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-17 09:19 | [13 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | [29 empty] | To Do | 2025-09-30 10:14
AM20-719 | TM1 ¦¦ Integration of AWS IAM roles with TM1 AWS Account Instance using JSON | Done | 10 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642068 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 17:14 | 2026-02-04 18:38 |  |  |  | 0 | As AWS expert, I would be integrating AWS IAM roles with TM1 Instance Acceptance criteria: * IAM roles are created successfully * Integration of defined IAM roles with TM1 instance so that user is able to access the TM1 instance. |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5190a6ea | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-09 07:30 | [13 empty] | 09/Jul/25 9:29 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Following are the details of the role created: role_arn = "arn:aws:iam::209479274829:role/TM1-IAMRole-EC2InstanceProfile" role_name = "TM1-IAMRole-EC2InstanceProfile" Account details: 209479274829 (SAA-TM1) Custom Role Details: The role covers the equivalent of â€œAmazonSSMManagedInstanceCoreâ€, basic CloudWatch Agent permissions, and general S3 access. _*NOTE*: THE FOLLOWING HAS BEEN ACHIEVED USING TERRAFORM._ | 09/Jul/25 9:30 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;.json file of the custom role is as follows: { Â "Version": "2012-10-17", Â "Statement": [ Â Â { Â Â Â "Sid": "SSMManagedInstanceCorePermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssm:DescribeAssociation", Â Â Â Â "ssm:GetDeployablePatchSnapshotForInstance", Â Â Â Â "ssm:GetDocument", Â Â Â Â "ssm:DescribeDocument", Â Â Â Â "ssm:GetManifest", Â Â Â Â "ssm:GetParameter", Â Â Â Â "ssm:GetParameters", Â Â Â Â "ssm:ListAssociations", Â Â Â Â "ssm:ListInstanceAssociations", Â Â Â Â "ssm:PutInventory", Â Â Â Â "ssm:PutComplianceItems", Â Â Â Â "ssm:PutConfigurePackageResult", Â Â Â Â "ssm:UpdateAssociationStatus", Â Â Â Â "ssm:UpdateInstanceAssociationStatus", Â Â Â Â "ssm:UpdateInstanceInformation" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "SSMMessageGatewayPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssmmessages:CreateControlChannel", Â Â Â Â "ssmmessages:CreateDataChannel", Â Â Â Â "ssmmessages:OpenControlChannel", Â Â Â Â "ssmmessages:OpenDataChannel" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "EC2MessagesPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ec2messages:AcknowledgeMessage", Â Â Â Â "ec2messages:DeleteMessage", Â Â Â Â "ec2messages:FailMessage", Â Â Â Â "ec2messages:GetEndpoint", Â Â Â Â "ec2messages:GetMessages", Â Â Â Â "ec2messages:SendReply" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "CloudWatchAgentPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "logs:CreateLogGroup", Â Â Â Â "logs:CreateLogStream", Â Â Â Â "logs:PutLogEvents", Â Â Â Â "logs:DescribeLogGroups", Â Â Â Â "logs:DescribeLogStreams", Â Â Â Â "cloudwatch:PutMetricData" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "S3AccessPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "s3:GetObject", Â Â Â Â "s3:PutObject", Â Â Â Â "s3:ListBucket" Â Â Â ], Â Â Â "Resource": "*" Â Â } Â ] } | 11/Jul/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed IAM roles is having required permissions | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-720 | Ec2 Cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818694 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-04 16:39 | 2026-02-04 17:37 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4bebd3dc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzvn: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 2:28 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Sanjot has cleaned up 2 ec2 instance from backend dev. | [26 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-10-28 14:27
AM20-721 | PROS ¦¦ Back-UP using Terraform | Done | 4 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | High | 1660115 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-10 15:41 | 2026-01-10 17:11 |  | 2025-10-31 09:32 |  | 0 | As AWS expert, I would like to provision backup using terraform * Incremental back up(daily back) * Full backup (Weekly) *Acceptance Criteria* : * The Life cycle manager has two schedule (Incremental and Full backup) successfully implemented * Back up must be automated using native AWS features and tools * Point-in-time recovery for database must be enabled to allow recovery to any second within retention window * Define retention policy and enforce retention ( 7 days, 35 days, monthly snapshot for 1 year) * Automatically transition of old backups to cold storage * Use AWS backup vault lock for Write once and Read many compliance * Backup must be encrypted at rest and in transit * Restore process is well documented and well tested * After restore data integrity checks and application consistency should be validated * Use AWS backup for central management of backup policies and vaults * Automate backup selection using resource tags * Backups must meet regulatory compliance like GDPR,HIPAA * and Audit trail of backup creation, deletion and restore events must be maintained * Periodic restore testing must be conducted and logged to validate data integrity * *AWS part:* * Use AWS config rules to enforce mandatory backup configurations * Use Cloudwatch to success/failure backups * Setup alerts for backup failure or missed backups via SNS * IAM Policies for access control to restrict who can create, view, delete and restore backups * All backup and restore operations must be logged in AWS Cloudtrail for traceability |  | Harsh Chandra | Onkar Mirajkar | Sanket Kale | Satya Varanasi | Yashwant Thakur |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;AM20-99_attachments.zip;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175550 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133603.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175548 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133705.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175552 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175549 | 30/Oct/25 3:47 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133947.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175551 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@558af396 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v9 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 15 | Sprint 16 | Sprint 17 | [93 empty] | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 |  | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | [65 empty] | YES | YES | 2025-05-29 08:54 | 10060_*:*_2_*:*_805556_*¦*_3_*:*_3_*:*_634223687_*¦*_10041_*:*_3_*:*_2241190792_*¦*_13940_*:*_2_*:*_212317_*¦*_10024_*:*_3_*:*_12955621982 | [12 empty] | 29/May/25 10:53 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;To be checked with Utkarsh and Satyabrata for terraform automation | 04/Jun/25 8:10 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;h6. TM1 ¦¦ Back-UP Backups will performed via DLM | 11/Jun/25 8:36 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;This is blocked due to Arvind Story as its not migrated | 25/Sep/25 9:28 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;currently working on wrapper module | 30/Sep/25 7:59 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;As per discuss with Aravind the server is not spined up as of now. | 30/Oct/25 3:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Validated and configured fine. PROS and informatica PROD servers backups has been configured and running fine. Daily backup with 7 days retention and weekly backup with 90 days retention. [^AM20-99_attachments.zip] !image-20251030-133705.png¦width=597,alt="image-20251030-133705.png"! !image-20251030-133947.png¦width=597,alt="image-20251030-133947.png"! !image-20251030-133909.png¦width=597,alt="image-20251030-133909.png"! !image-20251030-133603.png¦width=597,alt="image-20251030-133603.png"! | 31/Oct/25 9:32 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved as Backup is implemented successfully for PROS | [20 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-31 09:32
AM20-722 | Nexio AV ¦¦ establish internet connectivity via TGW | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650868 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 21:07 | 2026-01-29 22:43 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Harsh Chandra | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  | ;02/May/25 12:35 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;14400 | [5 empty] | 14400 | 0 | 14400 | 1 | 14400 | 0 | 14400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1e57c316 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:x | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:43 | [13 empty] | 29/Apr/25 7:43 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;internet connectivity has ben setup, sending for review | 02/May/25 12:37 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Tested through SSM {quote}Ping to 8.8.8.8 working Tracert to 8.8.8.8 working{quote} Forwarding for PO Approval | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:38
AM20-723 | IAM roles need to created based on LLD. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Satya Varanasi | Medium | 1832050 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Satya Varanasi | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Satya Varanasi | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 2026-01-09 21:02 | 2026-01-09 23:34 |  |  |  | 0 | IAM roles need to be created. Â·Â Â Â Â Â Â Â IAM-based access with predefined roles: oÂ Â *DNSAdmin*Â â€“ Full Route 53 management. oÂ Â *DNSOperator*Â â€“ Modify records, no zone deletions. oÂ Â *DNSViewer*Â â€“ Read-only access. |  | Faisal Sayed | Satya Varanasi |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 |  |  |  |  | ;12/Nov/25 10:19 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fec0f31 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mkiz: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:41 | [13 empty] | 12/Nov/25 6:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Update* * Permission policies for *DNS Admin*, *DNS Operator*, and *DNS Viewer* have been configured. * These will be implemented in the *Management Account (ID: 195973603339)* after approval from *Staya Sir*. h3. *Next Steps* * Schedule a call with *Staya Sir* to review and obtain approval for policy implementation. * Post-approval, apply the policies in the Management Account and validate access controls. | 12/Nov/25 10:19 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Call has been scheduled and IAM roles have been successfully created. Moving the item to *Staya Sirâ€™s review bucket* and updating the status to *In Review*. | 14/Nov/25 8:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Roles has been created according to LLD on main account. | [24 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-14 08:10
AM20-724 | Informatica Server - Dev ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1749537 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 14:23 | 2026-02-05 17:08 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 57600 |  | 0 | 86400 | 57600 | [9 empty] | AM20-145 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b90196e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0datf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 14:28 | [13 empty] | 18/Aug/25 4:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev MGN template has been configured, now we are looking AWS migration agent installation on server for sync, Sinjun going to take care tomorrow for the same i have scheduled the call. | 19/Aug/25 5:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;While checking AWS agent connectivity not working, checking with network team for further troubleshooting/fixing the issue. CSOC request has-been createdâ€CINC0909706â€ | 25/Aug/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network routing not implemented, currently it under approval process. | 26/Aug/25 1:11 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Firewall rules implemented. # Configured MGN agent setup on AWS for dev server migration. # Identified as connectivity not working. # Initiated network troubleshooting call towards fixing. # Identified as routing not configured. # Requested LIFT for approval # LIFT approval took 3days # Monday CSOC request raised and routing has ben implemented. # Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 29/Aug/25 8:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev agent installation and Test instance setup has been complted. | 01/Sep/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The test instance connectivity has been completed. Communicated to Peter for connectivity testing. The ip address is: 10.42.0.46. Sending this request for closing. | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-725 | flysaa Backend - Application alerting | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820107 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 15:04 | 2026-01-23 18:30 |  | 2025-11-14 11:07 |  | 0 | As devops expert I would like to configure application error from workloads running on our EKS cluster to be collected, classified and alerted via cloudwatch so that appropriate alert is passed to Servicenow via SNS/lamda function or Event bridge. Acceptance Criteria: * All the application specific errors are captured for alerting successfully * The alerts are being sent to ServiceNow with agreed format |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Deployed error Alarms to backend production account for fabric and amadeus.;14/Nov/25 8:17 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fd7ba2e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07d | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:39 | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Had a Discussion with Yashwant, will be reaching out to Hoosen for creating a request to deploy alarms to production. | 11/Nov/25 8:26 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Hoosen has created a change request for deploying the alarms, will be working on it when we get the timeslot allocated to deploy in production since we are not deploying alarms on backend dev and preprod. | 14/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed alarms on Production EKS Cluster. | 14/Nov/25 11:07 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-14 11:07
AM20-726 | MQ ¦¦ Monitoring and Alert Solution | Blocked | 4 | None( Backlog) |  |  | Diksha Koul | Medium | 1794147 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 16:13 | 2026-01-09 19:05 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if MQ server is stopped |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c39a10 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-02 17:42 | [13 empty] | 02/Nov/25 7:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over* : After creation of the MQ EC2 instance we can start the creation of MQ monitoring and alerting solution. | [29 empty] | To Do | 2025-09-30 10:17
AM20-727 | Route53 ¦¦ Post Cutover validation and Support for Airchef | Done | 0 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865870 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 16:01 | 2026-01-13 18:45 | 2025-12-14 18:50 | 2025-12-12 11:18 |  | 0 | As Product owner I wish to validate the behaviour of Airchef so that we can assure that the Airchef is working as expected and change caused by AWS does not create any issues. Acceptance Criteria: Airchef BAU is working as expected and the traffic is directed via AWS route53 |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@50f9cacc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7nf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-04 06:32 | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 04/Dec/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Original [airchefs.co.za¦http://airchefs.co.za] migration completed still on-prem to VDC cutover need to be implemented. | 05/Dec/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;On prem to VDC cutover has been completed and tested by SITA team, According to Hoosen Tlou <[hoosentlou@flysaa.com¦mailto:hoosentlou@flysaa.com]> current Airchefs servers are shutdown and decommissioned. Notified to team don't go for decom but Denise notified to go for decom. | 12/Dec/25 11:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-12-12 11:18
AM20-728 | (Airchef)Terraform Implementation for Creation of Route 53 Hosted Zones & Records. | In Progress |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Sanket Kale | Medium | 1827709 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-02-05 12:40 | 2026-02-05 14:21 |  |  |  | 0 | *Acceptance Criteria:* * *Deploy Public Hosted Zone* Use Terraform to provision a *Route 53 public hosted zone* for the domain [*airchef.co.za*¦http://airchef.co.za]. * *Manage DNS Records via Terraform* Implement Terraform configurations to create and manage various DNS record types (A, CNAME, MX, TXT, etc.) within the hosted zone. |  | Faisal Sayed | Sanket Kale | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [20 empty] | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28df5c12 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1vn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-07 05:56 | [13 empty] | 07/Nov/25 7:56 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Code review completed from my side its working. Created and deployed the base and component modules. | 10/Nov/25 9:07 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and tested on Sandbox environment | 14/Nov/25 4:01 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code deployment done sandbox and same tested. | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | In Progress | 2025-11-20 08:59
AM20-729 | Monitor health and logs of Lamda connector function to troubleshoot issue , if alerts in not processed | Done | 8 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747507 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 15:02 | 2026-02-06 15:08 |  |  |  | 0 | As Product owner I want to monitor health and logs of Lamda connector function so that I can troubleshoot issues quickly when alerts are not processed and ensure reliability of the alerting pipeline Acceptance Criteria: CloudWatch logs are enabled for the Lamda connector function to capture execution details, input events and error messages Cloudwatch Metrices (invocations, errors, throttles, duration) are available for function and updated in real time cloudwatch alarms are configured for * Errors >0 in last 5 minues * Throttles >0 * Duration exceeds timeout threshold A SNS is configured to capture failed Lamda execution Alerts from cloud watch are sent via SNS to notify ServiceNow CloudWatch Logs insights queries are available to quickly identify error trends and assist RCA Lamda health and alerting processing mertics are visulaized in a CloudWatch dashboard. |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 07/Aug/25 2:30 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1137015 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4db73908 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2qr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-07 12:31 | [13 empty] | 07/Aug/25 2:30 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[^LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx] Have attached the lambda detailed sheet. | 25/Aug/25 2:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;the alarms have been created for lambda functions in flysaa-backend and they are created for â€œerrorâ€, â€œthrottleâ€, â€œdurationâ€ and the thresholds are 1, 1 and 30sec respectively. the alarms notifications are now being sent to respective sns topics created which shall in-turn appear into service now dashboard as soon as the threshold values are met. | 25/Aug/25 6:32 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 06:32
AM20-730 | Informatica Server - Dev ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1749537 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 16:46 | 2026-01-24 20:35 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 57600 |  | 0 | 86400 | 57600 | [9 empty] | AM20-145 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b90196e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0datf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 14:28 | [13 empty] | 18/Aug/25 4:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev MGN template has been configured, now we are looking AWS migration agent installation on server for sync, Sinjun going to take care tomorrow for the same i have scheduled the call. | 19/Aug/25 5:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;While checking AWS agent connectivity not working, checking with network team for further troubleshooting/fixing the issue. CSOC request has-been createdâ€CINC0909706â€ | 25/Aug/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network routing not implemented, currently it under approval process. | 26/Aug/25 1:11 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Firewall rules implemented. # Configured MGN agent setup on AWS for dev server migration. # Identified as connectivity not working. # Initiated network troubleshooting call towards fixing. # Identified as routing not configured. # Requested LIFT for approval # LIFT approval took 3days # Monday CSOC request raised and routing has ben implemented. # Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 29/Aug/25 8:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev agent installation and Test instance setup has been complted. | 01/Sep/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The test instance connectivity has been completed. Communicated to Peter for connectivity testing. The ip address is: 10.42.0.46. Sending this request for closing. | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-731 | Import & Manage DNS Records via Terraform | Done | 8 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824829 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 15:02 | 2026-01-27 15:39 |  | 2025-11-15 14:39 |  | 0 | As a Cloud Platform Engineer I want Terraform code that models existing Route 53 records (and creates new ones) using aws_route53_record so that all DNS changes are version-controlled, peer-reviewed, and reproducible. *In Scope* * Â Public & private hosted zones (given zone_id) * Â Record types: A/AAAA, CNAME, TXT, MX, SRV, NS (delegations), PTR, and Alias (ALB/NLB/CloudFront/S3) * Â Routing policies: Simple, Weighted, Latency, Failover, Multi-Value * Â Health checks (referenced by record) * Â Import of existing records into state (terraform import) with code generation scaffolding * Â Bulk records via for_each maps Acceptance Criteria: # *Module Interface* Given a module input records (map of objects) and zone_id When I apply the module Then it renders one aws_route53_record per map item with correct name, type, ttl/alias, routing policy, and (optional) health check. # *Create New Records* Â Given a new item in records ( [Airchefs.co.za¦http://Airchefs.co.za] â†’ A â†’ ALB alias) *OR* ([flysaa.com¦http://flysaa.com] â†’ A â†’ ALB alias) When I run terraform apply Then the record is created and resolves via dig/nslookup with the expected value and TTL. # *Import Existing Records (Single)* Â Given an existing record set in the hosted zone Â When I run terraform import 'module.dns.aws_route53_record.this["[api.¦https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2Fapi.dev.example.com%2F&data=05%7C02%7Cyashwant.thakur02%40vodafone.com%7C17d1c2e405554efe772908de187c51d4%7C68283f3b84874c86adb3a5228f18b893%7C0%7C0%7C638975119406199329%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=oRvm%2FU%2BWpaEnyS1rnSXR%2FX7cSrnvEtIDK2FabJQqYiY%3D&reserved=0][Airchefs.co.za¦http://Airchefs.co.za] â†’ A â†’ ALB alias)¦A¦simple"]' '<zone_id>_<fqdn>_<type>' *OR* Â When I run terraform import 'module.dns.aws_route53_record.this["[flysaa.com¦http://flysaa.com] â†’ A â†’ ALB alias)¦A¦simple"]' '<zone_id>_<fqdn>_<type>' Â Then the resource is tracked in state and a subsequent plan is a no-op (no drift), provided the HCL matches.Â # *Import Existing Records (Bulk)* Â Given a CSV/JSON export of Route 53 record sets Â When I use the supplied mapping template to populate records and run the generated terraform import commands Â Then all imported records show as no changes on plan.Â # *Routing Policies* Â Weighted: Given two records with the same name/type and different set_identifier & weight When applied Then both weighted records are present and traffic splits per weight. Â Latency/Failover/Multi-Value: Similar acceptance via identifiers/actions; health checks wired for Failover and Multi-Value.Â # *TXT & Special Cases* Â Given a TXT record requiring quotes/escaping (SPF/Google site-verification) Â When applied Â Then the exact string appears in DNS (including spaces/quotes) and validation passes.Â # *Alias Targets* Â Given alias to ALB/NLB/CloudFront/S3 Website Â When applied Â Then target name and zone_id are set correctly and record resolves (no TTL required).Â # *Private Zones* Â Given zone_id for a private hosted zone Â When I create/import records Â Then theyâ€™re only resolvable from associated VPCs.Â # *Guardrails* Â Given prevent_destroy = true at module level (lifecycle) Â When a record is removed from input Â Then destroy is blocked with a clear message unless allow_destroy=true. |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4668ef43 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lps7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_343117453_*¦*_10041_*:*_1_*:*_885693461_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_343117453_*¦*_10041_*:*_1_*:*_885693461_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_343117453_*¦*_10041_*:*_1_*:*_885693461_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_343117453_*¦*_10041_*:*_1_*:*_885693461_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 19:11 | 10060_*:*_1_*:*_343117453_*¦*_10041_*:*_1_*:*_885693461_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 31/Oct/25 3:20 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Hi [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] , Please review this user story, I created this based on your LLD instruction. Please check if acceptance criteria needs alteration and make changes | 10/Nov/25 9:11 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and deployed on Sandbox environment | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-15 14:39
AM20-732 | Servicenow Payload severity updates for Lambda alarms | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Shreyash Talwekar | Medium | 1835024 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-12 13:12 | 2026-01-12 17:09 |  |  |  | 0 | Enhance the existing Lambda function that triggers when Lambda alarms enter an alarm state. Currently, the function gathers alarm-related metrics, collects function details, and sends an approved payload to ServiceNow. However, severity information from the alarm is not included in the payload. This story addresses that gap by updating the Lambda function to capture and transmit the correct severity level from the alarm to ServiceNow. *Acceptance Criteria:* * Lambda function must include severity details from the alarm in the payload. * Payload sent to ServiceNow should accurately reflect the alarm severity. |  | Faisal Sayed | Harsh Chandra | Shreyash Talwekar |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  | ;20/Nov/25 8:33 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;14400 | [6 empty] | 0 | 14400 |  |  | 0 | 14400 | [12 empty] | 21/Nov/25 7:04 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251121-050425.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187511 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@560f4ab3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxar: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 05:33 | [13 empty] | 20/Nov/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Requirements have been gathered. Lambda function code will be reconfigured to incorporate changes, followed by payload testing. Ticket will be updated upon successful completion of testing. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Lambda function has been updated per requirements to capture severity. A test event was executed to validate behavior and output; results are attached. Test outcome is successful, and the implementation is complete. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251121-050425.png¦width=555,alt="image-20251121-050425.png"! | 24/Nov/25 8:42 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reviewed output, LGTM. | [23 empty] | 1832856 | AM20-264 | Update ServiceNow Payloads with severity | Done | 2025-11-24 08:41
AM20-733 | Monitor and Alert on daily Cloudwatch log costs | Done |  | Sprint 14 | 2025-09-15 | 2025-09-26 | Aravind Raj | Medium | 1781403 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 17:49 | 2026-01-11 21:18 |  |  |  | 0 | As a clous infrastructure product owner I want to assess the daily CloudWatch logs costs and trigger an alarm if cost exceeds defined threshold so that I can detect excessive log injestion/retention and take timely action to optimize costs Use SAA-Audit account, account id : 300204747992 for implementation Acceptance Criteria: # *Daily Cost Assessment* System must fetch daily CloudWatch cost usage ( log storage + injestion + insight queries) from AWS cost explorer or Cloud watch Metrices Must provide breakdown by account and log group # *Threshold Configuration* Ability to set daily cost thresholds Alarm must be raised if daily costs exceed threshold # *Alerting Mechanism* Alerts should be sent via SNS->integrated notification channels (Email/ServiceNow) Alarm must be included impacted account, service (CloudWatch Logs) cost for the day and % deviation from baseline # *Historical Trend* Dashboard view showing last 7/30 days of CloudWatch daily cost trends Helps identify if cost spike in an anamaly or a graduate increase # *Operational Validations* Test run with synthetic high volume logging to validate alarm triggers Verify no false positives when daily costs are with threshold |  | Aravind Raj | Onkar Mirajkar | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fad0cf8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0gp97: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-17 05:55 | [13 empty] | 17/Sep/25 7:55 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Threshold Configuration -----Done Ability to set daily cost thresholds Alarm must be raised if daily costs exceed threshold Alerting Mechanism ----Done IF cost usage is above 2$ email will be trigeered | 17/Sep/25 7:56 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Dashboard view is pending | 19/Sep/25 8:18 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Dashboard is created and demo given to Yashwant. | 22/Sep/25 8:46 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have seen a short demo on friday itself, the dashboard and notification looks fine. | [23 empty] | 1772224 | AM20-164 | AirNavX ¦¦ Budget Management Configuration | Done | 2025-09-22 08:46
AM20-734 | NexioAV (Trellix) ¦¦ DR | Done | 5 | Sprint 9 | 2025-07-07 | 2025-07-18 | Yashwant Thakur | High | 1699562 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 14:35 | 2026-01-25 17:17 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Trellix-application.awsflysaa.com¦http://TM1-application.awsflysaa.com] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [13 empty] | 24/Jul/25 11:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250724-091921.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1130283 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4121fe0a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i08p7v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 10 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-08 06:08 | [13 empty] | 08/Jul/25 8:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Setting up Trellix server with AWS DR service is in progress, upon successful installation of software will initiate a replication and complete the setup. | 09/Jul/25 7:32 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;DR setup is completed followed by initial replication, upon software installation we will start replication again and perform failover and failback upon requirement. | 09/Jul/25 7:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Moving to blocked as sinjun yet to install the software. | 17/Jul/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Agent installation is completed, TM1 and frontend prod server are added for testing. | 17/Jul/25 8:09 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;will coordinate with the application owner and initiate a replication back. | 21/Jul/25 7:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Failover and Failback will be performed after getting formal approval from the application owner. | 21/Jul/25 7:04 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;replication is initialized upon bhavish confirmation. | 24/Jul/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have scheduled a call with sinjun today 1.30PM, will perform DR drill and close this userstory. | 24/Jul/25 11:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250724-091921.png¦width=682,height=443,alt="image-20250724-091921.png"! | 25/Jul/25 7:48 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [17 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-07-25 19:48
AM20-735 | Airnavx budget update | Done | 2 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834954 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 19:16 | 2026-01-25 22:01 | 2025-11-21 08:29 | 2025-11-27 09:17 |  | 0 | I would like to update budget of airnavx as per the revised LLD since the configuration of EC2 were change and budget should reflect the cost accordingly |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;20/Nov/25 8:19 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;36600 | [5 empty] | 28800 | 0 | 36600 | 1.27 | 28800 | 0 | 36600 | [12 empty] | 19/Nov/25 8:44 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251119-064353.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186120 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5ed5a68d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mwyr: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:49 | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:49 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will check the updated LLD document and will update the new pricing as per the updated one. | 19/Nov/25 8:44 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the Updated LLD v1.4 and updated the pricing in the management payers account as per the new LLD. !image-20251119-064353.png¦width=629,alt="image-20251119-064353.png"! same has been implemented in the budget account. | 27/Nov/25 9:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:17
AM20-736 | BackUP Server ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | Medium | 1681815 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 14:00 | 2026-01-20 15:21 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across BackUP server account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43003ef3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4f: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-05 06:17 | [13 empty] | 05/Jun/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Config and guard Duty is enabled and configured. Cloud Trails logging is enabled already. | 06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard rail implementation is applied for the S3 block public access | 13/Jun/25 2:36 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:36
AM20-737 | Nexio AV ¦¦ establish internet connectivity via TGW | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650868 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 17:17 | 2026-02-05 19:17 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Harsh Chandra | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  | ;02/May/25 12:35 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;14400 | [5 empty] | 14400 | 0 | 14400 | 1 | 14400 | 0 | 14400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1e57c316 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:x | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:43 | [13 empty] | 29/Apr/25 7:43 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;internet connectivity has ben setup, sending for review | 02/May/25 12:37 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Tested through SSM {quote}Ping to 8.8.8.8 working Tracert to 8.8.8.8 working{quote} Forwarding for PO Approval | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:38
AM20-738 | Trellix integration with AirnavX | Done | 1 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 17:08 | 2026-02-06 19:46 |  | 2025-11-12 08:22 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan AirNavX workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in AirNavX server * Trellix is able to access AirnavX account successfully and perform scanning |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 05/Nov/25 3:41 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ Trellix scanning status for New AWS AirNavV servers.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1178115 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f4c84b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 18 | [95 empty] | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [65 empty] | YES | YES | 2025-09-08 07:56 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [12 empty] | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 30/Sep/25 7:40 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working with Sinjun for trellix installation on these 2 servers. | 06/Oct/25 8:39 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Working with Sinjun for Trellix installation, hence will be spilled over | 09/Oct/25 4:29 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Sinjun Albert is going to install Trellix and he will confirm once integration done. | 17/Oct/25 11:17 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over reason - Blocked due to ongoing app installation issues, currently worked upon by app owner; post which this story will be progressed in subsequent sprint | 05/Nov/25 3:41 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Trellix software installed on New AWS AirNavX servers. All AirNavX servers able to discover from Trellix admin server and same has been confirmed by Sinjun. Attaching reference for support. [^RE_ Trellix scanning status for New AWS AirNavV servers.msg] | 12/Nov/25 8:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | Done | 2025-11-12 08:22
AM20-739 | Informatica ¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1755978 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 13:34 | 2026-01-22 16:08 |  |  |  | 0 |  |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3237a818 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0e0or: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-26 11:39 | [13 empty] | 26/Aug/25 1:39 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Firewall rules implemented. Identified as connectivity not working. Initiated network troubleshooting call towards fixing. Identified as routing not configured. Requested LIFT for approval LIFT approval took 3days Monday CSOC request raised and routing has ben implemented. Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 28/Aug/25 8:18 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested connectivity from informatica Prod/Dev env. Initially Network team not configured Routing after new Lift and CSOC request issue got resolved. Reference Lift & CSOC details: Routing: # CSOC:CHR0026807 # LIFT:CHG0067489 App comms: # LiFT = CHG0067488 # CSOC = CHR0026691 AWS agent Comms: CSOC logged CHR0023951 LiFT logged CHG0066992 (RITM0051174) | 01/Sep/25 8:03 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested. Based on comms we have successfully completed agent installation for prod/Dev and setup test instance for the same. Hence sending request for closer. | 03/Sep/25 8:55 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-740 | TM1 ¦¦ Configuring Application specific error in Cloudwatch for alerting | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730283 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 12:36 | 2026-01-29 14:23 |  |  |  | 0 | As a AWS expert I want to detect application specific error patterns in CloudWatch logs so that I can generate alerts for ServiceNow ticket creation and respond to runtime failure Acceptance Criteria: * Error pattern is defined and tested * Given an application output logs to cloudwatch when a known error occurs, then the pattern must correctly match that log * Metric filter is created - when error count exceeds the threshold then cloud watch alarm should trigger * Alert notification is sent, given the alarm is triggered when the condition is met then an alert must be sent to relevant teams |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [25 empty] | AM20-116 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3fa4464b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bnb3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:37 | [13 empty] | 04/Aug/25 6:37 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will start working on this from today. | 08/Aug/25 12:05 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Monitoring for specifically reporting & tm1serv application has been set. Alarm for Total Commit Usage has been created and configured to send those to ServiceNow. | 08/Aug/25 12:06 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Moving to Aravindâ€™s bucket for review. | 08/Aug/25 12:30 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;every cloud watch custom metrics are captured as error metrics and create an alarm for same. | 08/Aug/25 12:30 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;create a memoryutilization and disk utilization alarm and move to review | 08/Aug/25 8:43 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Monitoring metric is created for Overall Committed Memory Bytes and then further classified for each service that was mentioned in the mail. Alert has been created for â€œOverall Committed Memory Bytesâ€, so creating alarms for its further classification would be redundant. And in the email, we have a confirmation to create an alarm for â€œTotal Commit Sizeâ€ hence have created for â€œOverall Committed Memory Bytesâ€ and not for the per service. | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-741 | Terraform Development ¦¦ Creation of Outbound and inbound rules in NACL | Done | 8 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1651313 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 16:39 | 2026-01-14 19:57 | 2025-11-27 08:27 | 2025-11-28 12:00 |  | 0 | As Terraform expert, I want to be creating a network ACL with inbound and outbound rules using terraform code, so that I can apply stateless packet filtering at the subnet level Acceptance Criteria: * Define variable for CIDRs, ports and subnets * NACL resources is created and associated with target subnets * Application relevant flows needs to be populated * Application inbound rule and comms metric needs to populated for NACL * Outbound rules allow return traffic on the same ports. * Each rule has a unique number and direction * Rules are parameterized for environment flexibility * add rule description and tags. * Provision to add or deny additional rules with max of 20 rules to be allowed for NACL |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@442b4964 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mrnr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 19 | [96 empty] | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-20 07:06 | 10060_*:*_1_*:*_89634_*¦*_3_*:*_2_*:*_777961357_*¦*_10041_*:*_1_*:*_18654341144_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 20/Nov/25 9:06 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Working on base module code of terraform script. It will be completed by this Friday EOD. | 27/Nov/25 8:24 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform script completed and NACL resource created in sandbox environment. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-11-28 12:00
AM20-742 | Informatica Server ¦¦ Assessment & LLD | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650978 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 21:35 | 2026-01-12 00:25 |  |  |  | 0 | As Application expert I would be conducting assessment on Informatica server and document the low level design to record the migration approach and design *Acceptance Criteria*: * Document Low level design containing AWS infrastructure and approach to migrate informatica servers for sign-off. |  | Harsh Chandra | Sumit Nikam |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [10 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1bfd6374 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i027wj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 13:57 | [13 empty] | 29/Apr/25 3:56 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Have got details from Pieter. To be documented. | 02/May/25 11:02 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Assessment document prepared based on received inputs: [Informatica - Assessment.docx¦https://vodafone.sharepoint.com/:w:/r/sites/SouthAfricaAirlines/Shared%20Documents/20%20+%20app%20migration/20+%20Applications%20planning/Assessment%20Documentation/Assessment%20word%20files/Informatica%20-%20Assessment.docx?d=w42d28a53768b4302b78338d1c28a23e5&csf=1&web=1&e=OPyJH9] Few open points regarding application have been raised with Pieter. Document might be updated based on same. | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:39
AM20-743 | TM1 Migration activity with tagging | Done |  | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642044 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 14:39 | 2026-02-05 16:26 |  |  |  | 0 | As Application Expert, I would be migrating TM1 server from on-prem to AWS using migration tool Acceptance Criteria: TM1 migration is successfully migrated to AWS from on-prem. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;17/Apr/25 8:31 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;144000 | [5 empty] | 144000 | 0 | 144000 | 1 | 144000 | 0 | 144000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5e70c07a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00szn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-08 10:32 | [13 empty] | 08/Apr/25 12:31 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 migration is completed, awaiting for application commsmatrix implementation status, upon confirmation will launch test instance and will ask application owner to test and confirm functionality. | 09/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Expecting to do the testing of Application related port connectivity bw on-premises and AWS along with satyasairam, post that will launch the test over instance. | 14/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Still awaiting for the connectivity confirmation. | 15/Apr/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for comms matrix implementation, upon completion will launch test instance. | 17/Apr/25 8:29 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*Test launch instance is launched and will add this server to the AWS active directory(*[*awsflysaa.com*¦http://awsflysaa.com]*),* after NACL and SG implementation will handover application to the owner to test the functionality. | 17/Apr/25 8:30 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Tags: ¦App_tier¦Application¦ ¦AppName¦TM1-application¦ ¦Business_Unit¦TBD¦ ¦CostCenter¦SAA¦ ¦CreatedBy¦AWS-MGN¦ ¦DisasterRecovery¦Enabled¦ ¦Environment¦Production¦ ¦Instance_Size¦TBD¦ ¦Instance_Type¦TBD¦ ¦Name¦fmtvmap01¦ ¦Owner¦TBD¦ | [21 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-17 08:31
AM20-744 | Cleanup of AWS workload from Control tower | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1749509 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 12:48 | 2026-01-17 14:22 |  |  |  | 0 | As application owner I would like to cleanup redundant workloads from AWS through control tower so that we can achieve optimum utilization Acceptance Criteria: Cleanup is done with all redundant workloads/account deleted |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 14/Aug/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250814-064049.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139647 | 18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250818-060958.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1140604 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@557a9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0daor: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-14 06:41 | [13 empty] | 14/Aug/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have initiated mail with vodacom team, will do followup. !image-20250814-064049.png¦width=1272,height=492,alt="image-20250814-064049.png"! | 18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250818-060958.png¦width=1277,height=470,alt="image-20250818-060958.png"! AWS account cleanup, followed by by account renaming is completed. | 21/Aug/25 2:25 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:26
AM20-745 | Informatica Server ¦¦ LLD preparation | Done | 6 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1610565 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 18:11 | 2026-01-13 21:09 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Sankalp Rai | Yashwant Thakur |  |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;24/Jun/25 1:32 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;11/Aug/25 10:10 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7d2f4e8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a2v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | [104 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-10 14:18 | [13 empty] | 10/Mar/25 4:18 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 10/Mar/25 4:24 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder >> Call to Scheduled on or before 12th* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 20/May/25 10:24 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;1st Draft Complete. Need to review internally revised Start Date: 19th May 2025 End date: 23rd May 2025 | 24/Jun/25 1:32 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Review with customer is completed Awaiting information requested from Application Owner | 11/Aug/25 5:04 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-10-13 09:23
AM20-746 | Ec2 Cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818694 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-01 17:27 | 2026-02-01 19:33 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4bebd3dc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzvn: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 2:28 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Sanjot has cleaned up 2 ec2 instance from backend dev. | [26 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-10-28 14:27
AM20-747 | Route53 ¦¦ Alert Configuration | In Progress | 6 | Sprint 22 | 2026-01-05 | 2026-01-16 | Satya Varanasi | Medium | 1881343 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 18:28 | 2026-02-06 20:55 | 2026-01-08 08:39 |  |  | 0 | As a cloud infra platform team I want to implement automated alerting for Route53 DNS health, record changes and DNS health, record changes and DNS failover so that application teams and support teams can proactively detect outages, unauthorized changes and DNS failures across all AWS accounts. Acceptance Criteria: # Route 53 Health Check Alerts * Health checks must be created for all critical endpoints (HTTP, 1. HTTPS, TCP, or CloudWatch metric-based). * Â A CloudWatch alarm must automatically trigger if the health check status = Unhealthy. * Â Alarm must send a notification to an SNS topic configured for the environment (Dev/Pre-Prod/Prod). * Â Health check status must be visible on the central monitoring dashboard. # DNS Failover Alarms * Â Failover configurations (Primary/Secondary records) must be validated after deployment. * Â A CloudWatch alarm must trigger when Route 53 performs an automated failover action. Â Notification must include: * Â hosted zone name * Â record name * Â failover type (PRIMARY â†’ SECONDARY) * Â timestamp Â Application team must receive ServiceNow notification immediately. Â All failover events must be recorded in audit logs (CloudTrail). # Hosted Zone Change & Record Modification Alerts Â CloudTrail must be enabled for all Route 53 API events: * Â CreateHostedZone * Â ChangeResourceRecordSets * Â DeleteHostedZone 4.Â An EventBridge rule must detect record or zone changes and send alerts to SNS. Alert must contain: * user/role who made the change * old value vs new value * timestamp * AWS account ID # Unauthorized changes must automatically raise a ticket in ServiceNow/JIRA (if integrated). * All record changes must be stored for audit (S3/CloudTrail). * DNS Query Volume / Anomaly Alerts * Â CloudWatch metric "DNS Queries" must be monitored for abnormal spikes or drops. * Â CloudWatch Anomaly Detection must be configured with proper thresholds. * Â Alerts must trigger when query volume deviates beyond normal traffic window. * Â Notification must reach platform + application teams. * Â Alerts must indicate possible DDoS, misconfiguration, or routing issue.Â * DNS Latency or Resolver Issue Alerts * Â Route 53 Resolver metric "ResolverQueryError" or "DNS Resolution Failure" must be monitored. * Â Alerts must trigger when error rate exceeds threshold (ex: >5% errors for 5 mins). * Â Alerts must include resolver IP, VPC ID, region. * Â Incident must be auto-created in monitoring tool.Â # Alert Routing & Escalation * Â Alerts from all child accounts must centralize into a single parent-account SNS topic using cross-account permissions. * Â Separate channels must exist for PROD vs NON-PROD. * Â Severity mapping must follow organizational incident guidelines (SEV-1, SEV-2, SEV-3) # Â A centralized CloudWatch dashboard must show: * Â health check status * Â failover events * Â DNS query traffic * Â record change logs * Â Dashboard must be accessible from parent account to all authorized users. * Â Dashboard updated in near real-time (<1 min delay).Â # Security & Governance * Â IAM policies must restrict record modification to authorized roles. * Â All Route 53 API calls must be captured via CloudTrail. * Â Patchable misconfigurations (e.g., TTL mismatch, missing health checks) must be flagged automatically. * Â Alerts must comply with compliance policies (PCI, CIS benchmarks if applicable). # Integration Requirements * Â SNS must integrate with: * Â ServiceNowÂ * Alert payload must follow a standard message template. 10. Testing & Validation * Test failover must generate an alert. * Test manual record change must generate an audit alert. * Test endpoint failure must trigger "Unhealthy" alarm. |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2e5b4dfc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptvd: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-07 14:38 | [13 empty] | 07/Jan/26 4:38 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working on it. | [29 empty] | In Progress | 2026-01-08 08:27
AM20-748 | EC2, Codebuild and pipeline cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818698 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-25 19:01 | 2026-01-25 22:51 |  |  |  | 0 | As a DevOps, I want to validate if any unwanted resource out of codebuild, codepipeline or EC2 instances are running under flysaa backend accounts. If found, that resource should be deleted to optimize cost. Acceptance Criteria: Cleanup is performed w.r.t. EC2, codebuild, codepipeline on flysaa backend accounts |  | Aravind Raj | Sanjot Fotedar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@24f99243 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzw3: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-28 12:19 | [13 empty] | 28/Oct/25 2:18 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;2 early stage Bastion Hosts in flysaa dev account were manually created and have now been terminated as they were not managed by Terraform or aligned with naming standards. Rest all good in dev, preprod and prod | 28/Oct/25 2:26 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have seen 2 instance got terminated. | [25 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-10-28 14:26
AM20-749 | TM1 ¦¦ Migration tool installation | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620533 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 16:03 | 2026-01-22 17:53 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the TM1 SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | Working with nexio team on troubleshooting the replication issue and configuring required services to get the agent installation successful followed by replication.;07/Apr/25 10:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [5 empty] | AM20-14 | AM20-4 | [23 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@106887e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnnb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:26 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This user story is blocked due to [https://vodacom.atlassian.net/browse/AM20-14¦https://vodacom.atlassian.net/browse/AM20-14¦smart-link] the network setup, upon completion of network will pick this one up. | 21/Mar/25 12:19 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet is shared, requested [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] to create a connectivity between on-premises to cloud. After the connectivity established, will be able to pick this migration agent toll installation for TM1. | 25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created a replication template and post launch template, waiting for the connectivity to be established between on-premises and TM1 AWS account. | 27/Mar/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Shared Agent and access details to vodacom team, have raised CRQ request for agent installation. 28th is planned for agent installation followed by replication will be initiated. | 04/Apr/25 11:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;On-prem to AWS Connectivity is established, Agent installation is getting failed due to multiple time of attempt, now waiting for restart of server from the logs. will try to install again and update the proceeding's here, | 07/Apr/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Replication is in progress, waiting for initial snapshot to be created. | 07/Apr/25 10:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Though agent installation completed, marking this story to done. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-07 10:45
AM20-750 | AWS_SAA_Network ¦¦ Security Compliance Implementation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642120 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 14:46 | 2026-01-29 16:49 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on *Account no: 339712943527â€ƒâ€ƒAWS_SAA_Network* *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/Apr/25 9:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Network-Acccount-FailedControls.csv;https://vodacom.atlassian.net/rest/api/3/attachment/content/1092887 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@749b116f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00tcp: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-15 06:22 | [13 empty] | 15/Apr/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on implementing dependency services for CIS, NIST and FSBP | 17/Apr/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed enabling Guard Duty, Macie, Security Hub, followed by this have implemented controls for CIS, NIST, AWS FSBP standards. Still there are few failed controls to be remediated, since the implementation of services done by vodacom, will expect their support in implementing the controls. if the controls cannot be implemented will get a confirmation on the failed control list to close this user story. | 22/Apr/25 9:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;[^Network-Acccount-FailedControls.csv] Failed controls list to work with vodacom team, hence marking this story to done status. | 02/May/25 4:58 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-04-22 09:53
AM20-751 | Adding description for CloudWatch notifications sent to ServiceNow for AWS Lambda | Done |  | Sprint 21 | 2025-12-22 | 2026-01-02 | Shreyash Talwekar | Medium | 1883878 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2026-01-11 15:55 | 2026-01-11 18:51 |  |  |  | 0 | Update alarm payloads configured for Lambda functions alarms to sent the description alongwith other previous details to ServiceNow. |  | Faisal Sayed | Shreyash Talwekar |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cac3dfe | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pm6j: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-02 05:41 | [13 empty] | 02/Jan/26 7:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Lambda Function for Alarm Handling* *Overview:* This Lambda function is triggered whenever a CloudWatch alarm transitions to the {{ALARM}} state. *Functionality:* * Retrieves detailed metrics for the Lambda function that breached the configured threshold and triggered the alarm. * Constructs a payload containing the relevant metric details. * Publishes the payload to an Amazon SNS topic, which has ServiceNow configured as a subscriber for incident management. *Recent Enhancement:* A human-readable description has been added to the payload to improve clarity and facilitate better understanding in ServiceNow. This enhancement is now implemented and operational. | [26 empty] | 1881266 | AM20-302 | Convert Alarms description into simple user understandable format | Done | 2026-01-02 08:22
AM20-752 | ServiceNow Integration with Wave 1 application accounts for migration | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1718215 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 20:05 | 2026-02-05 20:58 |  |  |  | 0 | As AWS expert I would like to setup ServiceNow monitoring with all the application accounts so that in case of any alerts generated via CloudWatch agents, it can be cascaded to ServiceNow to form an incident tickets Below applications are considered TM1, Patch managment, NexioAV, Informatica server Acceptance Criteria: * ServiceNow monitoring is setup successfully in all the accounts targeted to be used for respective application migration * API for serviceNow is successfully configured for non-prod as well as prod accounts respectively * ServiceNow team confirmation is received that API is transferring the information successfully * E2E validation is completed ( App account-->cloudwatch-->SNS topic-->alerts-->Servicenow monitoring-->ServiceNow |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [13 empty] | 17/Jul/25 5:53 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250717-155331.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1127871 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7ecd77e5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aoff: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-17 06:11 | [13 empty] | 17/Jul/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 and Nexio AV service now integration is completed, unit testing will be completed. | 17/Jul/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Only after the demo and approval patching server will be added to the service now integration | 17/Jul/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will add informatica server integration today. | 17/Jul/25 5:53 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Informatica aws account integration is completed, test with a test server working fine as expected. !image-20250717-155331.png¦width=647,height=465,alt="image-20250717-155331.png"! | 21/Jul/25 7:05 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;patch management server is expected to setup in security account, so ill be doing security account integration with service now by today. | 21/Jul/25 6:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Security account service now integration is completed unit test yet to be performed. | 25/Jul/25 7:48 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-25 19:48
AM20-753 | Informatica Server ¦¦ Cutover | Done | 3 | Sprint 13 | 2025-09-01 | 2025-09-12 | Aravind Raj | Critical | 1751440 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 18:21 | 2026-01-09 20:09 |  |  |  | 0 | As AWS expert I would be performing the cutover for Informatica application. Acceptance Criteria: * Replication from on-prem is successfully stopped using API calls * Back up of informatica VDC Server * Monitoring disable - VDC Server * Shutting down Informatica application in VDC * Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [informatica-application.awsflysaa.com¦http://TM1-application.awsflysaa.com] Server to the AD * MAT Testing completed successfully by SAA |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;30/Sep/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;30/Sep/25 6:35 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 115200 | 28800 | 86400 | [12 empty] | 30/Sep/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250930-163418.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1160874 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1f84394d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 07:21 | [13 empty] | 05/Sep/25 9:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test server is launched and trying to fix connectivity issue. only after that cutover can be launched hence this will be a spillover. | 22/Sep/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This US is spillover since there were SAP connectivity issue. now the connectivity is resolved, we will be taking up this in this sprint. | 30/Sep/25 6:33 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;The Cut over is completed followed by user validation. Post cutover activities like SSM agent installation, Domain Join and Cloud watch agent installation all completed successfully. | 30/Sep/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250930-163418.png¦width=669,height=443,alt="image-20250930-163418.png"! | [26 empty] | Done | 2025-10-06 07:58
AM20-754 | TM1 ¦¦ E2E Integration testing of ServiceNow monitoring | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1729976 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 17:49 | 2026-01-28 21:16 |  |  |  | 0 | As Product Owner I would like to review e2e testing completed with servicenow team for all wave 1 application so that we can confirm to business that in case of any issue service ticket would be raised Acceptance Criteria: * Tickets/issues are getting raised successfully against the alerts raise via cloudwatch for all Wave1 applications * ServiceNow team signoff received * Showcase (demo) provided to all relevant stakeholders |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 19/Aug/25 1:26 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image (3).png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141522 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@98c0df5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bmab: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-28 07:32 | [13 empty] | 28/Jul/25 9:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Once after the TM1 cutover is completed we can proceed with this activity. | 11/Aug/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: Since the story was blocked due to configuration of monitoring and alerting on TM1 ec2 instances (application specific) which was completed on 8th Aug 2025 (evening), Diksha did not get any time to validate end to end solution. Hence, the spillover. | 19/Aug/25 10:40 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start working on this US from today. | 19/Aug/25 12:27 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Alerts are being generated and triggered now waiting for confirmation from Service now team to share the screenshot. | 19/Aug/25 1:26 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image (3).png¦width=1146,height=305,alt="image (3).png"! Attaching the screenshot which I got from service now team that they are getting the alerts generated by our side. | 21/Aug/25 2:33 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:33
AM20-755 | POC - Create Sustainability dashboards | To Do | 8 | Sprint 10 | 2025-07-21 | 2025-08-01 | Sankalp Rai | High | 1720042 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 14:38 | 2026-02-06 15:43 |  |  |  | 0 | As AWS Expert, I would create sustainability dashboard to access the power consumption, utilization and energy efficiency in alignment with well-architecture Acceptance Criteria * Enable AWS Sustainability Pillar in Well-Architected Reviews, optimize workloads for energy efficiency â€” right-sizing, minimizing network transfer, cold storage, etc. * Leverage S3 Lifecycle Policies & Intelligent Tiering |  | Harsh Chandra | Sankalp Rai |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63121580 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v09 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | Sprint 12 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:13 | [13 empty] | 11/Aug/25 10:12 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 12th August End Date: 21st August | 10/Sep/25 1:15 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Moving this to Backlog from Sprint 13 as suggested by Deepak Sharma, to currently focus on critical migration activities. This will be picked up in later sprints. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | To Do | 2025-10-13 09:27
AM20-756 | Trellix integration with AirnavX | Done | 1 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 14:32 | 2026-01-29 17:51 |  | 2025-11-12 08:22 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan AirNavX workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in AirNavX server * Trellix is able to access AirnavX account successfully and perform scanning |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 05/Nov/25 3:41 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ Trellix scanning status for New AWS AirNavV servers.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1178115 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f4c84b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 18 | [95 empty] | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [65 empty] | YES | YES | 2025-09-08 07:56 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [12 empty] | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 30/Sep/25 7:40 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working with Sinjun for trellix installation on these 2 servers. | 06/Oct/25 8:39 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Working with Sinjun for Trellix installation, hence will be spilled over | 09/Oct/25 4:29 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Sinjun Albert is going to install Trellix and he will confirm once integration done. | 17/Oct/25 11:17 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over reason - Blocked due to ongoing app installation issues, currently worked upon by app owner; post which this story will be progressed in subsequent sprint | 05/Nov/25 3:41 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Trellix software installed on New AWS AirNavX servers. All AirNavX servers able to discover from Trellix admin server and same has been confirmed by Sinjun. Attaching reference for support. [^RE_ Trellix scanning status for New AWS AirNavV servers.msg] | 12/Nov/25 8:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | Done | 2025-11-12 08:22
AM20-757 | AirNavX ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672697 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-31 14:11 | 2026-01-31 16:18 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across AirNavX account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cdd392e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04fqr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 06:27 | [13 empty] | 20/May/25 8:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on enabling the cloud config and guard duty along with macie. | 22/May/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;below mentioned service were enabled. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-22 08:19
AM20-758 | Centralized Cluster Creation Strategy | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Sanjot Fotedar | Medium | 1885775 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 18:43 | 2026-01-09 21:01 | 2026-01-08 08:38 |  |  | 0 | As A platform Owner I want to create a detailed design document for centralized management of EKS cluster across multiple AWS child accounts from a central account so that the solution is secure, scalable, compliant and operationally ready before implementation Acceptance Criteria: *Architecture and Account structure* - * Parent, central management and child application accounts * hub and spoke model connectivity model * shared vs isolation responsibilities *EKS management Strategy* - * Centralized model * Namespace isolation strategy * Cluster ownership and lifecycle boundaries *IAM and Security design* - * Cross account IAM roles and trust relationship * K8s RBAC mapping * Least privileges access model * SCP usage and guardrails *Network and Connectivity design* - * VPC architecture per account * Connectivity via TGW /VPC peering * Control plane and data plane traffic flow * DNS resolution strategy *Governance and Policy Enforcement* - * Kubernetes admission controls (Kyverno) * naming, tagging and quota standards * Policy exception handling process *Observability and Logging* - * Centralized logging and metrics flow * Alerting and escalation paths *Security and Compliance* - * EKS security monitoring * Image scanning approach * Compliance reporting and audit readiness *Operation model* - * RACI matrix (L1/L2/L3) * Incident and change management process * upgrade and patching strategy * Backup and DR approach |  | Sanjot Fotedar | [5 empty] | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [5 empty] | ;07/Jan/26 7:23 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;7200 | [5 empty] | 115200 | 108000 | 7200 | 0.06 | 115200 | 108000 | 7200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43715548 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptve: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-07 17:24 | [13 empty] | 07/Jan/26 7:23 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Started work on this. Currently evaluating the framework for assessing multi-tenancy readiness of existing eks cluster. Identifying key focus areas for hardening -Â namespace isolation, RBAC scope, network segmentation, resource governance, policy enforcement. | [29 empty] | In Progress | 2026-01-07 19:21
AM20-759 | Patching New Requirement ¦¦ Cache Drive for Patching | Done | 5 | Sprint 21 | 2025-12-22 | 2026-01-02 | Yashwant Thakur | Medium | 1863471 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 13:16 | 2026-01-11 13:29 | 2025-12-18 08:19 | 2026-01-02 11:27 |  | 0 | As Cloud Product manager I would like to use Cache drive for the EC2 servers where Storage is low to proceed with Patching so that we can successfully patch servers without any issue. Acceptance Criteria: * Before Patching is initiated Lamda function first assess if the given EC2 server has sufficient storage available. If the Storage is insufficient then it must attach cache drive to the server and reboot flow must be initiated * Post reboot the storage must be attached successfully * If the Storage is sufficient on the given EC2 instance then the patching should be progressed without any issue |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@66bf1276 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001r | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2026-01-02 06:08 | 3_*:*_1_*:*_1380825004_*¦*_10041_*:*_1_*:*_1796320497_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Jan/26 8:08 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Update* The *AWS Systems Manager (SSM) document* has been modified to optimize patch installation by leveraging a temporary attached volume. h3. *Technical Details* * The SSM document now: ** Utilizes an *attached temporary volume* mounted with drive letter {{T:}}. ** Downloads and installs patches onto this temporary volume during execution. * Post-installation: ** The system does *not maintain any dependency* on the temporary volume. ** The temporary volume is *manually deleted* after installation is complete (deletion is *not automated* within the document). | [29 empty] | Done | 2026-01-02 11:27
AM20-760 | Nexio AV ¦¦ Life Cycle Management ¦¦ Log Retention | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1730232 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 12:54 | 2026-01-26 13:04 |  |  |  | 0 | As Product Owner I would like to establish the life cycle management for log retention specific to Nexio AV account to have defined log retention policies for all critical log sources so that we can meet compliance, enable forensic investigation and optimize storage Acceptance Criteria: log retention policy is defined per account * Production env. - log retention period 90 days Â *Please note* that post retention period, these logs can either be deleted or moved to cold storage, which can be configured based on your confirmation however, data retrieval from cold storage is charged additionally. * All critical log sources are covered - cloudtrail, VPC flow logs, cloudwatch logs and other tools must be retained as per policy * Log retention is automated - log groups are created when they are detected * Logs reaches its retention threshold when the time expires it should either be deleted or moved to archive (cold storage) * Retention policy is editable so that it can be configured accordingly |  | Aravind Raj | Diksha Koul | Onkar Mirajkar | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [27 empty] | 06/Aug/25 9:45 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;Screenshot 2025-08-06 131412.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136044 | 29/Jul/25 9:39 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250729-073927.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1132067 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@410ec9e6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bn77: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-29 07:40 | [13 empty] | 29/Jul/25 9:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;No S3 bucket resource has been created on NEXIO AV as of now for retention period. !image-20250729-073927.png¦width=1545,height=507,alt="image-20250729-073927.png"! | 31/Jul/25 12:53 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Created Log metrics for NEXIO AV | 01/Aug/25 8:14 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created one life cycle rule for the deletion of logs after 90 days need to review it with Aravind. | 01/Aug/25 9:00 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;we will be having an confirmation email from the client and will be then implementing the retention life cycle rule on the centralized account as Logs will store to cold storage and retention days will be 90 days. | 05/Aug/25 11:11 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Retention rule has been created in the Log Archive account on S3 all environment as 90 days and also after 90 days it will get moved to cold storage. | 06/Aug/25 9:45 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!Screenshot 2025-08-06 131412.png¦width=934,height=354,alt="Screenshot 2025-08-06 131412.png"! Attaching the screenshot of the changes we have done in the log archive account. | 08/Aug/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Transition rule in place for centralized cloud trail logs to send to glacier after 90 days. | 11/Aug/25 7:59 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 07:59
AM20-761 | Informatica Server - Prod ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1752123 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 20:07 | 2026-02-02 21:24 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [10 empty] | AM20-136 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1d85433a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dlmz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-29 06:01 | [13 empty] | 29/Aug/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As it is handled by Arvind so assign to Arvind. | 05/Sep/25 9:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Agent installation is completed and replication followed by initial sync is completed too. | 05/Sep/25 10:29 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-05 10:29
AM20-762 | Rename Citrix account with informatica Prod: Re-establish Informatica ¦¦ Subnet Configuration and Setup platform | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1749511 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 17:21 | 2026-01-18 19:08 |  |  |  | 0 | As Network expert, I would like to provision subnet configuration for PROS application Acceptance criteria: * Subnet configuration completed successfully * Tagging of all network elements associated done succesfully * Traffic flow testing and validation is concluded |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153624.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141700 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153747.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141702 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-154222.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141701 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@e805dba | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dap7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 06:22 | [13 empty] | 12/Aug/25 8:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;We are looking account id rename or new id creation process accordingly i will proceed for next steps. | 19/Aug/25 5:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Citrix Account ID has been renamed with Informatica Prod â€œ536697248966 â€ƒâ€ƒ SAA_Informatica_PRODâ€ | 19/Aug/25 5:42 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet, NACL, RAM ,SG and connectivity has been established. !image-20250819-153624.png¦width=1417,height=750,alt="image-20250819-153624.png"! Connectivity has been tested and working fine. !image-20250819-153747.png¦width=1417,height=750,alt="image-20250819-153747.png"! ¦Informatica Prod-Public¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.0.208/28¦10.40.0.208 - 10.40.0.223¦10.40.0.209 - 10.40.0.222¦14¦/28¦ ¦Informatica Prod-Public(DR)¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.128/28¦10.40.1.128 - 10.40.1.143¦10.40.1.129 - 10.40.1.142¦14¦/28¦Â ¦AZ2¦ !image-20250819-154222.png¦width=1417,height=750,alt="image-20250819-154222.png"! | 19/Aug/25 5:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Assigning for review. | 21/Aug/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed with internet acess. | 25/Aug/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 06:33
AM20-763 | ServiceNow ¦¦ Logging and Monitoring | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651021 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 17:22 | 2026-01-30 21:09 |  |  |  | 0 | As an AWS expert, I want to monitor the health and logs of the Lamda connector function so that I can troubleshoot issues when alerts arenâ€™t processed properly Acceptance Criteria: * CloudWatch logs are enabled for Lambda * Metrics and dashboards are available for monitoring invocations, failures and response times. |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/May/25 9:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103910 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60acf139 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0285v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | [108 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 05:45 | [13 empty] | 02/May/25 7:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function to invoke the cloud watch is created and working as expected, Cloud watch dashboard for metrics will be created only after the workloads moved to cloud. service now monitoring can be in place only after successful integration with connector and service now PAAS endpoint. | 16/May/25 9:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have given demo with the email endpoints, waiting for the https endpoint to be received from SAA team to work with full functionality, | 22/May/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have received a endpoint today, yet to update SNS topic endpoint. https://sonicboom_em_saa_7161:wusEwo>G*Xmw@?XOA74\!pm0cx2.[4N;oFz<\!7vSE@liftdev.service-now.com/api/sn_em_connector/em/inbound_event?source=aws&sys_id=870cc1dfc3a5a6d04022f9777a013157 | 22/May/25 9:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 26/May/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 26/May/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;With respect to the endpoint have sent a mail to ashton, but there was response yet. awaiting on same. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. Â· | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 7:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Service now integration is completed with a new subscription HTTPS endpoint, have created a Cloud watch alarm for testing purpose which triggers a SNS as result service now dashboard receives a alert. | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-20 08:17
AM20-764 | Informatica ¦¦ Port opening, NACL and SG group Whitelisting | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1755982 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 19:12 | 2026-02-03 21:56 |  |  |  | 0 |  |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 28800 |  | 0 | 57600 | 28800 | [13 empty] | 05/Sep/25 10:50 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250905-084935.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148455 | 05/Sep/25 10:50 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250905-084949.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148454 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@40ed7680 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0e0p7: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-26 11:38 | [13 empty] | 26/Aug/25 1:37 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will be actioned after network and firewall setup implementation. So kept as blocked. | 28/Aug/25 8:34 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Firewall rules implementation has been completed. LiFT = CHG0067488 CSOC = CHR0026691 Still required validation, this will be validated after test instance available. | 01/Sep/25 8:05 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev side NACl/SG has been completed. Prod side basic setup done for domain join and remaining will be implemented today. | 04/Sep/25 8:23 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev/Prod side all ports has been whitelisted. Assigned servers to app team for testing. VDC side connectivity has been tested and working fine(Wanda has been confirmed). From Sita side customer needed FortiGate VPN access towards connecting to informatica subnets, Pieter has been requested user access and it is under approval process. | 05/Sep/25 10:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Currently SITA side testing going, EWS servers side, VDC side connectivity done. Connectivity testing point of view we will work on new user story, as per process implementation has been completed AWS side. !image-20250905-084935.png¦width=734,height=384,alt="image-20250905-084935.png"! !image-20250905-084949.png¦width=734,height=384,alt="image-20250905-084949.png"! | 08/Sep/25 6:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:34
AM20-765 | Other resources remediation - Config, GuardDuty, EC2, RDS and etc | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818710 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-11 19:10 | 2026-01-11 19:55 |  |  |  | 0 | Remediate dependencies services. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ff5f38c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzxn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have remediated dependencies services failed controls | [26 empty] | 1817984 | AM20-225 | Security controls remediation - Informatica and PROS Aws accounts | Done | 2025-10-28 11:21
AM20-766 | Airnavx ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620850 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 18:11 | 2026-01-16 20:09 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [8 empty] | AM20-10 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4559db6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 8 | Sprint 9 | Sprint 12 | Sprint 13 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-25 06:58 | [13 empty] | 25/Jun/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Harsh and Deepak update, this need to address after TM1 and informatica servers network action, hence i am keeping this as blocked(As per Harsh update) | 28/Jul/25 8:51 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Currently app under LLD review once review done i will initiate comms for the same. SO this will be moved to next sprint. | 04/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on it according to recent LLD call review. | 07/Aug/25 8:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared, with latest subnet details, i will initiate mail communication with customer/app owner for flows review or in case any additional flows needed they should notify further process. | 12/Aug/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Shared comms to app owner for review and add in case needed any additional flows for the same. | 25/Aug/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms under validation by app owner, so this is right story for spill over to this sprint. | 26/Aug/25 1:04 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Initially after follow-up customer prepared and send comms. # During review i identified as comms as not prepared right way and reshared the same comms to customer for validation. # After continuous 3 days follow-up we have received comms from customer as on date 25th Aug 10:00 PM. # There is no sufficient time to manage this story in this sprint due delay with customer. # Note: It has been communicated customer and management regularly but he took longer time to manage. | 29/Aug/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Reviewed and prepared AirNavX comms for VDC/SITA sheets and same sent app owner for LIFT/CSOC request towards implementation. | 03/Sep/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been reviewed and submitted to app owner for further process. | 03/Sep/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Albert has been submitted requested LIFT and CSOC request for ports androuting implementation. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 03/Sep/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The below is the current status: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Routing already in place hance not required any action on this and making this as completed.) | 08/Sep/25 6:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [15 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:36
AM20-767 | Nexio AV integration with TM1 environments to allow scanning | Done | 4 | Sprint 9 | 2025-07-07 | 2025-07-18 | Yashwant Thakur | High | 1698517 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 19:25 | 2026-01-22 22:53 |  |  |  | 0 | As Network expert, I would be helping integration of Trellix and TM1 so that trellix can scan TM1 servers. Acceptance Criteria: * TM1 servers can be access via trellix successfully * TM1 servers are scanned for any vulnerability by Trellix |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 23/Jul/25 8:13 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ SAA II Nexio AV LLD Walkthrough.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1129505 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6a53d9d8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i08j3n: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 10 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-01 06:21 | [13 empty] | 01/Jul/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Trellix setup not done, need to wait until trellix ready. | 17/Jul/25 8:11 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Agent installed on TM1 test instance and tested, it is working fine. | 23/Jul/25 8:13 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Successfully Trellix setup completed and tested TM1 server and frontend environments has been registered with new Trellix. [^RE_ SAA II Nexio AV LLD Walkthrough.msg] | 25/Jul/25 7:47 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-25 19:47
AM20-768 | Nexio AV ¦¦ Back-UP via terraform | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730133 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 15:27 | 2026-02-01 15:39 |  |  |  | 0 | As AWS expert, I would like to provision Life Cycle manager with two schedule - * Incremental back up(daily back) * Full backup (Weekly) *Acceptance Criteria* : * The Life cycle manager has two schedule (Incremental and Full backup) successfully implemented * Back up must be automated using native AWS features and tools * Point-in-time recovery for database must be enabled to allow recovery to any second within retention window * Define retention policy and enforce retention ( 7 days, 35 days, monthly snapshot for 1 year) * Automatically transition of old backups to cold storage * Use AWS backup vault lock for Write once and Read many compliance * Backup must be encrypted at rest and in transit * Restore process is well documented and well tested * After restore data integrity checks and application consistency should be validated * Use AWS backup for central management of backup policies and vaults * Automate backup selection using resource tags * Backups must meet regulatory compliance like GDPR,HIPAA * and Audit trail of backup creation, deletion and restore events must be maintained * Periodic restore testing must be conducted and logged to validate data integrity * *AWS part:* * Use AWS config rules to enforce mandatory backup configurations * Use Cloudwatch to success/failure backups * Setup alerts for backup failure or missed backups via SNS * IAM Policies for access control to restrict who can create, view, delete and restore backups * All backup and restore operations must be logged in AWS Cloudtrail for traceability |  | Aravind Raj | Sanket Kale | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4dfe6877 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bmvv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 05:09 | [13 empty] | 11/Aug/25 7:09 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;This task will be spill over because the terraform script written by the Utkarsh is not match our expectations. I need to re write the new scripts from the scratch. | 13/Aug/25 8:19 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Utkarshâ€™s code is written for creating resources in AWS backup. I have executed the script for Nexio Prod. | 18/Aug/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;deleted unwanted 37 backup AMI taken by vault. backup config is updated with frequency and retention period. | 20/Aug/25 8:11 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-20 08:11
AM20-769 | Push to FlySAA backend Alarm related code to the bitbucket in prod environment. | Done | 0 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1800257 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-26 12:26 | 2026-01-26 13:42 |  |  |  | 0 | Add existing terraform code to create CloudWatch alarms and other required AWS resources into the bitbucket. Â Add alarms for following: Â Kubernetes microservice CPU and Memory consumption alarms for Amadeus and Fabric microservices. Â Error Patterns observed in microservice logs. Â Healthcheck API endpoint return status monitoring. Â Configured Alerts to monitor RDS metrics. Â Also create EventBridges to capture alarm state change (Ok â†’ Alarm and Alarm â†’ Ok). Â Create Lambda jobs to be triggered by EventBridge which in turn sends notification to ServiceNow using existing SNS topics. | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@235e656e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0iw3n: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 17 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | Done | 2025-10-20 16:06
AM20-770 | Informatica Server ¦¦ Subnet creation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660595 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-23 21:52 | 2026-01-24 00:54 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Nexio AV application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Nexio AV and the configured based on the approved comms matrix |  | Aravind Raj | Harsh Chandra | Satya Varanasi | Shreyash Talwekar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 27/Jun/25 3:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-135131.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119370 | 27/Jun/25 3:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-135223.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119371 | 27/Jun/25 5:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155229.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119409 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@435a4769 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-16 08:08 | [13 empty] | 16/May/25 10:07 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Waiting for terraform code towards build this. | 20/May/25 5:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Deepak and team, this need to be addressed with terraform code the same has been prepared by Utkarsh, until core not ready this story may not possible to address. | 10/Jun/25 2:03 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still â€œShreyashâ€ checking Utkarsh script, this story depending with script testing and execution. | 16/Jun/25 9:06 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Terraform script is under modification by â€œShreyashâ€, as per his update it will be ready this week. Hence this is the reason for spill over Sprint7 to Sprint8. | 16/Jun/25 9:15 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Currently working on updating terraform script based on latest naming convention requirement. | 18/Jun/25 11:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The script is managing by â€œShreyashâ€ so i am assigning this task to him, once his work completes he will reassign to me. | 23/Jun/25 1:58 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We were able to create AWS resources (mentioned in previous mail ) using terraform scripts on sharedvpc-dev account. To address some requirements like adding naming conventions and state file management, we will have to add some changes in terraform scripts. Due to current sprint activities I might not be able to work on the changes in this sprint. | 27/Jun/25 3:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Prod Subnet/Route table has been created, & tested internet access and same working fine. !image-20250627-135131.png¦width=1261,height=434,alt="image-20250627-135131.png"! !image-20250627-135223.png¦width=1112,height=588,alt="image-20250627-135223.png"! sh-5.2$ ping [http://google.com¦http://google.com¦smart-link] PING [http://google.com¦http://google.com¦smart-link] (142.251.47.238) 56(84) bytes of data. 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=1 ttl=108 time=20.5 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=2 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=3 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=4 ttl=108 time=19.7 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=5 ttl=108 time=19.8 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=6 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=7 ttl=108 time=19.7 ms ^C --- [http://google.com¦http://google.com¦smart-link] ping statistics --- 7 packets transmitted, 7 received, 0% packet loss, time 6010ms rtt min/avg/max/mdev = 19.630/19.800/20.473/0.282 ms sh-5.2$ hostname [ip-10-40-0-213.awsflysaa.com¦http://ip-10-40-0-213.awsflysaa.com] sh-5.2$ ifconfig ens5: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 9001 inet 10.40.0.213 netmask 255.255.255.240 broadcast 10.40.0.223 inet6 fe80::4a7:ebff:fe03:c075 prefixlen 64 scopeid 0x20<link> ether 06:a7:eb:03:c0:75 txqueuelen 1000 (Ethernet) RX packets 1653 bytes 293385 (286.5 KiB) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 1809 bytes 265312 (259.0 KiB) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0 lo: flags=73<UP,LOOPBACK,RUNNING> mtu 65536 inet 127.0.0.1 netmask 255.0.0.0 inet6 ::1 prefixlen 128 scopeid 0x10<host> loop txqueuelen 1000 (Local Loopback) RX packets 12 bytes 1020 (1020.0 B) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 12 bytes 1020 (1020.0 B) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0. | 27/Jun/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev Subnet and route table has been created. !image-20250627-155229.png¦width=1259,height=431,alt="image-20250627-155229.png"! | 27/Jun/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet creation and sharing is done, have reviewed. | 29/Jun/25 8:13 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:13
AM20-771 | Security compliance actionpoint | To Do | 0 | None( Backlog) |  |  | Aravind Raj | Medium | 1868968 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 18:36 | 2026-01-30 20:12 | 2025-12-12 08:19 |  |  | 0 | As Product owner for Cloud Platform I would like to ensure that we are compliant with 98% from Infra Security perspective | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ee9de6f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001v | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-28 08:52
AM20-772 | Servicenow Payload severity updates for Lambda alarms | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Shreyash Talwekar | Medium | 1835024 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-31 19:36 | 2026-01-31 20:42 |  |  |  | 0 | Enhance the existing Lambda function that triggers when Lambda alarms enter an alarm state. Currently, the function gathers alarm-related metrics, collects function details, and sends an approved payload to ServiceNow. However, severity information from the alarm is not included in the payload. This story addresses that gap by updating the Lambda function to capture and transmit the correct severity level from the alarm to ServiceNow. *Acceptance Criteria:* * Lambda function must include severity details from the alarm in the payload. * Payload sent to ServiceNow should accurately reflect the alarm severity. |  | Faisal Sayed | Harsh Chandra | Shreyash Talwekar |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  | ;20/Nov/25 8:33 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;14400 | [6 empty] | 0 | 14400 |  |  | 0 | 14400 | [12 empty] | 21/Nov/25 7:04 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251121-050425.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187511 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@560f4ab3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxar: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 05:33 | [13 empty] | 20/Nov/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Requirements have been gathered. Lambda function code will be reconfigured to incorporate changes, followed by payload testing. Ticket will be updated upon successful completion of testing. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Lambda function has been updated per requirements to capture severity. A test event was executed to validate behavior and output; results are attached. Test outcome is successful, and the implementation is complete. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251121-050425.png¦width=555,alt="image-20251121-050425.png"! | 24/Nov/25 8:42 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reviewed output, LGTM. | [23 empty] | 1832856 | AM20-264 | Update ServiceNow Payloads with severity | Done | 2025-11-24 08:41
AM20-773 | Informatica ¦¦ Custom application Metrics | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1761210 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 17:34 | 2026-01-10 19:02 |  |  |  | 0 | # Configure & install cw agent. # Refer email for metrics to be monitored. # Create alerts as per approval in the email. |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@407cb340 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0elc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-17 06:01 | [13 empty] | 17/Sep/25 8:01 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Informatica Accounts (Dev & Prod) cutover is yet to be done. Actual workloads are yet to be migrated. Hence, blocked. | 01/Oct/25 8:24 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Configure & install cw agent - Done # Refer email for metrics to be monitored - Done # Create alerts as per approval in the email - Done | [28 empty] | Done | 2025-10-06 07:58
AM20-774 | AWS Centralized dashboard CloudWatch Dashboard for Nexio AV to monitor Performance, cost optimization and security Metrics | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718753 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 14:42 | 2026-02-04 15:48 |  |  |  | 0 | As AWS expert, I would like to create centralized CloudWatch to capture Performance, Security and Cost metrics from across accounts. Acceptance Criteria: * CloudWatch dashboards can be created in one account (Payer9 account) anf pull metrics from other accounts * User cross account IAM roles to allow Payer9 account to read cloudwatch from other accounts * Add Widgets sourcing metrics from each account * Setup AWS config aggregator in the Payer9 account to collect configuration and compliance data across all members accounts * Performance metrics - Use below Cloudwatch metrics * EC2 : CPU, Network, Disk I/O * RDS: CPU, READ/Write IOPS * Lambda: Duration, Error Rate * and source these into widgets in the centralized dashboard * Security Metrics: Centralized Security Hub is already enabled, which can pull in findings from GuardDuty, Config, Macie, Cloudtrail, Inspector etc. |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60b85e0b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aofj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-23 14:43 | [13 empty] | 23/Jul/25 4:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Created Trellix Dash board with CPU, Memory and Disk usage. | 25/Jul/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dash board prepared for CPU, Disk, Network and memory for Trellix application. | 25/Jul/25 8:09 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sent for review | 27/Jul/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Could see the metrics for trellix server, moving to PO approval, | 28/Jul/25 9:57 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:57
AM20-775 | Informatica Server ¦¦ Cutover | Done | 3 | Sprint 13 | 2025-09-01 | 2025-09-12 | Aravind Raj | Critical | 1751440 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 15:47 | 2026-01-18 17:42 |  |  |  | 0 | As AWS expert I would be performing the cutover for Informatica application. Acceptance Criteria: * Replication from on-prem is successfully stopped using API calls * Back up of informatica VDC Server * Monitoring disable - VDC Server * Shutting down Informatica application in VDC * Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [informatica-application.awsflysaa.com¦http://TM1-application.awsflysaa.com] Server to the AD * MAT Testing completed successfully by SAA |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;30/Sep/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;30/Sep/25 6:35 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 115200 | 28800 | 86400 | [12 empty] | 30/Sep/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250930-163418.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1160874 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1f84394d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 07:21 | [13 empty] | 05/Sep/25 9:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test server is launched and trying to fix connectivity issue. only after that cutover can be launched hence this will be a spillover. | 22/Sep/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This US is spillover since there were SAP connectivity issue. now the connectivity is resolved, we will be taking up this in this sprint. | 30/Sep/25 6:33 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;The Cut over is completed followed by user validation. Post cutover activities like SSM agent installation, Domain Join and Cloud watch agent installation all completed successfully. | 30/Sep/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250930-163418.png¦width=669,height=443,alt="image-20250930-163418.png"! | [26 empty] | Done | 2025-10-06 07:58
AM20-776 | Nexio AV ¦¦ LLD creation | Done | 2 | Sprint 2 | 2025-03-31 | 2025-04-11 | Yashwant Thakur | High | 1619786 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 19:41 | 2026-01-10 21:52 |  |  |  | 0 | As AWS architect, I would create LLD for Nexio AV application migration *Acceptance Criteria*: * Low level design documentation including proposed architecture completed |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;13/May/25 11:21 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [9 empty] | AM20-22 |  |  | 13/May/25 11:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;TrellixAV_DesignDocument_v1.1.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1099634 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28a7c8e2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsmv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 3 | Sprint 4 | Sprint 5 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-13 09:38 | [13 empty] | 13/May/25 11:38 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Document has been prepared for Trellix AV ePO server migration to AWS ¦Backup PolicyÂ ¦To be discussed with customer and finalized¦ ¦DR Policy¦To be discussed with customer and finalized¦ [^TrellixAV_DesignDocument_v1.1.docx] First Draft of LLD is attached Moving to In Review until we can share it with customer and Finalize the Document | 18/May/25 2:41 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [25 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-05-18 14:41
AM20-777 | ServiceNow ¦¦ CloudWatch Rule for Error detection | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650995 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 17:38 | 2026-02-03 17:49 |  |  |  | 0 | As a AWS engineer, I want to create CloudWatch alarms to send error-level logs to be notified of infrastructure issues Acceptance criteria: * CloudWatch metric filters to be configured to match specific error patterns or log levels |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fabfe65 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0280b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 06:03 | [13 empty] | 29/Apr/25 8:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will review utkarsh terraform script and will assign this story to him. | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed. | 07/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;We can use utkarsh terraform script for cloud watch alarm creation, but sns topic cant be modified so we need manual update to SNS access policy. | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:39 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [22 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:39
AM20-778 | Informatica ¦¦ Custom application Metrics | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1761210 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 14:22 | 2026-01-25 17:49 |  |  |  | 0 | # Configure & install cw agent. # Refer email for metrics to be monitored. # Create alerts as per approval in the email. |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@407cb340 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0elc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-17 06:01 | [13 empty] | 17/Sep/25 8:01 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Informatica Accounts (Dev & Prod) cutover is yet to be done. Actual workloads are yet to be migrated. Hence, blocked. | 01/Oct/25 8:24 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Configure & install cw agent - Done # Refer email for metrics to be monitored - Done # Create alerts as per approval in the email - Done | [28 empty] | Done | 2025-10-06 07:58
AM20-779 | SMS Alerting implementation- Opt in/Opt out | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-16 22:00 | 2026-01-16 23:28 |  | 2025-11-15 14:38 |  | 0 | As a cloud product owner I want application and platform alerts to be delivered via SMS from a dedicated long code so that on call engineers and stakeholders receive time critical notifications Acceptance criteria: *Long code configured and verified* - given the approved long code when I set SNS and SMS preferences then the long code is used as the origination identity for the supported countries and unsupported routes use the configured Sender ID feedback *E2E SMS on P1/P2* - Given the cloudWatch alarm changes to ALARM with severity ðŸ˜›1 when the alarm event is routed via EventBridge to the SNS topic than all active on-call receipients for the app+env recieve an SMS within 60s and message body includes app, env, alarm name, severity, runbook link and ACK instruction ¦¦*Severity*¦¦*objective signals*¦¦*examples*¦¦ ¦P1 - Critical, user impact¦harsh outage, data loss, security incdences¦API 5xx>10% 5m in production, RDS storage<5% 10m. certificate expiry < 3days, guard duty, unauthrized access¦ ¦P2 - Degradation,Urgent¦performance, throughput, redundancy lost,¦EKS node group<N healthy, ALB healthy, RDS IOPS deviation, CPU utilization, disk innode,¦ ¦P3 - Action soon¦Capacity/Ops issues, repeated flaps¦log patterns,¦ ¦P4 - Informational¦chnages , warnings, failures without user impact¦Daily back ok, lamda changes, deloyment success¦ *Delivery logging and metrics* - Given SMS messages are sent when carriers return delivery statuses then statuses are captured in CloudWatch logs and S3 and dashboards show sends, successes, failures, per country breakdown *Retry and escalations ( in the event of SMS failure)* - Given a send gets a transient failure when the system retries with backoff( up to 3 times in 5 minutes) then on persistent failure an escalation SMS is triggered to secondary contacts and a ticket is created in ServiceNow with failure details *Deduplication and storm control* - Given multiple identical alarms fire within 5 minutes when routing occurs then recipients receive at most one SMS per unique alarm/signature per 5 minute window and a summary SMS is sent after 15 minutes if >5 deduped alerts occurred. *Opt-out/Opt-in* - Given a recipient replied STOP when routing future SMS to that number then messages are surpassed and audit shows timestamp and actor and START re-enables *Cost Guardrails* - Given a monthly SMS budget when SNS spend reaches 80% then P2 alert is sent to Ops and at 100% sends are rate limited to P1 only until an override flag is set *Cross account publish* - Given alarms originate in child accounts when Event Bridge forwards to central account Then publishing to the central SNS topic succeeds via resources based and IAM roles |  | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Working on exploring the ways to implement cost guardrail for lambda. Exploring enabling cloudwatch metric to track the money spent on SMS sent through the account.;10/Nov/25 8:37 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on understanding how cost is shown in billing in case of SMS sent through SNS or SMS sent using End User Messaging.;11/Nov/25 3:39 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on updating lambda to get cross account cost metric to implement 80% cost guardrail to send notification only in case of P1 and P2 alarms when 80% threshold is breached.;11/Nov/25 3:40 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). Trying the opt-out mechanism for SA number(carrier blocking was cited as one of the issues behind blocking) and parallely raised a request to understand the issue.;13/Nov/25 8:04 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Deployed changes on production cluster.;14/Nov/25 8:18 AM;17cb9418-1850-4923-932b-7098ec51b6bb;14400 |  | 57600 | 0 | 129600 | 2.25 | 57600 | 0 | 129600 | [10 empty] | AM20-176 | [19 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3955b400 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h707: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:34 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Working on implementing cost guardrails to restrict sms sending to only P1 and P2 messages when 80% limit is utilised. | 11/Nov/25 8:25 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Will be testing using cost explorer API to fetch billing cost of SNS during Lambda execution. As per AWS docs, if we are using SNS for sending SMS then the metrics wonâ€™t get reflected on CloudWatch metrics. For opt-in/opt-out as per docs, user can send the STOP message to stop getting message. Need to try this part on our end. | 12/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Updated lambda to fetch amount spent on SMS sent using cost explorer API, currently able to fetch cross account. Working on updating Lambda to avoid duplication using DynamoDB. Testing in progress. | 13/Nov/25 8:02 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Able to fetch cost of sending SMS using API, able to avoid deduplication of alarms with the help of DynamoDB table. Currently Working on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). | 14/Nov/25 8:19 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed changes on production account. | 15/Nov/25 2:38 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-15 14:38
AM20-780 | AirNavX ¦¦ Setup and Validate SG and NACL | Done | 8 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747567 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 16:29 | 2026-01-09 20:01 |  |  |  | 0 | As AWS network expert I would like to setup the security group and NACL for Airnavx so that access for aitnavx allow secure access to allow communication with its services while ensureing access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for AirNavX or related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a70d23c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d30b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:54 | [13 empty] | 25/Aug/25 8:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Spill over Reason: Still comms under review, once reviewed i will start action the same. | 28/Aug/25 8:36 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will be addressed once comms implementation done. | 08/Sep/25 9:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms Implementation request has been submitted, LIFT has been approved SITA side under approval process. This story will not be addressed until Comms implementation. | 19/Sep/25 4:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Bhavish Modified comms with /27 to /28 and the same has been shared to Albert. | 19/Sep/25 4:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Now SITA has been implemented flows and the same need to validated. According to management the validation will be managed with new Story, hence i am resolving this story. | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-22 08:49
AM20-781 | Cynet ¦¦ Server Installation | To Do |  | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1887432 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 21:22 | 2026-01-17 23:38 | 2026-01-07 08:19 |  |  | 0 | As Product owner I want to install Cynet agent on Linux/Windows EC2 instance so that threat detechtion and response coverage is enabled Acceptance Criteria. *Linux*: * Installation package hosted/accessible securely (S3 with KMS, repo, or Cynet direct download). * SSM document / automation executes successfully on a pilot group and then on all in-scope instances. * Agent registers to correct Cynet tenant and shows â€œonline/healthyâ€ in console within defined SLA (e.g., 15 minutes). * Installation is idempotent (re-run does not break existing installation). * Logging captured: instance ID, hostname, timestamp, status, version, and failure reason if any. *Windows*: * Silent install works (msi/exe unattended flags), including token/tenant configuration. * Service is running after installation and agent appears healthy in console. * Windows Event Logs / install logs are retained for troubleshooting. * | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@19d1d99d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0q0i3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2026-01-06 13:12
AM20-782 | ServiceNow Monitoring ¦¦ Prod Implementation | Done | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1673102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-19 13:40 | 2026-01-19 15:58 |  |  |  | 0 | As AWS solution architect, I would like to implement ServiceNow monitoring in prod environment so that alerts can be generated and reach to ServiceNow in form of Tickets for further actions. Acceptance Criteria: * Setup of ServiceNow integration to pull AWS receive data using EventBridge * Unautherized API calls from GuardDuty and Security Hub * Setup Cloudwatch alarms or rules for all the resources entitled to be monitored and send these to SNS topic * Create SNS topic * Configure SNS HTTPS configuration so that SNS can directly invoke HTTPS endpoints * AWS Lambda function created to forward SNS messages by parsing it and sends REST API requests to ServiceNow. * Attach the Lamda to the SNS topic * Set the credentials in AWS Secret Manager * Lamda function can reach the ServiceNow endpoint through API gateway by using HTTPS and Secure authentication |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;04/Jul/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cfb2e84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04h5f: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-26 06:17 | [13 empty] | 26/May/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 8:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting to get a exact tags to be passed to Ec2 instance to receive at service now. *New HTTPS endpoint will be shared by feroz for the production workloads.* | 25/Jun/25 8:33 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;From 24th June we had a call with feroz, where we expected to get the production servicenow endpoint by nest week to configure in SNS, hence waiting for same to start this user story. | 02/Jul/25 7:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PRODUCTION ServiceNow Instance: [https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws¦https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws] SNS topic is updated with a new subscription and backend prod integration is completed, unit test yet to start. | 04/Jul/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Right now the production environments like Backend, TM1, AirnavX accounts are integrated with the prod service now endpoint and SNS is configured to get the alerts. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-04 08:15
AM20-783 | MQ ¦¦ POC customer Demo | Blocked | 6 | Sprint 6 | 2025-05-26 | 2025-06-06 | Sumit Nikam | High | 1672939 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-30 18:51 | 2026-01-30 19:53 | 2026-01-08 08:41 |  |  | 0 | As AWS architect, I would align with SAA stakeholders to give a demo on MQ PoC. *Acceptance Criteria*: * Demo given and next steps discussed with SAA. |  | Harsh Chandra | Sankalp Rai | Sumit Nikam |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67032dc2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pttb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 15 | Sprint 16 | Sprint 22 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 08:24 | [13 empty] | 20/May/25 10:23 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 26th May 2025 End Date: 30th May 2025 | 02/Jun/25 8:26 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;MQ has two option on AWS # Migrate existing MQ Servers to AWS # Use AWS Native MQ service We need a confirmation on approach from Sampi after which we will start working on LLD Document Moving to Blocked | 24/Sep/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Will be taken up once POC is completed in Sandbox | 17/Oct/25 11:21 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 30/Oct/25 9:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;LLD no longer needed To be considered for Modernization as per feedback from Gayaz. Next steps: # Analyze Amadeus response Perform PoC as per Amadeus requirements # Agreement with SAA based on PoC # SoW sigoff # Design Document # AmazonMQ Implementation # Queue by Queue migration | 08/Jan/26 8:48 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Awaiting for a go-ahead to setup a demo call with SAA. | [21 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | To Do | 2026-01-08 08:41
AM20-784 | PROS ¦¦ Establish connectivity port opening and firewall connectivity | Done | 3 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1773948 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 15:55 | 2026-01-24 16:21 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2f2b180d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwpv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-12 06:14 | [13 empty] | 12/Sep/25 8:14 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;On 11th the app owner Pieter has confirmed as we can go with single subnet for all 3 servers, Now i have initiated comms preparation. | 19/Sep/25 3:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been sent (16th Sep) and validated by Pieter on on 17th Sep 2025, again send mail to Pieter asking about any additional SITA side flows required or not. | 19/Sep/25 4:12 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Received feedback from Pieter and prepared final comms for SITA/VDC. Sent for LIFT and CSOC submiss towards for implementation. | 19/Sep/25 4:14 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Hence the action with SAA side, hence i am closing this Story. | [26 empty] | Done | 2025-09-22 08:50
AM20-785 | TM1 ¦¦ SSM provisioning and CloudWatch Agent with cutover instance | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1752616 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 20:20 | 2026-01-15 22:58 |  |  |  | 0 | As AWS expert, I would like to provision SSM and Cloudwatch on TM1 cutover instance Acceotance criteria: SSM instance and Cloudwatch instance is successfully provisioned |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Aug/25 8:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Aug/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@777f120 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dnlf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-13 06:17 | [13 empty] | 13/Aug/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cloud watch agent setup is completed, will configure the config.json file to fetch relevant server metrics and application metrics. | 13/Aug/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;after cloud watch configuration will start working on setting up SSM agent. | 14/Aug/25 8:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SSM agent installation is success upon stopping MacAfee and excluding from Trellix service. | 25/Aug/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 06:33
AM20-786 | SMS Alerting implementation- Opt in/Opt out | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824552 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-06 19:23 | 2026-02-06 21:34 |  | 2025-11-15 14:38 |  | 0 | As a cloud product owner I want application and platform alerts to be delivered via SMS from a dedicated long code so that on call engineers and stakeholders receive time critical notifications Acceptance criteria: *Long code configured and verified* - given the approved long code when I set SNS and SMS preferences then the long code is used as the origination identity for the supported countries and unsupported routes use the configured Sender ID feedback *E2E SMS on P1/P2* - Given the cloudWatch alarm changes to ALARM with severity ðŸ˜›1 when the alarm event is routed via EventBridge to the SNS topic than all active on-call receipients for the app+env recieve an SMS within 60s and message body includes app, env, alarm name, severity, runbook link and ACK instruction ¦¦*Severity*¦¦*objective signals*¦¦*examples*¦¦ ¦P1 - Critical, user impact¦harsh outage, data loss, security incdences¦API 5xx>10% 5m in production, RDS storage<5% 10m. certificate expiry < 3days, guard duty, unauthrized access¦ ¦P2 - Degradation,Urgent¦performance, throughput, redundancy lost,¦EKS node group<N healthy, ALB healthy, RDS IOPS deviation, CPU utilization, disk innode,¦ ¦P3 - Action soon¦Capacity/Ops issues, repeated flaps¦log patterns,¦ ¦P4 - Informational¦chnages , warnings, failures without user impact¦Daily back ok, lamda changes, deloyment success¦ *Delivery logging and metrics* - Given SMS messages are sent when carriers return delivery statuses then statuses are captured in CloudWatch logs and S3 and dashboards show sends, successes, failures, per country breakdown *Retry and escalations ( in the event of SMS failure)* - Given a send gets a transient failure when the system retries with backoff( up to 3 times in 5 minutes) then on persistent failure an escalation SMS is triggered to secondary contacts and a ticket is created in ServiceNow with failure details *Deduplication and storm control* - Given multiple identical alarms fire within 5 minutes when routing occurs then recipients receive at most one SMS per unique alarm/signature per 5 minute window and a summary SMS is sent after 15 minutes if >5 deduped alerts occurred. *Opt-out/Opt-in* - Given a recipient replied STOP when routing future SMS to that number then messages are surpassed and audit shows timestamp and actor and START re-enables *Cost Guardrails* - Given a monthly SMS budget when SNS spend reaches 80% then P2 alert is sent to Ops and at 100% sends are rate limited to P1 only until an override flag is set *Cross account publish* - Given alarms originate in child accounts when Event Bridge forwards to central account Then publishing to the central SNS topic succeeds via resources based and IAM roles |  | Harsh Chandra | Shreyash Talwekar | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Working on exploring the ways to implement cost guardrail for lambda. Exploring enabling cloudwatch metric to track the money spent on SMS sent through the account.;10/Nov/25 8:37 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on understanding how cost is shown in billing in case of SMS sent through SNS or SMS sent using End User Messaging.;11/Nov/25 3:39 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on updating lambda to get cross account cost metric to implement 80% cost guardrail to send notification only in case of P1 and P2 alarms when 80% threshold is breached.;11/Nov/25 3:40 PM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). Trying the opt-out mechanism for SA number(carrier blocking was cited as one of the issues behind blocking) and parallely raised a request to understand the issue.;13/Nov/25 8:04 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Deployed changes on production cluster.;14/Nov/25 8:18 AM;17cb9418-1850-4923-932b-7098ec51b6bb;14400 |  | 57600 | 0 | 129600 | 2.25 | 57600 | 0 | 129600 | [10 empty] | AM20-176 | [19 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3955b400 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h707: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:34 | 3_*:*_1_*:*_364054197_*¦*_10041_*:*_1_*:*_850843694_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Working on implementing cost guardrails to restrict sms sending to only P1 and P2 messages when 80% limit is utilised. | 11/Nov/25 8:25 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Will be testing using cost explorer API to fetch billing cost of SNS during Lambda execution. As per AWS docs, if we are using SNS for sending SMS then the metrics wonâ€™t get reflected on CloudWatch metrics. For opt-in/opt-out as per docs, user can send the STOP message to stop getting message. Need to try this part on our end. | 12/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Updated lambda to fetch amount spent on SMS sent using cost explorer API, currently able to fetch cross account. Working on updating Lambda to avoid duplication using DynamoDB. Testing in progress. | 13/Nov/25 8:02 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Able to fetch cost of sending SMS using API, able to avoid deduplication of alarms with the help of DynamoDB table. Currently Working on Opt-out Mechanism, yesterday tried auto opt-out with a STOP message to the sender number from an Indian number (this should work as per AWS Docs but number is not getting reflected in Opt-out list). | 14/Nov/25 8:19 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed changes on production account. | 15/Nov/25 2:38 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-15 14:38
AM20-787 | Tagging Compliance implementation | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834929 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 18:12 | 2026-01-18 18:19 | 2025-11-27 08:26 | 2025-11-28 11:38 |  | 0 | As product owner I would like to setup tagging compliance in centralized Cloudwatch dashboard so that I know how many workloads are not been tagged and take corrective actions accordingly |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;20/Nov/25 8:27 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;21/Nov/25 7:56 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;25/Nov/25 10:41 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;26/Nov/25 3:33 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;10800 | ;27/Nov/25 4:17 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;7200 |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 27/Nov/25 4:17 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251127-141419.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190266 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fa2be84 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mwv7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:50 | 3_*:*_1_*:*_633638841_*¦*_10041_*:*_1_*:*_597995286_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:50 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Satya sir is checking with leigh regarding the tag policy enable part after updating the tag policy will start working on the Tag compliance part. | 19/Nov/25 1:33 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have Enabled the Tag Compliance policy for all account. Waiting for security score. | 21/Nov/25 7:55 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Security score is visible for all accounts now next step is we are disabling the ID on with we donâ€™t require this tag compliance policy for all accounts. | 23/Nov/25 2:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have disabled the Tag Compliance policy for all the non required resource IDâ€™s for all 17 mandatory accounts. 746669190453â€ƒâ€ƒFlySAA_CMS_Backend_DevQA 216989128782Â Â Â Â Â Â Â FlySAA_CMS_Backend_PreProd 396608788916â€ƒâ€ƒFlySAA_CMS_Backend_Prod 209479274829â€ƒâ€ƒSAA TM1 345594574792â€ƒâ€ƒSAA AirnavxÂ 536697265099â€ƒâ€ƒSAA_NEXIOAV_PROD 650251698621â€ƒâ€ƒSAA_PROS_PROD 307946680641â€ƒâ€ƒSAA_Informatica_DEV 536697248966â€ƒâ€ƒSAA_Informatica_PROD 195973603339â€ƒâ€ƒvod001_001_payer9 300204747992â€ƒâ€ƒSAA-AuditÂ 730335236533â€ƒâ€ƒAWS_SAA_Security 080284287007â€ƒâ€ƒSAA-LogArchive 339712943527â€ƒâ€ƒAWS_SAA_Network 585768167545Â Â Â Â Â Â Â SharedVPCDevQA() 253490777663Â Â Â Â Â Â Â SharedVPCPreProd() 820242899278Â Â Â Â Â Â Â SharedVPCProd() | 25/Nov/25 10:40 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;For the Untagged one IDâ€™s we are remediating the failed ones as much as we can for all 17 accounts before getting the centralized dashboard enabled for Tag compliance. | 26/Nov/25 9:04 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Tag compliance security score is 95% for all 17 Accounts and to make it 100% we need to Tag IAM Roles for all Accounts and Each account contains more than 60 IAM Roles which is not possible for a Single person to tag them. I need team support to tag those IAM roles as its a manual work no automation will help as they are the existing resources not the new ones. | 26/Nov/25 3:32 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*UPDATE :* With the Help of lambda function we were able to tag all the IAM roles for all 17 accounts. Except the oneâ€™s which are not handled by our team and we are not authorized to tag them. | 27/Nov/25 4:17 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251127-141419.png¦width=629,alt="image-20251127-141419.png"! Tags has been implemented for all resources and in the security account under Security Hub we can see all the tagged resources and the information. | 28/Nov/25 11:38 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. Saw the data presented in review call. satisfied with results | [21 empty] | Done | 2025-11-28 11:38
AM20-788 | AWS Centralized dashboard CloudWatch Dashboard for Nexio AV to monitor Performance, cost optimization and security Metrics | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718753 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 21:14 | 2026-01-31 23:25 |  |  |  | 0 | As AWS expert, I would like to create centralized CloudWatch to capture Performance, Security and Cost metrics from across accounts. Acceptance Criteria: * CloudWatch dashboards can be created in one account (Payer9 account) anf pull metrics from other accounts * User cross account IAM roles to allow Payer9 account to read cloudwatch from other accounts * Add Widgets sourcing metrics from each account * Setup AWS config aggregator in the Payer9 account to collect configuration and compliance data across all members accounts * Performance metrics - Use below Cloudwatch metrics * EC2 : CPU, Network, Disk I/O * RDS: CPU, READ/Write IOPS * Lambda: Duration, Error Rate * and source these into widgets in the centralized dashboard * Security Metrics: Centralized Security Hub is already enabled, which can pull in findings from GuardDuty, Config, Macie, Cloudtrail, Inspector etc. |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60b85e0b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aofj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-23 14:43 | [13 empty] | 23/Jul/25 4:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Created Trellix Dash board with CPU, Memory and Disk usage. | 25/Jul/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dash board prepared for CPU, Disk, Network and memory for Trellix application. | 25/Jul/25 8:09 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sent for review | 27/Jul/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Could see the metrics for trellix server, moving to PO approval, | 28/Jul/25 9:57 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:57
AM20-789 | Restrict Admin access to VOIS team by creating dedicated IAM role | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Medium | 1736354 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 15:24 | 2026-02-03 16:09 |  |  |  | 0 | As Product Owner, I want to restrict VOIS team to have Admin role so that all of them cannot be superseded rights and bring more control on AWS management Acceptance criteria: * IAM role to be created for everyone except Sankalp and Aravind from AWS perspective * IAM role for network creation to be created and role assign to Satya * IAM role for rest of team members is of developer |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6edd432e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0c5zn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 06:20 | [13 empty] | 06/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have shared the Excel with the user list to team, upon there confirmation ill start creating custom policy with user groups. | 08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;¦UserID¦IAM user¦UserGroup¦IAM Role¦ ¦raja0001¦Aravind¦VOIS_Admin¦No changes, use existing roles itself¦ ¦rais0003¦Sankalp¦VOIS_Admin¦No changes, use existing roles itself¦ ¦SatyasairamV¦SatyaSairam¦VOIS_Admin¦No changes, use existing roles itself¦ ¦godir001¦Ravinder¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦kiraj001¦Jitender¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Sanjot¦Sanjot¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦nikas001¦Sumit¦VOIS_Admin¦No changes, use existing roles itself¦ ¦FaisalSayed¦Faizal¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SanketKale¦Sanket¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦pathp002¦Pankaj¦VOIS_DBAdmin_Usergroup¦AWS_VOIS_DBAdmin_Role¦ ¦onkar¦Onkar¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦DikshaK¦Diksha¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SatyabrataS¦SatyaBrata¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Shreyash¦Shreyash¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Harsh¦Harsh¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Yashwant¦Yashwant¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Utkarsh¦Utkarsh¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ Â Â Access to User group given as below, ¦VOIS_InfraAdmin_Usergroup¦VOIS_DevOpsAdmin_Usergroup¦VOIS_DBAdmin_Usergroup¦ ¦VPC FullAccess¦CodeBuild FullAccess¦RDS Full Access¦ ¦EC2 FullAccess¦CodePipeline FullAccess¦DMS Full Access¦ ¦S3 FullAccess¦EKS FullAccess¦IAM Full Access¦ ¦CloudWatch FullAccess¦EC2 except delete¦CloudTrail except delete¦ ¦RDS FullAccess¦S3 FullAccess¦KMS except delete¦ ¦IAM FullAccess¦CloudWatch except delete¦CloudWatch except delete¦ ¦CloudTrailFullAccess¦RDS except delete¦Read only¦ ¦MacieFullAccess¦IAM FullAccess¦ ¦ ¦GuardDutyFullAccess¦System managerFullAccess¦ ¦ ¦SecurityHubFullAccess¦LambdaFullAccess¦ ¦ ¦System managerFullAccess¦Event bridgeFullAccess¦ ¦ ¦LambdaFullAccess¦CloudTrail except delete¦ ¦ ¦KMSFullAccess¦Read only¦ ¦ ¦ACMFullAccess¦Secrets managerFullAccess¦ ¦ ¦Aws ConfigFullAccess¦SNSFullAccess¦ ¦ ¦Event bridgeFullAccess¦SESFullAccess¦ ¦ ¦InspectorFullAccess¦ECR FullAccess¦ ¦ ¦SupportFullAccess¦KMS except delete¦ ¦ ¦SNSFullAccess¦Â ¦ ¦ ¦SESFullAccess¦ ¦ ¦ ¦ReadOnly¦ ¦ ¦ ¦Secrets managerFullAccess¦ ¦ ¦ ¦ECRFullAccess¦ ¦ ¦ Â Users have access to the below AWS accounts, Â ¦AWS Account¦Account Name¦ ¦300204747992¦Audit¦ ¦730335236533¦Security¦ ¦080284287007¦LogArchive¦ ¦339712943527¦Network¦ ¦864899875361¦SharedServices¦ ¦585768167545¦SharedVpcDev¦ ¦253490777663¦SharedVpcPreprod¦ ¦820242899278¦SharedVpcProd¦ ¦746669190453¦Backend dev¦ ¦216989128782¦Backend Preprod¦ ¦396608788916¦Backend Prod¦ ¦209479274829¦Tm1¦ ¦345594574792¦AirNAVx¦ ¦536697265099¦NexioAV¦ | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-790 | AWS Centralized dashboard CloudWatch Dashboard for Nexio AV to monitor Performance, cost optimization and security Metrics | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718753 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 15:27 | 2026-01-11 18:39 |  |  |  | 0 | As AWS expert, I would like to create centralized CloudWatch to capture Performance, Security and Cost metrics from across accounts. Acceptance Criteria: * CloudWatch dashboards can be created in one account (Payer9 account) anf pull metrics from other accounts * User cross account IAM roles to allow Payer9 account to read cloudwatch from other accounts * Add Widgets sourcing metrics from each account * Setup AWS config aggregator in the Payer9 account to collect configuration and compliance data across all members accounts * Performance metrics - Use below Cloudwatch metrics * EC2 : CPU, Network, Disk I/O * RDS: CPU, READ/Write IOPS * Lambda: Duration, Error Rate * and source these into widgets in the centralized dashboard * Security Metrics: Centralized Security Hub is already enabled, which can pull in findings from GuardDuty, Config, Macie, Cloudtrail, Inspector etc. |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60b85e0b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aofj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-23 14:43 | [13 empty] | 23/Jul/25 4:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Created Trellix Dash board with CPU, Memory and Disk usage. | 25/Jul/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dash board prepared for CPU, Disk, Network and memory for Trellix application. | 25/Jul/25 8:09 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sent for review | 27/Jul/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Could see the metrics for trellix server, moving to PO approval, | 28/Jul/25 9:57 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:57
AM20-791 | AirNavX ¦¦ Create all EC2 instance using Terraform | Done | 0 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747550 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 12:50 | 2026-01-26 14:40 |  |  |  | 0 | As Product owner I would like to create EC2 instance (linux instance) in AirnavX account using terraform as it is green field solution so that AirnavX can be installed successfully and workloads can be run securely with proper governance control Acceptance criteria: EDC2 instance is provisioned in the correct subnet and AZ based on environment EC2 instance is launched with approved AMI as per OS and application requirements Instance type is selected according to Memory - 64 GB and CPUÂ - 8 cpu's, with a possibility to increase to a larger instance type if required Appropriate security group is attached to allow only required inbound/outbound traffic Instance tagged correctly with meta data CloudWatch agent installed and configured to collect system metrics and logs SSM agent is installed and instance is visible in AWS System Manager for patching commands EC2 instance boots successfully and is reachable via expected methods (SSM) |  | Satyabrata Sahoo | Yashwant Thakur |  |  |  |  | 712020:4b8d8093-596d-4394-a074-4a9a9636f86f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [29 empty] | 05/Sep/25 8:46 PM;d60b2ee4-0111-46b4-bb96-1c8a6e11be41;image-20250905-184351.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148823 | 05/Sep/25 8:46 PM;d60b2ee4-0111-46b4-bb96-1c8a6e11be41;image-20250905-184556.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148824 | 05/Sep/25 8:54 PM;d60b2ee4-0111-46b4-bb96-1c8a6e11be41;image-20250905-184949.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148825 | 05/Sep/25 8:54 PM;d60b2ee4-0111-46b4-bb96-1c8a6e11be41;image-20250905-185401.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148826 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@65476f0e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2y3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 20:50 | [13 empty] | 18/Aug/25 10:49 PM;712020:4b8d8093-596d-4394-a074-4a9a9636f86f;Base Module preparation is in progress. | 25/Aug/25 7:47 AM;712020:4b8d8093-596d-4394-a074-4a9a9636f86f;Modular EC2 Machine Terraform Code is ready and working as expected as show case in Demo, with all type of feature. Here Two Enhancement is required to the code. * Even Monitoring is enabled, there is no configuration related to Monitoring * Even Logging is enabled, There is no configuration to Logging These two enhancement required to conclude the stories. Hence this will be spill over. | 05/Sep/25 8:46 PM;712020:4b8d8093-596d-4394-a074-4a9a9636f86f;Updated the IAM Modules to create Instance Profile: base module: [feat(instance_profile): add modules by satyabrata-sahoo_voda Â· Pull Request #40 Â· VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa/pull/40] component module: [feat(iam_role): add instance profile by satyabrata-sahoo_voda Â· Pull Request #44 Â· VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/pull/44] Update the SSM Instance role which can be utilized by EC2: [flysaa / airnavx-flysaa-aws-terraform-project / Commit c0e4a7011932 â€” Bitbucket¦https://bitbucket.org/flysaa/airnavx-flysaa-aws-terraform-project/commits/c0e4a7011932921b2b32a2cd9ff95ca1cb069f78] EC2 instance Base Module: [terraform-base-modules-vfsa/modules/ec2-instance/variables.tf at ec2-instance/v0.1.1 Â· VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa/blob/ec2-instance/v0.1.1/modules/ec2-instance/variables.tf] EC2 Instance Component Module: [terraform-component-modules-vfsa/modules/ec2-instance at ec2-instance/v0.1.2 Â· VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/tree/ec2-instance/v0.1.2/modules/ec2-instance] Read me file on GITHUB: [terraform-component-modules-vfsa/modules/ec2-instance/README.md at master Â· VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/blob/master/modules/ec2-instance/README.md] Readme file in Bitbucket: [flysaa / airnavx-flysaa-aws-terraform-project ec2-instance.md â€” Bitbucket¦https://bitbucket.org/flysaa/airnavx-flysaa-aws-terraform-project/src/main/ec2-instance.md] End user can handled any installation using the script and configure it. Here SSM and CloudAgent has been installed. !image-20250905-184351.png¦width=100%,alt="image-20250905-184351.png"! !image-20250905-184556.png¦width=100%,alt="image-20250905-184556.png"! !image-20250905-184949.png¦width=100%,alt="image-20250905-184949.png"! !image-20250905-185401.png¦width=100%,alt="image-20250905-185401.png"! | 08/Sep/25 6:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:35
AM20-792 | Prepare Low Level design for migrating public DNS zones from on prem to AWS Route 53 | Done | 8 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1813226 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 15:25 | 2026-02-02 15:43 |  | 2025-11-12 08:17 |  | 0 | As Cloud solution architect I want to prepare a detailed low level design document for migration of existing public DNS zones from on-premises infrastructure to AWS Route 53 so that the implementation team has comprehensive technical reference covering architecture, configuration, dependencies, security and cutover details Acceptance criteria: LLD should define and include below points current state DNS architecture including list of zones, record types, TTLs, dependencies and authoritative name servers Target AWS architecture - including Route53 hosted zone hierarchy, account placement (centralized vs distributed), IAM roles/policies, query, logging, tagging and cross account access model record migration strategy and mapping describing how each existing record type (A,CNAME,MX,TXT,SPF,DKIM,SRV,ALIAS) will be represented in Route53 and any TTL adjustment needed Zone creation and import procedure - specifying tools( terraform, CLI), validation steps and naming conventions Cutover and roll back plan - covering TTL reduction timelines, registrat name server updates, validation and backout process Monitoring and alerting approach - query logging , health check, Cloudwatch integration, alerts channels (SNS/ServiceNow) Security and compliance considerations - access controls, audit logging. DNSSEC enablement plan and approval workflows Operational runbooks - pre-migration validation, cutover execution and post migration verification steps Risks, assumption, dependency |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1e65abb1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v04b | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 18 | [97 empty] | 3_*:*_1_*:*_951626717_*¦*_10041_*:*_1_*:*_1178762675_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_951626717_*¦*_10041_*:*_1_*:*_1178762675_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_951626717_*¦*_10041_*:*_1_*:*_1178762675_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_951626717_*¦*_10041_*:*_1_*:*_1178762675_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-11 06:33 | 3_*:*_1_*:*_951626717_*¦*_10041_*:*_1_*:*_1178762675_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 11/Nov/25 8:32 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Moving this to review as Sankalp has Jira access issues. | 12/Nov/25 8:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-11-12 08:17
AM20-793 | TM1 ¦¦ Cutover | Done | 4 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | High | 1651369 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 20:46 | 2026-02-02 00:13 |  |  |  | 0 | As AWS expert I would be performing the cutover for TM1 application. Acceptance Criteria: * Replication from on-prem is successfully stopped using API calls * Back up of TM1 VDC Server * Monitoring disable - VDC Server * Shutting down TM1 application in VDC * Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [TM1-application.awsflysaa.com¦http://TM1-application.awsflysaa.com] Server to the AD * MAT Testing completed successfully by SAA |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Aug/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 14/Aug/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250814-063655.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139643 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3da06808 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4i:x | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-04 06:12 | [13 empty] | 04/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for agent installation to complete | 13/Jun/25 5:58 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked with TM1 Agent Installation - [https://vodacom.atlassian.net/browse/FCBEM-593¦https://vodacom.atlassian.net/browse/FCBEM-593¦smart-link] | 27/Jul/25 10:00 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Performance testing is in progress. | 13/Aug/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have initiated a cutover and instance is up with the data and application. Testing is done awaiting for an formal approval on confirmation to finalize the cutover. have added server to the [awsflysaa.com¦http://awsflysaa.com] domain, installed cloud watch agent inside the server successfully. | 14/Aug/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cutover completed marking finalize cutover !image-20250814-063655.png¦width=1271,height=479,alt="image-20250814-063655.png"! | 20/Aug/25 8:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-08-20 08:10
AM20-794 | Informatica Server ¦¦ NACL and Security group creation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660593 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-21 15:06 | 2026-01-21 18:40 |  |  |  | 0 | As Network expert, I would be creating NACL and Security group along with inbound and outbound rules for Nexio AV Acceptance Criteria: NACL and Security group created successfully with all inbound and outbound rules |  | Aravind Raj | Harsh Chandra | Satya Varanasi | Shreyash Talwekar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 27/Jun/25 3:51 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-134901.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119369 | 27/Jun/25 3:51 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-134948.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119368 | 27/Jun/25 5:54 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155416.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119411 | 27/Jun/25 5:54 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155445.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119410 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4189bc9b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bbn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-16 08:01 | [13 empty] | 16/May/25 10:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Waiting for terraform code towards build this. | 20/May/25 5:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Deepak and team, this need to be addressed with terraform code the same has been prepared by Utkarsh, until core not ready this story may not possible to address. | 10/Jun/25 2:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still â€œShreyashâ€ checking Utkarsh script, this story depending with script testing and execution. | 16/Jun/25 9:06 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Terraform script is under modification by â€œShreyashâ€, as per his update it will be ready this week. Hence this is the reason for spill over Sprint7 to Sprint8. | 18/Jun/25 11:11 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The script is managing by â€œShreyashâ€ so i am assigning this task to him, once his work completes he will reassign to me. | 23/Jun/25 1:59 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We were able to create AWS resources (mentioned in previous mail ) using terraform scripts on sharedvpc-dev account. To address some requirements like adding naming conventions and state file management, we will have to add some changes in terraform scripts. Due to current sprint activities I might not be able to work on the changes in this sprint. | 27/Jun/25 3:46 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Prod NACL/SG has been created, & tested internet access and same working fine. !image-20250627-134901.png¦width=1092,height=400,alt="image-20250627-134901.png"! !image-20250627-134948.png¦width=1308,height=579,alt="image-20250627-134948.png"! sh-5.2$ ping [http://google.com¦http://google.com¦smart-link] PING [http://google.com¦http://google.com¦smart-link] (142.251.47.238) 56(84) bytes of data. 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=1 ttl=108 time=20.5 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=2 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=3 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=4 ttl=108 time=19.7 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=5 ttl=108 time=19.8 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=6 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=7 ttl=108 time=19.7 ms ^C --- [http://google.com¦http://google.com¦smart-link] ping statistics --- 7 packets transmitted, 7 received, 0% packet loss, time 6010ms rtt min/avg/max/mdev = 19.630/19.800/20.473/0.282 ms sh-5.2$ hostname [ip-10-40-0-213.awsflysaa.com¦http://ip-10-40-0-213.awsflysaa.com] sh-5.2$ ifconfig ens5: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 9001 inet 10.40.0.213 netmask 255.255.255.240 broadcast 10.40.0.223 inet6 fe80::4a7:ebff:fe03:c075 prefixlen 64 scopeid 0x20<link> ether 06:a7:eb:03:c0:75 txqueuelen 1000 (Ethernet) RX packets 1653 bytes 293385 (286.5 KiB) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 1809 bytes 265312 (259.0 KiB) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0 lo: flags=73<UP,LOOPBACK,RUNNING> mtu 65536 inet 127.0.0.1 netmask 255.0.0.0 inet6 ::1 prefixlen 128 scopeid 0x10<host> loop txqueuelen 1000 (Local Loopback) RX packets 12 bytes 1020 (1020.0 B) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 12 bytes 1020 (1020.0 B) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0. | 27/Jun/25 5:54 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev: NACL/SG got created. !image-20250627-155416.png¦width=1246,height=457,alt="image-20250627-155416.png"! !image-20250627-155445.png¦width=1155,height=624,alt="image-20250627-155445.png"! | 27/Jun/25 6:13 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;NACL and Route table created for informatica environment, route entry and NACL rules to be created upon network requirement. | 29/Jun/25 8:13 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [17 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-29 20:13
AM20-795 | Airnavx ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620850 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 15:22 | 2026-02-05 15:38 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [8 empty] | AM20-10 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4559db6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 8 | Sprint 9 | Sprint 12 | Sprint 13 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-25 06:58 | [13 empty] | 25/Jun/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Harsh and Deepak update, this need to address after TM1 and informatica servers network action, hence i am keeping this as blocked(As per Harsh update) | 28/Jul/25 8:51 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Currently app under LLD review once review done i will initiate comms for the same. SO this will be moved to next sprint. | 04/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on it according to recent LLD call review. | 07/Aug/25 8:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared, with latest subnet details, i will initiate mail communication with customer/app owner for flows review or in case any additional flows needed they should notify further process. | 12/Aug/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Shared comms to app owner for review and add in case needed any additional flows for the same. | 25/Aug/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms under validation by app owner, so this is right story for spill over to this sprint. | 26/Aug/25 1:04 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Initially after follow-up customer prepared and send comms. # During review i identified as comms as not prepared right way and reshared the same comms to customer for validation. # After continuous 3 days follow-up we have received comms from customer as on date 25th Aug 10:00 PM. # There is no sufficient time to manage this story in this sprint due delay with customer. # Note: It has been communicated customer and management regularly but he took longer time to manage. | 29/Aug/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Reviewed and prepared AirNavX comms for VDC/SITA sheets and same sent app owner for LIFT/CSOC request towards implementation. | 03/Sep/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been reviewed and submitted to app owner for further process. | 03/Sep/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Albert has been submitted requested LIFT and CSOC request for ports androuting implementation. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 03/Sep/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The below is the current status: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Routing already in place hance not required any action on this and making this as completed.) | 08/Sep/25 6:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [15 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:36
AM20-796 | TM1 ¦¦ Firewall Rule creation | Done | 2 | Sprint 3 | 2025-04-14 | 2025-04-25 | Sankalp Rai | Medium | 1644189 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 17:10 | 2026-02-03 18:41 |  |  |  | 0 | As AWS expert I will be creating firewall rules for TM1 application so that security compliance can be met Acceptance Criteria: * Firewall rules are created and sent to Vodacom implementation |  | Sankalp Rai | [5 empty] | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [5 empty] | ;17/Apr/25 11:05 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b493d0d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-14 07:44 | [13 empty] | 14/Apr/25 9:44 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Call Pending on Firewall placement. Call scheduled for 15th April 2025 Vodacom: Leigh to manage the Firewall and create Rules on Firewall VOIS: Raise request for Firewall Rule in the provided Format | 17/Apr/25 11:06 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;AWS Network Firewall is for monitoring internet traffic coming into AWS and going out of AWS. TM1 does not require any connectivity over internet. Connectivity to TerraData is being done internally Some of the VMs under TerraData right now are being moved to Shared VPC. SAP Rise connectivity is not required. Since TM1 does not require internet connectivity, there is no need to create AWS Network Firewall rules for TM1 Moving to in review for closure | [25 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-21 09:03
AM20-797 | Nexio AV ¦¦ Configuring Application specific error in Cloudwatch for alerting | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730277 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 13:28 | 2026-01-15 13:44 |  |  |  | 0 | As a AWS expert I want to detect application specific error patterns in CloudWatch logs so that I can generate alerts for ServiceNow ticket creation and respond to runtime failure Acceptance Criteria: * Error pattern is defined and tested * Given an application output logs to cloudwatch when a known error occurs, then the pattern must correctly match that log * Metric filter is created - when error count exceeds the threshold then cloud watch alarm should trigger * Alert notification is sent, given the alarm is triggered when the condition is met then an alert must be sent to relevant teams |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [25 empty] | AM20-117 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a72bd8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bnaz: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:37 | [13 empty] | 04/Aug/25 6:36 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will start working on this from today. | 08/Aug/25 9:01 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Used â€œGet-Servicesâ€ command with flags like running and contains trellix to analyse services to be monitored. 8 services identified. Created script for monitoring commit size of each service and in the â€œ*NexioAV/ServiceMemory*â€ namespace and the Overall commit size of EC2 is being monitored in â€œ*System/Memory*â€ namespace. Created alarm for Overall Commit Size threshold is 20GB for now since there is no communication on what should the threshold unlike TM1. | 11/Aug/25 4:27 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-798 | ServiceNow ¦¦ SNS Topic for Alerts | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650429 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 15:01 | 2026-02-02 17:26 |  |  |  | 0 | AS AWS Expert, I want to create an Amazon SNS topic so that AWS services can be publish alert messages to it. Acceptance Criteria: * AN SNS topic is created * Permissions are set to allow EventBridge and Lamda to publish to it * The topic supports the subscription |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@505787e3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [66 empty] | Unit Tested | [51 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-06 06:23 | [13 empty] | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed, and will modify the required configurations. Â· | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:38
AM20-799 | PROS ¦¦ LLD Creation | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Sankalp Rai | Medium | 1749504 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 20:14 | 2026-01-12 20:43 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1809d79f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0danv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | Sprint 15 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 06:06 | [13 empty] | 06/Oct/25 8:05 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;LLD document created. | 06/Oct/25 8:07 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;[PROS_Low Level Design Document_v1.0.docx¦https://vodafone.sharepoint.com/:w:/r/sites/SouthAfricaAirlines/Shared%20Documents/Technical%20Documents/SAA%20Design%20documents/LLD%20Documents/Wave%202%20apps/PROS%20LLD/PROS_Low%20Level%20Design%20Document_v1.0.docx?d=w4faebf320e0f4c53aedb5b192660de4f&csf=1&web=1&e=jOZXIo] | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-10-06 08:07
AM20-800 | CloudWatch Metrics configuration in all AWS account | To Do | 0 | None( Backlog) |  |  | Faisal Sayed | Medium | 1868810 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 13:14 | 2026-01-21 14:03 | 2026-01-06 08:22 |  |  | 0 | As Cloud Product Owner I wish to configure below metrices in Cloudwatch for all the AWS accounts so that we can monitor the memory and Disk availability for each applications residing over the AWS accounts. * Memory Available MBytes * LogicalDisk % Free Space * LogicalDisk Free Megabytes Acceptance Criteria * CloudWatch dashboard must consist of all the above mentioned metrics for all application so that we can view the memory and disk available space * Only specific IAM role must give permission to the CloudWatch agent to collect metrics from server * The above metrics view is restricted with relevant IAM role * The dashboard must be configured in centralized audit account ¦ ¦ | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@32f363c4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0002 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-28 08:08
AM20-801 | CMS Backend RDS instance (Pre-prod/Prod) analysis | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1833687 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 13:49 | 2026-01-28 15:55 |  | 2025-11-27 09:21 |  | 0 | As Product owner I like to analyse RDS for rightsizing based on utlization to reduce cost |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Nov/25 5:10 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;21600 | ;25/Nov/25 4:08 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;64800 |  |  |  |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 18/Nov/25 5:09 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251118-150648.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1185982 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6460780 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo2n: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 15:10 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 5:09 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;RDS cost analysis is started. Today, we have reduced backup retention period of preprod rds to 7 days from 35 days. Also, storage limit threshold for dev rds is updated to 200 GiB from 110GiB because it was generating alerts â€œ*_Storage size 100 GiB is approaching the maximum storage threshold 110 GiB. Increase the maximum storage threshold_*â€ !image-20251118-150648.png¦width=459,alt="image-20251118-150648.png"! Next we will monitor cpu, memory consumption across three environments | 25/Nov/25 4:15 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;h3. Next Steps for CMS Backend RDS Cost Optimization With discussion with Pankaj, we have identified the following points as next steps for CMS Backend RDS cost optimization: * Turn off non-prod RDS instances when not in use or during off-business hours and turn them back on when required. * Further reduce backup retention period for non-prod RDS instances (currently 7 days) to explore additional cost savings. These actions will be implemented post confirmation from FlySAA team. | 27/Nov/25 9:21 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:21
AM20-802 | TM1 ¦¦ Integration of AWS IAM roles with TM1 AWS Account Instance using JSON | Done | 10 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642068 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 18:26 | 2026-01-09 20:57 |  |  |  | 0 | As AWS expert, I would be integrating AWS IAM roles with TM1 Instance Acceptance criteria: * IAM roles are created successfully * Integration of defined IAM roles with TM1 instance so that user is able to access the TM1 instance. |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5190a6ea | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-09 07:30 | [13 empty] | 09/Jul/25 9:29 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Following are the details of the role created: role_arn = "arn:aws:iam::209479274829:role/TM1-IAMRole-EC2InstanceProfile" role_name = "TM1-IAMRole-EC2InstanceProfile" Account details: 209479274829 (SAA-TM1) Custom Role Details: The role covers the equivalent of â€œAmazonSSMManagedInstanceCoreâ€, basic CloudWatch Agent permissions, and general S3 access. _*NOTE*: THE FOLLOWING HAS BEEN ACHIEVED USING TERRAFORM._ | 09/Jul/25 9:30 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;.json file of the custom role is as follows: { Â "Version": "2012-10-17", Â "Statement": [ Â Â { Â Â Â "Sid": "SSMManagedInstanceCorePermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssm:DescribeAssociation", Â Â Â Â "ssm:GetDeployablePatchSnapshotForInstance", Â Â Â Â "ssm:GetDocument", Â Â Â Â "ssm:DescribeDocument", Â Â Â Â "ssm:GetManifest", Â Â Â Â "ssm:GetParameter", Â Â Â Â "ssm:GetParameters", Â Â Â Â "ssm:ListAssociations", Â Â Â Â "ssm:ListInstanceAssociations", Â Â Â Â "ssm:PutInventory", Â Â Â Â "ssm:PutComplianceItems", Â Â Â Â "ssm:PutConfigurePackageResult", Â Â Â Â "ssm:UpdateAssociationStatus", Â Â Â Â "ssm:UpdateInstanceAssociationStatus", Â Â Â Â "ssm:UpdateInstanceInformation" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "SSMMessageGatewayPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssmmessages:CreateControlChannel", Â Â Â Â "ssmmessages:CreateDataChannel", Â Â Â Â "ssmmessages:OpenControlChannel", Â Â Â Â "ssmmessages:OpenDataChannel" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "EC2MessagesPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ec2messages:AcknowledgeMessage", Â Â Â Â "ec2messages:DeleteMessage", Â Â Â Â "ec2messages:FailMessage", Â Â Â Â "ec2messages:GetEndpoint", Â Â Â Â "ec2messages:GetMessages", Â Â Â Â "ec2messages:SendReply" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "CloudWatchAgentPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "logs:CreateLogGroup", Â Â Â Â "logs:CreateLogStream", Â Â Â Â "logs:PutLogEvents", Â Â Â Â "logs:DescribeLogGroups", Â Â Â Â "logs:DescribeLogStreams", Â Â Â Â "cloudwatch:PutMetricData" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "S3AccessPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "s3:GetObject", Â Â Â Â "s3:PutObject", Â Â Â Â "s3:ListBucket" Â Â Â ], Â Â Â "Resource": "*" Â Â } Â ] } | 11/Jul/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed IAM roles is having required permissions | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-803 | RDS default config changes in Dev environment | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Pankaj Pathak | Medium | 1869424 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-16 14:53 | 2026-01-16 15:52 | 2026-01-02 08:18 |  |  | 0 | h2. Summary Changes are needed for the RDS default configuration. This includes modifying the default port for MySQL and changing the default database user. h2. Context The current setup uses the default MySQL port and user. Adjustments are required for improved security and monitoring. h2. Acceptance criteria * Change the default port for MySQL RDS from 3306 to a different port. * Change the default database user from 'admin' to a different username. * Enable enhanced monitoring for the production instance. h2. Other information N/A |  | Aravind Raj | Pankaj Pathak |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb |  |  |  |  | ;11/Dec/25 3:56 PM;0bd64ee0-8d59-462f-ab15-54fcd1a1fb2b;28800 | [6 empty] | 43200 | 28800 |  |  | 43200 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2aacc09d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obsr: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-05 13:32 | [13 empty] | 05/Dec/25 3:31 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Awaiting application team to confirm feasibility post updating port number. | 11/Dec/25 12:41 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;This subtask has dependency over application team availability to transition the port change on RDS instance. | 11/Dec/25 3:26 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;RDS Database port has been updated and shared with [~accountid:712020:5d317226-2402-463f-bda5-c2cac5f43c13] . However default superuser name â€œAdminâ€ is immutable and canâ€™t be updated. It can only be changed during instance creation. | 12/Dec/25 10:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;I could see the custom RDS port changes made only to dev environment, so switching back to in progress state. Upon completing preprod and prod this US can be marked as closed. | 02/Jan/26 8:27 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;This has been discussed with Project Owner and agreed and understood that this change is only feasible on Dev environment because it require downtime and changes around firewall and other important network components. On Dev RDS we updated port details and â€œadminâ€ user canâ€™t be changed as it is immutable. | [22 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2026-01-02 08:31
AM20-804 | Tagging validations for AWS workloads across environments | Done | 0 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1749567 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 18:07 | 2026-01-22 19:51 |  |  |  | 0 | As AWS expert, Tagging of all resources must be completed and verified |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@24bea93e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0daxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:59 | [13 empty] | 25/Aug/25 8:59 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill over :* I will be reviewing & Attaching the sheet here in US as on friday EOD sanjot & shreyash updated the tags and added them on sheet thatâ€™s why this story got spilled over. | 25/Aug/25 10:03 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have reviewed the sheet all tags are updated for all resources. [Validation sheet for Naming and tagging for FLYSAA_CMS_BACKEND DEV PREPROD & PROD.xlsx¦https://vodafone.sharepoint.com/:x:/r/sites/SouthAfricaAirlines/_layouts/15/Doc.aspx?sourcedoc=%7BD95F49D1-A6B2-4430-A48E-1925ADA79A0D%7D&file=Validation%20sheet%20for%20Naming%20and%20tagging%20for%20FLYSAA_CMS_BACKEND%20DEV%20PREPROD%20%26%20PROD.xlsx&action=default&mobileredirect=true] | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:56
AM20-805 | Cynet ¦¦ Server Installation | To Do |  | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1887432 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 20:21 | 2026-01-24 23:18 | 2026-01-07 08:19 |  |  | 0 | As Product owner I want to install Cynet agent on Linux/Windows EC2 instance so that threat detechtion and response coverage is enabled Acceptance Criteria. *Linux*: * Installation package hosted/accessible securely (S3 with KMS, repo, or Cynet direct download). * SSM document / automation executes successfully on a pilot group and then on all in-scope instances. * Agent registers to correct Cynet tenant and shows â€œonline/healthyâ€ in console within defined SLA (e.g., 15 minutes). * Installation is idempotent (re-run does not break existing installation). * Logging captured: instance ID, hostname, timestamp, status, version, and failure reason if any. *Windows*: * Silent install works (msi/exe unattended flags), including token/tenant configuration. * Service is running after installation and agent appears healthy in console. * Windows Event Logs / install logs are retained for troubleshooting. * | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@19d1d99d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0q0i3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2026-01-06 13:12
AM20-806 | (Airchef)Terraform code generation for Route 53 Hosted Zone Creation & Record Migration. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Faisal Sayed | Medium | 1827706 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-22 13:28 | 2026-01-22 15:48 |  |  |  | 0 | Hosted Zone Creation Develop infrastructure-as-code to provision a Route 53 hosted zone for the specified domain. The configuration should support tagging, environment-specific naming, and be reusable across deployments. DNS Record Management Implement a declarative script to define and manage DNS records within the hosted zone. This should include support for common record types (A, CNAME, MX, TXT) with configurable TTLs and values. |  | Faisal Sayed | Sanket Kale |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e |  |  |  |  | ;12/Nov/25 10:17 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 |  |  |  |  | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@53b50383 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1v7: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:56 | [13 empty] | 07/Nov/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status: Blocked* Awaiting SAA approval for the updated DNS records associated with the {{airchef}} domain. Terraform provisioning is currently on hold until the DNS configuration is finalized. | 12/Nov/25 6:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status Update:* * Task moved from *Blocked* to *In Progress*. * Terraform code for Route 53 provisioning has been developed and handed over to *Sanket*. * *Next Action:* Sanket to review and execute the code in the *sandbox account* for validation. | 12/Nov/25 6:55 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform code has been successfully reviewed and tested in the sandbox environment, and all validations are positive. Â | 12/Nov/25 10:16 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Code has been reviewed, tested successfully, and validated. Moving the sub-story to *Done*. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-12 10:12
AM20-807 | TM1 ¦¦ Subnet creation using terraform | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Satya Varanasi | Medium | 1620359 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 18:25 | 2026-01-20 22:10 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for TM1 application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for TM1 and the configured based on the approved comms matrix |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-11 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a96537d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnn3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:53 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 04/Apr/25 10:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation got completed Manuel. As terraform not ready. While creating this TM1 subnets. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-07 10:11
AM20-808 | Informatica Server - Dev ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1749537 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 21:46 | 2026-01-27 23:49 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 57600 |  | 0 | 86400 | 57600 | [9 empty] | AM20-145 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b90196e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0datf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 14:28 | [13 empty] | 18/Aug/25 4:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev MGN template has been configured, now we are looking AWS migration agent installation on server for sync, Sinjun going to take care tomorrow for the same i have scheduled the call. | 19/Aug/25 5:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;While checking AWS agent connectivity not working, checking with network team for further troubleshooting/fixing the issue. CSOC request has-been createdâ€CINC0909706â€ | 25/Aug/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network routing not implemented, currently it under approval process. | 26/Aug/25 1:11 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Firewall rules implemented. # Configured MGN agent setup on AWS for dev server migration. # Identified as connectivity not working. # Initiated network troubleshooting call towards fixing. # Identified as routing not configured. # Requested LIFT for approval # LIFT approval took 3days # Monday CSOC request raised and routing has ben implemented. # Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 29/Aug/25 8:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Dev agent installation and Test instance setup has been complted. | 01/Sep/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The test instance connectivity has been completed. Communicated to Peter for connectivity testing. The ip address is: 10.42.0.46. Sending this request for closing. | 03/Sep/25 8:56 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-809 | Voager connectivity | Done | 2 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1872880 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 17:52 | 2026-01-31 18:49 | 2025-12-14 19:04 | 2025-12-12 11:20 |  | 0 | Static Routes need to be setup. Advertise Subnets DX. Establish Routing |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;04/Dec/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [12 empty] | 02/Dec/25 5:02 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251202-150140.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1191675 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a461fc5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0oflf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-02 15:02 | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Dec/25 5:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Static routes has been implemented. Notified customer to submit CSOC for routing implementation.(CHR0031699) !image-20251202-150140.png¦width=612,alt="image-20251202-150140.png"! | 02/Dec/25 5:10 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Routing has been implemented and connectivity has been implemented. | 04/Dec/25 8:19 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Customer validated connectivity and working fine, hence resolving this story. | 12/Dec/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-12-12 11:20
AM20-810 | Nexio AV ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 5 | 2025-05-12 | 2025-05-23 | Satya Varanasi | High | 1650865 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 14:46 | 2026-01-23 17:53 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5c904e9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akl: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 15:23 | [13 empty] | 20/May/25 5:23 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This Story dependency with comms implementation, the same with SAA team. Once SAA team actioned this story will be handled and closed until that this will not possible to address.(Note: it may move next sprint also) | 10/Jun/25 2:08 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0; No longer needed based on recent conversation. * Based on request from Sinjun, the migration approach for Trellix/NexioAV has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. Â | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-10 14:08
AM20-811 | Terraform Role- resources creation required IAM role | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Sanket Kale | Medium | 1741159 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-05 16:00 | 2026-02-05 16:36 |  |  |  | 0 | Provide me all required roles and policy for the resource creation using terraform. Example : With Ec2 instance what all the policy you will be assigning with the role attached, in similar we many need for all the resources your creating using terraform. |  | Aravind Raj | Sanket Kale |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:91948faf-1676-4820-bf6b-d50a7992943e | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@57f5389f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckg3: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 05:07 | [13 empty] | 11/Aug/25 7:06 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;It will be spill over due to priority tasks of Nexio backup process. | [26 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-25 07:56
AM20-812 | Adding description for CloudWatch notifications sent to ServiceNow for AWS infrastructure resources | Done |  | Sprint 21 | 2025-12-22 | 2026-01-02 | Shreyash Talwekar | Medium | 1883876 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2026-01-10 19:40 | 2026-01-10 20:35 | 2025-12-18 08:18 |  |  | 0 | Update the lambda functions to sent description of CloudWatch alarms in the payload to be sent ServiceNow. |  | Diksha Koul | Shreyash Talwekar |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  |  | ;18/Dec/25 8:28 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;14400 | [5 empty] | 14400 | 0 | 14400 | 1 | 14400 | 0 | 14400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@449d7c5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pm6b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-18 06:31 | [13 empty] | 18/Dec/25 8:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have updated the reason and Description for all prod, dev & qa lambda functions and also tested that as well. | [26 empty] | 1881266 | AM20-302 | Convert Alarms description into simple user understandable format | Done | 2026-01-02 08:22
AM20-813 | Trellix integration with AirnavX | Done | 1 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 17:43 | 2026-01-10 18:31 |  | 2025-11-12 08:22 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan AirNavX workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in AirNavX server * Trellix is able to access AirnavX account successfully and perform scanning |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 05/Nov/25 3:41 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ Trellix scanning status for New AWS AirNavV servers.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1178115 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f4c84b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 18 | [95 empty] | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [65 empty] | YES | YES | 2025-09-08 07:56 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [12 empty] | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 30/Sep/25 7:40 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working with Sinjun for trellix installation on these 2 servers. | 06/Oct/25 8:39 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Working with Sinjun for Trellix installation, hence will be spilled over | 09/Oct/25 4:29 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Sinjun Albert is going to install Trellix and he will confirm once integration done. | 17/Oct/25 11:17 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over reason - Blocked due to ongoing app installation issues, currently worked upon by app owner; post which this story will be progressed in subsequent sprint | 05/Nov/25 3:41 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Trellix software installed on New AWS AirNavX servers. All AirNavX servers able to discover from Trellix admin server and same has been confirmed by Sinjun. Attaching reference for support. [^RE_ Trellix scanning status for New AWS AirNavV servers.msg] | 12/Nov/25 8:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | Done | 2025-11-12 08:22
AM20-814 | Nexio AV ¦¦ Configuring Application specific error in Cloudwatch for alerting | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | High | 1730277 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 12:57 | 2026-01-31 14:23 |  |  |  | 0 | As a AWS expert I want to detect application specific error patterns in CloudWatch logs so that I can generate alerts for ServiceNow ticket creation and respond to runtime failure Acceptance Criteria: * Error pattern is defined and tested * Given an application output logs to cloudwatch when a known error occurs, then the pattern must correctly match that log * Metric filter is created - when error count exceeds the threshold then cloud watch alarm should trigger * Alert notification is sent, given the alarm is triggered when the condition is met then an alert must be sent to relevant teams |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [25 empty] | AM20-117 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a72bd8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bnaz: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:37 | [13 empty] | 04/Aug/25 6:36 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will start working on this from today. | 08/Aug/25 9:01 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Used â€œGet-Servicesâ€ command with flags like running and contains trellix to analyse services to be monitored. 8 services identified. Created script for monitoring commit size of each service and in the â€œ*NexioAV/ServiceMemory*â€ namespace and the Overall commit size of EC2 is being monitored in â€œ*System/Memory*â€ namespace. Created alarm for Overall Commit Size threshold is 20GB for now since there is no communication on what should the threshold unlike TM1. | 11/Aug/25 4:27 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-815 | PROS ¦ Test-Over Instance | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | Medium | 1801095 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-30 17:10 | 2026-01-30 20:32 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@32a969b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0izhn: | [167 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 07/Oct/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Server replication is still on-going after completion of initial sync will start launching test instance. have updated the launch templet based on the LLD document. | 09/Oct/25 6:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test launch instance hand over is completed, awaiting for the response back from the application owner. | 17/Oct/25 11:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;connectivity issue is resolved, have received date to perform cutover. | [24 empty] | 1773952 | AM20-170 | PROS ¦¦ Cutover | Done | 2025-10-17 11:08
AM20-816 | Informatica Server - Prod ¦¦ Migration Agent provisioning | Done | 6 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Highest | 1752123 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 17:30 | 2026-01-27 20:00 |  |  |  | 0 | As AWS migration expert I want to install AWS migration agent on selected source servers for Informatica server of dev and prod environments so that I can replicate the workloads to AWS seamless migration and testing Acceptance criteria: A list of all source servers ( IP address, OS type, credentials) is documented and approved for agent installation The sourceservers meet the AWS agent pre-requisite outbound internet access or a proxy is available to allow the agent communication with AWS MGN endpoint The required IAM role with minimum permission is created and attached The MGN agent is downloaded from AWS and installed using authmated script or manually on all listed sources After installation each agent successfully connects to AWS MGN and the server status is visible in the AWS MGN console The replication process begins and initial data is visible in AWS MGN dashboard logs are collected to verify successful installation Agent installation is validated as part of the migration readiness checklist |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [10 empty] | AM20-136 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1d85433a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dlmz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-29 06:01 | [13 empty] | 29/Aug/25 8:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As it is handled by Arvind so assign to Arvind. | 05/Sep/25 9:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Agent installation is completed and replication followed by initial sync is completed too. | 05/Sep/25 10:29 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-05 10:29
AM20-817 | BackUP Server ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | Medium | 1681815 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 19:34 | 2026-02-02 23:09 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across BackUP server account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Jun/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43003ef3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4f: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-05 06:17 | [13 empty] | 05/Jun/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Config and guard Duty is enabled and configured. Cloud Trails logging is enabled already. | 06/Jun/25 8:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard rail implementation is applied for the S3 block public access | 13/Jun/25 2:36 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-13 14:36
AM20-818 | Disaster Recovery and Backup | In Progress |  | None( Epic) |  |  | Yashwant Thakur | Critical | 1717990 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 20:22 | 2026-02-03 22:56 |  |  |  | 0 | Automated Backup and Disaster Recovery Infrastructure via Terraform or manual |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [15 empty] | 432000 | 374400 | 86400 | [12 empty] | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133603.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175536 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133705.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175534 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175537 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133947.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175535 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2309b367 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-9 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | orange | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0anuj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-30 13:41 | [13 empty] | 30/Oct/25 3:40 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Validated PROS & Informatica backups, all are configure fine. Pros back up status: !image-20251030-133603.png¦width=612,alt="image-20251030-133603.png"! Policy: !image-20251030-133705.png¦width=597,alt="image-20251030-133705.png"! Informatica Prod Backup: !image-20251030-133909.png¦width=597,alt="image-20251030-133909.png"! Status: !image-20251030-133947.png¦width=597,alt="image-20251030-133947.png"! | 13/Nov/25 8:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Backup has been configured and working fine. DR step-up is done still sync in progress. Once sync completed we can initiate call for testing. | [28 empty] | In Progress | 2025-10-30 15:30
AM20-819 | MQ POC -SbrSplit Parser Testing | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1863568 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 17:11 | 2026-02-06 17:52 | 2026-01-04 09:12 | 2026-01-02 11:05 |  | 0 | I need to test SbrSplit MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [5 empty] | ;17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;18000 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;23/Dec/25 8:26 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18120 | 115200 | 0 | 115320 | 1 | 115200 | 0 | 115320 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2372d0ee | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o64r: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 21 | [97 empty] | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-09 06:22 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 09/Dec/25 8:21 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Testing has been started. Few errors were identified during execution of jar files. Being checked further. | 11/Dec/25 8:17 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Still working on error fixes | 17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Errors have been fixed and initial testing has been completed. | [27 empty] | Done | 2026-01-02 11:05
AM20-820 | ServiceNow ¦¦ CloudWatch Rule for Error detection | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650995 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 14:49 | 2026-01-30 16:29 |  |  |  | 0 | As a AWS engineer, I want to create CloudWatch alarms to send error-level logs to be notified of infrastructure issues Acceptance criteria: * CloudWatch metric filters to be configured to match specific error patterns or log levels |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fabfe65 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0280b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 06:03 | [13 empty] | 29/Apr/25 8:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will review utkarsh terraform script and will assign this story to him. | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed. | 07/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;We can use utkarsh terraform script for cloud watch alarm creation, but sns topic cant be modified so we need manual update to SNS access policy. | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:39 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [22 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:39
AM20-821 | Terraform code for route 53 implementation | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Satya Varanasi | Medium | 1835009 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-03 19:29 | 2026-02-03 20:29 | 2025-11-27 08:28 |  |  | 0 | [airchefs.co.za¦http://airchefs.co.za] hosted zone need to setup via Terraform. |  | Harsh Chandra | Sanket Kale | Satya Varanasi |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ca1ef33 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mx8b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-25 06:19 | [13 empty] | 25/Nov/25 8:19 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Hosted zone setup is completed on Network account and also validated with internal team. Updated the status as in review and reassign it to Satyasairam. | 27/Nov/25 10:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration done currently all pointing to [airchefs.co.za¦http://airchefs.co.za] is pointing to AWS. | [25 empty] | 1832849 | AM20-262 | Route53 implementation using terraform - Phase 1 | Done | 2025-11-27 10:24
AM20-822 | TM1 ¦¦ Replicated Test server creation | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1648987 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 12:44 | 2026-02-03 14:33 |  |  |  | 0 | AS AWS expert, I would be provisioning TM1 test server as replica server to allow to perform initial validations *Acceptance Criteria*: * TM1 replica test server is successfully created * Internal team is able to access server successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;21/Apr/25 11:47 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;24/Apr/25 5:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1f9453f2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:r | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-21 09:47 | [13 empty] | 21/Apr/25 11:46 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test Launch instance is launched with the help of launch template, able to telnet the TM1 server from bastion host. Waiting for TM1 local account credentials to login to server and verify the connectivity. | 24/Apr/25 5:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Server handover to application team yesterday, hence marking this to done status | 02/May/25 4:57 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-24 05:45
AM20-823 | AirNavX Account ¦¦ Security Compliance Implementation | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672716 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-30 12:43 | 2026-01-30 13:46 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of AirNavX account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250528-092239.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1106065 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@33a69e54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04ft7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-28 09:24 | [13 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Account - 345594574792 Controls were implemented and security score is updated is for all the three security standard frameworks- CIS, NIST and AWS FSBP !image-20250528-092239.png¦width=1279,height=589,alt="image-20250528-092239.png"! | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-28 11:24
AM20-824 | Rename Citrix account with informatica Prod: Re-establish Informatica ¦¦ Subnet Configuration and Setup platform | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1749511 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 22:15 | 2026-01-26 00:30 |  |  |  | 0 | As Network expert, I would like to provision subnet configuration for PROS application Acceptance criteria: * Subnet configuration completed successfully * Tagging of all network elements associated done succesfully * Traffic flow testing and validation is concluded |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153624.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141700 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153747.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141702 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-154222.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141701 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@e805dba | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dap7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 06:22 | [13 empty] | 12/Aug/25 8:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;We are looking account id rename or new id creation process accordingly i will proceed for next steps. | 19/Aug/25 5:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Citrix Account ID has been renamed with Informatica Prod â€œ536697248966 â€ƒâ€ƒ SAA_Informatica_PRODâ€ | 19/Aug/25 5:42 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet, NACL, RAM ,SG and connectivity has been established. !image-20250819-153624.png¦width=1417,height=750,alt="image-20250819-153624.png"! Connectivity has been tested and working fine. !image-20250819-153747.png¦width=1417,height=750,alt="image-20250819-153747.png"! ¦Informatica Prod-Public¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.0.208/28¦10.40.0.208 - 10.40.0.223¦10.40.0.209 - 10.40.0.222¦14¦/28¦ ¦Informatica Prod-Public(DR)¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.128/28¦10.40.1.128 - 10.40.1.143¦10.40.1.129 - 10.40.1.142¦14¦/28¦Â ¦AZ2¦ !image-20250819-154222.png¦width=1417,height=750,alt="image-20250819-154222.png"! | 19/Aug/25 5:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Assigning for review. | 21/Aug/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed with internet acess. | 25/Aug/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 06:33
AM20-825 | Nexio AV ¦¦ CloudTrail and GuardDuty & AWS config Implementation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | High | 1660681 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-28 18:36 | 2026-01-28 21:16 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across NexioAV account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;07/May/25 8:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@319a088e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bmj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-06 06:25 | [13 empty] | 06/May/25 8:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cloud Trails logs to push S3 bucket were implemented already through SCP, now working with guard duty and AWs config enablement. | 07/May/25 8:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Guard Duty and AWs config is enabled, along with trail. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-07 08:28
AM20-826 | TM1 ¦¦ Monitoring Servers post migration | Done | 1 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | High | 1651402 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 15:20 | 2026-01-18 18:46 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if TM1 server service is stopped |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 20/Aug/25 6:27 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250820-162717.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1142337 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2a36f4c8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4i:z | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-13 15:59 | [13 empty] | 13/Jun/25 5:58 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked with TM1 Agent Installation - [https://vodacom.atlassian.net/browse/FCBEM-593¦https://vodacom.atlassian.net/browse/FCBEM-593¦smart-link] | 13/Aug/25 12:42 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 cutover completed and monitoring enable but need to create TM1 dash board. | 18/Aug/25 4:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 dashboard has been created under 20Plus apps dashboard. | 19/Aug/25 5:46 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Alerts has been configured and currently in review stage. | 20/Aug/25 6:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Service now team the alerts has been reaching to from cloud watch dash board. Attaching reference screen shot. !image-20250820-162717.png¦width=1910,height=508,alt="image-20250820-162717.png"! | 21/Aug/25 6:09 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed | 25/Aug/25 6:31 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-08-25 06:31
AM20-827 | ServiceNow ¦¦ CloudWatch Rule for Error detection | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650995 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 15:39 | 2026-01-14 16:18 |  |  |  | 0 | As a AWS engineer, I want to create CloudWatch alarms to send error-level logs to be notified of infrastructure issues Acceptance criteria: * CloudWatch metric filters to be configured to match specific error patterns or log levels |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fabfe65 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0280b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 06:03 | [13 empty] | 29/Apr/25 8:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will review utkarsh terraform script and will assign this story to him. | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed. | 07/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;We can use utkarsh terraform script for cloud watch alarm creation, but sns topic cant be modified so we need manual update to SNS access policy. | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:39 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [22 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:39
AM20-828 | ServiceNow ¦¦ LLD preparation | Done | 4 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1610563 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 20:47 | 2026-01-24 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for ServiceNow application so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed |  | Aravind Raj | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;14/Apr/25 9:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;115200 | [5 empty] | 57600 | 0 | 115200 | 2 | 57600 | 0 | 115200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4842827b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 3/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 3 | 75 | 1 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsnj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 2 | Sprint 3 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-10 14:19 | [13 empty] | 10/Mar/25 4:19 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 12/Mar/25 8:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;ServiceNow LLD is prepared, formatting is in progress, will complete and attach the document here. | 14/Apr/25 9:39 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Completed: 10th April 2025 Presentation to be done on Wednesday 16th April 2025 Review done by: [~accountid:712020:5d317226-2402-463f-bda5-c2cac5f43c13] and Deepak | [24 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-04-21 09:02
AM20-829 | AMOS Follow-up Assessment | Blocked | 4 | None( Backlog) |  |  | Sumit Nikam | Medium | 1833693 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 14:18 | 2026-01-30 15:55 | 2025-11-28 11:14 |  |  | 0 | As Product owner I would like to reinitiate assessment for AMOS application so that we can finalize approach to modernize it |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7ed8f0ed | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0009 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-24 06:09 | [13 empty] | 24/Nov/25 8:09 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Still awaiting approval from SAA\Tumelo for migration to AWS. Moving this to blocked state since the assessment canâ€™t be resumed until then. | [29 empty] | To Do | 2025-11-12 10:56
AM20-830 | RDS Upgrade in Flysaa backend Dev environment | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1842266 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 14:19 | 2026-01-19 17:25 | 2025-11-26 08:48 | 2025-11-27 09:18 |  | 0 | h2. User story * When the RDS instance is upgraded, I want to ensure compatibility with MySQL 8.4 so that our application runs smoothly without issues. h2. Context The development RDS instance will be upgraded from MySQL version 5.7 to 8.4. This upgrade may affect the functionality and performance of the application. h2. Acceptance criteria * The RDS instance must be successfully upgraded to MySQL 8.4. * All application features should function correctly after the upgrade. * Performance benchmarks should be met post-upgrade. h2. Other information N/A |  | Pankaj Pathak | Yashwant Thakur |  |  |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7e1de089 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5lf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [65 empty] | YES | YES | 2025-11-20 06:25 | 10060_*:*_1_*:*_67789956_*¦*_10041_*:*_1_*:*_258568449_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_452205278 | [12 empty] | 20/Nov/25 8:24 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;The upgrade from MySQL version 5.7.44 to 8.0.42 was successful. The DB instance is running smoothly. We asked the application team (Donald and Gavin) to confirm everything is functioning well on their end. We are awaiting their response to close this story. | 25/Nov/25 2:00 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Ticket moved to In review. As we have completed internal review. | 27/Nov/25 9:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Post upgrade, Business confirmed that BAU is working as expected hence approving | [27 empty] | Done | 2025-11-27 09:18
AM20-831 | TM1 ¦¦ Migration tool installation | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620533 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 16:07 | 2026-02-05 19:22 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the TM1 SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | Working with nexio team on troubleshooting the replication issue and configuring required services to get the agent installation successful followed by replication.;07/Apr/25 10:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [5 empty] | AM20-14 | AM20-4 | [23 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@106887e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnnb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:26 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This user story is blocked due to [https://vodacom.atlassian.net/browse/AM20-14¦https://vodacom.atlassian.net/browse/AM20-14¦smart-link] the network setup, upon completion of network will pick this one up. | 21/Mar/25 12:19 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet is shared, requested [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] to create a connectivity between on-premises to cloud. After the connectivity established, will be able to pick this migration agent toll installation for TM1. | 25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created a replication template and post launch template, waiting for the connectivity to be established between on-premises and TM1 AWS account. | 27/Mar/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Shared Agent and access details to vodacom team, have raised CRQ request for agent installation. 28th is planned for agent installation followed by replication will be initiated. | 04/Apr/25 11:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;On-prem to AWS Connectivity is established, Agent installation is getting failed due to multiple time of attempt, now waiting for restart of server from the logs. will try to install again and update the proceeding's here, | 07/Apr/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Replication is in progress, waiting for initial snapshot to be created. | 07/Apr/25 10:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Though agent installation completed, marking this story to done. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-07 10:45
AM20-832 | PROS ¦¦ Alert integration with ServiceNow | Done | 0 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811853 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 16:49 | 2026-01-13 20:20 |  | 2025-10-31 17:28 |  | 0 | Acceptance Criteria: Perform validations post integration with ServiceNow ServiceNow team confirms that payload is reaching to servicenow and all the inputs including tags are reaching to Servicenow without any changes needed. formal Signoff from servicenow team needed |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [26 empty] | AM20-211 |  |  | 31/Oct/25 2:24 PM;86260165-7dca-48a8-8b3b-378ae5a34c47;Re_ Confirmation on PROS-Prod Alarm Notification.eml;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176071 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5f6051c6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k7bb: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_21679719_*¦*_10041_*:*_1_*:*_595258194_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_690798371 |  | 3_*:*_1_*:*_21679719_*¦*_10041_*:*_1_*:*_595258194_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_690798371 | 3_*:*_1_*:*_21679719_*¦*_10041_*:*_1_*:*_595258194_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_690798371 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_21679719_*¦*_10041_*:*_1_*:*_595258194_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_690798371 | [65 empty] | YES | YES | 2025-10-31 12:24 | 3_*:*_1_*:*_21679719_*¦*_10041_*:*_1_*:*_595258194_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_690798371 | [12 empty] | 31/Oct/25 2:23 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Confirmation taken form the Service Now Team regarding the Alert Notification generation for PROS Prod. Attaching the email for reference. | 31/Oct/25 2:24 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^Re_ Confirmation on PROS-Prod Alarm Notification.eml] | 31/Oct/25 5:28 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-10-31 17:28
AM20-833 | Teammate ¦¦ subnet creation using terraform | Done | 2 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620382 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 13:20 | 2026-01-09 15:01 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Teammate application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Teammate and the configured based on the approved comms matrix |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@776c05e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 3 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-04 08:58 | [13 empty] | 04/Apr/25 10:58 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets has been created | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-14 09:39
AM20-834 | POC ¦¦ installing SSM agent and cloud watch agent for linux and windows server | Done | 20 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1669245 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-16 20:03 | 2026-01-16 22:22 |  |  |  | 0 | As AWS Expert, I should be able to provision Cloudwatch and SSM agent in sandbox Acceptance Criteria: ssm agent should help to connect to server and to do patch manager, wheras cloud watch agent to push the system logs to the cloud watch log group and to push custom metrics to the cloud watch dashboard |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Onkar Mirajkar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4bb35693 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i043kj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-14 17:07 | [13 empty] | 14/May/25 7:07 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Uninstalled SSM agent and Installed SSM agent -Done | 14/May/25 7:07 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Configured/Installed CloudWatch Agent manually on Ec2 instance | 14/May/25 7:08 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Automating the Installing process for CloudWatch Agent ---Pending | 21/May/25 8:49 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;I provided Faisal with an overview of the installation process for the CloudWatch Agent using SSM, and he has begun working on it using Terraform. | 29/May/25 10:14 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;+*What is being achieved via Terraform Automation Script:*+ # *Automated Provisioning* * Spins up EC2, sets IAM role + profile. * No manual SSH stepsâ€”even the agent install & config is done via user-data (and reinforced via SSM). # *Full Observability* * Metrics: CPU, memory, disk, network in the CWAgent namespace. * Logs: System logs (/var/log/messages, /var/log/secure) in CloudWatch Logs, with 14â€day retention. # *Resilience & Drift-Correction* * SSM association ensures the agent stays configured (you can re-run â€œterraform applyâ€ to heal it). * Pre-created Log Groups prevent silent failures due to missing groups. *â€œThe terraform script is battle tested in Sandbox Account via terraform locally installed.â€* | 11/Jun/25 8:26 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;The Terraform script has been completed, thoroughly tested, and all feedback has been incorporated. I will schedule another review to finalize it. | 16/Jun/25 10:03 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# *Used SSM Documents to Automate Agent Installation*Â * We leveraged *AWS SSM Run Command* documents instead of manual scripts or hardcoding logic.Â * Specifically, we used:Â * {{AWS-ConfigureAWSPackage}} to *install the CloudWatch Agent*Â * {{AmazonCloudWatch-ManageAgent}} to *configure and start the agent* using a *Parameter Store JSON config* named {{/Windows_Monitor_CW}}.Â Â *ðŸ”¹ 2. Embedded SSM Associations in Terraform*Â * Inside our *main EC2 Terraform project*, we embedded two {{aws_ssm_association}} resources:Â * *install_cwagent_windows* â€“ installs CloudWatch agentÂ * *configure_cwagent_windows* â€“ tells the agent to pull its config from {{/Windows_Monitor_CW}} in SSM Parameter Store and start itÂ * Both associations *target EC2 instances by tag*: {{CWAgent = EnabledÂ }} * The EC2 instances were pre-tagged via Terraform to ensure automatic targetingÂ Â *ðŸ”¹ 3. Created a Third Association to Force Re-fetch Config*Â * In some cases, the agent might need to re-fetch its config after the EC2 instance is up and the services are stable.Â * So we created a *third SSM association*: {{force_fetch_start_agentÂ }} * Uses {{AWS-RunPowerShellScript}} to run:Â {{& "C:\Program Files\Amazon\AmazonCloudWatchAgent\amazon-cloudwatch-agent-ctl.ps1" -a fetch-config -m ec2 -c ssm:/Windows_Monitor_CW -sÂ }} Â * This *manually triggers the fetch* of the config from SSM Parameter Store and starts the agent again if neededÂ Â *ðŸ”¹ 4. Split This Trigger into a Separate Terraform Directory*Â * To keep your deployment clean and *modular*, we:Â * Created a new folder: {{terraform/cwagent-trigger/Â }} * Placed only the {{force_fetch_start_agent}} logic in this moduleÂ * Why?Â * This allows you to *run it manually or conditionally* after core EC2 and SSM setups are completeÂ * Ensures *clean execution ordering* and better control in CI/CDÂ * Prevents early execution before the agent is even installedÂ Â *ðŸ”¹ 5. Designed for Platform-Specific Control*Â * Logic is gated with:Â {{count = var.platform == "windows" && var.enable_windows_ssm_association ? 1 : 0Â }} Â * Ensures this entire operation is *executed only for Windows instances*, as Linux would follow a different path.Â | 24/Jun/25 6:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have reviewed the server deployed SSM agent installed successfully. | 29/Jun/25 8:14 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [18 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:14
AM20-835 | Convert Alarms description into simple user understandable format | Done | 4 | Sprint 21 | 2025-12-22 | 2026-01-02 | Yashwant Thakur | Medium | 1881266 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 15:07 | 2026-01-29 16:27 | 2026-01-04 09:12 | 2026-01-02 11:04 |  | 0 | As Product owner I like to convert alarm description into simple understandable language so that user or resolver group are able to understand what is causing the error for flysaa backend , Front end and airnavx. Acceptance Criteria: alarm description send to Service Now via SNS and Lamda function must be user understable and successfully cascaded to ServiceNow using API. |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;02/Jan/26 9:49 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 72000 | 28800 | 43200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@18246054 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pcib: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2026-01-02 07:49 | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Jan/26 9:48 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Description was added for infrastructure , Lambda function and Flysaa Frontend account alerts. Example payload of frontend account alert: {"Name": "FlySaaCms_ALB_HTTPCode_Target_4XX_Count","IP Address": "NA","Fully Qualified Domain Name": "[api.flysaa.com¦http://api.flysaa.com]","Company": "VFSA","Hostname": "app/FlySaaCmsWebALB/968b1f7492941705","Department": "App DevOps Team","Operating System": "Amazon Linux","DNS Domain": "[api-frontdev-flysaa.com¦http://api-frontdev-flysaa.com]","Disk Space (GB)": "NA","RAM (MB)": "NA","CPU Count": "2","CPU core count": "2","Alarm Time": "2026-01-01 19:42:30 UTC","Account ID": "261365109009","Environment": "prod","Cluster Name": "NA","MetricName": "HTTPCode_Target_4XX_Count","Current State": "ALARM","Reason": "Threshold Crossed: 3 out of the last 3 datapoints [6534.0 (01/01/26 19:35:00), 6206.0 (01/01/26 19:30:00), 3164.0 (01/01/26 19:25:00)] were greater than or equal to the threshold (3000.0) (minimum 3 datapoints for OK -> ALARM transition).","Severity": "Warning","Description": "Error Count for http request exceeded threshold for metric: HTTPCode_Target_4XX_Count ,Loadbalancer affected: app/FlySaaCmsWebALB/968b1f7492941705"} | 02/Jan/26 11:04 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2026-01-02 11:04
AM20-836 | Nexio AV ¦¦ LLD creation | Done | 2 | Sprint 2 | 2025-03-31 | 2025-04-11 | Yashwant Thakur | High | 1619786 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 18:45 | 2026-02-05 19:38 |  |  |  | 0 | As AWS architect, I would create LLD for Nexio AV application migration *Acceptance Criteria*: * Low level design documentation including proposed architecture completed |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;13/May/25 11:21 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [9 empty] | AM20-22 |  |  | 13/May/25 11:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;TrellixAV_DesignDocument_v1.1.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1099634 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28a7c8e2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsmv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 3 | Sprint 4 | Sprint 5 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-13 09:38 | [13 empty] | 13/May/25 11:38 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Document has been prepared for Trellix AV ePO server migration to AWS ¦Backup PolicyÂ ¦To be discussed with customer and finalized¦ ¦DR Policy¦To be discussed with customer and finalized¦ [^TrellixAV_DesignDocument_v1.1.docx] First Draft of LLD is attached Moving to In Review until we can share it with customer and Finalize the Document | 18/May/25 2:41 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [25 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-05-18 14:41
AM20-837 | TM1 ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 10 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620851 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 13:52 | 2026-01-20 15:30 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [8 empty] | AM20-11 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6582c1ff | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxslr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | [108 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-08 06:24 | [13 empty] | 08/Apr/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms implemented From VDC, SITA now need to follow-up with Leigh for AWS firewall rules implementation. | 08/Apr/25 5:17 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been implemented, we are testing ports with test box, once all done we will create new SG will whitelist ports. | 22/Apr/25 3:54 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;NACL and SG has been setup, still Teradata side pending, checking with Leigh. | 24/Apr/25 8:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Connectivity got implemented testing also done successful. | 29/Apr/25 7:48 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 apps mat testing done successful. Teradata connectivity port20,21 &22 will be established after moving relevant resources to shared vpc. For app migration there is no dependency. | 18/May/25 2:40 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [21 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:40
AM20-838 | Centralized Cluster Creation Strategy | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Sanjot Fotedar | Medium | 1885775 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 13:20 | 2026-01-20 16:57 | 2026-01-08 08:38 |  |  | 0 | As A platform Owner I want to create a detailed design document for centralized management of EKS cluster across multiple AWS child accounts from a central account so that the solution is secure, scalable, compliant and operationally ready before implementation Acceptance Criteria: *Architecture and Account structure* - * Parent, central management and child application accounts * hub and spoke model connectivity model * shared vs isolation responsibilities *EKS management Strategy* - * Centralized model * Namespace isolation strategy * Cluster ownership and lifecycle boundaries *IAM and Security design* - * Cross account IAM roles and trust relationship * K8s RBAC mapping * Least privileges access model * SCP usage and guardrails *Network and Connectivity design* - * VPC architecture per account * Connectivity via TGW /VPC peering * Control plane and data plane traffic flow * DNS resolution strategy *Governance and Policy Enforcement* - * Kubernetes admission controls (Kyverno) * naming, tagging and quota standards * Policy exception handling process *Observability and Logging* - * Centralized logging and metrics flow * Alerting and escalation paths *Security and Compliance* - * EKS security monitoring * Image scanning approach * Compliance reporting and audit readiness *Operation model* - * RACI matrix (L1/L2/L3) * Incident and change management process * upgrade and patching strategy * Backup and DR approach |  | Sanjot Fotedar | [5 empty] | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [5 empty] | ;07/Jan/26 7:23 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;7200 | [5 empty] | 115200 | 108000 | 7200 | 0.06 | 115200 | 108000 | 7200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43715548 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptve: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-07 17:24 | [13 empty] | 07/Jan/26 7:23 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Started work on this. Currently evaluating the framework for assessing multi-tenancy readiness of existing eks cluster. Identifying key focus areas for hardening -Â namespace isolation, RBAC scope, network segmentation, resource governance, policy enforcement. | [29 empty] | In Progress | 2026-01-07 19:21
AM20-839 | Informatica Server ¦¦ Budget Management Configuration | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772227 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 20:21 | 2026-01-13 23:04 |  |  |  | 0 | As AWS expert I would like to configure Informatica budget management and alerts so that stakeholders gets the frequent notifications on budgets and alerts if the budget crosses threshold Acceptance Criteria: * Budget management for Informatica is configured successfully * Alerts triggered if the budget crosses 80%, 85% and 90% of Threshold |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [10 empty] | AM20-164 |  |  | 18/Sep/25 10:44 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250918-084430.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1155401 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3d312d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq0n: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-09 06:44 | [13 empty] | 09/Sep/25 8:43 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Today will start creating the budget on the management account for Informatica Dev and Prod environment. | 09/Sep/25 11:00 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created the budget for Informatica Dev and Prod in Payers management account with threshold as 80%,85% & 90%. Now, will add the account in the Lambda function and also will add app. owner mail id & will test it. | 15/Sep/25 11:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have added the Account name and application owner email ids in lambda function also tested the budget alerting and we are successfully getting the alerts for budget management. | 17/Sep/25 9:13 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8; !image-20250918-084430.png¦width=852,height=577,alt="image-20250918-084430.png"! Attaching the evidence screenshot that the budget we have created are able to get the emails and details if it exceeded the threshold value 85%. | 18/Sep/25 2:46 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Demo was given to Yashwant but want Aravind to review it. | 22/Sep/25 8:36 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;the threshold of budget should be calculated based on the all the resources involved in the architecture and LLD, though its modifiable, i would suggest to update the value in firsthand itslef. | [24 empty] | Done | 2025-09-22 08:50
AM20-840 | Tag Validations for AirNavX | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820186 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 15:23 | 2026-01-15 18:33 |  | 2025-11-14 10:58 |  | 0 | As a Cloud governance engineer I want to validate that all resources and workloads related to newly migrated applications have the correct mandatory tags applied so that we can ensure accurate cost allocation, compliance reporting and automation alignment across all AirNavX account Acceptance Criteria: * Tags for all applicable application resource type ( EC2, EBS, RDS, S3 lamda, ALB/NLB, Cloudwatch log groups) are successfully captured. * If there are any tags not available then manually updated successfully * Validations runs across all migrated resources and as per agreed format |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:33 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;246000 | [5 empty] | 28800 | 0 | 246000 | 8.54 | 28800 | 0 | 246000 | [12 empty] | 13/Nov/25 9:26 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-072628.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182486 | 13/Nov/25 12:08 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-100724.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182794 | 13/Nov/25 12:08 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-100827.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182795 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1ffcb69e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l62j: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-06 06:25 | 3_*:*_2_*:*_618331356_*¦*_10041_*:*_2_*:*_775280284_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 06/Nov/25 8:25 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will Start checking all the tags are in place for AirnavX environment and will update them. | 06/Nov/25 9:35 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;AirnavX code build & code piplines & s3 proper taggings are missing. | 12/Nov/25 2:23 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Followed up with satyabrata he is occupied with some tasks and will connect with me tomorrow for this US. | 13/Nov/25 9:26 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251113-072628.png¦width=631,alt="image-20251113-072628.png"! S3 tagging has been updated by AWS CLI command. Now checking for code build and pipline. | 13/Nov/25 12:08 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251113-100724.png¦width=714,alt="image-20251113-100724.png"! Evidence for code pipline and code build updated tags. !image-20251113-100827.png¦width=695,alt="image-20251113-100827.png"! | 14/Nov/25 10:58 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-14 10:58
AM20-841 | Cleanup of AWS workload from Control tower | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1749509 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 18:56 | 2026-01-12 22:09 |  |  |  | 0 | As application owner I would like to cleanup redundant workloads from AWS through control tower so that we can achieve optimum utilization Acceptance Criteria: Cleanup is done with all redundant workloads/account deleted |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 14/Aug/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250814-064049.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139647 | 18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250818-060958.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1140604 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@557a9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0daor: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-14 06:41 | [13 empty] | 14/Aug/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have initiated mail with vodacom team, will do followup. !image-20250814-064049.png¦width=1272,height=492,alt="image-20250814-064049.png"! | 18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250818-060958.png¦width=1277,height=470,alt="image-20250818-060958.png"! AWS account cleanup, followed by by account renaming is completed. | 21/Aug/25 2:25 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:26
AM20-842 | Nexio AV ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 5 | 2025-05-12 | 2025-05-23 | Satya Varanasi | High | 1650865 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-14 18:14 | 2026-01-14 18:42 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5c904e9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akl: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 15:23 | [13 empty] | 20/May/25 5:23 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This Story dependency with comms implementation, the same with SAA team. Once SAA team actioned this story will be handled and closed until that this will not possible to address.(Note: it may move next sprint also) | 10/Jun/25 2:08 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0; No longer needed based on recent conversation. * Based on request from Sinjun, the migration approach for Trellix/NexioAV has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. Â | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-10 14:08
AM20-843 | Informatica Server ¦¦ LLD preparation | Done | 6 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1610565 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 12:33 | 2026-01-21 15:05 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Sankalp Rai | Yashwant Thakur |  |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;24/Jun/25 1:32 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;11/Aug/25 10:10 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7d2f4e8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a2v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | [104 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-10 14:18 | [13 empty] | 10/Mar/25 4:18 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 10/Mar/25 4:24 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder >> Call to Scheduled on or before 12th* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 20/May/25 10:24 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;1st Draft Complete. Need to review internally revised Start Date: 19th May 2025 End date: 23rd May 2025 | 24/Jun/25 1:32 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Review with customer is completed Awaiting information requested from Application Owner | 11/Aug/25 5:04 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-10-13 09:23
AM20-844 | Provision AWS GuardDuty using Terraform | Done | 10 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718154 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 17:38 | 2026-01-28 18:19 |  |  |  | 0 | As a cloud security engineer I want to provision and configure AWS GuardDuty using Terraform so that I can automatically detect and respond to potential threats in my AWS environment in a consistent and repeatable manner Acceptance Criteria: * Terraform must create a GuardDuty Detector in the primary AWS region. the detector must be enabled * for multiple AWS accounts Terraform must support creating a GuardDuty master-member relationship * Members must be invited and accepted automatically * GuardDuty should automatically published findings to the console API and this must not be disabled * Terraform must be modular to support enabling GuardDuty in any account and region * inputs like region, accountid, and enable flag must be configurable * All resources created via Terraform must include project defined tags * Forward GuardDuty findings to AWS security Hub or EventBridge |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@50808e38 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ansn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-22 06:28 | [13 empty] | 22/Jul/25 8:28 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Email sent to Ismaail and leigh about Request to Enable Centralized Management for GuardDuty and Amazon Inspector and currently I am working on Terrafrom script to create the base module for resources. | 23/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Leigh replied and asked to Ismaail for assisting. | 25/Jul/25 8:33 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;It will be spillover because there was a dependency on Ismail and he has updated on 23 July Only so thatâ€™s why I am not able to complete it on time. | 30/Jul/25 8:26 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script. Ready for the demo. | 11/Aug/25 4:30 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:30
AM20-845 | Migration of FLYSAA DNS Zones to AWS Route53 | To Do | 6 | None( Backlog) |  |  | Satya Varanasi | Medium | 1822276 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 19:48 | 2026-01-23 19:56 |  |  |  | 0 | As a cloud infrastructure Architect I want to migrate existing DNS zones from FLYSAA to AWS Route 53 so thar DNS management can be centralized with AWS, ensuring stability, availability and integration with other AWS services Acceptance Criteria: DNS Zone Discovery and Assessment * Existing FLYSAA DNS zones are inventoried and validated for record types (A, AAAA, CNAME, MA,TXT, SRV, NS, SOA, PTR etc.) * Dependencies on on-prem or third party systems are identified * Zone delegation hierarchy and authoritative name servers are documented * TTL Values and routing policies (simple, Weighted, latency, failover etc.) are reviewed for compatibility with Route53 Route 53 hosted Zone creation * Corresponding public/private hosted zones are created in Route 53 with identical zone names * Correct VPC associations are configured for private zones in the appropriate AWS accounts (dev, pre-prod and prod) * Hosted zones are tagged appropriately * Record Migration and Validation Record Migration and Validation * All DNS record from FLYSAA are migrated to Route 53 with matching values * Route 53 health checks and routing policies are configured as per existing logic * Random sample validation (at least 10%) of DNS resolution from client endpoints confirm accuracy * Validations confirm parity between source and target DNS records Cutover and Delegations * NS records in parent zones are updated to point to Route53 name servers * Change propagation and DNS TTL impact are communicated and managed * Post-cutover validation confirms DNS resolutions is working correctly from internal and external networks * A rollback plan is documented and tested before cutover Security, Audit and logging * Route53 DNS query logging is enabled to CloudWatch or S3 * Access to hosted zones is restricted using IAM roles and policies * GuardDuty and config rules validate DNS configuration integrity * Audit report is generated post migration with DNS record counts and comparison results Monitoring and Alerting * CloudWatch alarms are configured for health checks and DNS failure * SNS topics notify the platform operations team on failure or health check degradation * Dashboards display query metrics and latency per hosted zone Document * Update DNS architecture diagram reflects Route53 integration * SOPs for future DNS change requests are published in the knowledge base * Migration validation report is approved by the business |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [11 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5a13873 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g004 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-10-29 10:50
AM20-846 | ServiceNow ¦¦ Logging and Monitoring | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651021 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 17:53 | 2026-01-11 21:37 |  |  |  | 0 | As an AWS expert, I want to monitor the health and logs of the Lamda connector function so that I can troubleshoot issues when alerts arenâ€™t processed properly Acceptance Criteria: * CloudWatch logs are enabled for Lambda * Metrics and dashboards are available for monitoring invocations, failures and response times. |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/May/25 9:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103910 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60acf139 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0285v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | [108 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 05:45 | [13 empty] | 02/May/25 7:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function to invoke the cloud watch is created and working as expected, Cloud watch dashboard for metrics will be created only after the workloads moved to cloud. service now monitoring can be in place only after successful integration with connector and service now PAAS endpoint. | 16/May/25 9:01 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have given demo with the email endpoints, waiting for the https endpoint to be received from SAA team to work with full functionality, | 22/May/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have received a endpoint today, yet to update SNS topic endpoint. https://sonicboom_em_saa_7161:wusEwo>G*Xmw@?XOA74\!pm0cx2.[4N;oFz<\!7vSE@liftdev.service-now.com/api/sn_em_connector/em/inbound_event?source=aws&sys_id=870cc1dfc3a5a6d04022f9777a013157 | 22/May/25 9:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 26/May/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda and cloud watch event bridge configuration is completed in Audit account, IAM role configuration is completed only in backend dev and preprod, other account yet to be configured. | 26/May/25 8:16 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;With respect to the endpoint have sent a mail to ashton, but there was response yet. awaiting on same. | 02/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;waiting for valid endpoint. Â· | 04/Jun/25 8:13 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Follow mail sent by yashwant 03-06 , awaiting for new endpoint. | 20/Jun/25 7:59 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Service now integration is completed with a new subscription HTTPS endpoint, have created a Cloud watch alarm for testing purpose which triggers a SNS as result service now dashboard receives a alert. | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-20 08:17
AM20-847 | Provision AWS GuardDuty using Terraform | Done | 10 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718154 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 13:19 | 2026-01-31 15:11 |  |  |  | 0 | As a cloud security engineer I want to provision and configure AWS GuardDuty using Terraform so that I can automatically detect and respond to potential threats in my AWS environment in a consistent and repeatable manner Acceptance Criteria: * Terraform must create a GuardDuty Detector in the primary AWS region. the detector must be enabled * for multiple AWS accounts Terraform must support creating a GuardDuty master-member relationship * Members must be invited and accepted automatically * GuardDuty should automatically published findings to the console API and this must not be disabled * Terraform must be modular to support enabling GuardDuty in any account and region * inputs like region, accountid, and enable flag must be configurable * All resources created via Terraform must include project defined tags * Forward GuardDuty findings to AWS security Hub or EventBridge |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@50808e38 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ansn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-22 06:28 | [13 empty] | 22/Jul/25 8:28 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Email sent to Ismaail and leigh about Request to Enable Centralized Management for GuardDuty and Amazon Inspector and currently I am working on Terrafrom script to create the base module for resources. | 23/Jul/25 8:27 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Leigh replied and asked to Ismaail for assisting. | 25/Jul/25 8:33 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;It will be spillover because there was a dependency on Ismail and he has updated on 23 July Only so thatâ€™s why I am not able to complete it on time. | 30/Jul/25 8:26 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script. Ready for the demo. | 11/Aug/25 4:30 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:30
AM20-848 | Trellix integration with MQ | Blocked | 2 | None( Backlog) |  |  | Satya Varanasi | Medium | 1794150 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 16:24 | 2026-01-16 18:34 |  |  |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan MQ workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in MQ server * Trellix is able to access MQ account successfully and perform scanning |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b924c6e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g04 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-27 14:04 | [13 empty] | 27/Oct/25 4:03 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This action need to addressed once server build completes. | [29 empty] | To Do | 2025-09-30 10:19
AM20-849 | TM1 ¦¦ Alerts renaming & Configuration | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786760 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 16:14 | 2026-01-28 16:38 |  |  |  | 0 | As Product owner I would like to rename alerts and configuration based on agreement with ServiceNow team *Acceptance Criteria*: TM1 alarm renaming completed successfully and configurations updated |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 24/Sep/25 1:56 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250924-115610.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1158311 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@26e51892 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-23 08:55 | [13 empty] | 23/Sep/25 10:54 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I have started creating the alarms with correct naming & threshold value which were agreed with the customer and service now team previously. | 24/Sep/25 1:56 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20250924-115610.png¦width=1580,height=467,alt="image-20250924-115610.png"! Have created alarms as per correct naming and configuration updated. | 29/Sep/25 6:53 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Moving this to In review to Aravind to check the configuration. | 03/Oct/25 12:42 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have modified the alarm for disk and memory configuration, other alarm are looking good. | [26 empty] | Done | 2025-10-06 07:59
AM20-850 | MQ ¦¦ Monitoring and Alert Solution | Blocked | 4 | None( Backlog) |  |  | Diksha Koul | Medium | 1794147 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 22:04 | 2026-01-25 01:16 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if MQ server is stopped |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@15c39a10 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-02 17:42 | [13 empty] | 02/Nov/25 7:42 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over* : After creation of the MQ EC2 instance we can start the creation of MQ monitoring and alerting solution. | [29 empty] | To Do | 2025-09-30 10:17
AM20-851 | Budget management - AWS Cost Control on application | In Progress | 6 | Sprint 22 | 2026-01-05 | 2026-01-16 | Diksha Koul | Medium | 1885694 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 13:16 | 2026-01-21 15:52 | 2026-01-08 08:32 |  |  | 0 | As Product Owner, I would like to address frequent spikes on budget of AWS accounts so that we can manage cost within the forecasted cost. Acceptance Criteria: * Identify the root cost of cost spiked in EKS cluster, Audit account, SAA_Airnavx and CMS backend(Prod) * resolve the root cause to reduce the associated cost |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [5 empty] | ;08/Jan/26 7:38 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | [5 empty] | 86400 | 57600 | 28800 | 0.33 | 86400 | 57600 | 28800 | [12 empty] | 08/Jan/26 10:57 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-085716.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197716 | 08/Jan/26 11:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-093536.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197744 | 08/Jan/26 12:15 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-101131.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197769 | 08/Jan/26 12:15 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-101412.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197770 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3731daff | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptcb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-06 11:56 | [13 empty] | 06/Jan/26 1:55 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started working on the root cause and cost spike for AirnavX | 08/Jan/26 7:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have checked the costing spike for all accounts its showing that EC2 instances are consuming more cost. Now checking the cloud watch logs for them. | 08/Jan/26 10:57 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I checked in the *AirnavX Account* there are snapshots which has been created for all EC2 instances including the DR instance and also the backup is enabled. Attaching the screenshot below: !image-20260108-085716.png¦width=641,alt="image-20260108-085716.png"! This is also one reason that the costing is spiking. For *Audit Account* also i checked that the SNS and Cloudwatch is consuming lot of cost spike due to which the budget costing is spiked. Attaching the screenshot: !image-20260108-093536.png¦width=613,alt="image-20260108-093536.png"! For *CMS_Backend_Prod* the t3.xlarge instances that is EKS nodes is cost consuming as you can see below Attached Screenshot below showing nodes spike for 4 months. !image-20260108-101131.png¦width=496,alt="image-20260108-101131.png"! Also, below screenshot showing instance type size for EC2 and EKS nodes and there costing for 4 months. !image-20260108-101412.png¦width=583,alt="image-20260108-101412.png"! | [27 empty] | In Progress | 2026-01-06 12:51
AM20-852 | POC ¦¦ installing SSM agent and cloud watch agent for linux and windows server | Done | 20 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1669245 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-26 16:49 | 2026-01-26 17:43 |  |  |  | 0 | As AWS Expert, I should be able to provision Cloudwatch and SSM agent in sandbox Acceptance Criteria: ssm agent should help to connect to server and to do patch manager, wheras cloud watch agent to push the system logs to the cloud watch log group and to push custom metrics to the cloud watch dashboard |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Onkar Mirajkar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4bb35693 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i043kj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-14 17:07 | [13 empty] | 14/May/25 7:07 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Uninstalled SSM agent and Installed SSM agent -Done | 14/May/25 7:07 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Configured/Installed CloudWatch Agent manually on Ec2 instance | 14/May/25 7:08 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Automating the Installing process for CloudWatch Agent ---Pending | 21/May/25 8:49 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;I provided Faisal with an overview of the installation process for the CloudWatch Agent using SSM, and he has begun working on it using Terraform. | 29/May/25 10:14 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;+*What is being achieved via Terraform Automation Script:*+ # *Automated Provisioning* * Spins up EC2, sets IAM role + profile. * No manual SSH stepsâ€”even the agent install & config is done via user-data (and reinforced via SSM). # *Full Observability* * Metrics: CPU, memory, disk, network in the CWAgent namespace. * Logs: System logs (/var/log/messages, /var/log/secure) in CloudWatch Logs, with 14â€day retention. # *Resilience & Drift-Correction* * SSM association ensures the agent stays configured (you can re-run â€œterraform applyâ€ to heal it). * Pre-created Log Groups prevent silent failures due to missing groups. *â€œThe terraform script is battle tested in Sandbox Account via terraform locally installed.â€* | 11/Jun/25 8:26 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;The Terraform script has been completed, thoroughly tested, and all feedback has been incorporated. I will schedule another review to finalize it. | 16/Jun/25 10:03 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# *Used SSM Documents to Automate Agent Installation*Â * We leveraged *AWS SSM Run Command* documents instead of manual scripts or hardcoding logic.Â * Specifically, we used:Â * {{AWS-ConfigureAWSPackage}} to *install the CloudWatch Agent*Â * {{AmazonCloudWatch-ManageAgent}} to *configure and start the agent* using a *Parameter Store JSON config* named {{/Windows_Monitor_CW}}.Â Â *ðŸ”¹ 2. Embedded SSM Associations in Terraform*Â * Inside our *main EC2 Terraform project*, we embedded two {{aws_ssm_association}} resources:Â * *install_cwagent_windows* â€“ installs CloudWatch agentÂ * *configure_cwagent_windows* â€“ tells the agent to pull its config from {{/Windows_Monitor_CW}} in SSM Parameter Store and start itÂ * Both associations *target EC2 instances by tag*: {{CWAgent = EnabledÂ }} * The EC2 instances were pre-tagged via Terraform to ensure automatic targetingÂ Â *ðŸ”¹ 3. Created a Third Association to Force Re-fetch Config*Â * In some cases, the agent might need to re-fetch its config after the EC2 instance is up and the services are stable.Â * So we created a *third SSM association*: {{force_fetch_start_agentÂ }} * Uses {{AWS-RunPowerShellScript}} to run:Â {{& "C:\Program Files\Amazon\AmazonCloudWatchAgent\amazon-cloudwatch-agent-ctl.ps1" -a fetch-config -m ec2 -c ssm:/Windows_Monitor_CW -sÂ }} Â * This *manually triggers the fetch* of the config from SSM Parameter Store and starts the agent again if neededÂ Â *ðŸ”¹ 4. Split This Trigger into a Separate Terraform Directory*Â * To keep your deployment clean and *modular*, we:Â * Created a new folder: {{terraform/cwagent-trigger/Â }} * Placed only the {{force_fetch_start_agent}} logic in this moduleÂ * Why?Â * This allows you to *run it manually or conditionally* after core EC2 and SSM setups are completeÂ * Ensures *clean execution ordering* and better control in CI/CDÂ * Prevents early execution before the agent is even installedÂ Â *ðŸ”¹ 5. Designed for Platform-Specific Control*Â * Logic is gated with:Â {{count = var.platform == "windows" && var.enable_windows_ssm_association ? 1 : 0Â }} Â * Ensures this entire operation is *executed only for Windows instances*, as Linux would follow a different path.Â | 24/Jun/25 6:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have reviewed the server deployed SSM agent installed successfully. | 29/Jun/25 8:14 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [18 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:14
AM20-853 | Informatica ¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1755978 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 19:23 | 2026-02-05 22:24 |  |  |  | 0 |  |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3237a818 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0e0or: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-26 11:39 | [13 empty] | 26/Aug/25 1:39 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Firewall rules implemented. Identified as connectivity not working. Initiated network troubleshooting call towards fixing. Identified as routing not configured. Requested LIFT for approval LIFT approval took 3days Monday CSOC request raised and routing has ben implemented. Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 28/Aug/25 8:18 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested connectivity from informatica Prod/Dev env. Initially Network team not configured Routing after new Lift and CSOC request issue got resolved. Reference Lift & CSOC details: Routing: # CSOC:CHR0026807 # LIFT:CHG0067489 App comms: # LiFT = CHG0067488 # CSOC = CHR0026691 AWS agent Comms: CSOC logged CHR0023951 LiFT logged CHG0066992 (RITM0051174) | 01/Sep/25 8:03 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested. Based on comms we have successfully completed agent installation for prod/Dev and setup test instance for the same. Hence sending request for closer. | 03/Sep/25 8:55 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-854 | TM1 ¦¦ Subnet creation using terraform | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Satya Varanasi | Medium | 1620359 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 14:01 | 2026-01-18 17:04 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for TM1 application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for TM1 and the configured based on the approved comms matrix |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-11 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a96537d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnn3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:53 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 04/Apr/25 10:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation got completed Manuel. As terraform not ready. While creating this TM1 subnets. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-07 10:11
AM20-855 | CMS Frontend SMS PROD implementation | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865997 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 13:53 | 2026-01-27 15:33 | 2025-12-14 17:52 | 2025-12-12 14:50 |  | 0 | As a cloud platform application owner I want to perform a detailed assessment for enable SMS notification in the CMS frontend application hosted in AWS Acceptance Criteria Dedicated SNS topic created successfully for CMS frontend specific Subscribe long code to SNS topic successfully Complete Configuration of CloudWatch alarms for application error through custom metrics CloudWatch Alarms are created successfully AWS Lamda function is created with all the required error details in compliant with ServiceNow format including Severity Validation of Setup is completed successfully post implementation |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Worked on understanding the alarm list and discussing their priorities.;03/Dec/25 12:11 PM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on adding support for sms notification for critical alerts like ALB getting 400, 500 errors;09/Dec/25 8:00 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Re-deployed sms notification infrastructure on preprod env to mimic instance down scenario.;09/Dec/25 8:01 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on testing number of liferay instances running metric and updating lambda to make sure sms notification indicates which node is not working.;09/Dec/25 8:02 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on replicating logic for similar alarms.;09/Dec/25 8:04 AM;17cb9418-1850-4923-932b-7098ec51b6bb;14400 |  | 115200 | 7200 | 108000 | 0.93 | 115200 | 7200 | 108000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4211dfc7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7x7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-03 10:14 | 3_*:*_1_*:*_786052048_*¦*_10041_*:*_1_*:*_525749875_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 03/Dec/25 12:13 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Discussed with Hoosen regarding the list of alarms to enable SMS notification for and priorities to be assigned to them. Started working on configuring P1 alerts. | 09/Dec/25 8:08 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Status till now: # Worked on configuring sms notifications for critical alerts like ALB, number of liferay running and CPU utilization of instances ,RDS , alarms for metrics like procstat_num_fds, procstat_num_threads. # Replicated sms implementation on saa frontend preprod to test alarms involving stopping instances, alarms are sending correct info regarding which instances are down. # Working on adding sms support for metrics like homepage availability, fabric availability etc. | 10/Dec/25 8:19 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created and tested few alarms for monitoring metric like HomePage availability , Fabric Availability etc in prod. | 12/Dec/25 2:31 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created and Tested alarms in Prod and Preprod. | 12/Dec/25 2:50 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-12-12 14:50
AM20-856 | (Airchef)Terraform Implementation for Creation of Route 53 Hosted Zones & Records. | In Progress |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Sanket Kale | Medium | 1827709 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-25 13:43 | 2026-01-25 15:32 |  |  |  | 0 | *Acceptance Criteria:* * *Deploy Public Hosted Zone* Use Terraform to provision a *Route 53 public hosted zone* for the domain [*airchef.co.za*¦http://airchef.co.za]. * *Manage DNS Records via Terraform* Implement Terraform configurations to create and manage various DNS record types (A, CNAME, MX, TXT, etc.) within the hosted zone. |  | Faisal Sayed | Sanket Kale | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [20 empty] | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28df5c12 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1vn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-07 05:56 | [13 empty] | 07/Nov/25 7:56 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Code review completed from my side its working. Created and deployed the base and component modules. | 10/Nov/25 9:07 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and tested on Sandbox environment | 14/Nov/25 4:01 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code deployment done sandbox and same tested. | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | In Progress | 2025-11-20 08:59
AM20-857 | Nexio AV ¦¦ Life Cycle Management ¦¦ Log Retention | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1730232 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 17:13 | 2026-02-01 20:01 |  |  |  | 0 | As Product Owner I would like to establish the life cycle management for log retention specific to Nexio AV account to have defined log retention policies for all critical log sources so that we can meet compliance, enable forensic investigation and optimize storage Acceptance Criteria: log retention policy is defined per account * Production env. - log retention period 90 days Â *Please note* that post retention period, these logs can either be deleted or moved to cold storage, which can be configured based on your confirmation however, data retrieval from cold storage is charged additionally. * All critical log sources are covered - cloudtrail, VPC flow logs, cloudwatch logs and other tools must be retained as per policy * Log retention is automated - log groups are created when they are detected * Logs reaches its retention threshold when the time expires it should either be deleted or moved to archive (cold storage) * Retention policy is editable so that it can be configured accordingly |  | Aravind Raj | Diksha Koul | Onkar Mirajkar | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [27 empty] | 06/Aug/25 9:45 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;Screenshot 2025-08-06 131412.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136044 | 29/Jul/25 9:39 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250729-073927.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1132067 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@410ec9e6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bn77: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-29 07:40 | [13 empty] | 29/Jul/25 9:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;No S3 bucket resource has been created on NEXIO AV as of now for retention period. !image-20250729-073927.png¦width=1545,height=507,alt="image-20250729-073927.png"! | 31/Jul/25 12:53 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Created Log metrics for NEXIO AV | 01/Aug/25 8:14 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created one life cycle rule for the deletion of logs after 90 days need to review it with Aravind. | 01/Aug/25 9:00 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;we will be having an confirmation email from the client and will be then implementing the retention life cycle rule on the centralized account as Logs will store to cold storage and retention days will be 90 days. | 05/Aug/25 11:11 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Retention rule has been created in the Log Archive account on S3 all environment as 90 days and also after 90 days it will get moved to cold storage. | 06/Aug/25 9:45 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!Screenshot 2025-08-06 131412.png¦width=934,height=354,alt="Screenshot 2025-08-06 131412.png"! Attaching the screenshot of the changes we have done in the log archive account. | 08/Aug/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Transition rule in place for centralized cloud trail logs to send to glacier after 90 days. | 11/Aug/25 7:59 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 07:59
AM20-858 | Informatica Server ¦¦ Subnet creation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660595 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-27 14:25 | 2026-01-27 16:26 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Nexio AV application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Nexio AV and the configured based on the approved comms matrix |  | Aravind Raj | Harsh Chandra | Satya Varanasi | Shreyash Talwekar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 27/Jun/25 3:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-135131.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119370 | 27/Jun/25 3:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-135223.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119371 | 27/Jun/25 5:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155229.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119409 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@435a4769 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-16 08:08 | [13 empty] | 16/May/25 10:07 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Waiting for terraform code towards build this. | 20/May/25 5:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Deepak and team, this need to be addressed with terraform code the same has been prepared by Utkarsh, until core not ready this story may not possible to address. | 10/Jun/25 2:03 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still â€œShreyashâ€ checking Utkarsh script, this story depending with script testing and execution. | 16/Jun/25 9:06 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Terraform script is under modification by â€œShreyashâ€, as per his update it will be ready this week. Hence this is the reason for spill over Sprint7 to Sprint8. | 16/Jun/25 9:15 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Currently working on updating terraform script based on latest naming convention requirement. | 18/Jun/25 11:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The script is managing by â€œShreyashâ€ so i am assigning this task to him, once his work completes he will reassign to me. | 23/Jun/25 1:58 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We were able to create AWS resources (mentioned in previous mail ) using terraform scripts on sharedvpc-dev account. To address some requirements like adding naming conventions and state file management, we will have to add some changes in terraform scripts. Due to current sprint activities I might not be able to work on the changes in this sprint. | 27/Jun/25 3:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Prod Subnet/Route table has been created, & tested internet access and same working fine. !image-20250627-135131.png¦width=1261,height=434,alt="image-20250627-135131.png"! !image-20250627-135223.png¦width=1112,height=588,alt="image-20250627-135223.png"! sh-5.2$ ping [http://google.com¦http://google.com¦smart-link] PING [http://google.com¦http://google.com¦smart-link] (142.251.47.238) 56(84) bytes of data. 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=1 ttl=108 time=20.5 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=2 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=3 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=4 ttl=108 time=19.7 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=5 ttl=108 time=19.8 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=6 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=7 ttl=108 time=19.7 ms ^C --- [http://google.com¦http://google.com¦smart-link] ping statistics --- 7 packets transmitted, 7 received, 0% packet loss, time 6010ms rtt min/avg/max/mdev = 19.630/19.800/20.473/0.282 ms sh-5.2$ hostname [ip-10-40-0-213.awsflysaa.com¦http://ip-10-40-0-213.awsflysaa.com] sh-5.2$ ifconfig ens5: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 9001 inet 10.40.0.213 netmask 255.255.255.240 broadcast 10.40.0.223 inet6 fe80::4a7:ebff:fe03:c075 prefixlen 64 scopeid 0x20<link> ether 06:a7:eb:03:c0:75 txqueuelen 1000 (Ethernet) RX packets 1653 bytes 293385 (286.5 KiB) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 1809 bytes 265312 (259.0 KiB) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0 lo: flags=73<UP,LOOPBACK,RUNNING> mtu 65536 inet 127.0.0.1 netmask 255.0.0.0 inet6 ::1 prefixlen 128 scopeid 0x10<host> loop txqueuelen 1000 (Local Loopback) RX packets 12 bytes 1020 (1020.0 B) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 12 bytes 1020 (1020.0 B) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0. | 27/Jun/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev Subnet and route table has been created. !image-20250627-155229.png¦width=1259,height=431,alt="image-20250627-155229.png"! | 27/Jun/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet creation and sharing is done, have reviewed. | 29/Jun/25 8:13 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:13
AM20-859 | Informatica ¦¦ Alert integration with ServiceNow | Done | 4 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811851 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 20:36 | 2026-02-05 22:18 |  | 2025-10-31 09:35 |  | 0 | Acceptance Criteria: Perform validations post integration with ServiceNow ServiceNow team confirms that payload is reaching to servicenow and all the inputs including tags are reaching to Servicenow without any changes needed. formal Signoff from servicenow team needed |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [9 empty] | AM20-212 |  |  |  | 28/Oct/25 6:58 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251028-165729.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174301 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@104a0167 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k7b7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 |  | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | [65 empty] | YES | YES | 2025-10-23 13:19 | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | [12 empty] | 23/Oct/25 3:19 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Service Now integration with cloud watch through IAM role were completed. And [~accountid:712020:54791a09-30fd-4ab7-8a1d-068b13e544d8] created all required ALARM for the key metrics for Informatica Prod and Dev account already and i have reviewed it. | 28/Oct/25 6:58 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have checked with Priyanka and service now team they are getting the alerts as per they requested. !image-20251028-165729.png¦width=629,alt="image-20251028-165729.png"! Attaching the email confirmation evidence for the reference. | 31/Oct/25 9:35 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Integration completed with servicenow and mail confirmation received hence accepting user story to be done | [27 empty] | Done | 2025-10-31 09:35
AM20-860 | Rename Citrix account with informatica Prod: Re-establish Informatica ¦¦ Subnet Configuration and Setup platform | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1749511 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 19:57 | 2026-02-03 23:49 |  |  |  | 0 | As Network expert, I would like to provision subnet configuration for PROS application Acceptance criteria: * Subnet configuration completed successfully * Tagging of all network elements associated done succesfully * Traffic flow testing and validation is concluded |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153624.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141700 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153747.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141702 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-154222.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141701 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@e805dba | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dap7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 06:22 | [13 empty] | 12/Aug/25 8:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;We are looking account id rename or new id creation process accordingly i will proceed for next steps. | 19/Aug/25 5:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Citrix Account ID has been renamed with Informatica Prod â€œ536697248966 â€ƒâ€ƒ SAA_Informatica_PRODâ€ | 19/Aug/25 5:42 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet, NACL, RAM ,SG and connectivity has been established. !image-20250819-153624.png¦width=1417,height=750,alt="image-20250819-153624.png"! Connectivity has been tested and working fine. !image-20250819-153747.png¦width=1417,height=750,alt="image-20250819-153747.png"! ¦Informatica Prod-Public¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.0.208/28¦10.40.0.208 - 10.40.0.223¦10.40.0.209 - 10.40.0.222¦14¦/28¦ ¦Informatica Prod-Public(DR)¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.128/28¦10.40.1.128 - 10.40.1.143¦10.40.1.129 - 10.40.1.142¦14¦/28¦Â ¦AZ2¦ !image-20250819-154222.png¦width=1417,height=750,alt="image-20250819-154222.png"! | 19/Aug/25 5:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Assigning for review. | 21/Aug/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed with internet acess. | 25/Aug/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 06:33
AM20-861 | Informatica Server ¦¦ Application monitoring and Alerting | Cancelled | 4 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811839 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 20:45 | 2026-01-31 21:55 |  |  |  | 0 | AS Product owner I would like to configure alerting and monitoring for application specific alerts. Acceptance Criteria: Health/ready endpoints: health (basic)/ ready (deps checked) *Alerts*: non-2XX or latency > P95 target for 3-5 mins Startup time and failures: boot duration count of failed boots *Alerts*: boot>5sec or > 1 failed start in 15 mins Unhandled exceptions: total and by class module *Alerts*: error rate > 2% of requests for 5 mins Log anomaly rate: ERROR/WARN per minute vs baseline *Alert*: Spike above learned baseline Critical transaction success rate ( e.g login) *Alert*: Success<98% of 10 mins |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [9 empty] | AM20-209 |  |  |  | 31/Oct/25 11:28 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;RE_ Informatica & PROS __ Application monitoring.eml;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175948 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5ed55214 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k78z: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-27 04:33 | [13 empty] | 23/Oct/25 8:27 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;[~accountid:712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb] Please update comments in this story to reflect progress | 27/Oct/25 6:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;will configure (Health/ready endpoints: health (basic)/ ready (deps checked)) using synthetics & canary. | 31/Oct/25 11:28 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Attaching email where we have got email confirmation, that the alarms and monitoring is not needed since the client already have it in place. Hence, closing the story with this comment and also attaching the email for reference. | 31/Oct/25 11:28 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;[^RE_ Informatica & PROS __ Application monitoring.eml] | 31/Oct/25 5:27 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Since business has rejected the requirement | [25 empty] | Done | 2025-10-31 17:26
AM20-862 | Resources cleanup - Aws accounts | Done | 6 | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1817985 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-03 15:10 | 2026-02-03 16:33 |  | 2025-11-14 20:28 |  | 0 | As part of cost optimization we have planned to take a inventory of AWS resources deployed already. Further to cleanup unwanted and unutilized resources. |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 86400 | 86400 |  | 0 | 172800 | 172800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@47ec6456 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kwlv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 18 | [97 empty] | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [65 empty] | YES | YES |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [42 empty] | Done | 2025-11-14 20:28
AM20-863 | Cynet ¦¦ Server Installation | To Do |  | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1887432 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 15:27 | 2026-01-13 18:13 | 2026-01-07 08:19 |  |  | 0 | As Product owner I want to install Cynet agent on Linux/Windows EC2 instance so that threat detechtion and response coverage is enabled Acceptance Criteria. *Linux*: * Installation package hosted/accessible securely (S3 with KMS, repo, or Cynet direct download). * SSM document / automation executes successfully on a pilot group and then on all in-scope instances. * Agent registers to correct Cynet tenant and shows â€œonline/healthyâ€ in console within defined SLA (e.g., 15 minutes). * Installation is idempotent (re-run does not break existing installation). * Logging captured: instance ID, hostname, timestamp, status, version, and failure reason if any. *Windows*: * Silent install works (msi/exe unattended flags), including token/tenant configuration. * Service is running after installation and agent appears healthy in console. * Windows Event Logs / install logs are retained for troubleshooting. * | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@19d1d99d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0q0i3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2026-01-06 13:12
AM20-864 | MQ Modernization POC ¦¦ Parser testing based on sample pegasys parser | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832848 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 20:14 | 2026-02-03 23:02 | 2025-11-28 11:15 | 2025-11-28 12:00 |  | 0 | As DevOps Engineer, I need to test few existing MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6bedb0f1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo0r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:26 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:26 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;CPP to Java: Parser to be re-written with line to line conversion to retain logic. | 20/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Java Parser Covering Following High-level Algorithm- # Input * Receive a raw text message body (rawMessage) from AmazonMQ PEGASYS.OUT.UAT. # Pre-check * If rawMessage is null or empty â†’ return ParseResult with error = true (this is defensive; in normal operation this should not happen). # stripId() â€“ remove ID block if present 3.1. Let msg = rawMessage. 3.2. If msg contains "\nM42": * Call stripId(msg): * Find index of " /ID ". * From there, find "ACARS\r\n". * Return: msg_before_ID + msg_from_ACARS_onwards. 3.3. Else: keep msg unchanged. . # Construct buff and newbuff 4.1. buff = msg (the stripped or original message). 4.2. Append control chars: * CR = 13, NL = 10, ETX = 3. * newbuff = buff + CR + NL + ETX. # Split into lines & find .JNB 5.1. Split newbuff by '\n' into lines[]. 5.2. Search for first line where lines[i].startsWith(".JNB"). 5.3. If found, set counter = i + 1 (line after .JNB). 5.4. If not found or counter >= lines.length: * Default: create OutboundMessage(qMng, newbuff) â†’ MNG only. * Return this as ParseResult with error = false. # Extract relevant lines safely * line0 = lines[counter] (or "" if out of range). * line1 = lines[counter + 1] * line2 = lines[counter + 2] * line3 = lines[counter + 3] Using helpers: * safeLine(lines, index) â€“ returns "" if index out of range. # Extract tokens (T1, T2, etc.) safely Using safeSub(s, begin, endExclusive) to avoid index errors. 7.1. T1 = line0[0..3) â†’ message type (MVT, DIV, ASM, SSM, CGO, etc.). 7.2. T2 = line1[1..5) â†’ secondary code (CIRQ, CICX, etc.). 7.3. line1_0_2 = line1[0..2) â†’ used to check "SA". 7.4. line2_0_2 = line2[0..2) â†’ used to check "ED". 7.5. line3_0_3 = line3[0..3) â†’ used to check "TIM". # Prepare result container * outputs = new ArrayList<OutboundMessage>(); # Rule 1 (SSM/CGO â†’ ICARGO) * If T1 is "SSM" or "CGO": * outputs.add(new OutboundMessage(qIcargo, buff)); 10. Rule 2 (CIRQ/CICX â†’ SIP) * If T2 is "CIRQ" or "CICX": * Add OutboundMessage(qSip, buff) to outputs. * Return ParseResult(outputs, false, null) immediately 11. Rule 3 (MVT / DIV / ASM) 11.1. If T1 in { "MVT", "DIV", "ASM" }: 11.1.1 ASM + TIM * If T1 == "ASM" and line3_0_3 == "TIM": * Add OutboundMessage(qCimp, buff) (CIMP). * Add OutboundMessage(qIcargo, buff) (ICARGO). * Then continue. 11.1.2 MVT-specific * If T1 == "MVT": * If line1_0_2 == "SA" (SA flight): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG with CR/LF/ETX). * Add OutboundMessage(qIcargo, buff) (ICARGO). * If line2_0_2 == "ED": * Add OutboundMessage(qCimp, buff) (CIMP). * Add another OutboundMessage(qIcargo, buff) (ICARGO again â€“ same as C++ double-write). * Else (non-SA): * Add OutboundMessage(qMng, newbuff) (MNG only). 11.1.3 DIV/ASM (fallback) * Else (T1 is DIV or ASM without TIM rule): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG). 12. Rule 4 (other message types) * Else (T1 is not MVT, DIV, ASM, and not CIRQ/CICX): * Add OutboundMessage(qMng, newbuff) (MNG only). 13. Return final result * return new ParseResult(outputs, false, null); | 24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Additional parser related to Pegasys called SbrSplit has been shared by Sampi. Analysis has been started for the same. | 28/Nov/25 11:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SbrSplit parser - CPP has been converted into java based code. Repo structure has also been transformed to adopt microservice alike design. [https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git¦https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git] Parser to be tested in next sprint. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [25 empty] | Done | 2025-11-28 12:00
AM20-865 | AWS Centralized dashboard CloudWatch Dashboard for Nexio AV to monitor Performance, cost optimization and security Metrics | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718753 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 12:32 | 2026-01-29 12:42 |  |  |  | 0 | As AWS expert, I would like to create centralized CloudWatch to capture Performance, Security and Cost metrics from across accounts. Acceptance Criteria: * CloudWatch dashboards can be created in one account (Payer9 account) anf pull metrics from other accounts * User cross account IAM roles to allow Payer9 account to read cloudwatch from other accounts * Add Widgets sourcing metrics from each account * Setup AWS config aggregator in the Payer9 account to collect configuration and compliance data across all members accounts * Performance metrics - Use below Cloudwatch metrics * EC2 : CPU, Network, Disk I/O * RDS: CPU, READ/Write IOPS * Lambda: Duration, Error Rate * and source these into widgets in the centralized dashboard * Security Metrics: Centralized Security Hub is already enabled, which can pull in findings from GuardDuty, Config, Macie, Cloudtrail, Inspector etc. |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60b85e0b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aofj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-23 14:43 | [13 empty] | 23/Jul/25 4:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Created Trellix Dash board with CPU, Memory and Disk usage. | 25/Jul/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dash board prepared for CPU, Disk, Network and memory for Trellix application. | 25/Jul/25 8:09 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sent for review | 27/Jul/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Could see the metrics for trellix server, moving to PO approval, | 28/Jul/25 9:57 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:57
AM20-866 | Nexio AV ¦¦ Security compliance Implementation | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | High | 1660206 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-31 17:55 | 2026-01-31 18:38 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Nexio AV account *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;13/May/25 7:39 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;13/May/25 7:39 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 13/May/25 7:38 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250513-053834.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1099411 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@26327809 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a2j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-07 06:31 | [13 empty] | 07/May/25 8:30 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Security compliance implemented, awaiting for the security score to update. | 13/May/25 7:38 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Controls were implemented and score updated successfully. !image-20250513-053834.png¦width=1276,height=567,alt="image-20250513-053834.png"! | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-13 07:39
AM20-867 | Rehosting & Replatforming of applications from on-Prem to AWS | To Do |  | None( Epic) |  |  |  | High | 1620350 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 14:56 | 2026-01-17 17:50 |  |  |  | 0 | Application migration (re-hosting or re-platforming of on-prem applications to AWS cloud. The activities includes, deployment of DMS tool in SAA servers, migration related activities, configuration, 3rd party application connectivity's, setting up of issue resolution, backup and restore validations, DR, DNS change, UAT, Delta migration, issue fixes and final handover activities | [23 empty] | 273600 | 100800 | 144000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3525bd44 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-3 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | yellow | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxn1b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-03-04 11:35
AM20-868 | Add-On ¦¦ WAF Rule creation for Voyager | To Do | 4 | None( Backlog) |  |  | Aravind Raj | Medium | 1842274 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 13:50 | 2026-01-20 15:49 |  |  |  | 0 | [20 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@37603ed1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5m3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-17 08:33
AM20-869 | POC for replacing IBM MQ with AWS MQ | To Do | 0 | None( Backlog) |  |  |  | Medium | 1795168 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 14:52 | 2026-01-29 18:02 |  |  |  | 0 | [57 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63afd04c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akq: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:36
AM20-870 | Security group and NACL rules remediation | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818704 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-09 18:46 | 2026-01-09 20:55 |  |  |  | 0 | Should restrict port 22, 3389, 1433, 3306 from all traffic 0.0.0.0/0 across all the AWS accounts. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [11 empty] | 17856 | 17856 |  | 0 | 17856 | 17856 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3bed953e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzwr: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 11:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SG inbound rules are updated to restrict port to allow all traffic 0.0.0.0/0 | [26 empty] | 1817984 | AM20-225 | Security controls remediation - Informatica and PROS Aws accounts | Done | 2025-10-28 11:20
AM20-871 | Servicenow Payload severity updates for Lambda alarms | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Shreyash Talwekar | Medium | 1835024 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-03 21:33 | 2026-02-03 21:49 |  |  |  | 0 | Enhance the existing Lambda function that triggers when Lambda alarms enter an alarm state. Currently, the function gathers alarm-related metrics, collects function details, and sends an approved payload to ServiceNow. However, severity information from the alarm is not included in the payload. This story addresses that gap by updating the Lambda function to capture and transmit the correct severity level from the alarm to ServiceNow. *Acceptance Criteria:* * Lambda function must include severity details from the alarm in the payload. * Payload sent to ServiceNow should accurately reflect the alarm severity. |  | Faisal Sayed | Harsh Chandra | Shreyash Talwekar |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  | ;20/Nov/25 8:33 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;14400 | [6 empty] | 0 | 14400 |  |  | 0 | 14400 | [12 empty] | 21/Nov/25 7:04 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251121-050425.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187511 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@560f4ab3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxar: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 05:33 | [13 empty] | 20/Nov/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Requirements have been gathered. Lambda function code will be reconfigured to incorporate changes, followed by payload testing. Ticket will be updated upon successful completion of testing. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Lambda function has been updated per requirements to capture severity. A test event was executed to validate behavior and output; results are attached. Test outcome is successful, and the implementation is complete. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251121-050425.png¦width=555,alt="image-20251121-050425.png"! | 24/Nov/25 8:42 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reviewed output, LGTM. | [23 empty] | 1832856 | AM20-264 | Update ServiceNow Payloads with severity | Done | 2025-11-24 08:41
AM20-872 | Billing and other solution required roles | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741166 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-03 17:10 | 2026-02-03 19:25 |  |  |  | 0 |  |  | Aravind Raj | Onkar Mirajkar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | [29 empty] | 06/Aug/25 10:30 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;IAM Role Documention.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136095 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f932959 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckgr: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 08:31 | [13 empty] | 06/Aug/25 10:30 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;[^IAM Role Documention.docx] Please Review and Verify | [26 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-11 09:19
AM20-873 | Airnavx ¦¦ establish internet connectivity via NAT Gateway and TGW | In Review | 0 | Sprint 1 | 2025-03-17 | 2025-03-28 | Sankalp Rai | High | 1620884 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 13:47 | 2026-01-09 14:09 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-10 | AM20-16 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@13dfa190 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akp: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-21 07:32 | [13 empty] | 21/Apr/25 9:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Please review | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | In Progress | 2025-04-08 08:20
AM20-874 | Documentation on IAM and RBAC | Done | 5 | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | High | 1731884 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 20:59 | 2026-01-23 21:43 |  |  |  | 0 | As product owner, I like to document all the IAM - RBAC created to control the access of workloads and process to provision IAM, Terraform code location. Acceptance Criteria: Document completed having IAM roles name, purpose, Terraform code location( if applicable), Process to add respective resources |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;25/Aug/25 7:57 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;72000 | [5 empty] | 72000 | 43200 | 72000 | 1 | 72000 | 43200 | 72000 | [12 empty] | 05/Sep/25 9:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SAA_IAM Configuration_v1.1.doc;https://vodacom.atlassian.net/rest/api/3/attachment/content/1148372 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2bce2e91 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0brrf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-30 14:24 | [13 empty] | 30/Jul/25 4:24 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created Sub story and assigned to respective members. | 11/Aug/25 7:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;due to VOIS user account modification IAM roles and policy is still a ongoing process, and other sub story need to be done | 11/Aug/25 7:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Hence this story would be spill over. | 14/Aug/25 8:44 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Waiting for sanket update on substory Will accumulate EKS roles with the help of ravinder excel sheet. | 25/Aug/25 7:53 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Received sanket data today will include that to the IAM document and close this by today. | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 07:55
AM20-875 | AirNavX ¦¦ Port opening, NACL and SG group Whitelisting | Done | 5 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772278 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 21:08 | 2026-01-10 21:33 |  |  |  | 0 | As a cloud infrastructure engineer I want to provision NACL, Security groups and port whitelisting with validated connectivity so that the new application can be securly deployed in AWS with controlled access, compliance to security standards and verified communication paths Acceptance Criteria: * Security groups are created per application tier * required inbound and outbound rules are defined for each tier ( HTTPS: 443 inbound from ALB to web, DB port 3306 from App SG) * no overly permissive rules (0.0.0.0/0) NACL config: * Network ACL applied at subnet level with stateless allow/deny rules for required application port * Both inbound and outbound NACL rules are explicitly documented * Default NACLs are not used Whitelisting: * External IP range for trusted users/ partners are whitelisted * Whitelisting rules are implemented at the SG/NACL level based on environment needs * Documentation include source IPs, purpose and without expiry date Connectivity validations: * E2E connectivity test performed APP--DBflow, External user ---Application endpoint (via ALB/API Gateway) * Connectivity validated using tools like telnet, nc and AWS connectivity tests * Validated evidence captured in the deployment checklist Security and compliance: * All configurations follow least privilege principle * Changes are auditable in CloudTrail with tagging (App, Env, Owner, ChangeID) Deliverable: * SG & NACL rule tables (port, protocol, source/destination) * Whitelist IP registry with owners and validity * Validation test results signed off by infra + security team |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4a97e1ad | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq8r: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-19 14:18 | [13 empty] | 19/Sep/25 4:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared and implemented. with the help of LIFT and CSOC. VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 19/Sep/25 4:19 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Bhavesh we have changed subnet from /27 to /28 and updated comms and shared Sita for implementation. | 19/Sep/25 4:21 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on Albert SITA has been implemented comms via subnet level. according to management i am closing this request and i will working on validation part with new request. | 19/Sep/25 4:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on Albert SITA has been implemented comms via subnet level. according to management i am closing this request and i will working on validation part with new request. | [26 empty] | Done | 2025-09-22 08:50
AM20-876 | TM1 ¦¦ Subnet creation using terraform | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Satya Varanasi | Medium | 1620359 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 18:51 | 2026-01-30 21:18 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for TM1 application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for TM1 and the configured based on the approved comms matrix |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-11 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a96537d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnn3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:53 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 04/Apr/25 10:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation got completed Manuel. As terraform not ready. While creating this TM1 subnets. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-07 10:11
AM20-877 | (Airchef)Terraform code generation for Route 53 Hosted Zone Creation & Record Migration. | Done |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Faisal Sayed | Medium | 1827706 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-24 20:16 | 2026-01-25 00:05 |  |  |  | 0 | Hosted Zone Creation Develop infrastructure-as-code to provision a Route 53 hosted zone for the specified domain. The configuration should support tagging, environment-specific naming, and be reusable across deployments. DNS Record Management Implement a declarative script to define and manage DNS records within the hosted zone. This should include support for common record types (A, CNAME, MX, TXT) with configurable TTLs and values. |  | Faisal Sayed | Sanket Kale |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e |  |  |  |  | ;12/Nov/25 10:17 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 |  |  |  |  | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@53b50383 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1v7: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-12 04:56 | [13 empty] | 07/Nov/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status: Blocked* Awaiting SAA approval for the updated DNS records associated with the {{airchef}} domain. Terraform provisioning is currently on hold until the DNS configuration is finalized. | 12/Nov/25 6:49 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Status Update:* * Task moved from *Blocked* to *In Progress*. * Terraform code for Route 53 provisioning has been developed and handed over to *Sanket*. * *Next Action:* Sanket to review and execute the code in the *sandbox account* for validation. | 12/Nov/25 6:55 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Terraform code has been successfully reviewed and tested in the sandbox environment, and all validations are positive. Â | 12/Nov/25 10:16 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Code has been reviewed, tested successfully, and validated. Moving the sub-story to *Done*. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | Done | 2025-11-12 10:12
AM20-878 | Bastion Host creation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642039 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 14:24 | 2026-02-02 16:07 |  |  |  | 0 | As AWS expert, I would be creating two Bastion host by launching Private EC2 instance and AMI for preferred operating system and configure Security groups and apply Inbound and Outbound Rule * One for Internal Migration team (having internet access) * Another for Nexio and Customer access with RDS enabled Acceptance Criteria: * Bastion host provisioned successfully * access is provided to Nexio and business team by SSH client and connect to bastion host public IP adddress using private key |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;17/Apr/25 2:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 57600 | 14400 | 28800 | 0.5 | 57600 | 14400 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@327eec44 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00syj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-15 16:18 | [13 empty] | 15/Apr/25 6:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Separate Network setup with internet gateway and pubic IP will be required for shared service account 864899875361, after network setup would create bastion server for internal team usage. [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] may need your help in setting up network. | 17/Apr/25 2:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;I have created a Bastion host in network account and have customized RDP port number from 3389 to *54925* for security measures. Â As we all know the jump server can be RDP accessed by two user in parallel, have created a user account named *VOIS_User01 and VOIS_User02* with Administrator privilege, password will be shared separately. Â Bastion Host Details; Â *Server name: Bastion-Host-Internal* *Server IP: 16.28.7.145(ElasticIP)* *Server RDP Port: 54925* | 17/Apr/25 2:16 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Bastion host for Nexio will be created after sometime. | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-17 14:16
AM20-879 | Nexio AV ¦¦ Firewall Rule creation | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Satya Varanasi | Medium | 1650869 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 19:01 | 2026-01-16 19:31 |  |  |  | 0 | As AWS expert I will be creating firewall rules for Nexio AV application so that security compliance can be met Acceptance Criteria: * Firewall rules are created and sent to Vodacom implementation |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@76b1f9b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:y | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:45 | [13 empty] | 29/Apr/25 7:44 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;FW rules will be implemented after comms implementation. This may need to move next sprint. | 20/May/25 5:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This Story dependency with comms implementation, the same with SAA team. Once SAA team actioned this story will be handled and closed until that this will not possible to address.(Note: it may move next sprint also) | 10/Jun/25 2:09 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;No longer needed based on recent conversation. * Based on request from Sinjun, the migration approach for Trellix/NexioAV has been altered, we are moving away from lift and shift approach to Greenfield installations for Nexio(Trellix) servers. * VOIS team would be responsible for providing AWS infrastructure, establishing connectivity * Nexio team would do the installation of Trellix servers on provided AWS infrastructure. | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-10 14:09
AM20-880 | TM1 ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 10 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620851 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 21:17 | 2026-01-21 21:29 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [8 empty] | AM20-11 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6582c1ff | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxslr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | [108 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-08 06:24 | [13 empty] | 08/Apr/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms implemented From VDC, SITA now need to follow-up with Leigh for AWS firewall rules implementation. | 08/Apr/25 5:17 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been implemented, we are testing ports with test box, once all done we will create new SG will whitelist ports. | 22/Apr/25 3:54 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;NACL and SG has been setup, still Teradata side pending, checking with Leigh. | 24/Apr/25 8:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Connectivity got implemented testing also done successful. | 29/Apr/25 7:48 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 apps mat testing done successful. Teradata connectivity port20,21 &22 will be established after moving relevant resources to shared vpc. For app migration there is no dependency. | 18/May/25 2:40 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [21 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:40
AM20-881 | PROS ¦¦ Monitoring and Alerting Servers post migration | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773954 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 16:46 | 2026-01-29 18:30 |  | 2025-10-31 17:21 |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if PROS service is stopped |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@37ad6335 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 |  | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [65 empty] | YES | YES | 2025-10-31 12:27 | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [12 empty] | 31/Oct/25 2:26 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Post Migration: I have installed the SSM Agent for all the PROS prod instances. Configured CloudWatch Agent. Created Systems Manager Parameters for the CloudWatch Agent to fetch the config. Custom Metrics part completed. Monitoring done. Alerts generated for the metrics. | 31/Oct/25 5:20 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-10-31 17:21
AM20-882 | AirNavX ¦¦ Subnet creation using terraform | Done | 0 | Sprint 1 | 2025-03-17 | 2025-03-28 | Sankalp Rai | High | 1620392 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 16:41 | 2026-01-09 20:27 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for AirnavX application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for AirNavX and the configured based on the approved comms matrix |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4777a0ee | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnaf: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:52 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 09/Apr/25 5:44 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets has been created. Please review | 17/Apr/25 11:10 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Subnet was created manually Subnet > created Route table > Created SG > Created NACL > Created AD Firewall flow > Implemented Send for PO Approval | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-21 09:01
AM20-883 | Creating Transit Gateway attachment with centralized subnet in Shared VPC account | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-24 16:11 | 2026-01-24 17:42 |  |  |  | 0 | As Network expert I would like to Create Transit Gateway attachment with centralized subnet in Shared VPC account *Acceptance Criteria*: * Transit Gateway attachment is successfully created with centralized subnet |  | Harsh Chandra | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100033 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052941.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100030 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-053047.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100031 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-053208.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100032 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-074925.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103901 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-074943.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103902 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075022.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103900 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075049.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103899 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075143.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103903 | [9 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@64ab5b36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i039pn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-07 16:16 | [13 empty] | 07/May/25 6:15 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dedicated TG attachment subnet created and attached. Testing is pending. | 12/May/25 7:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Test will be initiated today | 14/May/25 7:34 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TG attachment has been configured. Need to test internet connectivity with other accounts. All details shared below. ¦10.40.1.160/28¦10.40.1.160 - 10.40.1.175¦10.40.1.161 - 10.40.1.174¦14¦/28¦AZ1¦Â ¦ ¦10.40.1.176/28¦10.40.1.176 - 10.40.1.191¦10.40.1.177 - 10.40.1.190¦14¦/28¦Â ¦AZ2¦ !image-20250514-052909.png¦width=1135,height=580,alt="image-20250514-052909.png"! !image-20250514-052941.png¦width=1126,height=583,alt="image-20250514-052941.png"! Route table; !image-20250514-053047.png¦width=1126,height=536,alt="image-20250514-053047.png"! Interface associations: !image-20250514-053208.png¦width=1137,height=568,alt="image-20250514-053208.png"! | 14/May/25 5:08 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Common TG attach created and working for multi account, but still need to test further with different scenarios. This required further testing for closer. | 14/May/25 7:13 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;All tests done and working according to our requirement. | 19/May/25 11:26 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Could not verify the routing to internet Routing to internet to be verified and updated Assigning back to [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 19/May/25 5:57 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Routes has been showed overcall. All are configured according to requirement. S C:\Windows\system32> tracert [http://google.com¦http://google.com¦smart-link] Â Tracing route to [http://google.com¦http://google.com¦smart-link] [192.178.54.142] over a maximum of 30 hops: Â Â 1Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 2Â Â Â <1 msÂ Â Â <1 msÂ Â Â <1 msÂ 172.22.2.132---> security account---going to IGW Â 3Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 4Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 5Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 6Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 7Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 99.83.116.121---> AWS datacenter Â 8Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 172.253.65.163---> Google DC Â 9Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 192.178.73.217---->google dc 10Â Â Â 18 msÂ Â Â 18 msÂ Â Â 18 msÂ [tzjnba-ah-in-f14.1e100.net¦http://tzjnba-ah-in-f14.1e100.net] [192.178.54.142]--->google dc Â Trace complete. PS C:\Windows\system32> | 20/May/25 5:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This story reassigned yesterday for routing validation so this will be closed this sprint. | 22/May/25 9:52 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As discussed we have validated routing entries and tracert has been updated with details. Subnets: !image-20250522-074925.png¦width=1109,height=569,alt="image-20250522-074925.png"! !image-20250522-074943.png¦width=1114,height=569,alt="image-20250522-074943.png"! Roue table: !image-20250522-075022.png¦width=1112,height=520,alt="image-20250522-075022.png"! !image-20250522-075049.png¦width=1107,height=559,alt="image-20250522-075049.png"! !image-20250522-075143.png¦width=1100,height=565,alt="image-20250522-075143.png"! Please review the same. | 30/May/25 2:46 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Review Done Transitioning to PO approval | 02/Jun/25 9:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-02 09:19
AM20-884 | TM1 ¦¦ Firewall Rule creation | Done | 2 | Sprint 3 | 2025-04-14 | 2025-04-25 | Sankalp Rai | Medium | 1644189 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 13:18 | 2026-02-06 14:04 |  |  |  | 0 | As AWS expert I will be creating firewall rules for TM1 application so that security compliance can be met Acceptance Criteria: * Firewall rules are created and sent to Vodacom implementation |  | Sankalp Rai | [5 empty] | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [5 empty] | ;17/Apr/25 11:05 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b493d0d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-14 07:44 | [13 empty] | 14/Apr/25 9:44 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Call Pending on Firewall placement. Call scheduled for 15th April 2025 Vodacom: Leigh to manage the Firewall and create Rules on Firewall VOIS: Raise request for Firewall Rule in the provided Format | 17/Apr/25 11:06 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;AWS Network Firewall is for monitoring internet traffic coming into AWS and going out of AWS. TM1 does not require any connectivity over internet. Connectivity to TerraData is being done internally Some of the VMs under TerraData right now are being moved to Shared VPC. SAP Rise connectivity is not required. Since TM1 does not require internet connectivity, there is no need to create AWS Network Firewall rules for TM1 Moving to in review for closure | [25 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-21 09:03
AM20-885 | Tag Validations for Informatica | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820185 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 20:45 | 2026-01-15 23:41 |  | 2025-11-12 08:22 |  | 0 | As a Cloud governance engineer I want to validate that all resources and workloads related to newly migrated applications have the correct mandatory tags applied so that we can ensure accurate cost allocation, compliance reporting and automation alignment across all Informatica account Acceptance Criteria: * Tags for all applicable application resource type ( EC2, EBS, RDS, S3 lamda, ALB/NLB, Cloudwatch log groups) are successfully captured. * If there are any tags not available then manually updated successfully * Validations runs across all migrated resources and as per agreed format |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:34 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;209400 | [5 empty] | 28800 | 0 | 209400 | 7.27 | 28800 | 0 | 209400 | [12 empty] | 07/Nov/25 9:09 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251107-070856.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1179412 | 07/Nov/25 9:09 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251107-070933.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1179416 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@196a21d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l62b: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 11:53 | 3_*:*_1_*:*_156032581_*¦*_10041_*:*_1_*:*_708499839_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 1:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started verifying the tags are being applied on all resources for both Informatica Dev and Prod environment. | 05/Nov/25 4:19 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have updated all mandatory tags for all Informatica Dev & Prod Environment. | 07/Nov/25 9:09 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251107-070856.png¦width=629,alt="image-20251107-070856.png"! | 07/Nov/25 9:09 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251107-070933.png¦width=629,alt="image-20251107-070933.png"! | 12/Nov/25 8:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-12 08:22
AM20-886 | Patch Solution cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818696 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-13 20:51 | 2026-01-13 21:09 |  |  |  | 0 |  |  | Aravind Raj | Faisal Sayed |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@698194ac | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzvv: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-31 09:18 | [13 empty] | 31/Oct/25 11:17 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;The Patching instances are still needed, it shall be in stopped state when not in use and terminated once the patching demo is done which has been postponed. [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] [~accountid:712020:54791a09-30fd-4ab7-8a1d-068b13e544d8] | [26 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-11-14 20:26
AM20-887 | PROS ¦¦ Migration agent installation | Done | 0 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1786910 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 18:29 | 2026-01-30 19:51 |  |  |  | 0 | AS AWS Product owner I want to install migration agents in both source and target accounts so that workloads can be discovered replicated and migrated securly and reliable into AWS, capture disk, network activity and replicate workloads in AWS Acceptance Criteria: *Replication receiver* - Given the target AWS account is selected when the migration service creates replication servers or staging area subnets then the target account provisions EC2 instances and storage for replication *IAM trust policies* - The migration hub service role is created in the target account when the source account publishes replication traffic, then cross account IAM trust allows replication without manual credential handling *Networking and Security* - The replication server is deployed in a VPC when traffic flows from source to target then it uses encrypted channels and passes through SG/NACLrules validated against compliance baselines *Resources readiness* - Migrated workloads are created in the target when cutover happens the EC2, RDS and AWS service provision successfully in the correct subnet, AZ and security group *Monitoring and rollback* - Agents are sending replication data when a failure occurs then alerts are generated in CoudWatch/SNS and rollback to the last stable snapshot is possible |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5de8572e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hc4b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:15 | [13 empty] | 24/Sep/25 8:14 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Need to check with Sinjun/Wanda for change request initiation for agent installation. | 25/Sep/25 5:25 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Change has been submitted â€œCHG0067735â€ and approved, we required Sinjun support for Agent installation. | 26/Sep/25 12:19 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still Migration agent comms not implemented and it is under approval process. | 09/Oct/25 4:32 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Agent has been installed on all 3 PROS servers and test instance has been created and handed over to customer for connectivity testing. Hence i am closing this story. | 17/Oct/25 7:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:17
AM20-888 | AirNavX Account ¦¦ Security Compliance Implementation | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672716 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-06 17:05 | 2026-02-06 17:11 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of AirNavX account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250528-092239.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1106065 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@33a69e54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04ft7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-28 09:24 | [13 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Account - 345594574792 Controls were implemented and security score is updated is for all the three security standard frameworks- CIS, NIST and AWS FSBP !image-20250528-092239.png¦width=1279,height=589,alt="image-20250528-092239.png"! | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-28 11:24
AM20-889 | Airnavx ¦¦ Establish connectivity by Firewall whitelisting & Ports opened | Done | 6 | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620850 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 15:03 | 2026-01-31 17:06 |  |  |  | 0 | As Network expert I would place request with SAA to do firewall opening for AWS subnets and open ports for connectivity establishment *Acceptance Criteria*: * PORT and firewall is whilelisted and open and connectivity with VDC/SAADC is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [8 empty] | AM20-10 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4559db6 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 8 | Sprint 9 | Sprint 12 | Sprint 13 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-25 06:58 | [13 empty] | 25/Jun/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According Harsh and Deepak update, this need to address after TM1 and informatica servers network action, hence i am keeping this as blocked(As per Harsh update) | 28/Jul/25 8:51 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Currently app under LLD review once review done i will initiate comms for the same. SO this will be moved to next sprint. | 04/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on it according to recent LLD call review. | 07/Aug/25 8:38 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared, with latest subnet details, i will initiate mail communication with customer/app owner for flows review or in case any additional flows needed they should notify further process. | 12/Aug/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Shared comms to app owner for review and add in case needed any additional flows for the same. | 25/Aug/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms under validation by app owner, so this is right story for spill over to this sprint. | 26/Aug/25 1:04 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;# Initially after follow-up customer prepared and send comms. # During review i identified as comms as not prepared right way and reshared the same comms to customer for validation. # After continuous 3 days follow-up we have received comms from customer as on date 25th Aug 10:00 PM. # There is no sufficient time to manage this story in this sprint due delay with customer. # Note: It has been communicated customer and management regularly but he took longer time to manage. | 29/Aug/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Reviewed and prepared AirNavX comms for VDC/SITA sheets and same sent app owner for LIFT/CSOC request towards implementation. | 03/Sep/25 9:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been reviewed and submitted to app owner for further process. | 03/Sep/25 9:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Albert has been submitted requested LIFT and CSOC request for ports androuting implementation. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 03/Sep/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The below is the current status: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Routing already in place hance not required any action on this and making this as completed.) | 08/Sep/25 6:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [15 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-09-08 06:36
AM20-890 | ServiceNow ¦¦ Secure Integration with Cloud ServiceNow | Done | 8 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650451 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 13:24 | 2026-01-11 14:05 |  |  |  | 0 | As a AWS Cloud architect, I want the Amazon SNS to securely connect to the on-prem ServiceNow instance so that error alerts can be logged as incidents. Acceptance Criteria: * ServiceNow API credentials are stored securely in AWS Secrets manager * Network connectivity is verified via NAT gateway/VPN * HTTP request to ServiceNow are authenticated and secure |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;13/May/25 11:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;24/Jun/25 1:30 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;10/Jul/25 9:30 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;57600 |  |  |  | 115200 | 0 | 115200 | 1 | 115200 | 0 | 115200 | [12 empty] | 15/May/25 11:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;Ashton response on delay for SNow endpoint.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100994 | 22/May/25 9:56 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103907 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5538b454 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 08:59 | [13 empty] | 02/May/25 10:58 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Current State: AWS Level configuration of ServiceNow with Lambda Function and SNS is complete. Next Steps: # Setup a call with ServiceNow Cloud team to do the POC # Setup SNS to Push notifications to ServiceNow # Setup required matrices # Validate the functionality. # Get Sign-off on successful Setup | 15/May/25 11:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Delay from ServiceNow app owner ( Ashton) in providing the ServiceNow API endpoint, conversations comms screenshot attached. Potential spill over [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] | 20/May/25 10:18 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;¦Setup on AWS in complete. API endpoint is to be provided by Ashton Steyn. Once the end point is added to SNS, we would be able to test if the notification is received correctly in ServiceNow Cloud. Next Step would be to showcase this entire setup to Denise and Bhavesh and get Sign off. Action Points API EndPoint pending on Ashton Steyn. Need Availability of Denise and Bhavesh to showcase the POC and get SignOff on the POC¦ | 22/May/25 9:57 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 02/Jun/25 8:22 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;API Provided by Ashton, could not be configured in SNS Topic. We are getting error â€œURL is not valid, INVALIDâ€ We are waiting for an update from Ashton on how to resolve this error. | 19/Jun/25 7:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Call planned with ServiceNow team on 19th June to provide walkthrough and clarify open queries, needed to proceed with next steps [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] | 24/Jun/25 1:30 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Setup Completed POC Completed End Point for Prod to be provided by service now team (Feroz). | 10/Jul/25 9:30 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Setup >> Completed POC >> Completed End Point for Prod to be provided by service now team (Feroz) >> Completed Moving to review for closure | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-891 | Trellix integration with MQ | Blocked | 2 | None( Backlog) |  |  | Satya Varanasi | Medium | 1794150 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 14:33 | 2026-01-20 15:46 |  |  |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan MQ workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in MQ server * Trellix is able to access MQ account successfully and perform scanning |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3b924c6e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g04 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-27 14:04 | [13 empty] | 27/Oct/25 4:03 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This action need to addressed once server build completes. | [29 empty] | To Do | 2025-09-30 10:19
AM20-892 | TM1 ¦¦ establish internet connectivity via TGW | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620885 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 14:20 | 2026-02-03 17:10 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [26 empty] | AM20-15 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@232fa3c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxslz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-01 17:41 | [13 empty] | 01/Apr/25 7:40 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Internet connectivity has-been established and tested. | 04/Apr/25 10:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Internet setup has been completed and tested working fine. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-14 09:39
AM20-893 | TM1 ¦¦ Life Cycle Management ¦¦ Log Retention | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1730214 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 15:54 | 2026-01-24 16:39 |  |  |  | 0 | As Product Owner I would like to establish the life cycle management for log retention specific to TM1 account to have defined log retention policies for all critical log sources so that we can meet compliance, enable forensic investigation and optimize storage Acceptance Criteria: log retention policy is defined per account * Production env. - log retention period 90 days Â *Please note* that post retention period, these logs can either be deleted or moved to cold storage, which can be configured based on your confirmation however, data retrieval from cold storage is charged additionally. * All critical log sources are covered - cloudtrail, VPC flow logs, cloudwatch logs and other tools must be retained as per policy * Log retention is automated - log groups are created when they are detected * Logs reaches its retention threshold when the time expires it should either be deleted ot moved to archive (cold storage) * Retention policy is auditable so that it can be configured accordingly |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;06/Aug/25 8:18 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@b33f9af | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bn5n: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 06:18 | [13 empty] | 06/Aug/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Centralized bucket retention policy is added to move to glacier infrequent access after 90 days from standard class. | 11/Aug/25 4:27 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:27
AM20-894 | Patching New Requirement ¦¦ Automatic reboots post Patching | Done | 6 | Sprint 21 | 2025-12-22 | 2026-01-02 | Yashwant Thakur | Medium | 1863370 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 21:11 | 2026-01-27 22:17 | 2026-01-04 09:12 | 2026-01-02 11:27 |  | 0 | As a cloud platform product owner I would like Patching workflow to automatically trigger the controlled reboot once the patching is completed so that the servers come back online and running with the updated Patch applied without any manual intervention Acceptance Criteria: * Reboot trigger - AN EC2 instance with patching enabled when the patching task for that instance completed successfully system must trigger a reboot workflow * Given that instance tagged with *Reboot=Yes* when the patching completes then the instance must be rebooted and given the instance tagged with *Reboot=No* when the patching completes then the instance reboot is skipped * If the reboot fails, it should try minimum of 3 times and if the reboot is failed than an alert is sent to ServiceNow via SNS so that the incidents can be recorded * Agonistic Reboot workflow - Given the EC2 is linux or windows , post reboot it should be able to run the automatic commands successfully * Given that the reboot is performed when the EC2 returns online then both the system status and instance status must reach *Status = OK* within the defined timeout of 5-10 mins. |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [5 empty] | ;17/Dec/25 8:21 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;86400 | [5 empty] | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 17/Dec/25 8:43 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251217-064315.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1195352 | 17/Dec/25 8:44 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251217-064400.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1195353 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@706d20f8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001i | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_1380898735_*¦*_10041_*:*_1_*:*_1797880683_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1380898735_*¦*_10041_*:*_1_*:*_1797880683_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1380898735_*¦*_10041_*:*_1_*:*_1797880683_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1380898735_*¦*_10041_*:*_1_*:*_1797880683_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-17 06:35 | 3_*:*_1_*:*_1380898735_*¦*_10041_*:*_1_*:*_1797880683_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 17/Dec/25 8:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Summary â€“ CloudWatch Logs â†’ EC2 Restart Automation (Postâ€‘Patch)* Implemented an endâ€‘toâ€‘end serverless workflow that monitors SSM patch logs and automatically restarts EC2 instances tagged for restart once compliance is detected. *Outcome* * âœ… Realâ€‘time detection of *FINAL_STATUS: COMPLIANT* in the latest SSM patch log stream * âœ… Automatic reboot/start of EC2 instances with {{Restart=True}} tag, based on instance state * âœ… Robust logging, error handling, and leastâ€‘privilege access *Architecture (Highâ€‘Level)* SSM Patch â†’ CloudWatch Logs â†’ Subscription Filter â†’ Lambda â†’ EC2 Actions * Monitors *latest* log stream only to prevent duplicate actions * Latency typically < 3 minutes from compliance log to instance action *Key Logic & Actions* * Validate source log group and most recent stream * Detect compliance message * Discover instances via tag {{Restart=True}} ** Running â†’ {{reboot}} ** Stopped â†’ {{start}} ** Other states â†’ skip (logged with reason) *Security & Permissions (Summary)* * Lambda execution role: minimal permissions for CloudWatch Logs (write/describe) and EC2 (describe/reboot/start) * CloudWatch Logs â†’ Lambda invoke permission scoped to the specific log group *Testing & Validation* * Simulated compliance events via CloudShell. * Verified: subscription trigger, Lambda execution, latestâ€‘stream check, instance discovery/actions, error handling, and logging. | 17/Dec/25 8:43 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251217-064315.png¦width=486,alt="image-20251217-064315.png"! | 17/Dec/25 8:44 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251217-064400.png¦width=486,alt="image-20251217-064400.png"! | 02/Jan/26 7:56 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *1. Overview* The configuration enables automated EC2 instance reboot post-installation compliance by leveraging AWS services such as CloudWatch Logs, Lambda, and EC2 tagging. h3. *2. Trigger Condition* * An *EC2 instance* is tagged with a specific key-value pair (e.g., {{restart=true}}). * This tag acts as the primary condition for initiating the workflow. h3. *3. Log Monitoring* * A *CloudWatch Logs subscription filter* is configured to monitor log streams. * It searches for the phrase *â€œfinal status: compliantâ€* in the latest log entries. * This ensures the reboot only occurs after successful compliance verification. h3. *4. Lambda Invocation* * Upon detecting the compliance status in the logs, the subscription filter triggers an *AWS Lambda function*. * The Lambda function: ** Processes the payload from CloudWatch. ** Validates the EC2 instance tags. ** Confirms the restart condition. h3. *5. EC2 Reboot Action* * After validation, the Lambda function initiates a *reboot operation* on the targeted EC2 instance. * This guarantees the restart happens *post-installation and compliance checks*. h3. *6. Key AWS Components* * *Amazon EC2*: Target instance for reboot. * *CloudWatch Logs*: Monitors log streams for compliance status. * *Subscription Filter*: Detects specific log patterns. * *AWS Lambda*: Handles logic and initiates reboot. | [26 empty] | Done | 2026-01-02 11:27
AM20-895 | Security and compliance implementation on PROS account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622524 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 21:06 | 2026-01-13 22:10 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on PROS account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in PROS DEV account * NIST policy implementation successfully done in PROS DEV account * AWSFSBP policy implementation successfully done in PROS DEV account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Mar/25 2:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [8 empty] | AM20-19 | AM20-17 |  |  | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250317-060821.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1079558 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a53b25a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxson: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-13 06:02 | [13 empty] | 13/Mar/25 8:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on the controls with the dependency services for the security frameworks. | 14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;The controls were implemented in Pros DEV account, Pros Production account will be picked up in separate user story. | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250317-060821.png¦width=1277,height=642,alt="image-20250317-060821.png"! | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-14 14:22
AM20-896 | AirNavX ¦¦ Validation for SG and NACL | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Satya Varanasi | Medium | 1786688 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-30 21:37 | 2026-01-30 23:46 |  |  |  | 0 | As Product owner I would like to validate SG and NACL in AirnavX account so that to ensure that is correctly configured as required and netwrok access is restricted to least privilege, compliant with security standards and traceable to the right owners *Acceptance Criteria*: Ingress Rule: * Validate only required ports are open * Check if the rules are restricted to known source IPs or SGs * Avoid overly permissive rules like ALL Traffic/ All Ports Egress Rule: * Confirm outbound rules are limited to required destinations/services * Avoid all traffic / 0.0.0.0/0 * Remove duplicate or unused rules * Check if multiple rules overlap unnecessarily * Validate SGs have proper tags (name, environment, owner) for traceability * Confirm unused SGs are not attached to ENIs NACL: * Check both inbound and outbound rules match expected traffic flow * validate rule numbers and ensure no conflicts/overlaps * Ensure the implicit DENY is preserved and only necessary allow rules are added * Avoid overly permissive entries * Since NACL are stateless, confirm return traffic rules exist for each allowed inbound connection * Validate that the correct subnets are associated with the right NACL * Avoid leaving critical subnets with the default NACL explicitly required * Confirm VPC flow logs are enabled for subnets tied to NACLs to validate actual traffic patterns against intended rules |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@f3dd427 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0hatf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-25 15:29 | [13 empty] | 25/Sep/25 5:28 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Airnavx Comms has been implemented and the need to configure respective account and initiate testing. Currently team working on server deployment process, once done we will configure rules and will initiate testing. | 06/Oct/25 8:41 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Comms has been implemented, NACL and SG is setup. App owner is able to access and install the application. Hence closing the story | [28 empty] | Done | 2025-10-06 08:41
AM20-897 | MQ Modernization POC ¦¦ Parser testing based on sample pegasys parser | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832848 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 16:22 | 2026-02-02 18:17 | 2025-11-28 11:15 | 2025-11-28 12:00 |  | 0 | As DevOps Engineer, I need to test few existing MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6bedb0f1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo0r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:26 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:26 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;CPP to Java: Parser to be re-written with line to line conversion to retain logic. | 20/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Java Parser Covering Following High-level Algorithm- # Input * Receive a raw text message body (rawMessage) from AmazonMQ PEGASYS.OUT.UAT. # Pre-check * If rawMessage is null or empty â†’ return ParseResult with error = true (this is defensive; in normal operation this should not happen). # stripId() â€“ remove ID block if present 3.1. Let msg = rawMessage. 3.2. If msg contains "\nM42": * Call stripId(msg): * Find index of " /ID ". * From there, find "ACARS\r\n". * Return: msg_before_ID + msg_from_ACARS_onwards. 3.3. Else: keep msg unchanged. . # Construct buff and newbuff 4.1. buff = msg (the stripped or original message). 4.2. Append control chars: * CR = 13, NL = 10, ETX = 3. * newbuff = buff + CR + NL + ETX. # Split into lines & find .JNB 5.1. Split newbuff by '\n' into lines[]. 5.2. Search for first line where lines[i].startsWith(".JNB"). 5.3. If found, set counter = i + 1 (line after .JNB). 5.4. If not found or counter >= lines.length: * Default: create OutboundMessage(qMng, newbuff) â†’ MNG only. * Return this as ParseResult with error = false. # Extract relevant lines safely * line0 = lines[counter] (or "" if out of range). * line1 = lines[counter + 1] * line2 = lines[counter + 2] * line3 = lines[counter + 3] Using helpers: * safeLine(lines, index) â€“ returns "" if index out of range. # Extract tokens (T1, T2, etc.) safely Using safeSub(s, begin, endExclusive) to avoid index errors. 7.1. T1 = line0[0..3) â†’ message type (MVT, DIV, ASM, SSM, CGO, etc.). 7.2. T2 = line1[1..5) â†’ secondary code (CIRQ, CICX, etc.). 7.3. line1_0_2 = line1[0..2) â†’ used to check "SA". 7.4. line2_0_2 = line2[0..2) â†’ used to check "ED". 7.5. line3_0_3 = line3[0..3) â†’ used to check "TIM". # Prepare result container * outputs = new ArrayList<OutboundMessage>(); # Rule 1 (SSM/CGO â†’ ICARGO) * If T1 is "SSM" or "CGO": * outputs.add(new OutboundMessage(qIcargo, buff)); 10. Rule 2 (CIRQ/CICX â†’ SIP) * If T2 is "CIRQ" or "CICX": * Add OutboundMessage(qSip, buff) to outputs. * Return ParseResult(outputs, false, null) immediately 11. Rule 3 (MVT / DIV / ASM) 11.1. If T1 in { "MVT", "DIV", "ASM" }: 11.1.1 ASM + TIM * If T1 == "ASM" and line3_0_3 == "TIM": * Add OutboundMessage(qCimp, buff) (CIMP). * Add OutboundMessage(qIcargo, buff) (ICARGO). * Then continue. 11.1.2 MVT-specific * If T1 == "MVT": * If line1_0_2 == "SA" (SA flight): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG with CR/LF/ETX). * Add OutboundMessage(qIcargo, buff) (ICARGO). * If line2_0_2 == "ED": * Add OutboundMessage(qCimp, buff) (CIMP). * Add another OutboundMessage(qIcargo, buff) (ICARGO again â€“ same as C++ double-write). * Else (non-SA): * Add OutboundMessage(qMng, newbuff) (MNG only). 11.1.3 DIV/ASM (fallback) * Else (T1 is DIV or ASM without TIM rule): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG). 12. Rule 4 (other message types) * Else (T1 is not MVT, DIV, ASM, and not CIRQ/CICX): * Add OutboundMessage(qMng, newbuff) (MNG only). 13. Return final result * return new ParseResult(outputs, false, null); | 24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Additional parser related to Pegasys called SbrSplit has been shared by Sampi. Analysis has been started for the same. | 28/Nov/25 11:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SbrSplit parser - CPP has been converted into java based code. Repo structure has also been transformed to adopt microservice alike design. [https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git¦https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git] Parser to be tested in next sprint. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [25 empty] | Done | 2025-11-28 12:00
AM20-898 | Lambda function to observe state in cloudwatch alarms configured for monitoring other lambda | Done | 2 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1812682 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 17:06 | 2026-02-06 17:24 |  | 2025-10-31 17:23 |  | 0 | As Product manager I would like to create Lambda function to observe state in cloudwatch alarms configured for monitoring other lambda function and send Â alert payload to servicenow as per the shared format to servicenow so that any failure of lamda is captured and remediation can be initiated. # Create Eventbridge to monitor the state change in alarm. # Create Lambda function to send alarm notifications to ServiceNow when threshold is breached. # Configure event bridge as the trigger for lambda function |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;31/Oct/25 11:21 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f18c499 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kag3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-27 04:51 | 3_*:*_1_*:*_10848683_*¦*_10041_*:*_1_*:*_1207061380_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 27/Oct/25 6:51 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Will review the description & configuration needs and will connect with Shreyash for getting more clarity. Once I get the whole picture will move the story to In Progress. | 31/Oct/25 11:20 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Create Eventbridge to monitor the state change in alarm. - Done # Create Lambda function to send alarm notifications to ServiceNow when threshold is breached. - Done # Configure event bridge as the trigger for lambda function - Done Tested it with a test alarm event. [~accountid:712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8] | 31/Oct/25 5:23 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though no demo was provided, based on Faisal comments approving it. | [27 empty] | Done | 2025-10-31 17:23
AM20-899 | Informatica ¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1755978 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 18:24 | 2026-01-22 22:19 |  |  |  | 0 |  |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3237a818 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0e0or: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-26 11:39 | [13 empty] | 26/Aug/25 1:39 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Firewall rules implemented. Identified as connectivity not working. Initiated network troubleshooting call towards fixing. Identified as routing not configured. Requested LIFT for approval LIFT approval took 3days Monday CSOC request raised and routing has ben implemented. Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 28/Aug/25 8:18 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested connectivity from informatica Prod/Dev env. Initially Network team not configured Routing after new Lift and CSOC request issue got resolved. Reference Lift & CSOC details: Routing: # CSOC:CHR0026807 # LIFT:CHG0067489 App comms: # LiFT = CHG0067488 # CSOC = CHR0026691 AWS agent Comms: CSOC logged CHR0023951 LiFT logged CHG0066992 (RITM0051174) | 01/Sep/25 8:03 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested. Based on comms we have successfully completed agent installation for prod/Dev and setup test instance for the same. Hence sending request for closer. | 03/Sep/25 8:55 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-900 | Trellix Integration with Informatica servers | Done | 1 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satya Varanasi | High | 1751443 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 15:46 | 2026-02-05 19:27 |  |  |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan TM1 workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in TM1 server * Trellix is able to access TM1 account successfully and perform scanning |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@34aaf28e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabm:i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:57 | [13 empty] | 25/Aug/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will required to action on after implementation. | 28/Aug/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will required to action on after implementation. | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 01/Oct/25 8:15 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Cutover and Trellix integration has been completed successful. | [23 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-06 08:38
AM20-901 | ServiceNow Integration with FlySAA Back-end servers for error/ reporting | Done | 5 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1685592 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 17:03 | 2026-01-13 18:31 |  |  |  | 0 | As AWS expert, I should be able to integrate ServiceNow API with FlySAA Back-end server so that in case of any error/issues, alerts can be generated and transformed into tickets in ServiceNow. Acceptance Criteria: Tickets are generate in ServiceNow against Alerts that are getting generated for FlySAA Back-End server events successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [13 empty] | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064203.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124194 | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064240.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124193 | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064306.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124195 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@78ab6644 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:06 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-02 05:24 | [13 empty] | 02/Jul/25 7:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Integration have done for backend dev with service now *dev* endpoint. Integration have done for backend prod with service now *prod* endpoint. Preprod yet to configure. | 08/Jul/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will configure the preprod endpoint with service now integration today. | 09/Jul/25 7:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Servicenow preprod integration is completed unit testing will be performed by today. | 09/Jul/25 8:41 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;746669190453 FlySAA_CMS_Backend_DevQA 216989128782 FlySAA_CMS_Backend_PreProd 396608788916 FlySAA_CMS_Backend_Prod These backend environments set with the service now integration and expected to get all the tags of instance with an alarm details. | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250709-064203.png¦width=663,height=458,alt="image-20250709-064203.png"! !image-20250709-064240.png¦width=606,height=397,alt="image-20250709-064240.png"! !image-20250709-064306.png¦width=645,height=440,alt="image-20250709-064306.png"! | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-09 08:43
AM20-902 | flysaa Backend - Application alerting | Done | 2 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820107 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 16:20 | 2026-01-23 18:34 |  | 2025-11-14 11:07 |  | 0 | As devops expert I would like to configure application error from workloads running on our EKS cluster to be collected, classified and alerted via cloudwatch so that appropriate alert is passed to Servicenow via SNS/lamda function or Event bridge. Acceptance Criteria: * All the application specific errors are captured for alerting successfully * The alerts are being sent to ServiceNow with agreed format |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Deployed error Alarms to backend production account for fabric and amadeus.;14/Nov/25 8:17 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fd7ba2e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07d | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 06:39 | 3_*:*_1_*:*_345238987_*¦*_10041_*:*_1_*:*_1124634693_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 10/Nov/25 8:39 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Had a Discussion with Yashwant, will be reaching out to Hoosen for creating a request to deploy alarms to production. | 11/Nov/25 8:26 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Hoosen has created a change request for deploying the alarms, will be working on it when we get the timeslot allocated to deploy in production since we are not deploying alarms on backend dev and preprod. | 14/Nov/25 8:18 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Deployed alarms on Production EKS Cluster. | 14/Nov/25 11:07 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-14 11:07
AM20-903 | Add-On ¦¦ WAF Rule creation for Voyager | To Do | 4 | None( Backlog) |  |  | Aravind Raj | Medium | 1842274 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 20:39 | 2026-01-26 00:34 |  |  |  | 0 | [20 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@37603ed1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5m3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-17 08:33
AM20-904 | (Airchef)Terraform Implementation for Creation of Route 53 Hosted Zones & Records. | In Progress |  | Sprint 18 | 2025-11-10 | 2025-11-21 | Sanket Kale | Medium | 1827709 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Faisal Sayed | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 2026-01-22 12:29 | 2026-01-22 13:43 |  |  |  | 0 | *Acceptance Criteria:* * *Deploy Public Hosted Zone* Use Terraform to provision a *Route 53 public hosted zone* for the domain [*airchef.co.za*¦http://airchef.co.za]. * *Manage DNS Records via Terraform* Implement Terraform configurations to create and manage various DNS record types (A, CNAME, MX, TXT, etc.) within the hosted zone. |  | Faisal Sayed | Sanket Kale | Satya Varanasi |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [20 empty] | AM20-247 | [25 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@28df5c12 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0m1vn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-07 05:56 | [13 empty] | 07/Nov/25 7:56 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Code review completed from my side its working. Created and deployed the base and component modules. | 10/Nov/25 9:07 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and tested on Sandbox environment | 14/Nov/25 4:01 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Code deployment done sandbox and same tested. | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | [23 empty] | 1822269 | AM20-247 | AWS route53 code implementation and testing for airchef.com and flyass.com on sandbox. | In Progress | 2025-11-20 08:59
AM20-905 | Nexio AV ¦¦ Security compliance Implementation | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Aravind Raj | High | 1660206 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-28 19:47 | 2026-01-28 22:16 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Nexio AV account *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;13/May/25 7:39 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;13/May/25 7:39 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 13/May/25 7:38 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250513-053834.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1099411 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@26327809 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a2j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-07 06:31 | [13 empty] | 07/May/25 8:30 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Security compliance implemented, awaiting for the security score to update. | 13/May/25 7:38 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Controls were implemented and score updated successfully. !image-20250513-053834.png¦width=1276,height=567,alt="image-20250513-053834.png"! | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-13 07:39
AM20-906 | Informatica ¦¦ Custom application Metrics | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1761210 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 12:54 | 2026-01-13 15:01 |  |  |  | 0 | # Configure & install cw agent. # Refer email for metrics to be monitored. # Create alerts as per approval in the email. |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@407cb340 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0elc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-17 06:01 | [13 empty] | 17/Sep/25 8:01 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Informatica Accounts (Dev & Prod) cutover is yet to be done. Actual workloads are yet to be migrated. Hence, blocked. | 01/Oct/25 8:24 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Configure & install cw agent - Done # Refer email for metrics to be monitored - Done # Create alerts as per approval in the email - Done | [28 empty] | Done | 2025-10-06 07:58
AM20-907 | TM1 Migration activity with tagging | Done |  | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642044 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 14:14 | 2026-01-20 15:47 |  |  |  | 0 | As Application Expert, I would be migrating TM1 server from on-prem to AWS using migration tool Acceptance Criteria: TM1 migration is successfully migrated to AWS from on-prem. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;17/Apr/25 8:31 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;144000 | [5 empty] | 144000 | 0 | 144000 | 1 | 144000 | 0 | 144000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5e70c07a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00szn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-08 10:32 | [13 empty] | 08/Apr/25 12:31 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 migration is completed, awaiting for application commsmatrix implementation status, upon confirmation will launch test instance and will ask application owner to test and confirm functionality. | 09/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Expecting to do the testing of Application related port connectivity bw on-premises and AWS along with satyasairam, post that will launch the test over instance. | 14/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Still awaiting for the connectivity confirmation. | 15/Apr/25 8:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for comms matrix implementation, upon completion will launch test instance. | 17/Apr/25 8:29 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*Test launch instance is launched and will add this server to the AWS active directory(*[*awsflysaa.com*¦http://awsflysaa.com]*),* after NACL and SG implementation will handover application to the owner to test the functionality. | 17/Apr/25 8:30 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Tags: ¦App_tier¦Application¦ ¦AppName¦TM1-application¦ ¦Business_Unit¦TBD¦ ¦CostCenter¦SAA¦ ¦CreatedBy¦AWS-MGN¦ ¦DisasterRecovery¦Enabled¦ ¦Environment¦Production¦ ¦Instance_Size¦TBD¦ ¦Instance_Type¦TBD¦ ¦Name¦fmtvmap01¦ ¦Owner¦TBD¦ | [21 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-17 08:31
AM20-908 | CloudWatch log analysis for Cost optimization | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834933 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 13:40 | 2026-01-24 14:12 | 2025-11-28 13:47 | 2025-11-28 13:59 |  | 0 | As Product owner I like to analyse the Cloudwatch logs and eliminate any duplicate logs to ensure that cost is being charged fairly and take action to reduce the current cost, which is very high at this point of time |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Worked on analysis CloudWatch cost spent on backend dev account to see the detailed spend and identify the sectors with most spent. ;18/Nov/25 8:19 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on identifying cloudwatch components contributing majorly to the CloudWatch costs.;19/Nov/25 8:21 AM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | ;24/Nov/25 4:49 PM;17cb9418-1850-4923-932b-7098ec51b6bb;7200 | Worked on identifying ingestion in log group to control putLogevents cost;24/Nov/25 4:50 PM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 | Worked on disabling enhanced monitoring , this will disable scraping pod level metrics to save cost on ObservationUsage.;24/Nov/25 4:51 PM;17cb9418-1850-4923-932b-7098ec51b6bb;21600 |  | 86400 | 0 | 93600 | 1.08 | 86400 | 0 | 93600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cb03268 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mww3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:20 | 3_*:*_1_*:*_877424994_*¦*_10041_*:*_1_*:*_425246690_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:20 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Worked on analysis CloudWatch cost spent on backend dev account to see the detailed spend and identify the sectors with most spent. | 19/Nov/25 8:30 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Enabled CloudTrail to monitor CloudWatch Data Events so that we can track which API is getting used and interacting with CloudWatch. | 24/Nov/25 4:49 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Worked on creating dashboard to identify log ingestion in each log group , updated fluent bit config to send logs only for flysaa backend amadeus and fabric microservices only to CloudWatch, also disabled sending logs to these log groups: # /aws/containerinsights/<eks-dev-cluster>/dataplane # /aws/containerinsights/<eks-dev-cluster>/host # /flysaa/dev/eks Disabled enhanced monitoring for eks cluster to save on ObservationUsage costs. | 28/Nov/25 1:59 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-28 13:59
AM20-909 | ServiceNow ¦¦ LLD preparation | Done | 4 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1610563 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 14:51 | 2026-02-03 16:01 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for ServiceNow application so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed |  | Aravind Raj | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;14/Apr/25 9:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;115200 | [5 empty] | 57600 | 0 | 115200 | 2 | 57600 | 0 | 115200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4842827b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 3/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 3 | 75 | 1 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxsnj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 2 | Sprint 3 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-10 14:19 | [13 empty] | 10/Mar/25 4:19 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 12/Mar/25 8:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;ServiceNow LLD is prepared, formatting is in progress, will complete and attach the document here. | 14/Apr/25 9:39 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Completed: 10th April 2025 Presentation to be done on Wednesday 16th April 2025 Review done by: [~accountid:712020:5d317226-2402-463f-bda5-c2cac5f43c13] and Deepak | [24 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-04-21 09:02
AM20-910 | Trellix integration with PROS | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773956 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 14:33 | 2026-02-03 17:20 |  | 2025-10-30 08:26 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan PROS workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in PROS server * Trellix is able to access PROS account successfully and perform scanning |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 29/Oct/25 8:43 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-064238.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174346 | 29/Oct/25 8:53 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-065302.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174368 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bb75c16 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [65 empty] | YES | YES | 2025-09-24 07:35 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [12 empty] | 24/Sep/25 9:34 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;To get this US completed we have to complete Building up the EC2 instance and then only the Trellix agent reconfiguration will get done to scan the PROS workloads for any vulnerabilities, malware reporting. | 03/Oct/25 9:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* Pros connectivity issue is still going and its pending from there end. Also, the EC2 instance creation is yet not started so thatâ€™s why this US will go to the spill over to next sprint. | 17/Oct/25 11:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* The EC2 instance creation is just completed on the last day of the sprint. Thatâ€™s why the US was not able to complete in this sprint now after completion of the EC2 instances we can follow up with sinjun and get the update regarding the Trellix integration with PROS account. | 29/Oct/25 8:26 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation from Sinjun that the Trellix integration is done for PROS account servers. Have shared the email with sinjun. | 29/Oct/25 8:43 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-064238.png¦width=629,alt="image-20251029-064238.png"! Attaching his confirmation which i got over teams | 29/Oct/25 8:53 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-065302.png¦width=629,alt="image-20251029-065302.png"! | 30/Oct/25 8:26 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-30 08:26
AM20-911 | TM1 ¦¦ establish internet connectivity via TGW | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620885 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 13:07 | 2026-01-24 17:00 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [26 empty] | AM20-15 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@232fa3c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxslz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-01 17:41 | [13 empty] | 01/Apr/25 7:40 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Internet connectivity has-been established and tested. | 04/Apr/25 10:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Internet setup has been completed and tested working fine. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-14 09:39
AM20-912 | Monitor health and logs of Lamda connector function to troubleshoot issue , if alerts in not processed | Done | 8 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747507 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 18:21 | 2026-01-29 18:30 |  |  |  | 0 | As Product owner I want to monitor health and logs of Lamda connector function so that I can troubleshoot issues quickly when alerts are not processed and ensure reliability of the alerting pipeline Acceptance Criteria: CloudWatch logs are enabled for the Lamda connector function to capture execution details, input events and error messages Cloudwatch Metrices (invocations, errors, throttles, duration) are available for function and updated in real time cloudwatch alarms are configured for * Errors >0 in last 5 minues * Throttles >0 * Duration exceeds timeout threshold A SNS is configured to capture failed Lamda execution Alerts from cloud watch are sent via SNS to notify ServiceNow CloudWatch Logs insights queries are available to quickly identify error trends and assist RCA Lamda health and alerting processing mertics are visulaized in a CloudWatch dashboard. |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [13 empty] | 07/Aug/25 2:30 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1137015 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4db73908 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2qr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-07 12:31 | [13 empty] | 07/Aug/25 2:30 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[^LAMBDA FUNCTIONS IN ALL FLYSAA BACKEND DEV, PRE PROD AND PROD.xlsx] Have attached the lambda detailed sheet. | 25/Aug/25 2:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;the alarms have been created for lambda functions in flysaa-backend and they are created for â€œerrorâ€, â€œthrottleâ€, â€œdurationâ€ and the thresholds are 1, 1 and 30sec respectively. the alarms notifications are now being sent to respective sns topics created which shall in-turn appear into service now dashboard as soon as the threshold values are met. | 25/Aug/25 6:32 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 06:32
AM20-913 | Provisioning of EC2 via Terraform in Nexio AV account | Done | 4 | Sprint 9 | 2025-07-07 | 2025-07-18 | Yashwant Thakur | High | 1686366 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 13:06 | 2026-01-15 16:23 |  |  |  | 0 | As a AWS expert, I would expert, I would be able to provision EC2 instance in Nexio AV account using terraform code so that the AV can be installed by the respective application Admins Acceptance Criteria: * EC2 successfully gets provisioned in Nexio AV account by terraform code |  | Faisal Sayed | Satya Varanasi |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 08/Jul/25 8:55 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250708-065045.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1123568 | 08/Jul/25 8:55 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250708-065120.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1123569 | 08/Jul/25 8:55 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250708-065236.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1123567 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@621b3d4b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-03 13:53 | [13 empty] | 03/Jul/25 3:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Cloud watch agent installation is not automated via terraform, as we can see from the metrics. This action handled by Faisal so i am assigning this story to Faisal. | 04/Jul/25 12:19 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Implemented EC2 provisioning using Terraform with support for both Linux and Windows modules. Each module includes: * EC2 instance creation with the option for multiple encrypted EBS volumes. * Separate modules for Linux and Windows OS to allow tailored configurations. * Automated installation and configuration of SSM Agent and CloudWatch Agent. * Support for tagging across all provisioned resources. * IAM handling: ability to use an existing IAM instance profile or create a new one as needed, with optional support for custom IAM roles. The implementation ensures modularity, flexibility, and security compliance across environments. | 08/Jul/25 8:55 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to story things has been configured via terraform script. Tested instance storge and configured as encrypted volumes. !image-20250708-065236.png¦width=1309,height=628,alt="image-20250708-065236.png"! Cloud watch agent configured with memory and disk monitoring. !image-20250708-065045.png¦width=1300,height=608,alt="image-20250708-065045.png"! !image-20250708-065120.png¦width=1295,height=624,alt="image-20250708-065120.png"! | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-11 13:46
AM20-914 | POC for replacing IBM MQ with AWS MQ | To Do | 0 | None( Backlog) |  |  |  | Medium | 1795168 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 12:59 | 2026-01-12 15:51 |  |  |  | 0 | [57 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63afd04c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akq: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:36
AM20-915 | Adding description for CloudWatch notifications sent to ServiceNow for AWS infrastructure resources | Done |  | Sprint 21 | 2025-12-22 | 2026-01-02 | Shreyash Talwekar | Medium | 1883876 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2026-01-09 12:42 | 2026-01-09 16:10 | 2025-12-18 08:18 |  |  | 0 | Update the lambda functions to sent description of CloudWatch alarms in the payload to be sent ServiceNow. |  | Diksha Koul | Shreyash Talwekar |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  |  | ;18/Dec/25 8:28 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;14400 | [5 empty] | 14400 | 0 | 14400 | 1 | 14400 | 0 | 14400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@449d7c5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pm6b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-18 06:31 | [13 empty] | 18/Dec/25 8:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have updated the reason and Description for all prod, dev & qa lambda functions and also tested that as well. | [26 empty] | 1881266 | AM20-302 | Convert Alarms description into simple user understandable format | Done | 2026-01-02 08:22
AM20-916 | ServiceNow Integration with FlySAA Back-end servers for error/ reporting | Done | 5 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1685592 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 14:58 | 2026-01-13 18:06 |  |  |  | 0 | As AWS expert, I should be able to integrate ServiceNow API with FlySAA Back-end server so that in case of any error/issues, alerts can be generated and transformed into tickets in ServiceNow. Acceptance Criteria: Tickets are generate in ServiceNow against Alerts that are getting generated for FlySAA Back-End server events successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [13 empty] | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064203.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124194 | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064240.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124193 | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250709-064306.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1124195 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@78ab6644 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:06 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-02 05:24 | [13 empty] | 02/Jul/25 7:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Integration have done for backend dev with service now *dev* endpoint. Integration have done for backend prod with service now *prod* endpoint. Preprod yet to configure. | 08/Jul/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will configure the preprod endpoint with service now integration today. | 09/Jul/25 7:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Servicenow preprod integration is completed unit testing will be performed by today. | 09/Jul/25 8:41 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;746669190453 FlySAA_CMS_Backend_DevQA 216989128782 FlySAA_CMS_Backend_PreProd 396608788916 FlySAA_CMS_Backend_Prod These backend environments set with the service now integration and expected to get all the tags of instance with an alarm details. | 09/Jul/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250709-064203.png¦width=663,height=458,alt="image-20250709-064203.png"! !image-20250709-064240.png¦width=606,height=397,alt="image-20250709-064240.png"! !image-20250709-064306.png¦width=645,height=440,alt="image-20250709-064306.png"! | [22 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-09 08:43
AM20-917 | Citrix ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672695 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-31 18:43 | 2026-01-31 21:31 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across Citrix account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4f5d9411 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04fqj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 06:27 | [13 empty] | 20/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on enabling the cloud config and guard duty along with macie. | 22/May/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;below mentioned service were enabled. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-22 08:19
AM20-918 | Citrix ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672695 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-03 22:13 | 2026-02-03 23:02 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across Citrix account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4f5d9411 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04fqj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 06:27 | [13 empty] | 20/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on enabling the cloud config and guard duty along with macie. | 22/May/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;below mentioned service were enabled. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-22 08:19
AM20-919 | IAM role used for Patch Solutions | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741163 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-18 18:07 | 2026-01-18 20:42 |  |  |  | 0 |  |  | Aravind Raj | Faisal Sayed |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@35ee02d7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckgj: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-04 04:32 | [13 empty] | 04/Aug/25 6:31 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*In Security Acc* # [saa-security-central-patch-bucket-windows-lambda-roleÂ ¦https://730335236533-kttygmoz.af-south-1.console.aws.amazon.com/go/view?arn=arn%3Aaws%3Aiam%3A%3A730335236533%3Arole%2Fsaa-security-central-patch-bucket-windows-lambda-role&source=lambda] # [ComplianceSyncLambdaRole¦https://730335236533-kttygmoz.af-south-1.console.aws.amazon.com/go/view?arn=arn%3Aaws%3Aiam%3A%3A730335236533%3Arole%2FComplianceSyncLambdaRole&source=lambda] # SAA_Security_WSUS_Central_Server_EC2_Role *In FlySAA-Backend-Dev Acc* # ssm-flysaa-backend-dev-spoke-windows-instance-role # [sm-flysaa-backend-dev-spoke-crossaccount-lambda-role-1¦https://746669190453-quvjamav.us-east-1.console.aws.amazon.com/iam/home?region=af-south-1#/roles/details/sm-flysaa-backend-dev-spoke-crossaccount-lambda-role-1] # [ssm-flysaa-backend-dev-spoke-crossaccount-lambda-role¦https://746669190453-quvjamav.us-east-1.console.aws.amazon.com/iam/home?region=af-south-1#/roles/details/ssm-flysaa-backend-dev-spoke-crossaccount-lambda-role] | 04/Aug/25 6:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;User Permissions: # EC2 Full Access. # Lambda Full Access # SSM Full Access # S3 Full Access # IAM Write Access | 12/Aug/25 10:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Provide me the policy list with the roles you have used. | 12/Aug/25 11:28 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;{adf:display=block} {"type":"table","attrs":{"isNumberColumnEnabled":false,"layout":"center","localId":"29cd7e76-bf6f-40fa-9142-c6fb8bb33df1"},"content":[{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Name Of Role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Account"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Permission Policies"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Permission Policy"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":4},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-flysaa-backend-dev-spoke-windows-instance-role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonS3FullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMManagedInstanceCore"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"KMSFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-flysaa-backend-dev-spoke-windows-instance-s3-policy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":4},"content":[{"type":"paragraph","content":[{"type":"text","text":"sm-flysaa-backend-dev-spoke-crossaccount-lambda-role-1"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AllowSSMExecution"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CloudWatchLogsFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Trust RealtionshipÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":3},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-flysaa-backend-dev-spoke-crossaccount-lambda-role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CloudWatchLogsFullAccess"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-backend-dev"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"ssm-ec2-read-access"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]}]} {adf} | 12/Aug/25 11:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;{adf:display=block} {"type":"table","attrs":{"isNumberColumnEnabled":false,"layout":"center","localId":"4bd8311d-ebb8-4ed2-b8da-1e130a493dfb"},"content":[{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":5},"content":[{"type":"paragraph","content":[{"type":"text","text":"saa-security-central-patch-bucket-windows-lambda-role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWSLambdaBasicExecutionRole"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWSLambdaRole"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CrossAccountLambdaExecutionPolicy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"lambda-access-to-s3"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"StartAutomationRole-Linux"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"ComplianceSyncLambdaRole"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"lambda-permission-policy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{"rowspan":3},"content":[{"type":"paragraph","content":[{"type":"text","text":"SAA_Security_WSUS_Central_Server_EC2_Role"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AllowPutToCentralPatchBucket"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"Customer Inline"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AmazonSSMManagedInstanceCore"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]},{"type":"tableRow","content":[{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"flysaa-securityÂ "}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"CloudWatchAgentServerPolicy"}]}]},{"type":"tableCell","attrs":{},"content":[{"type":"paragraph","content":[{"type":"text","text":"AWS Managed"}]}]}]}]} {adf} | [22 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-21 18:09
AM20-920 | Adding alarms for AWS account config changes. | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Shreyash Talwekar | Medium | 1799088 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2026-01-30 12:52 | 2026-01-30 13:43 |  |  |  | 0 | Add terraform code to configure below mentioned alarms for observing the cloudwatch logs regarding any changes done on AWS account. {noformat}AWSConfigChanges = { metric = "AWSConfigChanges", pattern = "{($.eventName = \"PutBucketPolicy\") ¦¦ ($.eventName = \"RunInstances\") ¦¦ ($.eventName = \"ModifyDBInstance\") ¦¦ ($.eventName = \"PutRolePolicy\")}" }, SecurityGroupChanges = { metric = "SecurityGroupChanges", pattern = "{($.eventName = \"CreateSecurityGroup\") ¦¦ ($.eventName = \"DeleteSecurityGroup\") ¦¦ ($.eventName = \"AuthorizeSecurityGroupIngress\") ¦¦ ($.eventName = \"AuthorizeSecurityGroupEgress\") ¦¦ ($.eventName = \"RevokeSecurityGroupIngress\") ¦¦ ($.eventName = \"RevokeSecurityGroupEgress\") ¦¦ ($.eventName = \"ModifySecurityGroupRules\")}" }, CMKDisablingOrDeletion = { metric = "CMKDisablingOrDeletion", pattern = "{($.eventName = \"DisableKey\") ¦¦ ($.eventName = \"ScheduleKeyDeletion\")}" }, CloudTrailConfigurationChanges = { metric = "CloudTrailConfigurationChanges", pattern = "{($.eventName = \"CreateTrail\") ¦¦ ($.eventName = \"UpdateTrail\") ¦¦ ($.eventName = \"DeleteTrail\") ¦¦ ($.eventName = \"StartLogging\") ¦¦ ($.eventName = \"StopLogging\") ¦¦ ($.eventName = \"PutEventSelectors\")}" }, ConsoleAuthenticationFailures = { metric = "ConsoleAuthenticationFailures", pattern = "{($.eventName = \"ConsoleLogin\") && ($.responseElements.ConsoleLogin = \"Failure\")}" }, ConsoleSignInWithoutMFA = { metric = "ConsoleSignInWithoutMFA", pattern = "{($.eventName = \"ConsoleLogin\") && ($.responseElements.ConsoleLogin = \"Success\") && ($.requestParameters.mfaAuthenticated = \"false\")}" }, IAMPolicyChanges = { metric = "IAMPolicyChanges", pattern = "{($.eventName = \"CreatePolicy\") ¦¦ ($.eventName = \"DeletePolicy\") ¦¦ ($.eventName = \"PutPolicy\") ¦¦ ($.eventName = \"AttachRolePolicy\") ¦¦ ($.eventName = \"DetachRolePolicy\") ¦¦ ($.eventName = \"AttachUserPolicy\") ¦¦ ($.eventName = \"DetachUserPolicy\")}" }, NACLChanges = { metric = "NACLChanges", pattern = "{($.eventName = \"CreateNetworkAcl\") ¦¦ ($.eventName = \"DeleteNetworkAcl\") ¦¦ ($.eventName = \"CreateNetworkAclEntry\") ¦¦ ($.eventName = \"DeleteNetworkAclEntry\") ¦¦ ($.eventName = \"ReplaceNetworkAclEntry\") ¦¦ ($.eventName = \"ModifyNetworkAcl\")}" }, NetworkGatewayChanges = { metric = "NetworkGatewayChanges", pattern = "{($.eventName = \"CreateVpnGateway\") ¦¦ ($.eventName = \"DeleteVpnGateway\") ¦¦ ($.eventName = \"AttachVpnGateway\") ¦¦ ($.eventName = \"DetachVpnGateway\") ¦¦ ($.eventName = \"ModifyVpnGateway\") ¦¦ ($.eventName = \"CreateTransitGateway\") ¦¦ ($.eventName = \"DeleteTransitGateway\") ¦¦ ($.eventName = \"ModifyTransitGateway\") ¦¦ ($.eventName = \"CreateTransitGatewayAttachment\") ¦¦ ($.eventName = \"DeleteTransitGatewayAttachment\") ¦¦ ($.eventName = \"ModifyTransitGatewayVpcAttachment\")}" }, RootAccountUsage = { metric = "RootAccountUsage", pattern = "{($.userIdentity.type = \"Root\")}" }, RouteTableChanges = { metric = "RouteTableChanges", pattern = "{($.eventName = \"CreateRouteTable\") ¦¦ ($.eventName = \"DeleteRouteTable\") ¦¦ ($.eventName = \"CreateRoute\") ¦¦ ($.eventName = \"DeleteRoute\") ¦¦ ($.eventName = \"AssociateRouteTable\") ¦¦ ($.eventName = \"DisassociateRouteTable\") ¦¦ ($.eventName = \"ReplaceRouteTableAssociation\")}" }, S3BucketPolicyChanges = { metric = "S3BucketPolicyChanges", pattern = "{($.eventName = \"PutBucketPolicy\") ¦¦ ($.eventName = \"DeleteBucketPolicy\")}" }, UnauthorizedAPICalls = { metric = "UnauthorizedAPICalls", pattern = "{($.errorCode = \"AccessDenied\") ¦¦ ($.errorCode = \"UnauthorizedOperation\")}" }, VPCChanges = { metric = "VPCChanges", pattern = "{($.eventName = \"CreateVpc\") ¦¦ ($.eventName = \"DeleteVpc\") ¦¦ ($.eventName = \"ModifyVpcAttribute\") ¦¦ ($.eventName = \"CreateSubnet\") ¦¦ ($.eventName = \"DeleteSubnet\") ¦¦ ($.eventName = \"ModifySubnetAttribute\") ¦¦ ($.eventName = \"AssociateRouteTable\") ¦¦ ($.eventName = \"DisassociateRouteTable\") ¦¦ ($.eventName = \"CreateInternetGateway\") ¦¦ ($.eventName = \"DeleteInternetGateway\") ¦¦ ($.eventName = \"AttachInternetGateway\") ¦¦ ($.eventName = \"DetachInternetGateway\") ¦¦ ($.eventName = \"CreateNatGateway\") ¦¦ ($.eventName = \"DeleteNatGateway\")}" }{noformat} |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43895d15 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ir97: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [41 empty] | 1786761 | AM20-182 | Push to FlySAA backend Alarm related code to the bitbucket in dev and preprod environment | Done | 2025-10-03 10:48
AM20-921 | Restrict Admin access to VOIS team by creating dedicated IAM role | Done | 4 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Medium | 1736354 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 17:12 | 2026-01-13 17:47 |  |  |  | 0 | As Product Owner, I want to restrict VOIS team to have Admin role so that all of them cannot be superseded rights and bring more control on AWS management Acceptance criteria: * IAM role to be created for everyone except Sankalp and Aravind from AWS perspective * IAM role for network creation to be created and role assign to Satya * IAM role for rest of team members is of developer |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6edd432e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0c5zn: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 06:20 | [13 empty] | 06/Aug/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have shared the Excel with the user list to team, upon there confirmation ill start creating custom policy with user groups. | 08/Aug/25 8:14 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;¦UserID¦IAM user¦UserGroup¦IAM Role¦ ¦raja0001¦Aravind¦VOIS_Admin¦No changes, use existing roles itself¦ ¦rais0003¦Sankalp¦VOIS_Admin¦No changes, use existing roles itself¦ ¦SatyasairamV¦SatyaSairam¦VOIS_Admin¦No changes, use existing roles itself¦ ¦godir001¦Ravinder¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦kiraj001¦Jitender¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Sanjot¦Sanjot¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦nikas001¦Sumit¦VOIS_Admin¦No changes, use existing roles itself¦ ¦FaisalSayed¦Faizal¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SanketKale¦Sanket¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦pathp002¦Pankaj¦VOIS_DBAdmin_Usergroup¦AWS_VOIS_DBAdmin_Role¦ ¦onkar¦Onkar¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦DikshaK¦Diksha¦VOIS_InfraAdmin_Usergroup¦AWS_VOIS_InfraAdmin_Role¦ ¦SatyabrataS¦SatyaBrata¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Shreyash¦Shreyash¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ ¦Harsh¦Harsh¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Yashwant¦Yashwant¦Reader Access¦AWS_VOIS_Reader_Role¦ ¦Utkarsh¦Utkarsh¦VOIS_DevOpsAdmin_Usergroup¦AWS_VOIS_DevOpsAdmin_Role¦ Â Â Access to User group given as below, ¦VOIS_InfraAdmin_Usergroup¦VOIS_DevOpsAdmin_Usergroup¦VOIS_DBAdmin_Usergroup¦ ¦VPC FullAccess¦CodeBuild FullAccess¦RDS Full Access¦ ¦EC2 FullAccess¦CodePipeline FullAccess¦DMS Full Access¦ ¦S3 FullAccess¦EKS FullAccess¦IAM Full Access¦ ¦CloudWatch FullAccess¦EC2 except delete¦CloudTrail except delete¦ ¦RDS FullAccess¦S3 FullAccess¦KMS except delete¦ ¦IAM FullAccess¦CloudWatch except delete¦CloudWatch except delete¦ ¦CloudTrailFullAccess¦RDS except delete¦Read only¦ ¦MacieFullAccess¦IAM FullAccess¦ ¦ ¦GuardDutyFullAccess¦System managerFullAccess¦ ¦ ¦SecurityHubFullAccess¦LambdaFullAccess¦ ¦ ¦System managerFullAccess¦Event bridgeFullAccess¦ ¦ ¦LambdaFullAccess¦CloudTrail except delete¦ ¦ ¦KMSFullAccess¦Read only¦ ¦ ¦ACMFullAccess¦Secrets managerFullAccess¦ ¦ ¦Aws ConfigFullAccess¦SNSFullAccess¦ ¦ ¦Event bridgeFullAccess¦SESFullAccess¦ ¦ ¦InspectorFullAccess¦ECR FullAccess¦ ¦ ¦SupportFullAccess¦KMS except delete¦ ¦ ¦SNSFullAccess¦Â ¦ ¦ ¦SESFullAccess¦ ¦ ¦ ¦ReadOnly¦ ¦ ¦ ¦Secrets managerFullAccess¦ ¦ ¦ ¦ECRFullAccess¦ ¦ ¦ Â Users have access to the below AWS accounts, Â ¦AWS Account¦Account Name¦ ¦300204747992¦Audit¦ ¦730335236533¦Security¦ ¦080284287007¦LogArchive¦ ¦339712943527¦Network¦ ¦864899875361¦SharedServices¦ ¦585768167545¦SharedVpcDev¦ ¦253490777663¦SharedVpcPreprod¦ ¦820242899278¦SharedVpcProd¦ ¦746669190453¦Backend dev¦ ¦216989128782¦Backend Preprod¦ ¦396608788916¦Backend Prod¦ ¦209479274829¦Tm1¦ ¦345594574792¦AirNAVx¦ ¦536697265099¦NexioAV¦ | 11/Aug/25 4:28 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-11 04:28
AM20-922 | Cabin Crew App discovery | Done | 6 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1823348 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 15:13 | 2026-01-12 17:36 |  | 2025-11-14 11:10 |  | 0 | As Product and Application Architect I would like to analyse the Cabin crew application so that I can suggest the best possible way to modernize and migrate to AWS. Acceptance Criteria: * Application Overview and business context is captured ( Business criticality, use case, compliance and security needs, Pain point) * Current Architecture assessment ( Front end stack, Backend, integration, dabtabase, storage and compute requirements and assess modernize angles * Security and Governance - IAM and RBAC model, secret and configuration storage, certificate management, logging and audit requirements * Performance and Capacity utilization - CPU, memory and disk usage, scalability needs, Latency and throughput requirements are gathered * Dependency and integration landscape captured * Cost and Licensing requirements clarified (current cost of application, licenses etc.) * Modernization readiness documented * Modernization strategy proposed successfully * Operational readiness documented |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:19 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | [5 empty] | 86400 | 64800 | 21600 | 0.25 | 86400 | 64800 | 21600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@36e1c984 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ljtn: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 12:35 | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 2:35 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Cabin Crew is still under discussion and more clarity is expected by Dec-25(Project in pipeline) | 14/Nov/25 8:18 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;We have gathered all the information we could but since SAA is still working to understand business scope, we will close this story with current progress and have separate assessment story in future once we have complete information. | 14/Nov/25 11:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-14 11:10
AM20-923 | Trellix integration with AirnavX | Done | 1 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 16:53 | 2026-01-10 17:07 |  | 2025-11-12 08:22 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan AirNavX workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in AirNavX server * Trellix is able to access AirnavX account successfully and perform scanning |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 05/Nov/25 3:41 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;RE_ Trellix scanning status for New AWS AirNavV servers.msg;https://vodacom.atlassian.net/rest/api/3/attachment/content/1178115 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f4c84b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 18 | [95 empty] | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [65 empty] | YES | YES | 2025-09-08 07:56 | 3_*:*_2_*:*_1482176011_*¦*_10041_*:*_1_*:*_2325586469_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1657138717 | [12 empty] | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 30/Sep/25 7:40 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working with Sinjun for trellix installation on these 2 servers. | 06/Oct/25 8:39 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Working with Sinjun for Trellix installation, hence will be spilled over | 09/Oct/25 4:29 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to Sinjun Albert is going to install Trellix and he will confirm once integration done. | 17/Oct/25 11:17 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over reason - Blocked due to ongoing app installation issues, currently worked upon by app owner; post which this story will be progressed in subsequent sprint | 05/Nov/25 3:41 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Trellix software installed on New AWS AirNavX servers. All AirNavX servers able to discover from Trellix admin server and same has been confirmed by Sinjun. Attaching reference for support. [^RE_ Trellix scanning status for New AWS AirNavV servers.msg] | 12/Nov/25 8:22 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | Done | 2025-11-12 08:22
AM20-924 | MQ Modernization POC ¦¦ Parser testing based on sample pegasys parser | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832848 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 20:00 | 2026-01-28 23:19 | 2025-11-28 11:15 | 2025-11-28 12:00 |  | 0 | As DevOps Engineer, I need to test few existing MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | ;19/Nov/25 8:35 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;28/Nov/25 11:43 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;10800 | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6bedb0f1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo0r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:26 | 3_*:*_1_*:*_876093459_*¦*_10041_*:*_1_*:*_581918527_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:26 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;CPP to Java: Parser to be re-written with line to line conversion to retain logic. | 20/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Java Parser Covering Following High-level Algorithm- # Input * Receive a raw text message body (rawMessage) from AmazonMQ PEGASYS.OUT.UAT. # Pre-check * If rawMessage is null or empty â†’ return ParseResult with error = true (this is defensive; in normal operation this should not happen). # stripId() â€“ remove ID block if present 3.1. Let msg = rawMessage. 3.2. If msg contains "\nM42": * Call stripId(msg): * Find index of " /ID ". * From there, find "ACARS\r\n". * Return: msg_before_ID + msg_from_ACARS_onwards. 3.3. Else: keep msg unchanged. . # Construct buff and newbuff 4.1. buff = msg (the stripped or original message). 4.2. Append control chars: * CR = 13, NL = 10, ETX = 3. * newbuff = buff + CR + NL + ETX. # Split into lines & find .JNB 5.1. Split newbuff by '\n' into lines[]. 5.2. Search for first line where lines[i].startsWith(".JNB"). 5.3. If found, set counter = i + 1 (line after .JNB). 5.4. If not found or counter >= lines.length: * Default: create OutboundMessage(qMng, newbuff) â†’ MNG only. * Return this as ParseResult with error = false. # Extract relevant lines safely * line0 = lines[counter] (or "" if out of range). * line1 = lines[counter + 1] * line2 = lines[counter + 2] * line3 = lines[counter + 3] Using helpers: * safeLine(lines, index) â€“ returns "" if index out of range. # Extract tokens (T1, T2, etc.) safely Using safeSub(s, begin, endExclusive) to avoid index errors. 7.1. T1 = line0[0..3) â†’ message type (MVT, DIV, ASM, SSM, CGO, etc.). 7.2. T2 = line1[1..5) â†’ secondary code (CIRQ, CICX, etc.). 7.3. line1_0_2 = line1[0..2) â†’ used to check "SA". 7.4. line2_0_2 = line2[0..2) â†’ used to check "ED". 7.5. line3_0_3 = line3[0..3) â†’ used to check "TIM". # Prepare result container * outputs = new ArrayList<OutboundMessage>(); # Rule 1 (SSM/CGO â†’ ICARGO) * If T1 is "SSM" or "CGO": * outputs.add(new OutboundMessage(qIcargo, buff)); 10. Rule 2 (CIRQ/CICX â†’ SIP) * If T2 is "CIRQ" or "CICX": * Add OutboundMessage(qSip, buff) to outputs. * Return ParseResult(outputs, false, null) immediately 11. Rule 3 (MVT / DIV / ASM) 11.1. If T1 in { "MVT", "DIV", "ASM" }: 11.1.1 ASM + TIM * If T1 == "ASM" and line3_0_3 == "TIM": * Add OutboundMessage(qCimp, buff) (CIMP). * Add OutboundMessage(qIcargo, buff) (ICARGO). * Then continue. 11.1.2 MVT-specific * If T1 == "MVT": * If line1_0_2 == "SA" (SA flight): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG with CR/LF/ETX). * Add OutboundMessage(qIcargo, buff) (ICARGO). * If line2_0_2 == "ED": * Add OutboundMessage(qCimp, buff) (CIMP). * Add another OutboundMessage(qIcargo, buff) (ICARGO again â€“ same as C++ double-write). * Else (non-SA): * Add OutboundMessage(qMng, newbuff) (MNG only). 11.1.3 DIV/ASM (fallback) * Else (T1 is DIV or ASM without TIM rule): * Add OutboundMessage(qStar, buff) (STAR). * Add OutboundMessage(qMng, newbuff) (MNG). 12. Rule 4 (other message types) * Else (T1 is not MVT, DIV, ASM, and not CIRQ/CICX): * Add OutboundMessage(qMng, newbuff) (MNG only). 13. Return final result * return new ParseResult(outputs, false, null); | 24/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Additional parser related to Pegasys called SbrSplit has been shared by Sampi. Analysis has been started for the same. | 28/Nov/25 11:46 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SbrSplit parser - CPP has been converted into java based code. Repo structure has also been transformed to adopt microservice alike design. [https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git¦https://sumit.mangaldasnikam@bitbucket.org/flysaa/mqpoc.git] Parser to be tested in next sprint. | 28/Nov/25 12:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [25 empty] | Done | 2025-11-28 12:00
AM20-925 | Centralized Cluster Creation Strategy | In Progress | 8 | Sprint 22 | 2026-01-05 | 2026-01-16 | Sanjot Fotedar | Medium | 1885775 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 19:06 | 2026-01-18 21:08 | 2026-01-08 08:38 |  |  | 0 | As A platform Owner I want to create a detailed design document for centralized management of EKS cluster across multiple AWS child accounts from a central account so that the solution is secure, scalable, compliant and operationally ready before implementation Acceptance Criteria: *Architecture and Account structure* - * Parent, central management and child application accounts * hub and spoke model connectivity model * shared vs isolation responsibilities *EKS management Strategy* - * Centralized model * Namespace isolation strategy * Cluster ownership and lifecycle boundaries *IAM and Security design* - * Cross account IAM roles and trust relationship * K8s RBAC mapping * Least privileges access model * SCP usage and guardrails *Network and Connectivity design* - * VPC architecture per account * Connectivity via TGW /VPC peering * Control plane and data plane traffic flow * DNS resolution strategy *Governance and Policy Enforcement* - * Kubernetes admission controls (Kyverno) * naming, tagging and quota standards * Policy exception handling process *Observability and Logging* - * Centralized logging and metrics flow * Alerting and escalation paths *Security and Compliance* - * EKS security monitoring * Image scanning approach * Compliance reporting and audit readiness *Operation model* - * RACI matrix (L1/L2/L3) * Incident and change management process * upgrade and patching strategy * Backup and DR approach |  | Sanjot Fotedar | [5 empty] | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | [5 empty] | ;07/Jan/26 7:23 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;7200 | [5 empty] | 115200 | 108000 | 7200 | 0.06 | 115200 | 108000 | 7200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@43715548 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptve: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-07 17:24 | [13 empty] | 07/Jan/26 7:23 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Started work on this. Currently evaluating the framework for assessing multi-tenancy readiness of existing eks cluster. Identifying key focus areas for hardening -Â namespace isolation, RBAC scope, network segmentation, resource governance, policy enforcement. | [29 empty] | In Progress | 2026-01-07 19:21
AM20-926 | Informatica ¦¦ Alerting and Monitoring Solution | Done | 4 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1800159 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-03 20:21 | 2026-02-03 20:39 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment. Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O. * Dashboards are created to monitor key services. * SNS Alert should be generated if Informatica server is stopped. |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 09/Oct/25 9:21 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251009-071913.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1165179 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3ac6b815 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ivor: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-06 09:08 | [13 empty] | 06/Oct/25 11:07 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start creating the dashboard and alerting for Informatica Dev and Prod environment. | 06/Oct/25 12:13 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I enabled the CloudWatch metrics for Informatica Dev and Prod for CPU, memory, disc, network I/O. Dashboards are also created to monitor key services. --- *DONE.* Now Alerting and monitoring needs to be created with proper naming and threshold values â€“ *PENDING*. | 07/Oct/25 12:19 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Created alarms and monitoring for informatica prod and dev for CPU and Status Check failed â€“ *DONE.* | 08/Oct/25 12:38 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;All alerts including the Disk and memory utilization for Informatica Prod and Dev has been created with proper naming and threshold value. --- *DONE.* | 09/Oct/25 9:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251009-071913.png¦width=1575,height=673,alt="image-20251009-071913.png"! Have created the Informatica prod and dev alerting rules setup the threshold value for them. | 09/Oct/25 10:46 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Moving this US to in review to Aravind. If require any modification. | 13/Oct/25 6:34 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have reviewed has some query will discuss with diksha and close. | 15/Oct/25 11:58 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Aravind reviewed the changes and gave his approval now we can move it to PO approval. | 17/Oct/25 7:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | Done | 2025-10-17 07:17
AM20-927 | POC - Create Sustainability dashboards | To Do | 8 | Sprint 10 | 2025-07-21 | 2025-08-01 | Sankalp Rai | High | 1720042 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 21:43 | 2026-01-27 23:07 |  |  |  | 0 | As AWS Expert, I would create sustainability dashboard to access the power consumption, utilization and energy efficiency in alignment with well-architecture Acceptance Criteria * Enable AWS Sustainability Pillar in Well-Architected Reviews, optimize workloads for energy efficiency â€” right-sizing, minimizing network transfer, cold storage, etc. * Leverage S3 Lifecycle Policies & Intelligent Tiering |  | Harsh Chandra | Sankalp Rai |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63121580 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v09 | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 11 | Sprint 12 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-11 08:13 | [13 empty] | 11/Aug/25 10:12 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Start Date: 12th August End Date: 21st August | 10/Sep/25 1:15 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Moving this to Backlog from Sprint 13 as suggested by Deepak Sharma, to currently focus on critical migration activities. This will be picked up in later sprints. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | To Do | 2025-10-13 09:27
AM20-928 | Handover of Patching solution | Done | 4 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1866136 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 22:01 | 2026-02-04 01:27 | 2025-12-14 17:52 | 2025-12-12 11:19 |  | 0 | As product owner I want Diksha to take handover along with Satya from Faisal so that she can support customer |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [5 empty] | ;09/Dec/25 12:43 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | ;10/Dec/25 3:38 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 09/Dec/25 12:55 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251209-105350.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1193694 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@58f0f8fd | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7xd: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-09 10:45 | 3_*:*_1_*:*_96936957_*¦*_10041_*:*_1_*:*_1043660087_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 09/Dec/25 12:45 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started the Hands on for patching first worked on pre-requisites and AWS cli and cloud watch agent installation on the Sandbox EC2 instance. The Session has been recorded as well. | 09/Dec/25 12:55 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251209-105350.png¦width=641,alt="image-20251209-105350.png"! This server is created as a Test Patching server for the Windows patching activity. As of now this has been kept in stopped state later after the patching will get done we will delete the server moving further. The below pointers has been completed. * *Provisioned Test Environment* ** Deployed a test EC2 instance in the designated sandbox environment. * *Network Configuration* ** Configured VPC endpoints to enable *private connectivity for AWS Systems Manager (SSM)*, ensuring secure management without requiring a public IP. * *Identity and Access Management (IAM)* ** Created IAM roles, policies, and instance profiles for EC2 to support required permissions. ** Implemented a *cross-account IAM role* for Lambda in the security account, enabling patching operations in the sandbox environment. ** Updated trust relationships to align with cross-account access requirements. * *Instance Setup and Agent Installation* ** Downloaded and installed *AWS CLI*, *CloudWatch Agent*, and *SSM Agent* on the EC2 instance. ** Deployed a custom compliance reporting script within the instance. * *Automation and Management* ** Authored and deployed a *custom SSM document* to support patching and compliance workflows. | 10/Dec/25 3:37 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Below pending points are also covered today and the handover of the patching is completed. * *S3 Bucket Configuration* ** Set up an Amazon S3 bucket with the required folder structure. ** Apply appropriate *IAM permissions* and *bucket policies* to ensure secure access. ** Configure *S3 event notifications* to trigger downstream processes as needed. * *Lambda Automation for Patching* ** Develop and deploy a Lambda function to *automate patching activities* within the sandbox account. ** Ensure the Lambda function uses the *cross-account IAM role* created today, granting it the necessary permissions to execute patching tasks in the sandbox environment. ** Validate the Lambda execution policy and trust relationship for compliance and least-privilege access. | 10/Dec/25 3:38 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[Recap: Patch Implementation - Internal Tuesday, December 9 ¦ Meeting ¦ Microsoft Teams¦https://teams.microsoft.com/l/meetingrecap?driveId=b%21d5bfbASx8UyuyN5zJPY_C1jj3vg4dqxGo4vsecE4YZu3kE97HxTiSrSKd-pI-KUx&driveItemId=016NKAQFNQOEZURWCDERFYBPVICI6NDJX2&sitePath=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQCwcTNI2EMkS4C-qBI80ab6Af6L1MuuoLAsP4web0CEjFk&fileUrl=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQCwcTNI2EMkS4C-qBI80ab6Af6L1MuuoLAsP4web0CEjFk&iCalUid=040000008200E00074C5B7101A82E00800000000A47F206EE268DC01000000000000000010000000321233C36A404C46934C1B5B72B7F07A&threadId=19%3Ameeting_ZjBlZDVhMjMtNDI4ZC00NjQ5LThiMzgtM2FiMDhhNTIyZDg2%40thread.v2&organizerId=8f4c76ce-ca6e-44bd-bbde-0eb6186f9df7&tenantId=68283f3b-8487-4c86-adb3-a5228f18b893&callId=76b0f585-b89d-412b-b23f-2527a464dab5&threadType=Meeting&meetingType=Scheduled&subType=RecapSharingLink_RecapChiclet] [Recap: Patch Implementation - Internal Wednesday, December 10 ¦ Meeting ¦ Microsoft Teams¦https://teams.microsoft.com/l/meetingrecap?driveId=b%21d5bfbASx8UyuyN5zJPY_C1jj3vg4dqxGo4vsecE4YZu3kE97HxTiSrSKd-pI-KUx&driveItemId=016NKAQFKGUFQPO2BR7VC3OZIJ4T4BALUJ&sitePath=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQBGoWD3aDH9RbdlCeT4EC6JAf1ANE41qecWYg-ZpI8nWPs&fileUrl=https%3A%2F%2Fvodafone-my.sharepoint.com%2F%3Av%3A%2Fp%2Ffaisal_sayed%2FIQBGoWD3aDH9RbdlCeT4EC6JAf1ANE41qecWYg-ZpI8nWPs&iCalUid=040000008200E00074C5B7101A82E00800000000F3F48BFDF868DC01000000000000000010000000D320B3E36531F44C8156C61B7DCD0871&threadId=19%3Ameeting_YTQ3OGI1ODMtM2JjMy00YTkzLTlhNjQtYWUwMGY4OTFlZDAz%40thread.v2&organizerId=8f4c76ce-ca6e-44bd-bbde-0eb6186f9df7&tenantId=68283f3b-8487-4c86-adb3-a5228f18b893&callId=3fb32e76-7aa1-40f8-a245-6ac6fdac8f6c&threadType=Meeting&meetingType=Scheduled&subType=RecapSharingLink_RecapChiclet] Both recording links has been attached above. | [26 empty] | Done | 2025-12-12 11:19
AM20-929 | Cynet ¦¦ Server Installation | To Do |  | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1887432 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 14:35 | 2026-01-09 16:12 | 2026-01-07 08:19 |  |  | 0 | As Product owner I want to install Cynet agent on Linux/Windows EC2 instance so that threat detechtion and response coverage is enabled Acceptance Criteria. *Linux*: * Installation package hosted/accessible securely (S3 with KMS, repo, or Cynet direct download). * SSM document / automation executes successfully on a pilot group and then on all in-scope instances. * Agent registers to correct Cynet tenant and shows â€œonline/healthyâ€ in console within defined SLA (e.g., 15 minutes). * Installation is idempotent (re-run does not break existing installation). * Logging captured: instance ID, hostname, timestamp, status, version, and failure reason if any. *Windows*: * Silent install works (msi/exe unattended flags), including token/tenant configuration. * Service is running after installation and agent appears healthy in console. * Windows Event Logs / install logs are retained for troubleshooting. * | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@19d1d99d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0q0i3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2026-01-06 13:12
AM20-930 | Informatica ¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1755978 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 18:28 | 2026-02-01 18:42 |  |  |  | 0 |  |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3237a818 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0e0or: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-26 11:39 | [13 empty] | 26/Aug/25 1:39 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Firewall rules implemented. Identified as connectivity not working. Initiated network troubleshooting call towards fixing. Identified as routing not configured. Requested LIFT for approval LIFT approval took 3days Monday CSOC request raised and routing has ben implemented. Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 28/Aug/25 8:18 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested connectivity from informatica Prod/Dev env. Initially Network team not configured Routing after new Lift and CSOC request issue got resolved. Reference Lift & CSOC details: Routing: # CSOC:CHR0026807 # LIFT:CHG0067489 App comms: # LiFT = CHG0067488 # CSOC = CHR0026691 AWS agent Comms: CSOC logged CHR0023951 LiFT logged CHG0066992 (RITM0051174) | 01/Sep/25 8:03 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested. Based on comms we have successfully completed agent installation for prod/Dev and setup test instance for the same. Hence sending request for closer. | 03/Sep/25 8:55 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-931 | TM1 ¦¦ Integration of AWS IAM roles with TM1 AWS Account Instance using JSON | Done | 10 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642068 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 17:17 | 2026-01-13 18:37 |  |  |  | 0 | As AWS expert, I would be integrating AWS IAM roles with TM1 Instance Acceptance criteria: * IAM roles are created successfully * Integration of defined IAM roles with TM1 instance so that user is able to access the TM1 instance. |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5190a6ea | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-09 07:30 | [13 empty] | 09/Jul/25 9:29 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Following are the details of the role created: role_arn = "arn:aws:iam::209479274829:role/TM1-IAMRole-EC2InstanceProfile" role_name = "TM1-IAMRole-EC2InstanceProfile" Account details: 209479274829 (SAA-TM1) Custom Role Details: The role covers the equivalent of â€œAmazonSSMManagedInstanceCoreâ€, basic CloudWatch Agent permissions, and general S3 access. _*NOTE*: THE FOLLOWING HAS BEEN ACHIEVED USING TERRAFORM._ | 09/Jul/25 9:30 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;.json file of the custom role is as follows: { Â "Version": "2012-10-17", Â "Statement": [ Â Â { Â Â Â "Sid": "SSMManagedInstanceCorePermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssm:DescribeAssociation", Â Â Â Â "ssm:GetDeployablePatchSnapshotForInstance", Â Â Â Â "ssm:GetDocument", Â Â Â Â "ssm:DescribeDocument", Â Â Â Â "ssm:GetManifest", Â Â Â Â "ssm:GetParameter", Â Â Â Â "ssm:GetParameters", Â Â Â Â "ssm:ListAssociations", Â Â Â Â "ssm:ListInstanceAssociations", Â Â Â Â "ssm:PutInventory", Â Â Â Â "ssm:PutComplianceItems", Â Â Â Â "ssm:PutConfigurePackageResult", Â Â Â Â "ssm:UpdateAssociationStatus", Â Â Â Â "ssm:UpdateInstanceAssociationStatus", Â Â Â Â "ssm:UpdateInstanceInformation" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "SSMMessageGatewayPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssmmessages:CreateControlChannel", Â Â Â Â "ssmmessages:CreateDataChannel", Â Â Â Â "ssmmessages:OpenControlChannel", Â Â Â Â "ssmmessages:OpenDataChannel" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "EC2MessagesPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ec2messages:AcknowledgeMessage", Â Â Â Â "ec2messages:DeleteMessage", Â Â Â Â "ec2messages:FailMessage", Â Â Â Â "ec2messages:GetEndpoint", Â Â Â Â "ec2messages:GetMessages", Â Â Â Â "ec2messages:SendReply" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "CloudWatchAgentPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "logs:CreateLogGroup", Â Â Â Â "logs:CreateLogStream", Â Â Â Â "logs:PutLogEvents", Â Â Â Â "logs:DescribeLogGroups", Â Â Â Â "logs:DescribeLogStreams", Â Â Â Â "cloudwatch:PutMetricData" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "S3AccessPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "s3:GetObject", Â Â Â Â "s3:PutObject", Â Â Â Â "s3:ListBucket" Â Â Â ], Â Â Â "Resource": "*" Â Â } Â ] } | 11/Jul/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed IAM roles is having required permissions | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-932 | Voager connectivity | Done | 2 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1872880 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 18:36 | 2026-01-21 20:14 | 2025-12-14 19:04 | 2025-12-12 11:20 |  | 0 | Static Routes need to be setup. Advertise Subnets DX. Establish Routing |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;04/Dec/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [12 empty] | 02/Dec/25 5:02 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251202-150140.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1191675 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a461fc5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0oflf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-02 15:02 | 3_*:*_1_*:*_141577985_*¦*_10041_*:*_1_*:*_104152046_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Dec/25 5:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Static routes has been implemented. Notified customer to submit CSOC for routing implementation.(CHR0031699) !image-20251202-150140.png¦width=612,alt="image-20251202-150140.png"! | 02/Dec/25 5:10 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Routing has been implemented and connectivity has been implemented. | 04/Dec/25 8:19 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Customer validated connectivity and working fine, hence resolving this story. | 12/Dec/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-12-12 11:20
AM20-933 | AMOS Follow-up Assessment | Blocked | 4 | None( Backlog) |  |  | Sumit Nikam | Medium | 1833693 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 12:54 | 2026-01-12 14:43 | 2025-11-28 11:14 |  |  | 0 | As Product owner I would like to reinitiate assessment for AMOS application so that we can finalize approach to modernize it |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7ed8f0ed | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0009 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-24 06:09 | [13 empty] | 24/Nov/25 8:09 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Still awaiting approval from SAA\Tumelo for migration to AWS. Moving this to blocked state since the assessment canâ€™t be resumed until then. | [29 empty] | To Do | 2025-11-12 10:56
AM20-934 | Add-On ¦¦ WAF Rule creation for Voyager | To Do | 4 | None( Backlog) |  |  | Aravind Raj | Medium | 1842274 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 14:54 | 2026-01-24 14:59 |  |  |  | 0 | [20 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@37603ed1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5m3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-17 08:33
AM20-935 | Resources cleanup - Aws accounts | Done | 6 | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1817985 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-01 17:21 | 2026-02-01 19:38 |  | 2025-11-14 20:28 |  | 0 | As part of cost optimization we have planned to take a inventory of AWS resources deployed already. Further to cleanup unwanted and unutilized resources. |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 86400 | 86400 |  | 0 | 172800 | 172800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@47ec6456 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kwlv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 18 | [97 empty] | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [65 empty] | YES | YES |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [42 empty] | Done | 2025-11-14 20:28
AM20-936 | ServiceNow ¦¦ Lamda function as SNS Subscriber | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651014 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 12:36 | 2026-01-24 13:00 |  |  |  | 0 | As a Cloud engineer, I want a Lamda function subscribed to the SNS topic so that it can process alerts and forward them to ServiceNow Acceptance Criteria: * The Lamda function is triggered on new SNS messages * It parses event data and sends an HTTP POST request to ServiceNow |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 | ;25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@353710af | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0284j: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 03:49 | [13 empty] | 24/Apr/25 5:49 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Working with the lambda function python script, since the function needs to works with cross account for getting the tags. initially the lambda function developed to get the tags from the same account, whereas here the requirement is to get the tag to Audit account to trigger a SNS. | 25/Apr/25 6:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Lambda function is created in Audit account -300204747992, and its working fine as expected. | 02/May/25 4:57 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-25 06:34
AM20-937 | Resources inventory | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Diksha Koul | Medium | 1818700 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-31 20:57 | 2026-01-31 21:09 |  |  |  | 0 | Get the resource inventory for the below accounts: * 746669190453Â FlySAA_CMS_Backend_DevQA * 216989128782 FlySAA_CMS_Backend_PreProd * 396608788916Â FlySAA_CMS_Backend_Prod * 209479274829Â SAA TM1 * 345594574792Â SAA Airnavx * 536697265099Â SAA_NEXIOAV_PROD * 307946680641Â SAA_Informatica_DEV * 536697248966Â SAA_Informatica_PROD * 650251698621Â SAA_PROS_PROD |  | Aravind Raj | Diksha Koul |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 02/Nov/25 7:48 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;Resource Inventory.xlsx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1176266 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@39f20e89 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzwb: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-28 06:38 | [13 empty] | 28/Oct/25 8:37 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start collecting all data for the given accounts as per the acceptance criteria. And will attach that here for the review. | 29/Oct/25 10:01 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;For Airnavx , informatica dev & prod and Tm1 resource details are fetched in excel sheet but for few resources i donâ€™t have permission to see the list or table. | 02/Nov/25 7:47 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The inventory sheet has been completed from my end also attached in the US. but the resources for which i donâ€™t have permission infront of them i have added no permission comment. | 02/Nov/25 7:48 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[^Resource Inventory.xlsx] | [23 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-11-02 19:49
AM20-938 | TM1 ¦¦ establish internet connectivity via TGW | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Yashwant Thakur | High | 1620885 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 14:18 | 2026-01-10 17:13 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [26 empty] | AM20-15 | [20 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@232fa3c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxslz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-01 17:41 | [13 empty] | 01/Apr/25 7:40 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Internet connectivity has-been established and tested. | 04/Apr/25 10:50 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Internet setup has been completed and tested working fine. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-14 09:39
AM20-939 | CMS Backend RDS instance (Pre-prod/Prod) analysis | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1833687 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 15:32 | 2026-01-25 19:00 |  | 2025-11-27 09:21 |  | 0 | As Product owner I like to analyse RDS for rightsizing based on utlization to reduce cost |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Nov/25 5:10 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;21600 | ;25/Nov/25 4:08 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;64800 |  |  |  |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 18/Nov/25 5:09 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251118-150648.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1185982 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6460780 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo2n: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 15:10 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 5:09 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;RDS cost analysis is started. Today, we have reduced backup retention period of preprod rds to 7 days from 35 days. Also, storage limit threshold for dev rds is updated to 200 GiB from 110GiB because it was generating alerts â€œ*_Storage size 100 GiB is approaching the maximum storage threshold 110 GiB. Increase the maximum storage threshold_*â€ !image-20251118-150648.png¦width=459,alt="image-20251118-150648.png"! Next we will monitor cpu, memory consumption across three environments | 25/Nov/25 4:15 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;h3. Next Steps for CMS Backend RDS Cost Optimization With discussion with Pankaj, we have identified the following points as next steps for CMS Backend RDS cost optimization: * Turn off non-prod RDS instances when not in use or during off-business hours and turn them back on when required. * Further reduce backup retention period for non-prod RDS instances (currently 7 days) to explore additional cost savings. These actions will be implemented post confirmation from FlySAA team. | 27/Nov/25 9:21 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:21
AM20-940 | AirNavX ¦¦ DR Setup and Backup | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772205 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 16:12 | 2026-02-05 16:17 |  | 2025-11-15 14:39 |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Informatica-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;14/Nov/25 8:19 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;230400 | ;14/Nov/25 8:20 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;28800 | ;14/Nov/25 3:37 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;57600 |  |  |  | 57600 | 0 | 316800 | 5.5 | 57600 | 0 | 316800 | [12 empty] | 14/Nov/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251114-061617.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1183951 | 14/Nov/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251114-061715.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1183950 | 14/Nov/25 8:18 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251114-061854.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1183952 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3d404a54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lnxr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | Sprint 16 | Sprint 18 | [95 empty] | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 |  | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | [65 empty] | YES | YES | 2025-09-08 07:57 | 3_*:*_1_*:*_26377373_*¦*_10041_*:*_1_*:*_2328420892_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3887316143 | [12 empty] | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 17/Oct/25 11:18 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over reason - Blocked due to ongoing app installation issues, currently worked upon by app owner; post which this story will be progressed in subsequent sprint | 14/Nov/25 8:18 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;AirNavX DR setup completed as well as daily weekly backup has been configured the same working fine. Backup relvent: !image-20251114-061617.png¦width=612,alt="image-20251114-061617.png"! !image-20251114-061715.png¦width=589,alt="image-20251114-061715.png"! DR: !image-20251114-061854.png¦width=597,alt="image-20251114-061854.png"! | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-15 14:39
AM20-941 | Adding windows server to the AWS managed AD | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651361 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 17:35 | 2026-02-04 18:36 |  |  |  | 0 | As AWS expert, I would be creating Powershell script for Windows server to integrate AWS-AD. Acceptance Criteria: * Powershall script is created successfully and should be able to integrate AWS-AD |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 57600 | 28800 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5e39db2e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02a6b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 06:19 | [13 empty] | 24/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 test instance is added to the AWS managed AD server using a manual approach itself. | 24/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;i documented the process we can use this for future reference. | 02/May/25 4:56 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Approved from Yashwant behalf due to his Jira login issue | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-24 08:20
AM20-942 | Informatica Server ¦¦ LLD preparation | Done | 6 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1610565 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 14:03 | 2026-01-28 15:11 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Sankalp Rai | Yashwant Thakur |  |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;24/Jun/25 1:32 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;11/Aug/25 10:10 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7d2f4e8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a2v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | [104 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-10 14:18 | [13 empty] | 10/Mar/25 4:18 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 10/Mar/25 4:24 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder >> Call to Scheduled on or before 12th* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 20/May/25 10:24 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;1st Draft Complete. Need to review internally revised Start Date: 19th May 2025 End date: 23rd May 2025 | 24/Jun/25 1:32 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Review with customer is completed Awaiting information requested from Application Owner | 11/Aug/25 5:04 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-10-13 09:23
AM20-943 | Create Hosted Zone via Terraform | Done | 8 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824841 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 13:20 | 2026-02-01 15:22 |  | 2025-11-15 14:39 |  | 0 | As a Cloud Platform Engineer I want a Terraform module that creates a Route 53 Hosted Zone (Public or Private) so that teams can provision DNS consistently across accounts and environments. *Scope* * Supports Public and Private hosted zones. * For Private zones: supports single and cross-account VPC associations. * Optional DNSSEC for Public zones (toggle). * Standardized tags, outputs, and README. *Acceptance Criteria (Functional)* # *Zone Type & Creation* Â Given zone_type âˆˆ {public, private} When I run terraform apply Then an AWS Route 53 hosted zone is created with the provided name ([Airchef.co.za¦https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2Fcorp.example.com%2F&data=05%7C02%7Cyashwant.thakur02%40vodafone.com%7Ce00faab9b43b48d8658008de187b13e5%7C68283f3b84874c86adb3a5228f18b893%7C0%7C0%7C638975114066746666%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=c7zVCLwqZ0TyO4ZgLXI7nmQwcYQASdX%2Bd%2BoDRecN0Gw%3D&reserved=0] and [flysaa.com¦http://flysaa.com] ) in the Network account/workspace. # *Public Hosted Zone Outputs* Â Given a Public zone When apply completes Then module outputs include: zone_id, zone_arn, name_servers (list), soa_record (string), and zone_name.Â # *Private Hosted Zone VPC Associations* (Same Account) Given zone_type = private and a list of VPC IDs in the same account When apply completes Then the zone is associated with all listed VPCs and associated_vpc_ids are output.Â # *Private Hosted Zone Cross-Account Associations* Given zone_type = private, a target zone account, and VPCs in other accounts When apply completes Then: VPC association authorization is created in the zoneâ€™s account. Zone associations are established from each workload account (using provider aliases). Associations are idempotent and re-applies do not error.Â # *DNSSEC (Optional, Public Only)* Â Given enable_dnssec = true and a valid KMS key alias/ARN When apply completes Then DNSSEC signing is enabled for the zone, and outputs include dnssec_status and ds_record (for registrar).Â # *Tagging Standard* Â Given tags map When resources are created Then all supported resources include tags: Environment, Owner, CostCenter, ManagedBy = terraform.Â # *Naming & Validation* Â Given invalid domain names (trailing dot, uppercase, spaces) When plan runs Then validation fails with a clear error message before creating resources. |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@c68852a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lps3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 19:11 | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 31/Oct/25 3:21 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Hi [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] , Please review this user story, I created this based on your LLD instruction. Please check if acceptance criteria needs alteration and make changes | 10/Nov/25 9:11 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and deployed on Sandbox environment | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-15 14:39
AM20-944 | MQ Migration - POC ¦¦ Sandbox environment | Done | 8 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1785826 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 19:11 | 2026-01-20 22:47 | 2025-11-21 13:35 | 2025-11-15 14:39 |  | 0 | Set up aÂ sandbox environmentÂ using AmazonMQ to test the proposed approach in collaboration with the Amadeus team. |  | Harsh Chandra | Sumit Nikam | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | Prepared rough arch design for PoC purpose based on available info.;14/Nov/25 8:20 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | Analyzed cpp parser info shared by Sampi ;14/Nov/25 8:20 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Further analysis done based on Amadeus feedback and ICP document.;14/Nov/25 8:21 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Created PoC environment with Public IP (EIP) allocated to NLB, ActiveMQ broker from AmazonMQ, a windows and linux instance for testing with necessary connectivity.;14/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | Analyzed sample message along with cpp parser further.;14/Nov/25 8:23 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 |  | 115200 | 14400 | 100800 | 0.87 | 115200 | 14400 | 100800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@79b4a52 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0h70b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | Sprint 18 | [95 empty] | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 |  | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | [65 empty] | YES | YES | 2025-09-24 06:14 | 3_*:*_2_*:*_3330929725_*¦*_10041_*:*_1_*:*_501448823_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1119890288 | [12 empty] | 24/Sep/25 8:13 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Amadeus shared document has been reviewed. Setup in sandbox has been started. | 26/Sep/25 8:11 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;A sample queue with ActiveMQ being created. Following up with Sampi for parser requirements. | 29/Sep/25 8:28 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Additional dependencies identified during POC. Have asked Amadeus to check and confirm: # *Supported Protocols* Which message protocols do you recommend for integration with Amadeus? * OpenWire/JMS (ActiveMQ) * AMQP 0-9-1 (RabbitMQ) # *IBM MQ Header Mapping* Which IBM MQ MQMD fields are mandatory for Amadeus integration (e.g., Format=1AIEDI, ReplyToQ, CorrelationID)? If we use Amazon MQ (ActiveMQ) or RabbitMQ, can these fields be provided as JMS/AMQP properties (e.g., JMSReplyTo, JMSCorrelationID, custom header x-format=1AIEDI)? If not, do you have a mapping guide for IBM MQMD to JMS/AMQP headers? # *Character Set and Separators* Do you require character set B with binary EDIFACT separators (0x1D, 0x1F, 0x1C), or do you also accept printable characters (+, :, ')? If both are accepted, is there a preferred encoding for production? # *Maximum Message Size* What is the maximum supported message size for messages exchanged with Amadeus? # *EDIFACT Envelope Validation* Do you validate the UNB/UNH/UNT/UNZ envelopes on your side, or should we handle this validation before sending messages? # *Message Persistence* Should we configure all messages as persistent, or should we match the persistence settings from the ICP (e.g., LinkA3 non-persistent, others persistent)? # *Dead-Letter Queue (DLQ) Handling* Do you require a specific dead-letter queue (DLQ) contract on our side, or is a standard broker-level DLQ sufficient? If a DLQ contract is required, do you expect a specific queue name or message format? # *Synchronous Request/Reply SLAs* What are the expected SLAs (response time, timeout, retry policy) for synchronous request/reply flows (Association Codes O/T)? | 30/Sep/25 8:19 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Following up with Sampi for MQ parsers for analysis. Following up with Amadeus for configuration details. | 01/Oct/25 4:32 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Discussion done with Sampi to understand current parsing configs and queues in use. We have given overview of AmazonMQ based setup and asked for rest of the parsers for further analysis. | 06/Oct/25 8:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Awaiting inputs on configuration details from application owner, hence will be spilled over. | 17/Oct/25 11:21 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 30/Oct/25 9:48 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Information received from Amadeus but needs to be spilled over to next sprint since we do not have sufficient time to complete within current sprint. | 07/Nov/25 7:57 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;One to One message mapping is working as expected. We are facing challenges for following: 1. Sync Communication among producer and consumer # One to Many message delivery being checked further. | 10/Nov/25 8:17 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Custom header addition has been added in message exchange. Testing in progress | 12/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Unable to parse properties as per instructions from Amadeus. Checking further. Following up with Sampi in parallel to get test messages for testing parsing capability. | 13/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Working on MQMD fields as per ICP document from Amadeus. | 14/Nov/25 11:54 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;POC has been carried out for Pegasys app parser as a part of which, Existing CPP based SDN Split parser was converted to the java based parser which was using ActiveMQ library. A sample message was then sent to Pegasys input queue {{PEGASYS.OUT.UAT}} And based on message content, rewritten parser running with java analyzed the content and routed the incoming message to one of the following output queues based on the content and rules defined: {noformat}parser.queue.star=PEGASYS.STAR.UAT parser.queue.mng=PEGASYS.MNG.UAT parser.queue.cimp=PEGASYS.CIMP.UAT parser.queue.sip=PEGASYS.SIP.OUT parser.queue.icargo=PEGASYS.ICARGO.UAT parser.queue.err=MNG.PEGASYS.ERR.UAT{noformat} | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | Done | 2025-11-15 14:39
AM20-945 | Update ServiceNow Payloads with severity | Done | 4 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1832856 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 13:34 | 2026-01-26 14:06 | 2025-11-25 08:24 | 2025-11-27 09:16 |  | 0 | As Product owner I would like to send severity to ServiceNow as well in the payload so that alerts can be classified based on Critical, High, Medium, Low and the incident can be generated accordingly. Acceptance Criteria: Lamda function to be updated with Severity SNS should be able to send mandatory parameters along with severity to ServiceNow successfully |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 115200 | 57600 | 72000 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ed98b6b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo2j: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-19 10:36 | 3_*:*_1_*:*_513651875_*¦*_10041_*:*_1_*:*_682133726_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 19/Nov/25 12:35 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Discussed with Aravind regarding adding severity to payload and tested execution for infra alarms in dev env. | 24/Nov/25 4:42 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Alarms payloads are now configured with severity field, working on updating list of alarms to be sent to ServiceNow. | 27/Nov/25 9:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:16
AM20-946 | Cabin Crew App discovery | Done | 6 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1823348 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 17:37 | 2026-01-11 19:42 |  | 2025-11-14 11:10 |  | 0 | As Product and Application Architect I would like to analyse the Cabin crew application so that I can suggest the best possible way to modernize and migrate to AWS. Acceptance Criteria: * Application Overview and business context is captured ( Business criticality, use case, compliance and security needs, Pain point) * Current Architecture assessment ( Front end stack, Backend, integration, dabtabase, storage and compute requirements and assess modernize angles * Security and Governance - IAM and RBAC model, secret and configuration storage, certificate management, logging and audit requirements * Performance and Capacity utilization - CPU, memory and disk usage, scalability needs, Latency and throughput requirements are gathered * Dependency and integration landscape captured * Cost and Licensing requirements clarified (current cost of application, licenses etc.) * Modernization readiness documented * Modernization strategy proposed successfully * Operational readiness documented |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:19 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | [5 empty] | 86400 | 64800 | 21600 | 0.25 | 86400 | 64800 | 21600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@36e1c984 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ljtn: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 12:35 | 3_*:*_1_*:*_755129358_*¦*_10041_*:*_1_*:*_533024257_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 2:35 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Cabin Crew is still under discussion and more clarity is expected by Dec-25(Project in pipeline) | 14/Nov/25 8:18 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;We have gathered all the information we could but since SAA is still working to understand business scope, we will close this story with current progress and have separate assessment story in future once we have complete information. | 14/Nov/25 11:10 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-14 11:10
AM20-947 | Route53 cutover for FlySAA.com | Done | 2 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865867 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-05 17:14 | 2026-02-05 19:05 | 2025-12-14 18:49 | 2025-12-12 11:18 |  | 0 | As product Ownwer I like to perform cutover for Route53 for [FlySAA.com¦http://FlySAA.com] Acceptance Criteria: The [flysaa.com¦http://flysaa.com] application must be highly available and resilient to single-region outages (e.g., 99.99% uptime). *Route 53 Implementation:* Configure *Failover Routing* policies. A primary record is associated with an active endpoint. A secondary, passive record is configured as a backup. Route 53 health checks automatically switch traffic to the secondary region if the primary endpoint is deemed unhealthy. |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;04/Dec/25 8:30 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;43200 | [5 empty] | 28800 | 0 | 43200 | 1.5 | 28800 | 0 | 43200 | [12 empty] | 04/Dec/25 8:30 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251204-063001.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1192161 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@769d9d3b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7mz: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-02 16:21 | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Dec/25 6:20 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Latest zone file has been imported under public hosted zone route53 AWS.. Earlier 313 after upload 318 records has-been created. | 04/Dec/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;DNS pointer has been modified to route53. C:\Users\VaranasiS>nslookup -query=NS [flysaa.com¦http://flysaa.com] Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: [flysaa.com¦http://flysaa.com] nameserver = [ns-1419.awsdns-49.org¦http://ns-1419.awsdns-49.org] [flysaa.com¦http://flysaa.com] nameserver = [ns-308.awsdns-38.com¦http://ns-308.awsdns-38.com] [flysaa.com¦http://flysaa.com] nameserver = [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] [flysaa.com¦http://flysaa.com] nameserver = [ns-1777.awsdns-30.co.uk¦http://ns-1777.awsdns-30.co.uk] [ns-1419.awsdns-49.org¦http://ns-1419.awsdns-49.org] internet address = 205.251.197.139 [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] internet address = 205.251.194.93 [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] AAAA IPv6 address = 2600:9000:5302:5d00::1 [ns-1777.awsdns-30.co.uk¦http://ns-1777.awsdns-30.co.uk] internet address = 205.251.198.241 C:\Users\VaranasiS> | 04/Dec/25 8:23 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Customer requested to add new alias zone for ALB. ¦[flysaa.com¦http://flysaa.com]¦A¦Simple¦-¦Yes¦[flysaa-cms-alb-402247724.af-south-1.elb.amazonaws.com¦http://flysaa-cms-alb-402247724.af-south-1.elb.amazonaws.com].¦ ¦ Zone has been created and validated after DNS cutover and same working fine. !image-20251204-063001.png¦width=591,alt="image-20251204-063001.png"! | 05/Dec/25 8:29 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SAA SSL DNS has been modified according to request. the change requested under â€œCHG0068431/ CHR0031920â€ has been successfully implemented. Below you will find the latest and updated record for your reference. Â Â C:\Users\VaranasiS>nslookup [upwards.flysaa.com¦http://upwards.flysaa.com] Server:Â UnKnown Address:Â 2401:4900:50:9::7d5 Â Non-authoritative answer: Name:Â Â Â [upwards.flysaa.com¦http://upwards.flysaa.com] Address:Â [102.130.96.4¦https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2F102.130.96.4%2F&data=05%7C02%7Csatyasairam.varanasi%40vodafone.com%7C3d58714d9d324c04956d08de33430e8a%7C68283f3b84874c86adb3a5228f18b893%7C0%7C0%7C639004560572522291%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=w7K%2F%2Fjsk9kHTi00XQSJKC3mq2iHGjbBvw1316zlJjyk%3D&reserved=0] Â Â C:\Users\VaranasiS> Â | 12/Dec/25 11:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-12-12 11:18
AM20-948 | AWS Infra Readiness for Migration | To Do |  | None( Epic) |  |  |  | High | 1620376 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 21:33 | 2026-01-10 00:22 |  |  |  | 0 | AWS Platform for all 20+ application must be ready which includes provisioning of AWS workloads in respective application account, Security & Industry standard compliance implementation, connectivity, RBAC and resource tagging in place | [23 empty] | 3398400 | 2736000 | 748920 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6680bbd | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-13 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | dark_green | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxn7b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-03-04 11:47
AM20-949 | Adding description for CloudWatch notifications sent to ServiceNow for AWS infrastructure resources | Done |  | Sprint 21 | 2025-12-22 | 2026-01-02 | Shreyash Talwekar | Medium | 1883876 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2026-01-09 14:53 | 2026-01-09 17:52 | 2025-12-18 08:18 |  |  | 0 | Update the lambda functions to sent description of CloudWatch alarms in the payload to be sent ServiceNow. |  | Diksha Koul | Shreyash Talwekar |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  |  | ;18/Dec/25 8:28 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;14400 | [5 empty] | 14400 | 0 | 14400 | 1 | 14400 | 0 | 14400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@449d7c5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pm6b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-18 06:31 | [13 empty] | 18/Dec/25 8:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have updated the reason and Description for all prod, dev & qa lambda functions and also tested that as well. | [26 empty] | 1881266 | AM20-302 | Convert Alarms description into simple user understandable format | Done | 2026-01-02 08:22
AM20-950 | PROS¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773953 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 20:12 | 2026-02-07 00:05 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4ce03565 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:04 | [13 empty] | 24/Sep/25 8:04 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS migration agent comms has been implemented. SAA = REQ0056503 (CHG0067695) CSOC = CHR0027812 | 25/Sep/25 5:24 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still CSOC under approval, also we have identified as some miss match in Agent Comms. I have updated and shared to Wanda for CSOC updation. | 06/Oct/25 8:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over - Comms implementation delayed from SAA, hence will be spilled over and worked upon in subsequent sprint | 09/Oct/25 4:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration agent comms has been implemented and agent has been installed n all 3 PROS servers, Created test instance and handover to customer for testing. | 17/Oct/25 7:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:16
AM20-951 | TM1 ¦¦ Migration tool installation | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1620533 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 16:29 | 2026-01-27 19:57 |  |  |  | 0 | As Migration expert I will install AWS migration tool agent in the TM1 SAA server and in AWS account so that migration can be initiated *Acceptance criteria*: AWS migration tool agent has been installed successfully |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | Working with nexio team on troubleshooting the replication issue and configuring required services to get the agent installation successful followed by replication.;07/Apr/25 10:11 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [5 empty] | AM20-14 | AM20-4 | [23 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@106887e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnnb: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-11 06:26 | [13 empty] | 11/Mar/25 8:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This user story is blocked due to [https://vodacom.atlassian.net/browse/AM20-14¦https://vodacom.atlassian.net/browse/AM20-14¦smart-link] the network setup, upon completion of network will pick this one up. | 21/Mar/25 12:19 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet is shared, requested [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] to create a connectivity between on-premises to cloud. After the connectivity established, will be able to pick this migration agent toll installation for TM1. | 25/Mar/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Created a replication template and post launch template, waiting for the connectivity to be established between on-premises and TM1 AWS account. | 27/Mar/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Shared Agent and access details to vodacom team, have raised CRQ request for agent installation. 28th is planned for agent installation followed by replication will be initiated. | 04/Apr/25 11:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;On-prem to AWS Connectivity is established, Agent installation is getting failed due to multiple time of attempt, now waiting for restart of server from the logs. will try to install again and update the proceeding's here, | 07/Apr/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Replication is in progress, waiting for initial snapshot to be created. | 07/Apr/25 10:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Though agent installation completed, marking this story to done. | [20 empty] | 1620350 | AM20-3 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-07 10:45
AM20-952 | Transit Gateway setup for Dev environment | Done | 6 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1702418 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 20:36 | 2026-01-19 23:25 |  |  |  | 0 | As Network Expert, I would be able to setup Transit network gateway for Dev environment Acceptance Criteria: Transit Gateway is provisioned successfully in Dev environment. |  | Aravind Raj | Satya Varanasi |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [13 empty] | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132834.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121470 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132924.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121472 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133228.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121473 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133337.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121469 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133439.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121471 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67c2563b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i095nv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-01 16:49 | [13 empty] | 01/Jul/25 6:49 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;There is no Preprod env for 20+ app migration list, hence we are not setting up Preprod TG attachment, in case needed near future we will setup according to requirement. In this sprint we will setup TG attach for Dev env. | 03/Jul/25 3:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Common TG Attach has be setup on shared VPC dev Account and tested internet connectivity via informatica DEV subnet. !image-20250703-132834.png¦width=1306,height=662,alt="image-20250703-132834.png"! !image-20250703-132924.png¦width=1204,height=668,alt="image-20250703-132924.png"! TG-Attach subnets: !image-20250703-133228.png¦width=1243,height=475,alt="image-20250703-133228.png"! TG attachment details. !image-20250703-133337.png¦width=1189,height=448,alt="image-20250703-133337.png"! Subnet associations !image-20250703-133439.png¦width=1215,height=611,alt="image-20250703-133439.png"! | 04/Jul/25 12:05 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed, test server is working with internet. | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-04 12:05
AM20-953 | Creating Transit Gateway attachment with centralized subnet in Shared VPC account | Done | 4 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660102 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-13 20:52 | 2026-01-13 21:45 |  |  |  | 0 | As Network expert I would like to Create Transit Gateway attachment with centralized subnet in Shared VPC account *Acceptance Criteria*: * Transit Gateway attachment is successfully created with centralized subnet |  | Harsh Chandra | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100033 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052941.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100030 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-053047.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100031 | 14/May/25 7:34 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-053208.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100032 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-074925.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103901 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-074943.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103902 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075022.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103900 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075049.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103899 | 22/May/25 9:52 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-075143.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103903 | [9 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@64ab5b36 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i039pn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-07 16:16 | [13 empty] | 07/May/25 6:15 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dedicated TG attachment subnet created and attached. Testing is pending. | 12/May/25 7:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Test will be initiated today | 14/May/25 7:34 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TG attachment has been configured. Need to test internet connectivity with other accounts. All details shared below. ¦10.40.1.160/28¦10.40.1.160 - 10.40.1.175¦10.40.1.161 - 10.40.1.174¦14¦/28¦AZ1¦Â ¦ ¦10.40.1.176/28¦10.40.1.176 - 10.40.1.191¦10.40.1.177 - 10.40.1.190¦14¦/28¦Â ¦AZ2¦ !image-20250514-052909.png¦width=1135,height=580,alt="image-20250514-052909.png"! !image-20250514-052941.png¦width=1126,height=583,alt="image-20250514-052941.png"! Route table; !image-20250514-053047.png¦width=1126,height=536,alt="image-20250514-053047.png"! Interface associations: !image-20250514-053208.png¦width=1137,height=568,alt="image-20250514-053208.png"! | 14/May/25 5:08 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Common TG attach created and working for multi account, but still need to test further with different scenarios. This required further testing for closer. | 14/May/25 7:13 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;All tests done and working according to our requirement. | 19/May/25 11:26 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Could not verify the routing to internet Routing to internet to be verified and updated Assigning back to [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 19/May/25 5:57 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Routes has been showed overcall. All are configured according to requirement. S C:\Windows\system32> tracert [http://google.com¦http://google.com¦smart-link] Â Tracing route to [http://google.com¦http://google.com¦smart-link] [192.178.54.142] over a maximum of 30 hops: Â Â 1Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 2Â Â Â <1 msÂ Â Â <1 msÂ Â Â <1 msÂ 172.22.2.132---> security account---going to IGW Â 3Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 4Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 5Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 6Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Â Â Â *Â Â Â Â Request timed out. Â 7Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 99.83.116.121---> AWS datacenter Â 8Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 172.253.65.163---> Google DC Â 9Â Â Â 21 msÂ Â Â 21 msÂ Â Â 21 msÂ 192.178.73.217---->google dc 10Â Â Â 18 msÂ Â Â 18 msÂ Â Â 18 msÂ [tzjnba-ah-in-f14.1e100.net¦http://tzjnba-ah-in-f14.1e100.net] [192.178.54.142]--->google dc Â Trace complete. PS C:\Windows\system32> | 20/May/25 5:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This story reassigned yesterday for routing validation so this will be closed this sprint. | 22/May/25 9:52 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As discussed we have validated routing entries and tracert has been updated with details. Subnets: !image-20250522-074925.png¦width=1109,height=569,alt="image-20250522-074925.png"! !image-20250522-074943.png¦width=1114,height=569,alt="image-20250522-074943.png"! Roue table: !image-20250522-075022.png¦width=1112,height=520,alt="image-20250522-075022.png"! !image-20250522-075049.png¦width=1107,height=559,alt="image-20250522-075049.png"! !image-20250522-075143.png¦width=1100,height=565,alt="image-20250522-075143.png"! Please review the same. | 30/May/25 2:46 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Review Done Transitioning to PO approval | 02/Jun/25 9:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-02 09:19
AM20-954 | Airnavx ¦¦ Lift Request creation | Done | 1 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | Medium | 1761196 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 18:30 | 2026-01-20 20:34 |  |  |  | 0 | As Network expert I have to raise Lift request so that Network Firewall implementation CSOC request for port, routing connectivity can be established with VDC Acceptance criteria: Post Lift request, firewall, port and routing connectivity is established successfully |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@70851109 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0el9v: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 08:42 | [13 empty] | 05/Sep/25 10:41 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;AirNavX Lift request has been created and completed. The requests have been logged.: VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231(Network team confirmed as routing in place hence no routing required. CSOC and under implementation process from VDC/SITA side. | 08/Sep/25 6:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-09-08 06:34
AM20-955 | Create Hosted Zone via Terraform | Done | 8 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1824841 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 20:27 | 2026-01-11 21:15 |  | 2025-11-15 14:39 |  | 0 | As a Cloud Platform Engineer I want a Terraform module that creates a Route 53 Hosted Zone (Public or Private) so that teams can provision DNS consistently across accounts and environments. *Scope* * Supports Public and Private hosted zones. * For Private zones: supports single and cross-account VPC associations. * Optional DNSSEC for Public zones (toggle). * Standardized tags, outputs, and README. *Acceptance Criteria (Functional)* # *Zone Type & Creation* Â Given zone_type âˆˆ {public, private} When I run terraform apply Then an AWS Route 53 hosted zone is created with the provided name ([Airchef.co.za¦https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2Fcorp.example.com%2F&data=05%7C02%7Cyashwant.thakur02%40vodafone.com%7Ce00faab9b43b48d8658008de187b13e5%7C68283f3b84874c86adb3a5228f18b893%7C0%7C0%7C638975114066746666%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=c7zVCLwqZ0TyO4ZgLXI7nmQwcYQASdX%2Bd%2BoDRecN0Gw%3D&reserved=0] and [flysaa.com¦http://flysaa.com] ) in the Network account/workspace. # *Public Hosted Zone Outputs* Â Given a Public zone When apply completes Then module outputs include: zone_id, zone_arn, name_servers (list), soa_record (string), and zone_name.Â # *Private Hosted Zone VPC Associations* (Same Account) Given zone_type = private and a list of VPC IDs in the same account When apply completes Then the zone is associated with all listed VPCs and associated_vpc_ids are output.Â # *Private Hosted Zone Cross-Account Associations* Given zone_type = private, a target zone account, and VPCs in other accounts When apply completes Then: VPC association authorization is created in the zoneâ€™s account. Zone associations are established from each workload account (using provider aliases). Associations are idempotent and re-applies do not error.Â # *DNSSEC (Optional, Public Only)* Â Given enable_dnssec = true and a valid KMS key alias/ARN When apply completes Then DNSSEC signing is enabled for the zone, and outputs include dnssec_status and ds_record (for registrar).Â # *Tagging Standard* Â Given tags map When resources are created Then all supported resources include tags: Environment, Owner, CostCenter, ManagedBy = terraform.Â # *Naming & Validation* Â Given invalid domain names (trailing dot, uppercase, spaces) When plan runs Then validation fails with a clear error message before creating resources. |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 115200 | 115200 |  | 0 | 115200 | 115200 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@c68852a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0lps3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-10 19:11 | 10060_*:*_1_*:*_343114423_*¦*_10041_*:*_1_*:*_885254306_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 31/Oct/25 3:21 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Hi [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] , Please review this user story, I created this based on your LLD instruction. Please check if acceptance criteria needs alteration and make changes | 10/Nov/25 9:11 PM;712020:91948faf-1676-4820-bf6b-d50a7992943e;code reviewed and deployed on Sandbox environment | 15/Nov/25 2:39 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-15 14:39
AM20-956 | Adding windows server to the AWS managed AD | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1651361 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-09 15:46 | 2026-01-09 16:46 |  |  |  | 0 | As AWS expert, I would be creating Powershell script for Windows server to integrate AWS-AD. Acceptance Criteria: * Powershall script is created successfully and should be able to integrate AWS-AD |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;24/Apr/25 8:20 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 57600 | 28800 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5e39db2e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02a6b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-24 06:19 | [13 empty] | 24/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;TM1 test instance is added to the AWS managed AD server using a manual approach itself. | 24/Apr/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;i documented the process we can use this for future reference. | 02/May/25 4:56 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Approved from Yashwant behalf due to his Jira login issue | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-24 08:20
AM20-957 | RDS default config changes in Dev environment | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Pankaj Pathak | Medium | 1869424 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-09 14:59 | 2026-01-09 17:39 | 2026-01-02 08:18 |  |  | 0 | h2. Summary Changes are needed for the RDS default configuration. This includes modifying the default port for MySQL and changing the default database user. h2. Context The current setup uses the default MySQL port and user. Adjustments are required for improved security and monitoring. h2. Acceptance criteria * Change the default port for MySQL RDS from 3306 to a different port. * Change the default database user from 'admin' to a different username. * Enable enhanced monitoring for the production instance. h2. Other information N/A |  | Aravind Raj | Pankaj Pathak |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb |  |  |  |  | ;11/Dec/25 3:56 PM;0bd64ee0-8d59-462f-ab15-54fcd1a1fb2b;28800 | [6 empty] | 43200 | 28800 |  |  | 43200 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2aacc09d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obsr: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-05 13:32 | [13 empty] | 05/Dec/25 3:31 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Awaiting application team to confirm feasibility post updating port number. | 11/Dec/25 12:41 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;This subtask has dependency over application team availability to transition the port change on RDS instance. | 11/Dec/25 3:26 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;RDS Database port has been updated and shared with [~accountid:712020:5d317226-2402-463f-bda5-c2cac5f43c13] . However default superuser name â€œAdminâ€ is immutable and canâ€™t be updated. It can only be changed during instance creation. | 12/Dec/25 10:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;I could see the custom RDS port changes made only to dev environment, so switching back to in progress state. Upon completing preprod and prod this US can be marked as closed. | 02/Jan/26 8:27 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;This has been discussed with Project Owner and agreed and understood that this change is only feasible on Dev environment because it require downtime and changes around firewall and other important network components. On Dev RDS we updated port details and â€œadminâ€ user canâ€™t be changed as it is immutable. | [22 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2026-01-02 08:31
AM20-958 | MQ POC -SbrSplit Parser Testing | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1863568 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-16 19:55 | 2026-01-16 21:50 | 2026-01-04 09:12 | 2026-01-02 11:05 |  | 0 | I need to test SbrSplit MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [5 empty] | ;17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;18000 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;23/Dec/25 8:26 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18120 | 115200 | 0 | 115320 | 1 | 115200 | 0 | 115320 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2372d0ee | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o64r: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 21 | [97 empty] | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-09 06:22 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 09/Dec/25 8:21 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Testing has been started. Few errors were identified during execution of jar files. Being checked further. | 11/Dec/25 8:17 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Still working on error fixes | 17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Errors have been fixed and initial testing has been completed. | [27 empty] | Done | 2026-01-02 11:05
AM20-959 | Resources cleanup - Aws accounts | Done | 6 | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1817985 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-18 20:46 | 2026-01-19 00:17 |  | 2025-11-14 20:28 |  | 0 | As part of cost optimization we have planned to take a inventory of AWS resources deployed already. Further to cleanup unwanted and unutilized resources. |  | Harsh Chandra | [5 empty] | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [11 empty] | 86400 | 86400 |  | 0 | 172800 | 172800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@47ec6456 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kwlv: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 18 | [97 empty] | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [65 empty] | YES | YES |  | 3_*:*_1_*:*_0_*¦*_10041_*:*_1_*:*_1851932164 | [42 empty] | Done | 2025-11-14 20:28
AM20-960 | ServiceNow ¦¦ E2E Test validations for TM1 | Done | 2 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1651027 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 13:38 | 2026-01-19 15:56 |  |  |  | 0 | As AWS engineer, I want to test the full alert pipeline from event generation on TM1 to incident creation in ServiceNow so that we can confirm end-to-end functionality Acceptance Criteria: * A simulated error in TM1 triggers the CloudWatch rule * SNS publishes the event * Lamda sends the data to ServiceNow * A ticket is created in ServiceNow with correct details |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;04/Jul/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@54dd1363 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:04 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-02 05:26 | [13 empty] | 02/Jul/25 7:25 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;PRODUCTION ServiceNow Instance: [https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws¦https://sonicboom_em_saa_7161:uZrBuHA8LWj53z8F@lift.service-now.com/api/sn_em_connector/em/inbound_event?source=aws] TM1 server to be integrated with the service now endpoint. | 04/Jul/25 8:12 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Servicenow integration followed by unit test is completed, the SNS topic is configured to get the alerts. | [25 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-04 08:12
AM20-961 | Billing and other solution required roles | Done |  | Sprint 11 | 2025-08-04 | 2025-08-15 | Aravind Raj | Medium | 1741166 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-20 17:21 | 2026-01-20 19:13 |  |  |  | 0 |  |  | Aravind Raj | Onkar Mirajkar |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | [29 empty] | 06/Aug/25 10:30 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;IAM Role Documention.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1136095 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7f932959 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ckgr: | [167 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-06 08:31 | [13 empty] | 06/Aug/25 10:30 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;[^IAM Role Documention.docx] Please Review and Verify | [26 empty] | 1731884 | AM20-118 | Documentation on IAM and RBAC | Done | 2025-08-11 09:19
AM20-962 | RDS default config changes in Dev environment | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Pankaj Pathak | Medium | 1869424 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-06 12:42 | 2026-02-06 15:55 | 2026-01-02 08:18 |  |  | 0 | h2. Summary Changes are needed for the RDS default configuration. This includes modifying the default port for MySQL and changing the default database user. h2. Context The current setup uses the default MySQL port and user. Adjustments are required for improved security and monitoring. h2. Acceptance criteria * Change the default port for MySQL RDS from 3306 to a different port. * Change the default database user from 'admin' to a different username. * Enable enhanced monitoring for the production instance. h2. Other information N/A |  | Aravind Raj | Pankaj Pathak |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:9362ee53-daad-4931-b2ee-8cd252c13acb |  |  |  |  | ;11/Dec/25 3:56 PM;0bd64ee0-8d59-462f-ab15-54fcd1a1fb2b;28800 | [6 empty] | 43200 | 28800 |  |  | 43200 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2aacc09d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obsr: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-12-05 13:32 | [13 empty] | 05/Dec/25 3:31 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;Awaiting application team to confirm feasibility post updating port number. | 11/Dec/25 12:41 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;This subtask has dependency over application team availability to transition the port change on RDS instance. | 11/Dec/25 3:26 PM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;RDS Database port has been updated and shared with [~accountid:712020:5d317226-2402-463f-bda5-c2cac5f43c13] . However default superuser name â€œAdminâ€ is immutable and canâ€™t be updated. It can only be changed during instance creation. | 12/Dec/25 10:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;I could see the custom RDS port changes made only to dev environment, so switching back to in progress state. Upon completing preprod and prod this US can be marked as closed. | 02/Jan/26 8:27 AM;712020:9362ee53-daad-4931-b2ee-8cd252c13acb;This has been discussed with Project Owner and agreed and understood that this change is only feasible on Dev environment because it require downtime and changes around firewall and other important network components. On Dev RDS we updated port details and â€œadminâ€ user canâ€™t be changed as it is immutable. | [22 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | Done | 2026-01-02 08:31
AM20-963 | Backup Server ¦¦ Security compliance implementation | Done | 3 | Sprint 7 | 2025-06-09 | 2025-06-20 | Aravind Raj | Medium | 1681806 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 16:02 | 2026-01-21 18:34 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Backup Server *Acceptance Criteria*: * Renaming of PROS account to Back-Up Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;12/Jun/25 5:41 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 14400 | 43200 | 1 | 43200 | 14400 | 43200 | [12 empty] | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250612-153959.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1113715 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@48024563 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4b: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-09 05:41 | [13 empty] | 09/Jun/25 7:41 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will start working on enabling security frameworks like CIS, NIST, AWS FSBP. | 10/Jun/25 8:15 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled controls, will be working on the controls remediation. | 11/Jun/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;controls are implemented waiting for the security score to be update Â· | 12/Jun/25 5:40 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;CIS, NIST and FSBP controls were enabled and required controls remediated. !image-20250612-153959.png¦width=1279,height=626,alt="image-20250612-153959.png"! | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-12 17:41
AM20-964 | Adding description for CloudWatch notifications sent to ServiceNow for AWS Lambda | Done |  | Sprint 21 | 2025-12-22 | 2026-01-02 | Shreyash Talwekar | Medium | 1883878 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2026-01-20 13:26 | 2026-01-20 15:24 |  |  |  | 0 | Update alarm payloads configured for Lambda functions alarms to sent the description alongwith other previous details to ServiceNow. |  | Faisal Sayed | Shreyash Talwekar |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cac3dfe | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pm6j: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-02 05:41 | [13 empty] | 02/Jan/26 7:40 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;h3. *Lambda Function for Alarm Handling* *Overview:* This Lambda function is triggered whenever a CloudWatch alarm transitions to the {{ALARM}} state. *Functionality:* * Retrieves detailed metrics for the Lambda function that breached the configured threshold and triggered the alarm. * Constructs a payload containing the relevant metric details. * Publishes the payload to an Amazon SNS topic, which has ServiceNow configured as a subscriber for incident management. *Recent Enhancement:* A human-readable description has been added to the payload to improve clarity and facilitate better understanding in ServiceNow. This enhancement is now implemented and operational. | [26 empty] | 1881266 | AM20-302 | Convert Alarms description into simple user understandable format | Done | 2026-01-02 08:22
AM20-965 | Central EKS management Account Setup | To Do | 0 | None( Backlog) |  |  |  | Medium | 1886264 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 13:07 | 2026-01-22 14:29 | 2026-01-05 08:27 |  |  | 0 | As a Cloud platform, I want to establish a central EKS management account so that all EKS cluster across child accounts can be governed and managed from a single control plane Acceptance Criteria: Central AWS account is designated as EKS management Account IAM roles created to allow cross account EKS access Trust relationships established between * Central account * All child application account # SCP prevent direct EKS admin access from the child account # Network connectivity (TGW/VPC peering) validated # Design approved by AWS architecture, Security expert | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@b37afdb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [126 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [200 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0001s | [57 empty] | Online Dev | [109 empty] | Business | [200 empty] | YES | YES | [44 empty] | To Do | 2026-01-04 09:03
AM20-966 | Trellix integration with PROS | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773956 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 12:50 | 2026-01-10 15:04 |  | 2025-10-30 08:26 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan PROS workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in PROS server * Trellix is able to access PROS account successfully and perform scanning |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 29/Oct/25 8:43 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-064238.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174346 | 29/Oct/25 8:53 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-065302.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174368 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bb75c16 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [65 empty] | YES | YES | 2025-09-24 07:35 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [12 empty] | 24/Sep/25 9:34 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;To get this US completed we have to complete Building up the EC2 instance and then only the Trellix agent reconfiguration will get done to scan the PROS workloads for any vulnerabilities, malware reporting. | 03/Oct/25 9:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* Pros connectivity issue is still going and its pending from there end. Also, the EC2 instance creation is yet not started so thatâ€™s why this US will go to the spill over to next sprint. | 17/Oct/25 11:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* The EC2 instance creation is just completed on the last day of the sprint. Thatâ€™s why the US was not able to complete in this sprint now after completion of the EC2 instances we can follow up with sinjun and get the update regarding the Trellix integration with PROS account. | 29/Oct/25 8:26 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation from Sinjun that the Trellix integration is done for PROS account servers. Have shared the email with sinjun. | 29/Oct/25 8:43 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-064238.png¦width=629,alt="image-20251029-064238.png"! Attaching his confirmation which i got over teams | 29/Oct/25 8:53 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-065302.png¦width=629,alt="image-20251029-065302.png"! | 30/Oct/25 8:26 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-30 08:26
AM20-967 | CSA assessment | Done | 8 | Sprint 2 | 2025-03-31 | 2025-04-11 | Sumit Nikam | Medium | 1627466 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 13:04 | 2026-02-06 16:29 |  |  |  | 0 | As application architect I would assess current CSA application architecture, functional complexity, ease of migration, current and future scalability requirements, dependencies between different components and data consistency across services. Acceptance Criteria: Document consisting of current and to-be architecture, proposed microservices,, dependencies and data consistency approach is successfully completed |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;02/Apr/25 6:36 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;02/Apr/25 6:37 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 |  |  | 115200 | 21600 | 93600 | 0.81 | 115200 | 21600 | 93600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@11a4dc28 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 4 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxso7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-26 06:12 | [13 empty] | 26/Mar/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;High level plan for CSA Modernization has been prepared, reviewed internally and shared with Vodacom. Next step is to prepare for SOW document. | 01/Apr/25 7:11 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Working along with Yashwant for SOW document preparation and review | 02/Apr/25 6:36 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Reviewing functional details shared by Sampi | 04/Apr/25 3:26 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Follow-up discussion completed with Sampi. | 04/Apr/25 8:08 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved. SOW completed | [22 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-04-04 20:08
AM20-968 | Informatica Server ¦¦ LLD preparation | Done | 6 | Sprint 13 | 2025-09-01 | 2025-09-12 | Yashwant Thakur | High | 1610565 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 14:36 | 2026-01-27 15:17 |  |  |  | 0 | As AWS architect, I would create connectivity traceability for informatica Server so that I can prepare Low level design accordingly from migration perspective *Acceptance Criteria*: * Connectivity traceability refinement and agreed with SAA for sign off * Low level design documentation including proposed architecture completed * Back-up cost and policy documented |  | Sankalp Rai | Yashwant Thakur |  |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;24/Jun/25 1:32 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;11/Aug/25 10:10 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 |  |  |  |  | 86400 | 0 | 57600 | 0.66 | 86400 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7d2f4e8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 4/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 4 | 100 | 0 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03a2v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | [104 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-03-10 14:18 | [13 empty] | 10/Mar/25 4:18 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 10/Mar/25 4:24 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;*Day 1* # *Review the assessment data with Application owners and relevant stake holder >> Call to Scheduled on or before 12th* Sankalp > Infrastructure Sumit > Application Pankaj > Database *Day 2* # *Post assessment, Finalize the approach for migration, If change is needed* # *Documentation for LLD* Compilation of the document > Sankalp Infrastructure > Sankalp Apps input > Sumit Database > Pankaj Comm Matrix > Satyasairam *Day 4* # *Review with internal stake holders* *Day 5* # *Review with Application team / SAA Stake holders / Vodacom Stake holders* # *Implement and submit for final review and approval* | 20/May/25 10:24 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;1st Draft Complete. Need to review internally revised Start Date: 19th May 2025 End date: 23rd May 2025 | 24/Jun/25 1:32 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;LLD Review with customer is completed Awaiting information requested from Application Owner | 11/Aug/25 5:04 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1582119 | FCBEM-117 | AWS Platform readiness | Done | 2025-10-13 09:23
AM20-969 | ServiceNow ¦¦ SNS Topic for Alerts | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650429 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 20:43 | 2026-01-26 21:07 |  |  |  | 0 | AS AWS Expert, I want to create an Amazon SNS topic so that AWS services can be publish alert messages to it. Acceptance Criteria: * AN SNS topic is created * Permissions are set to allow EventBridge and Lamda to publish to it * The topic supports the subscription |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@505787e3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [66 empty] | Unit Tested | [51 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-06 06:23 | [13 empty] | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed, and will modify the required configurations. Â· | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:38
AM20-970 | EKS public sharing | To Do |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Sumit Nikam | Medium | 1869422 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-11 16:14 | 2026-01-11 16:44 | 2026-01-08 08:37 |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3ef27d1f | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0obsj: | [167 empty] | Business | [12 empty] | Sprint 20 | Sprint 21 | Sprint 22 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [41 empty] | 1843633 | AM20-280 | Remediate Failed controls for Flysaa Backend Accounts | To Do | 2025-11-28 11:12
AM20-971 | AirNavX Account ¦¦ Security Compliance Implementation | Done | 4 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672716 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-31 14:13 | 2026-01-31 14:46 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on Informatica Server *Acceptance Criteria*: * Renaming of AirNavX account to Informatica Server is done successfully * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;28/May/25 11:24 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250528-092239.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1106065 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@33a69e54 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04ft7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-28 09:24 | [13 empty] | 28/May/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS Account - 345594574792 Controls were implemented and security score is updated is for all the three security standard frameworks- CIS, NIST and AWS FSBP !image-20250528-092239.png¦width=1279,height=589,alt="image-20250528-092239.png"! | [26 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-28 11:24
AM20-972 | Informatica Server ¦¦ Budget Management Configuration | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772227 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 15:17 | 2026-01-25 15:22 |  |  |  | 0 | As AWS expert I would like to configure Informatica budget management and alerts so that stakeholders gets the frequent notifications on budgets and alerts if the budget crosses threshold Acceptance Criteria: * Budget management for Informatica is configured successfully * Alerts triggered if the budget crosses 80%, 85% and 90% of Threshold |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [10 empty] | AM20-164 |  |  | 18/Sep/25 10:44 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20250918-084430.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1155401 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3d312d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq0n: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-09 06:44 | [13 empty] | 09/Sep/25 8:43 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Today will start creating the budget on the management account for Informatica Dev and Prod environment. | 09/Sep/25 11:00 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created the budget for Informatica Dev and Prod in Payers management account with threshold as 80%,85% & 90%. Now, will add the account in the Lambda function and also will add app. owner mail id & will test it. | 15/Sep/25 11:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have added the Account name and application owner email ids in lambda function also tested the budget alerting and we are successfully getting the alerts for budget management. | 17/Sep/25 9:13 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8; !image-20250918-084430.png¦width=852,height=577,alt="image-20250918-084430.png"! Attaching the evidence screenshot that the budget we have created are able to get the emails and details if it exceeded the threshold value 85%. | 18/Sep/25 2:46 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Demo was given to Yashwant but want Aravind to review it. | 22/Sep/25 8:36 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;the threshold of budget should be calculated based on the all the resources involved in the architecture and LLD, though its modifiable, i would suggest to update the value in firsthand itslef. | [24 empty] | Done | 2025-09-22 08:50
AM20-973 | MQ POC -SbrSplit Parser Testing | Done | 8 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1863568 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 19:40 | 2026-02-03 21:43 | 2026-01-04 09:12 | 2026-01-02 11:05 |  | 0 | I need to test SbrSplit MQ parsers to ensure viability of using AmazonMQ without impacting the existing app functionality. |  | Sumit Nikam | [5 empty] | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | [5 empty] | ;17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;18000 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;17/Dec/25 8:30 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | ;23/Dec/25 8:26 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18120 | 115200 | 0 | 115320 | 1 | 115200 | 0 | 115320 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2372d0ee | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o64r: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 21 | [97 empty] | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-09 06:22 | 3_*:*_1_*:*_1209869960_*¦*_10041_*:*_1_*:*_1102236707_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 09/Dec/25 8:21 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Testing has been started. Few errors were identified during execution of jar files. Being checked further. | 11/Dec/25 8:17 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Still working on error fixes | 17/Dec/25 8:29 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Errors have been fixed and initial testing has been completed. | [27 empty] | Done | 2026-01-02 11:05
AM20-974 | Informatica Server ¦¦ Subnet creation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660595 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-16 20:23 | 2026-01-16 21:02 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Nexio AV application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Nexio AV and the configured based on the approved comms matrix |  | Aravind Raj | Harsh Chandra | Satya Varanasi | Shreyash Talwekar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 27/Jun/25 3:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-135131.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119370 | 27/Jun/25 3:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-135223.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119371 | 27/Jun/25 5:52 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155229.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119409 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@435a4769 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-16 08:08 | [13 empty] | 16/May/25 10:07 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Waiting for terraform code towards build this. | 20/May/25 5:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Deepak and team, this need to be addressed with terraform code the same has been prepared by Utkarsh, until core not ready this story may not possible to address. | 10/Jun/25 2:03 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still â€œShreyashâ€ checking Utkarsh script, this story depending with script testing and execution. | 16/Jun/25 9:06 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Terraform script is under modification by â€œShreyashâ€, as per his update it will be ready this week. Hence this is the reason for spill over Sprint7 to Sprint8. | 16/Jun/25 9:15 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Currently working on updating terraform script based on latest naming convention requirement. | 18/Jun/25 11:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The script is managing by â€œShreyashâ€ so i am assigning this task to him, once his work completes he will reassign to me. | 23/Jun/25 1:58 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We were able to create AWS resources (mentioned in previous mail ) using terraform scripts on sharedvpc-dev account. To address some requirements like adding naming conventions and state file management, we will have to add some changes in terraform scripts. Due to current sprint activities I might not be able to work on the changes in this sprint. | 27/Jun/25 3:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Prod Subnet/Route table has been created, & tested internet access and same working fine. !image-20250627-135131.png¦width=1261,height=434,alt="image-20250627-135131.png"! !image-20250627-135223.png¦width=1112,height=588,alt="image-20250627-135223.png"! sh-5.2$ ping [http://google.com¦http://google.com¦smart-link] PING [http://google.com¦http://google.com¦smart-link] (142.251.47.238) 56(84) bytes of data. 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=1 ttl=108 time=20.5 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=2 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=3 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=4 ttl=108 time=19.7 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=5 ttl=108 time=19.8 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=6 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=7 ttl=108 time=19.7 ms ^C --- [http://google.com¦http://google.com¦smart-link] ping statistics --- 7 packets transmitted, 7 received, 0% packet loss, time 6010ms rtt min/avg/max/mdev = 19.630/19.800/20.473/0.282 ms sh-5.2$ hostname [ip-10-40-0-213.awsflysaa.com¦http://ip-10-40-0-213.awsflysaa.com] sh-5.2$ ifconfig ens5: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 9001 inet 10.40.0.213 netmask 255.255.255.240 broadcast 10.40.0.223 inet6 fe80::4a7:ebff:fe03:c075 prefixlen 64 scopeid 0x20<link> ether 06:a7:eb:03:c0:75 txqueuelen 1000 (Ethernet) RX packets 1653 bytes 293385 (286.5 KiB) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 1809 bytes 265312 (259.0 KiB) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0 lo: flags=73<UP,LOOPBACK,RUNNING> mtu 65536 inet 127.0.0.1 netmask 255.0.0.0 inet6 ::1 prefixlen 128 scopeid 0x10<host> loop txqueuelen 1000 (Local Loopback) RX packets 12 bytes 1020 (1020.0 B) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 12 bytes 1020 (1020.0 B) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0. | 27/Jun/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev Subnet and route table has been created. !image-20250627-155229.png¦width=1259,height=431,alt="image-20250627-155229.png"! | 27/Jun/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Subnet creation and sharing is done, have reviewed. | 29/Jun/25 8:13 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [16 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:13
AM20-975 | Servicenow Payload severity updates for Lambda alarms | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Shreyash Talwekar | Medium | 1835024 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-02-06 14:07 | 2026-02-06 17:29 |  |  |  | 0 | Enhance the existing Lambda function that triggers when Lambda alarms enter an alarm state. Currently, the function gathers alarm-related metrics, collects function details, and sends an approved payload to ServiceNow. However, severity information from the alarm is not included in the payload. This story addresses that gap by updating the Lambda function to capture and transmit the correct severity level from the alarm to ServiceNow. *Acceptance Criteria:* * Lambda function must include severity details from the alarm in the payload. * Payload sent to ServiceNow should accurately reflect the alarm severity. |  | Faisal Sayed | Harsh Chandra | Shreyash Talwekar |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  | ;20/Nov/25 8:33 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;14400 | [6 empty] | 0 | 14400 |  |  | 0 | 14400 | [12 empty] | 21/Nov/25 7:04 AM;86260165-7dca-48a8-8b3b-378ae5a34c47;image-20251121-050425.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187511 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@560f4ab3 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxar: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 05:33 | [13 empty] | 20/Nov/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Requirements have been gathered. Lambda function code will be reconfigured to incorporate changes, followed by payload testing. Ticket will be updated upon successful completion of testing. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;*Update:* Lambda function has been updated per requirements to capture severity. A test event was executed to validate behavior and output; results are attached. Test outcome is successful, and the implementation is complete. | 21/Nov/25 7:04 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;!image-20251121-050425.png¦width=555,alt="image-20251121-050425.png"! | 24/Nov/25 8:42 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reviewed output, LGTM. | [23 empty] | 1832856 | AM20-264 | Update ServiceNow Payloads with severity | Done | 2025-11-24 08:41
AM20-976 | AWS_SAA_Security ¦¦ Security Compliance Implementation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642119 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 21:09 | 2026-02-04 01:02 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on shared service account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation on *Account no: 30335236533â€ƒâ€ƒAWS_SAA_Security* *Acceptance Criteria*: * CIS policy implementation successfully done in shared service account * NIST policy implementation successfully done in shared service account * AWSFSBP policy implementation successfully done in shared service account |  | Aravind Raj | Harsh Chandra | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2cb06c96 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00tcn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-09 06:21 | [13 empty] | 09/Apr/25 8:21 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have enabled dependencies service like security hub, macie, guard duty for the compliance controls, will start working on the remediation towards other controls. | 14/Apr/25 8:18 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed implementing controls, awaiting for security score update. Will close this story along with score update. | 17/Apr/25 8:37 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have completed enabling Guard Duty, Macie, Security Hub, followed by this have implemented controls for CIS, NIST, AWS FSBP standards. Still there are few failed controls to be remediated, since the implementation of services done by vodacom, will expect their support in implementing the controls. if the controls cannot be implemented will get a confirmation on the failed control list to close this user story. | 24/Apr/25 5:50 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is not able to enable with the access i have, so requested vodacom team to support. | 28/Apr/25 4:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;AWS config is enabled after SCP modification, for failed controls vodacom will do the remediation. | 02/May/25 4:58 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-04-28 16:01
AM20-977 | Implement JSON Message Parsing in AWS sandbox ActiveMQ POC | Done | 4 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811820 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 17:00 | 2026-01-18 18:03 |  | 2025-10-31 17:25 |  | 0 | As part of validating AWS ActiveMQ integration with a Spring Boot application, we will deploy Producerâ€“Consumer.java files to conduct POC to include JSON message parsing capability. The Producer will publish structured JSON messages to ActiveMQ queue, and Consumer will parse and process the JSON payload. This will help validate end-to-end message exchange, parsing logic, and overall integration readiness in AWS sandbox environment. *Acceptance Criteria* * Deploy ActiveMQ in AWS Sandbox environment. * ActiveMQ broker is accessible from Spring Boot application in EC2 windows of AWS sandbox. * Producer publishes a sample JSON message to ActiveMQ queue. * Consumer retrieves the message and successfully parses the JSON payload using a standard parser (e.g., Jackson). * Parsed data fields are printed for verification. * Message transmission and parsing flow verified end-to-end without errors. |  | Sanjot Fotedar | Sumit Nikam | Yashwant Thakur |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;24/Oct/25 10:15 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 57600 | 28800 | 28800 | [12 empty] | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124615.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174186 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124631.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174189 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124648.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174188 | 28/Oct/25 2:50 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251028-124656.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174187 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5c659eaf | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k74r: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 |  | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-23 13:51 | 10060_*:*_1_*:*_250783232_*¦*_3_*:*_1_*:*_454937934_*¦*_10041_*:*_1_*:*_596024045_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 23/Oct/25 3:51 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Following steps are completed: * We have deployed ActiveMQ in AWS sandbox account. * Deploy EC2 windows server manually in same sandbox account align under same network with MQ server. * Tested successfully MQ server connectivity from EC2 windows server. * Installed JDK-17 version , maven to support java spring boot applications. * Developed and deployed java application with pom.xml | 28/Oct/25 2:50 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;* Developed [Producer.java¦http://Producer.java] to publish JSON messages to AWS ActiveMQ queue. * Developed [ConsumerTest.java¦http://Consumer.java] to consume and parse JSON messages. * Verified successful message send/receive flow over SSL connection. * Validated JSON parsing using Jackson and confirmed expected output. * Resolved encoding and dependency issues during build. * End-to-end functionality tested in AWS sandbox account. * MQ server Dashboard shows expected outcome. !image-20251028-124615.png¦width=443,alt="image-20251028-124615.png"! !image-20251028-124631.png¦width=443,alt="image-20251028-124631.png"! !image-20251028-124648.png¦width=443,alt="image-20251028-124648.png"! !image-20251028-124656.png¦width=443,alt="image-20251028-124656.png"! | 31/Oct/25 12:31 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;We have reviewed implementation in sandbox and could see working messaging flow from provider to the consumer via AmazonMQ running with ActiveMQ broker. Next step is to modify the config and test config based on feedback from Amadeus. | 31/Oct/25 5:25 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-10-31 17:25
AM20-978 | Informatica ¦¦ Custom application Metrics | Done | 4 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1761210 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 13:09 | 2026-02-03 14:22 |  |  |  | 0 | # Configure & install cw agent. # Refer email for metrics to be monitored. # Create alerts as per approval in the email. |  | Faisal Sayed | [5 empty] | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@407cb340 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0elc3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 15 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-17 06:01 | [13 empty] | 17/Sep/25 8:01 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Informatica Accounts (Dev & Prod) cutover is yet to be done. Actual workloads are yet to be migrated. Hence, blocked. | 01/Oct/25 8:24 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# Configure & install cw agent - Done # Refer email for metrics to be monitored - Done # Create alerts as per approval in the email - Done | [28 empty] | Done | 2025-10-06 07:58
AM20-979 | Route53 ¦¦ Post Cutover validation and Support for Airchef | Done | 0 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865870 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-10 12:42 | 2026-01-10 15:27 | 2025-12-14 18:50 | 2025-12-12 11:18 |  | 0 | As Product owner I wish to validate the behaviour of Airchef so that we can assure that the Airchef is working as expected and change caused by AWS does not create any issues. Acceptance Criteria: Airchef BAU is working as expected and the traffic is directed via AWS route53 |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@50f9cacc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7nf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-04 06:32 | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 04/Dec/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Original [airchefs.co.za¦http://airchefs.co.za] migration completed still on-prem to VDC cutover need to be implemented. | 05/Dec/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;On prem to VDC cutover has been completed and tested by SITA team, According to Hoosen Tlou <[hoosentlou@flysaa.com¦mailto:hoosentlou@flysaa.com]> current Airchefs servers are shutdown and decommissioned. Notified to team don't go for decom but Denise notified to go for decom. | 12/Dec/25 11:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-12-12 11:18
AM20-980 | Rename Citrix account with informatica Prod: Re-establish Informatica ¦¦ Subnet Configuration and Setup platform | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1749511 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 17:55 | 2026-01-27 20:58 |  |  |  | 0 | As Network expert, I would like to provision subnet configuration for PROS application Acceptance criteria: * Subnet configuration completed successfully * Tagging of all network elements associated done succesfully * Traffic flow testing and validation is concluded |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153624.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141700 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-153747.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141702 | 19/Aug/25 5:42 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250819-154222.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141701 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@e805dba | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dap7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 06:22 | [13 empty] | 12/Aug/25 8:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;We are looking account id rename or new id creation process accordingly i will proceed for next steps. | 19/Aug/25 5:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Citrix Account ID has been renamed with Informatica Prod â€œ536697248966 â€ƒâ€ƒ SAA_Informatica_PRODâ€ | 19/Aug/25 5:42 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet, NACL, RAM ,SG and connectivity has been established. !image-20250819-153624.png¦width=1417,height=750,alt="image-20250819-153624.png"! Connectivity has been tested and working fine. !image-20250819-153747.png¦width=1417,height=750,alt="image-20250819-153747.png"! ¦Informatica Prod-Public¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.0.208/28¦10.40.0.208 - 10.40.0.223¦10.40.0.209 - 10.40.0.222¦14¦/28¦ ¦Informatica Prod-Public(DR)¦1¦ProductionÂ ¦Â ¦10.40.0.0/18¦10.40.1.128/28¦10.40.1.128 - 10.40.1.143¦10.40.1.129 - 10.40.1.142¦14¦/28¦Â ¦AZ2¦ !image-20250819-154222.png¦width=1417,height=750,alt="image-20250819-154222.png"! | 19/Aug/25 5:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Assigning for review. | 21/Aug/25 6:10 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed with internet acess. | 25/Aug/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 06:33
AM20-981 | Ingesting 500 of lines of inbound and outbound rules from excel to Terraform code for enablement | Done | 6 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1869689 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 21:54 | 2026-01-18 01:24 | 2025-12-14 17:51 | 2025-12-12 14:51 |  | 0 |  |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bae0685 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ocbn: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-05 06:26 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Dec/25 8:26 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script deployment. Currently we are adding the inbound and outbound rule with excel only. | 12/Dec/25 2:51 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approving provided we see workable solution during demo | [28 empty] | Done | 2025-12-12 14:51
AM20-982 | TM1 ¦¦ Monitoring Servers post migration | Done | 1 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | High | 1651402 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 20:42 | 2026-01-15 20:58 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if TM1 server service is stopped |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 20/Aug/25 6:27 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250820-162717.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1142337 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2a36f4c8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4i:z | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-13 15:59 | [13 empty] | 13/Jun/25 5:58 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked with TM1 Agent Installation - [https://vodacom.atlassian.net/browse/FCBEM-593¦https://vodacom.atlassian.net/browse/FCBEM-593¦smart-link] | 13/Aug/25 12:42 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 cutover completed and monitoring enable but need to create TM1 dash board. | 18/Aug/25 4:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 dashboard has been created under 20Plus apps dashboard. | 19/Aug/25 5:46 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Alerts has been configured and currently in review stage. | 20/Aug/25 6:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Service now team the alerts has been reaching to from cloud watch dash board. Attaching reference screen shot. !image-20250820-162717.png¦width=1910,height=508,alt="image-20250820-162717.png"! | 21/Aug/25 6:09 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed | 25/Aug/25 6:31 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-08-25 06:31
AM20-983 | Route53 ¦¦ Post Cutover validation and Support for Airchef | Done | 0 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865870 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 12:37 | 2026-01-12 16:35 | 2025-12-14 18:50 | 2025-12-12 11:18 |  | 0 | As Product owner I wish to validate the behaviour of Airchef so that we can assure that the Airchef is working as expected and change caused by AWS does not create any issues. Acceptance Criteria: Airchef BAU is working as expected and the traffic is directed via AWS route53 |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@50f9cacc | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7nf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-04 06:32 | 3_*:*_1_*:*_88746092_*¦*_10041_*:*_1_*:*_600800712_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 04/Dec/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Original [airchefs.co.za¦http://airchefs.co.za] migration completed still on-prem to VDC cutover need to be implemented. | 05/Dec/25 9:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;On prem to VDC cutover has been completed and tested by SITA team, According to Hoosen Tlou <[hoosentlou@flysaa.com¦mailto:hoosentlou@flysaa.com]> current Airchefs servers are shutdown and decommissioned. Notified to team don't go for decom but Denise notified to go for decom. | 12/Dec/25 11:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-12-12 11:18
AM20-984 | Centralized Utilization CloudWatch Dashboard | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820131 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 17:43 | 2026-02-03 18:07 |  | 2025-11-14 10:59 |  | 0 | As a cloud finops engineer I want to view utilization metrics of all workloads across all child accounts in one place so that I can identify performance inefficiencies and optimize cost Acceptance Criteria: CloudWatch cross account observability is enabled between Parent and child accounts CloudWatch Dashboards show metrics from EC2, RDS,EKS,S3 and Lamda for each environment Metrics are visualized per account, environment and service * CPU utilization (EC2) * Disk Performance (EC2) * NetworkIn NetworkOut (EC2) * Memory utilization (RDS) * IO performance (RDS) * Storage usage (S3) * Error Rate (S3) * Invocation health (Lamda) * Traffic (ALB/NLB) * Availability - Helthyhostcount (ALB/NLB) * Account utilization score (Cross Account) * Tag compliance (Cross account) CloudWatch Dashboard auto refreshes daily and supports drill down views |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | create the dashboard for all cross accounts.;14/Nov/25 8:29 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;275400 | [5 empty] | 57600 | 57600 | 275400 | 4.78 | 57600 | 57600 | 275400 | [12 empty] | 12/Nov/25 2:00 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251112-115953.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182044 | 12/Nov/25 2:01 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251112-120058.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182047 | 13/Nov/25 12:11 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251113-101129.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1182802 | [15 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5149805 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l5u3: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-07 06:59 | 3_*:*_1_*:*_603237568_*¦*_10041_*:*_1_*:*_865227267_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 07/Nov/25 8:59 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start working on this US whatever resources are created we will create and update the custom metric as per accounts and will try to create the Cloudwatch dashboard and alerts accordingly. | 12/Nov/25 1:59 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have created the dashboard for all cross accounts on the *SAA_Audit* account. Dashboard Name : *Central Dashboard* This Dashboards show metrics from EC2, RDS,EKS,S3 and Lamda for each environment. | 12/Nov/25 2:00 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251112-115953.png¦width=714,alt="image-20251112-115953.png"! Screenshot has been attached as an evidence that the Dashboard has been created. | 12/Nov/25 2:01 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251112-120058.png¦width=714,alt="image-20251112-120058.png"! | 12/Nov/25 4:09 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Now checking for the tag compliance policy. | 13/Nov/25 12:11 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;For Cross account utilization score we have Dashboard in Payer Account which is out organization management account. We can see all account wise score , costing as well as percentage. !image-20251113-101129.png¦width=714,alt="image-20251113-101129.png"! | 14/Nov/25 8:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Tag Compliance remained pending due to some tag policy disable issue. Will taking this in next sprint. | 14/Nov/25 10:56 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;As discussed in the Sprint review call we will have to get in touch with leigh for his approval for enabling the Tag policy for the Cross account thatâ€™s why this Tag compliance part we are taking in next sprint. | 14/Nov/25 10:59 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | Done | 2025-11-14 10:59
AM20-985 | Tag Validations for PROS | Done | 4 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1820182 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 16:01 | 2026-01-29 19:06 |  | 2025-11-14 11:11 |  | 0 | As a Cloud governance engineer I want to validate that all resources and workloads related to newly migrated applications have the correct mandatory tags applied so that we can ensure accurate cost allocation, compliance reporting and automation alignment across all PROS account Acceptance Criteria: * Tags for all applicable application resource type ( EC2, EBS, RDS, S3 lamda, ALB/NLB, Cloudwatch log groups) are successfully captured. * If there are any tags not available then manually updated successfully * Validations runs across all migrated resources and as per agreed format |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Nov/25 8:32 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;216600 | [5 empty] | 57600 | 0 | 216600 | 3.76 | 57600 | 0 | 216600 | [12 empty] | 07/Nov/25 9:07 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251107-070750.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1179411 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4310b374 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0l61v: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_146887020_*¦*_10041_*:*_1_*:*_717589963_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_146887020_*¦*_10041_*:*_1_*:*_717589963_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_146887020_*¦*_10041_*:*_1_*:*_717589963_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_146887020_*¦*_10041_*:*_1_*:*_717589963_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 14:21 | 3_*:*_1_*:*_146887020_*¦*_10041_*:*_1_*:*_717589963_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 4:20 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will Start checking all the tags are in place for PROS environment and will update them. | 06/Nov/25 11:35 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;All mandatory tags are being updated for PROS environment including Cloud watch Alarms. | 07/Nov/25 9:07 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251107-070750.png¦width=629,alt="image-20251107-070750.png"! | 14/Nov/25 11:11 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [26 empty] | Done | 2025-11-14 11:11
AM20-986 | TM1 ¦¦ Integration of AWS IAM roles with TM1 AWS Account Instance using JSON | Done | 10 | Sprint 3 | 2025-04-14 | 2025-04-25 | Yashwant Thakur | Medium | 1642068 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 18:04 | 2026-01-26 21:44 |  |  |  | 0 | As AWS expert, I would be integrating AWS IAM roles with TM1 Instance Acceptance criteria: * IAM roles are created successfully * Integration of defined IAM roles with TM1 instance so that user is able to access the TM1 instance. |  | Aravind Raj | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 144000 | 144000 |  | 0 | 144000 | 144000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5190a6ea | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00t0v: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [106 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-09 07:30 | [13 empty] | 09/Jul/25 9:29 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Following are the details of the role created: role_arn = "arn:aws:iam::209479274829:role/TM1-IAMRole-EC2InstanceProfile" role_name = "TM1-IAMRole-EC2InstanceProfile" Account details: 209479274829 (SAA-TM1) Custom Role Details: The role covers the equivalent of â€œAmazonSSMManagedInstanceCoreâ€, basic CloudWatch Agent permissions, and general S3 access. _*NOTE*: THE FOLLOWING HAS BEEN ACHIEVED USING TERRAFORM._ | 09/Jul/25 9:30 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;.json file of the custom role is as follows: { Â "Version": "2012-10-17", Â "Statement": [ Â Â { Â Â Â "Sid": "SSMManagedInstanceCorePermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssm:DescribeAssociation", Â Â Â Â "ssm:GetDeployablePatchSnapshotForInstance", Â Â Â Â "ssm:GetDocument", Â Â Â Â "ssm:DescribeDocument", Â Â Â Â "ssm:GetManifest", Â Â Â Â "ssm:GetParameter", Â Â Â Â "ssm:GetParameters", Â Â Â Â "ssm:ListAssociations", Â Â Â Â "ssm:ListInstanceAssociations", Â Â Â Â "ssm:PutInventory", Â Â Â Â "ssm:PutComplianceItems", Â Â Â Â "ssm:PutConfigurePackageResult", Â Â Â Â "ssm:UpdateAssociationStatus", Â Â Â Â "ssm:UpdateInstanceAssociationStatus", Â Â Â Â "ssm:UpdateInstanceInformation" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "SSMMessageGatewayPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ssmmessages:CreateControlChannel", Â Â Â Â "ssmmessages:CreateDataChannel", Â Â Â Â "ssmmessages:OpenControlChannel", Â Â Â Â "ssmmessages:OpenDataChannel" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "EC2MessagesPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "ec2messages:AcknowledgeMessage", Â Â Â Â "ec2messages:DeleteMessage", Â Â Â Â "ec2messages:FailMessage", Â Â Â Â "ec2messages:GetEndpoint", Â Â Â Â "ec2messages:GetMessages", Â Â Â Â "ec2messages:SendReply" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "CloudWatchAgentPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "logs:CreateLogGroup", Â Â Â Â "logs:CreateLogStream", Â Â Â Â "logs:PutLogEvents", Â Â Â Â "logs:DescribeLogGroups", Â Â Â Â "logs:DescribeLogStreams", Â Â Â Â "cloudwatch:PutMetricData" Â Â Â ], Â Â Â "Resource": "*" Â Â }, Â Â { Â Â Â "Sid": "S3AccessPermissions", Â Â Â "Effect": "Allow", Â Â Â "Action": [ Â Â Â Â "s3:GetObject", Â Â Â Â "s3:PutObject", Â Â Â Â "s3:ListBucket" Â Â Â ], Â Â Â "Resource": "*" Â Â } Â ] } | 11/Jul/25 11:34 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed IAM roles is having required permissions | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-987 | Monitor and Alert on daily Cloudwatch log costs | Done |  | Sprint 14 | 2025-09-15 | 2025-09-26 | Aravind Raj | Medium | 1781403 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 13:46 | 2026-01-21 14:33 |  |  |  | 0 | As a clous infrastructure product owner I want to assess the daily CloudWatch logs costs and trigger an alarm if cost exceeds defined threshold so that I can detect excessive log injestion/retention and take timely action to optimize costs Use SAA-Audit account, account id : 300204747992 for implementation Acceptance Criteria: # *Daily Cost Assessment* System must fetch daily CloudWatch cost usage ( log storage + injestion + insight queries) from AWS cost explorer or Cloud watch Metrices Must provide breakdown by account and log group # *Threshold Configuration* Ability to set daily cost thresholds Alarm must be raised if daily costs exceed threshold # *Alerting Mechanism* Alerts should be sent via SNS->integrated notification channels (Email/ServiceNow) Alarm must be included impacted account, service (CloudWatch Logs) cost for the day and % deviation from baseline # *Historical Trend* Dashboard view showing last 7/30 days of CloudWatch daily cost trends Helps identify if cost spike in an anamaly or a graduate increase # *Operational Validations* Test run with synthetic high volume logging to validate alarm triggers Verify no false positives when daily costs are with threshold |  | Aravind Raj | Onkar Mirajkar | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [46 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5fad0cf8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0gp97: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-17 05:55 | [13 empty] | 17/Sep/25 7:55 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Threshold Configuration -----Done Ability to set daily cost thresholds Alarm must be raised if daily costs exceed threshold Alerting Mechanism ----Done IF cost usage is above 2$ email will be trigeered | 17/Sep/25 7:56 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Dashboard view is pending | 19/Sep/25 8:18 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Dashboard is created and demo given to Yashwant. | 22/Sep/25 8:46 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have seen a short demo on friday itself, the dashboard and notification looks fine. | [23 empty] | 1772224 | AM20-164 | AirNavX ¦¦ Budget Management Configuration | Done | 2025-09-22 08:46
AM20-988 | Cleanup of AWS workload from Control tower | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1749509 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-19 20:30 | 2026-01-19 22:40 |  |  |  | 0 | As application owner I would like to cleanup redundant workloads from AWS through control tower so that we can achieve optimum utilization Acceptance Criteria: Cleanup is done with all redundant workloads/account deleted |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 14/Aug/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250814-064049.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139647 | 18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250818-060958.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1140604 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@557a9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0daor: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-14 06:41 | [13 empty] | 14/Aug/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have initiated mail with vodacom team, will do followup. !image-20250814-064049.png¦width=1272,height=492,alt="image-20250814-064049.png"! | 18/Aug/25 8:10 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250818-060958.png¦width=1277,height=470,alt="image-20250818-060958.png"! AWS account cleanup, followed by by account renaming is completed. | 21/Aug/25 2:25 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:26
AM20-989 | Trellix integration with PROS | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773956 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 18:39 | 2026-02-06 22:29 |  | 2025-10-30 08:26 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan PROS workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in PROS server * Trellix is able to access PROS account successfully and perform scanning |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 29/Oct/25 8:43 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-064238.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174346 | 29/Oct/25 8:53 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-065302.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174368 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bb75c16 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [65 empty] | YES | YES | 2025-09-24 07:35 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [12 empty] | 24/Sep/25 9:34 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;To get this US completed we have to complete Building up the EC2 instance and then only the Trellix agent reconfiguration will get done to scan the PROS workloads for any vulnerabilities, malware reporting. | 03/Oct/25 9:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* Pros connectivity issue is still going and its pending from there end. Also, the EC2 instance creation is yet not started so thatâ€™s why this US will go to the spill over to next sprint. | 17/Oct/25 11:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* The EC2 instance creation is just completed on the last day of the sprint. Thatâ€™s why the US was not able to complete in this sprint now after completion of the EC2 instances we can follow up with sinjun and get the update regarding the Trellix integration with PROS account. | 29/Oct/25 8:26 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation from Sinjun that the Trellix integration is done for PROS account servers. Have shared the email with sinjun. | 29/Oct/25 8:43 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-064238.png¦width=629,alt="image-20251029-064238.png"! Attaching his confirmation which i got over teams | 29/Oct/25 8:53 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-065302.png¦width=629,alt="image-20251029-065302.png"! | 30/Oct/25 8:26 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-30 08:26
AM20-990 | TM1 ¦¦ Replicated Test server creation | Done | 4 | Sprint 4 | 2025-04-28 | 2025-05-09 | Aravind Raj | High | 1648987 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 15:45 | 2026-02-01 19:26 |  |  |  | 0 | AS AWS expert, I would be provisioning TM1 test server as replica server to allow to perform initial validations *Acceptance Criteria*: * TM1 replica test server is successfully created * Internal team is able to access server successfully |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  |  | ;21/Apr/25 11:47 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;24/Apr/25 5:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1f9453f2 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:r | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-21 09:47 | [13 empty] | 21/Apr/25 11:46 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test Launch instance is launched with the help of launch template, able to telnet the TM1 server from bastion host. Waiting for TM1 local account credentials to login to server and verify the connectivity. | 24/Apr/25 5:45 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Server handover to application team yesterday, hence marking this to done status | 02/May/25 4:57 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;approved on Yashwantâ€™s behalf as he is facing Jira login issues | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-24 05:45
AM20-991 | Trellix integration with PROS | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773956 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 21:22 | 2026-01-12 22:16 |  | 2025-10-30 08:26 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan PROS workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in PROS server * Trellix is able to access PROS account successfully and perform scanning |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 29/Oct/25 8:43 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-064238.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174346 | 29/Oct/25 8:53 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-065302.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174368 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bb75c16 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [65 empty] | YES | YES | 2025-09-24 07:35 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [12 empty] | 24/Sep/25 9:34 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;To get this US completed we have to complete Building up the EC2 instance and then only the Trellix agent reconfiguration will get done to scan the PROS workloads for any vulnerabilities, malware reporting. | 03/Oct/25 9:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* Pros connectivity issue is still going and its pending from there end. Also, the EC2 instance creation is yet not started so thatâ€™s why this US will go to the spill over to next sprint. | 17/Oct/25 11:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* The EC2 instance creation is just completed on the last day of the sprint. Thatâ€™s why the US was not able to complete in this sprint now after completion of the EC2 instances we can follow up with sinjun and get the update regarding the Trellix integration with PROS account. | 29/Oct/25 8:26 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation from Sinjun that the Trellix integration is done for PROS account servers. Have shared the email with sinjun. | 29/Oct/25 8:43 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-064238.png¦width=629,alt="image-20251029-064238.png"! Attaching his confirmation which i got over teams | 29/Oct/25 8:53 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-065302.png¦width=629,alt="image-20251029-065302.png"! | 30/Oct/25 8:26 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-30 08:26
AM20-992 | Add-On ¦¦ WAF Rule creation for Voyager | To Do | 4 | None( Backlog) |  |  | Aravind Raj | Medium | 1842274 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 20:11 | 2026-02-02 20:44 |  |  |  | 0 | [20 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@37603ed1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5m3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-17 08:33
AM20-993 | Trellix integration with PROS | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773956 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 13:54 | 2026-01-29 17:03 |  | 2025-10-30 08:26 |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan PROS workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in PROS server * Trellix is able to access PROS account successfully and perform scanning |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 29/Oct/25 8:43 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-064238.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174346 | 29/Oct/25 8:53 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251029-065302.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174368 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bb75c16 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwrn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [65 empty] | YES | YES | 2025-09-24 07:35 | 3_*:*_1_*:*_576144_*¦*_10041_*:*_1_*:*_1652486380_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_3020953298 | [12 empty] | 24/Sep/25 9:34 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;To get this US completed we have to complete Building up the EC2 instance and then only the Trellix agent reconfiguration will get done to scan the PROS workloads for any vulnerabilities, malware reporting. | 03/Oct/25 9:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* Pros connectivity issue is still going and its pending from there end. Also, the EC2 instance creation is yet not started so thatâ€™s why this US will go to the spill over to next sprint. | 17/Oct/25 11:21 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;*Spill Over :* The EC2 instance creation is just completed on the last day of the sprint. Thatâ€™s why the US was not able to complete in this sprint now after completion of the EC2 instances we can follow up with sinjun and get the update regarding the Trellix integration with PROS account. | 29/Oct/25 8:26 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation from Sinjun that the Trellix integration is done for PROS account servers. Have shared the email with sinjun. | 29/Oct/25 8:43 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-064238.png¦width=629,alt="image-20251029-064238.png"! Attaching his confirmation which i got over teams | 29/Oct/25 8:53 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image-20251029-065302.png¦width=629,alt="image-20251029-065302.png"! | 30/Oct/25 8:26 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-30 08:26
AM20-994 | Bastion Host creation | Done | 4 | Sprint 3 | 2025-04-14 | 2025-04-25 | Aravind Raj | Medium | 1642039 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 16:53 | 2026-02-06 17:36 |  |  |  | 0 | As AWS expert, I would be creating two Bastion host by launching Private EC2 instance and AMI for preferred operating system and configure Security groups and apply Inbound and Outbound Rule * One for Internal Migration team (having internet access) * Another for Nexio and Customer access with RDS enabled Acceptance Criteria: * Bastion host provisioned successfully * access is provided to Nexio and business team by SSH client and connect to bastion host public IP adddress using private key |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;17/Apr/25 2:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | [5 empty] | 57600 | 14400 | 28800 | 0.5 | 57600 | 14400 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@327eec44 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i00syj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-15 16:18 | [13 empty] | 15/Apr/25 6:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Separate Network setup with internet gateway and pubic IP will be required for shared service account 864899875361, after network setup would create bastion server for internal team usage. [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] may need your help in setting up network. | 17/Apr/25 2:15 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;I have created a Bastion host in network account and have customized RDP port number from 3389 to *54925* for security measures. Â As we all know the jump server can be RDP accessed by two user in parallel, have created a user account named *VOIS_User01 and VOIS_User02* with Administrator privilege, password will be shared separately. Â Bastion Host Details; Â *Server name: Bastion-Host-Internal* *Server IP: 16.28.7.145(ElasticIP)* *Server RDP Port: 54925* | 17/Apr/25 2:16 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Bastion host for Nexio will be created after sometime. | [24 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-17 14:16
AM20-995 | Informatica ¦¦ Alert integration with ServiceNow | Done | 4 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1811851 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 21:56 | 2026-02-03 01:43 |  | 2025-10-31 09:35 |  | 0 | Acceptance Criteria: Perform validations post integration with ServiceNow ServiceNow team confirms that payload is reaching to servicenow and all the inputs including tags are reaching to Servicenow without any changes needed. formal Signoff from servicenow team needed |  | Aravind Raj | Diksha Koul | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [9 empty] | AM20-212 |  |  |  | 28/Oct/25 6:58 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251028-165729.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1174301 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@104a0167 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0k7b7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 |  | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | [65 empty] | YES | YES | 2025-10-23 13:19 | 3_*:*_2_*:*_171168391_*¦*_10041_*:*_1_*:*_943292851_*¦*_13940_*:*_2_*:*_25043 | [12 empty] | 23/Oct/25 3:19 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Service Now integration with cloud watch through IAM role were completed. And [~accountid:712020:54791a09-30fd-4ab7-8a1d-068b13e544d8] created all required ALARM for the key metrics for Informatica Prod and Dev account already and i have reviewed it. | 28/Oct/25 6:58 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have checked with Priyanka and service now team they are getting the alerts as per they requested. !image-20251028-165729.png¦width=629,alt="image-20251028-165729.png"! Attaching the email confirmation evidence for the reference. | 31/Oct/25 9:35 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Integration completed with servicenow and mail confirmation received hence accepting user story to be done | [27 empty] | Done | 2025-10-31 09:35
AM20-996 | Airnavx budget update | Done | 2 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1834954 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 20:34 | 2026-01-12 23:42 | 2025-11-21 08:29 | 2025-11-27 09:17 |  | 0 | I would like to update budget of airnavx as per the revised LLD since the configuration of EC2 were change and budget should reflect the cost accordingly |  | Diksha Koul | Yashwant Thakur |  |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;20/Nov/25 8:19 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;36600 | [5 empty] | 28800 | 0 | 36600 | 1.27 | 28800 | 0 | 36600 | [12 empty] | 19/Nov/25 8:44 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20251119-064353.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186120 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5ed5a68d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mwyr: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 06:49 | 3_*:*_1_*:*_171040030_*¦*_10041_*:*_1_*:*_426743082_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 8:49 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will check the updated LLD document and will update the new pricing as per the updated one. | 19/Nov/25 8:44 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the Updated LLD v1.4 and updated the pricing in the management payers account as per the new LLD. !image-20251119-064353.png¦width=629,alt="image-20251119-064353.png"! same has been implemented in the budget account. | 27/Nov/25 9:17 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:17
AM20-997 | MQ-PROD ¦¦Setup Subnet, NACL and SG Creation and Validation | Done | 3 | Sprint 16 | 2025-10-13 | 2025-10-24 | Yashwant Thakur | Medium | 1794109 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-18 21:23 | 2026-01-19 00:18 |  | 2025-10-31 09:34 |  | 0 | As AWS network expert I would like to setup the security group and NACL for MQ so that access for MQ allow secure access to allow communication with its services while ensuring access control and security compliance Acceptance Criteria A new security group is created with meaningful name and description Inbound rule allow only the required ports for MQ or related service communication inbound access is restricted to specific IP addresses, security group or CIDR Outbound rules are configured to allow only required destinations Security group does not allow unrestricted access (SSH/RDP) unless through a bastion Security group is attached to correct EC2 instance, ELB etc no overlapping or conflicting rules are defined that could result in unintended access All traffic is logged using VPC flow logs and integrated to centralized logging Seperate custom NACL are created for public and private subnets with appropriate naming conventions NACL is correctly associated with target subnets No NACL rule allows unrestricted traffic unless required NACL rules are ordered correctly by rule number ingress and egress requirements are met based on the application tier Tags are applied to the Security Group |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 43200 | 43200 |  | 0 | 43200 | 43200 | [13 empty] | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090000.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175254 | 30/Oct/25 11:00 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-090022.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175253 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@680e7164 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0i6ob: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 17 | [97 empty] | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [65 empty] | YES | YES | 2025-10-17 09:19 | 3_*:*_1_*:*_240781693_*¦*_10041_*:*_1_*:*_857469443_*¦*_13940_*:*_1_*:*_0_*¦*_10024_*:*_1_*:*_1496467792 | [12 empty] | 17/Oct/25 11:19 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over comment - Blocked because of pending information from Amadeus; post which this story will be taken up | 27/Oct/25 4:05 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Started working on it. | 30/Oct/25 11:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;According to requirement i have done platform setup. Subnets: ¦Subnet address¦Range of addresses¦Useable IPs¦Hosts¦Divide¦Used Status¦App Name¦ ¦10.40.0.224/28¦10.40.0.224 - 10.40.0.239¦10.40.0.225 - 10.40.0.238¦14¦Divide¦Done¦MQ PROD PRIVATE¦ ¦10.40.0.240/28¦10.40.0.240 - 10.40.0.255¦10.40.0.241 - 10.40.0.254¦14¦Divide¦Done¦MQ PROD PUBLIC¦ ¦10.40.1.32/28¦10.40.1.32 - 10.40.1.47¦10.40.1.33 - 10.40.1.46¦14¦Divide¦Done¦MQ PROD DR¦ ¦10.40.1.48/28¦10.40.1.48 - 10.40.1.63¦10.40.1.49 - 10.40.1.62¦14¦Divide¦Done¦MQ PROD DR¦ Subnets screen: !image-20251030-090022.png¦width=597,alt="image-20251030-090022.png"! EC2 connectivity screen: !image-20251030-090000.png¦width=597,alt="image-20251030-090000.png"! | 31/Oct/25 9:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Though MQ migration is put on hold however since the objective and acceptance criteria is met, approving the User story to close | [26 empty] | Done | 2025-10-31 09:34
AM20-998 | Budget management - AWS Cost Control on application | In Progress | 6 | Sprint 22 | 2026-01-05 | 2026-01-16 | Diksha Koul | Medium | 1885694 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 13:12 | 2026-01-13 16:14 | 2026-01-08 08:32 |  |  | 0 | As Product Owner, I would like to address frequent spikes on budget of AWS accounts so that we can manage cost within the forecasted cost. Acceptance Criteria: * Identify the root cost of cost spiked in EKS cluster, Audit account, SAA_Airnavx and CMS backend(Prod) * resolve the root cause to reduce the associated cost |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [5 empty] | ;08/Jan/26 7:38 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | [5 empty] | 86400 | 57600 | 28800 | 0.33 | 86400 | 57600 | 28800 | [12 empty] | 08/Jan/26 10:57 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-085716.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197716 | 08/Jan/26 11:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-093536.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197744 | 08/Jan/26 12:15 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-101131.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197769 | 08/Jan/26 12:15 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-101412.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197770 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3731daff | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptcb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-06 11:56 | [13 empty] | 06/Jan/26 1:55 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started working on the root cause and cost spike for AirnavX | 08/Jan/26 7:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have checked the costing spike for all accounts its showing that EC2 instances are consuming more cost. Now checking the cloud watch logs for them. | 08/Jan/26 10:57 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I checked in the *AirnavX Account* there are snapshots which has been created for all EC2 instances including the DR instance and also the backup is enabled. Attaching the screenshot below: !image-20260108-085716.png¦width=641,alt="image-20260108-085716.png"! This is also one reason that the costing is spiking. For *Audit Account* also i checked that the SNS and Cloudwatch is consuming lot of cost spike due to which the budget costing is spiked. Attaching the screenshot: !image-20260108-093536.png¦width=613,alt="image-20260108-093536.png"! For *CMS_Backend_Prod* the t3.xlarge instances that is EKS nodes is cost consuming as you can see below Attached Screenshot below showing nodes spike for 4 months. !image-20260108-101131.png¦width=496,alt="image-20260108-101131.png"! Also, below screenshot showing instance type size for EC2 and EKS nodes and there costing for 4 months. !image-20260108-101412.png¦width=583,alt="image-20260108-101412.png"! | [27 empty] | In Progress | 2026-01-06 12:51
AM20-999 | Transit Gateway setup for Dev environment | Done | 6 | Sprint 9 | 2025-07-07 | 2025-07-18 | Aravind Raj | High | 1702418 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 17:13 | 2026-01-17 19:48 |  |  |  | 0 | As Network Expert, I would be able to setup Transit network gateway for Dev environment Acceptance Criteria: Transit Gateway is provisioned successfully in Dev environment. |  | Aravind Raj | Satya Varanasi |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [13 empty] | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132834.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121470 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-132924.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121472 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133228.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121473 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133337.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121469 | 03/Jul/25 3:34 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250703-133439.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1121471 | [13 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67c2563b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i095nv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-01 16:49 | [13 empty] | 01/Jul/25 6:49 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;There is no Preprod env for 20+ app migration list, hence we are not setting up Preprod TG attachment, in case needed near future we will setup according to requirement. In this sprint we will setup TG attach for Dev env. | 03/Jul/25 3:34 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Common TG Attach has be setup on shared VPC dev Account and tested internet connectivity via informatica DEV subnet. !image-20250703-132834.png¦width=1306,height=662,alt="image-20250703-132834.png"! !image-20250703-132924.png¦width=1204,height=668,alt="image-20250703-132924.png"! TG-Attach subnets: !image-20250703-133228.png¦width=1243,height=475,alt="image-20250703-133228.png"! TG attachment details. !image-20250703-133337.png¦width=1189,height=448,alt="image-20250703-133337.png"! Subnet associations !image-20250703-133439.png¦width=1215,height=611,alt="image-20250703-133439.png"! | 04/Jul/25 12:05 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;reviewed, test server is working with internet. | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-07-04 12:05
AM20-1000 | ServiceNow ¦¦ Secure Integration with Cloud ServiceNow | Done | 8 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650451 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 12:41 | 2026-02-01 15:37 |  |  |  | 0 | As a AWS Cloud architect, I want the Amazon SNS to securely connect to the on-prem ServiceNow instance so that error alerts can be logged as incidents. Acceptance Criteria: * ServiceNow API credentials are stored securely in AWS Secrets manager * Network connectivity is verified via NAT gateway/VPN * HTTP request to ServiceNow are authenticated and secure |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  | ;13/May/25 11:38 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;24/Jun/25 1:30 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | ;10/Jul/25 9:30 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;57600 |  |  |  | 115200 | 0 | 115200 | 1 | 115200 | 0 | 115200 | [12 empty] | 15/May/25 11:57 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;Ashton response on delay for SNow endpoint.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100994 | 22/May/25 9:56 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;ServiceNow API endpoints provided by Ashton.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103907 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5538b454 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-02 08:59 | [13 empty] | 02/May/25 10:58 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Current State: AWS Level configuration of ServiceNow with Lambda Function and SNS is complete. Next Steps: # Setup a call with ServiceNow Cloud team to do the POC # Setup SNS to Push notifications to ServiceNow # Setup required matrices # Validate the functionality. # Get Sign-off on successful Setup | 15/May/25 11:58 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Delay from ServiceNow app owner ( Ashton) in providing the ServiceNow API endpoint, conversations comms screenshot attached. Potential spill over [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] | 20/May/25 10:18 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;¦Setup on AWS in complete. API endpoint is to be provided by Ashton Steyn. Once the end point is added to SNS, we would be able to test if the notification is received correctly in ServiceNow Cloud. Next Step would be to showcase this entire setup to Denise and Bhavesh and get Sign off. Action Points API EndPoint pending on Ashton Steyn. Need Availability of Denise and Bhavesh to showcase the POC and get SignOff on the POC¦ | 22/May/25 9:57 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Screenshot of ServiceNow API endpoint provided by Ashton attached | 02/Jun/25 8:22 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;API Provided by Ashton, could not be configured in SNS Topic. We are getting error â€œURL is not valid, INVALIDâ€ We are waiting for an update from Ashton on how to resolve this error. | 19/Jun/25 7:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Call planned with ServiceNow team on 19th June to provide walkthrough and clarify open queries, needed to proceed with next steps [~accountid:712020:8b1a5d94-1767-4111-80eb-b21856098c47] [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] | 24/Jun/25 1:30 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Setup Completed POC Completed End Point for Prod to be provided by service now team (Feroz). | 10/Jul/25 9:30 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Setup >> Completed POC >> Completed End Point for Prod to be provided by service now team (Feroz) >> Completed Moving to review for closure | 11/Jul/25 1:46 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [18 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-07-11 13:46
AM20-1001 | TM1 ¦¦ Firewall Rule creation | Done | 2 | Sprint 3 | 2025-04-14 | 2025-04-25 | Sankalp Rai | Medium | 1644189 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 19:06 | 2026-01-11 19:48 |  |  |  | 0 | As AWS expert I will be creating firewall rules for TM1 application so that security compliance can be met Acceptance Criteria: * Firewall rules are created and sent to Vodacom implementation |  | Sankalp Rai | [5 empty] | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [5 empty] | ;17/Apr/25 11:05 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b493d0d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-14 07:44 | [13 empty] | 14/Apr/25 9:44 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Call Pending on Firewall placement. Call scheduled for 15th April 2025 Vodacom: Leigh to manage the Firewall and create Rules on Firewall VOIS: Raise request for Firewall Rule in the provided Format | 17/Apr/25 11:06 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;AWS Network Firewall is for monitoring internet traffic coming into AWS and going out of AWS. TM1 does not require any connectivity over internet. Connectivity to TerraData is being done internally Some of the VMs under TerraData right now are being moved to Shared VPC. SAP Rise connectivity is not required. Since TM1 does not require internet connectivity, there is no need to create AWS Network Firewall rules for TM1 Moving to in review for closure | [25 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-21 09:03
AM20-1002 | Documentation on Budget Management | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1747516 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 13:51 | 2026-01-25 15:19 |  |  |  | 0 | As Product Owner, I would like to create a detailed documentation on Budget management solution Acceptance Criteria: Document should consist of below sections with detailed description. * IAM roles /groups and policy created for it * Details of any Lamda functions are configured * process to add users to the group to allow edit/view/remove privileges * Dashboard and configurations details * Process to change, update budget allocated, notification iteration etc. * Details of naming convention and tagging as applicable * Architectural diagram as applicable |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [13 empty] | 22/Aug/25 12:23 PM;9e4636e8-9dfc-4a33-901b-fcd75015926a;AWS_Budget_Management.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1143135 | 14/Aug/25 7:01 AM;9e4636e8-9dfc-4a33-901b-fcd75015926a;Budget Documentation (24287a92-0ff3-4da3-9f2c-3378740b4c97).docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1139610 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@58ed7f61 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0d2rv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-14 05:03 | [13 empty] | 14/Aug/25 7:02 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Document has been attached. Please verify [~accountid:712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa] | 22/Aug/25 12:23 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;[^AWS_Budget_Management.docx] AWS Budget Document attached | 25/Aug/25 6:34 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-25 06:34
AM20-1003 | Terraform Development ¦¦ Define CloudWatch Agent config and Automate Agent Start via Terraform | Done | 20 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1661298 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-11 16:35 | 2026-01-11 19:10 |  |  |  | 0 | As Devops Engineer, I would like to define the CloudWatch Agentâ€™s configuration and Automate Cloud Watch Agent start using Terraform so that the metrics and logs it collects are consistent across environments Acceptance Criteria: * Terraform manages the agent config JSON file as a template * The config files includes, CPU, Memory, disk and Network metrics and application/system log files paths. * The file is stored locally or pushed to EC2 during provisioning via user_data * Terraform - provisioned EC2 instances start the CloudWatch agent on boot * The agent fetches the config file and start sending data to CloudWatch * Verification - Metrics and logs appear in CloudWatch console post launch |  | Aravind Raj | Faisal Sayed | Harsh Chandra | Yashwant Thakur |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [8 empty] | 288000 | 288000 |  | 0 | 288000 | 288000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7aab33b8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4h: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 7 | Sprint 8 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-11 06:40 | [13 empty] | 11/Jun/25 8:39 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;* The Terraform script for configuring and starting the CloudWatch agent is ready for both Linux and Windows instances. * Linux automation is working as expected. * Faced issues with Windows agent installation during EC2 provisioning. * Initial approach used user data to download and install the CloudWatch agent. * Encountered failure due to network not being ready at the time of user data execution. * Attempted to resolve this with a 60-second sleep delay, but it was unsuccessful. * New approach identified: using SSM documents to automate agent installation post-boot. * Will implement this alternative and move the changes to code review. * A meeting will be scheduled following successful implementation. | 16/Jun/25 10:03 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# *Used SSM Documents to Automate Agent Installation*Â * We leveraged *AWS SSM Run Command* documents instead of manual scripts or hardcoding logic.Â * Specifically, we used:Â * {{AWS-ConfigureAWSPackage}} to *install the CloudWatch Agent*Â * {{AmazonCloudWatch-ManageAgent}} to *configure and start the agent* using a *Parameter Store JSON config* named {{/Windows_Monitor_CW}}.Â Â *ðŸ”¹ 2. Embedded SSM Associations in Terraform*Â * Inside our *main EC2 Terraform project*, we embedded two {{aws_ssm_association}} resources:Â * *install_cwagent_windows* â€“ installs CloudWatch agentÂ * *configure_cwagent_windows* â€“ tells the agent to pull its config from {{/Windows_Monitor_CW}} in SSM Parameter Store and start itÂ * Both associations *target EC2 instances by tag*: {{CWAgent = EnabledÂ }} * The EC2 instances were pre-tagged via Terraform to ensure automatic targetingÂ Â *ðŸ”¹ 3. Created a Third Association to Force Re-fetch Config*Â * In some cases, the agent might need to re-fetch its config after the EC2 instance is up and the services are stable.Â * So we created a *third SSM association*: {{force_fetch_start_agentÂ }} * Uses {{AWS-RunPowerShellScript}} to run:Â {{& "C:\Program Files\Amazon\AmazonCloudWatchAgent\amazon-cloudwatch-agent-ctl.ps1" -a fetch-config -m ec2 -c ssm:/Windows_Monitor_CW -sÂ }} Â * This *manually triggers the fetch* of the config from SSM Parameter Store and starts the agent again if neededÂ Â *ðŸ”¹ 4. Split This Trigger into a Separate Terraform Directory*Â * To keep your deployment clean and *modular*, we:Â * Created a new folder: {{terraform/cwagent-trigger/Â }} * Placed only the {{force_fetch_start_agent}} logic in this moduleÂ * Why?Â * This allows you to *run it manually or conditionally* after core EC2 and SSM setups are completeÂ * Ensures *clean execution ordering* and better control in CI/CDÂ * Prevents early execution before the agent is even installedÂ Â *ðŸ”¹ 5. Designed for Platform-Specific Control*Â * Logic is gated with:Â {{count = var.platform == "windows" && var.enable_windows_ssm_association ? 1 : 0Â }} Â * Ensures this entire operation is *executed only for Windows instances*, as Linux would follow a different path.Â | 24/Jun/25 6:55 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;cloud watch agent installation is done using terraform script, have enabled only memory and disk utilization as of now. | 29/Jun/25 8:14 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-06-29 20:15
AM20-1004 | Other resources remediation - Config, GuardDuty, EC2, RDS and etc | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818710 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-24 18:56 | 2026-01-24 21:08 |  |  |  | 0 | Remediate dependencies services. |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6ff5f38c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzxn: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 28/Oct/25 11:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;have remediated dependencies services failed controls | [26 empty] | 1817984 | AM20-225 | Security controls remediation - Informatica and PROS Aws accounts | Done | 2025-10-28 11:21
AM20-1005 | PROS ¦¦ Monitoring and Alerting Servers post migration | Done | 4 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773954 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 18:00 | 2026-01-12 20:10 |  | 2025-10-31 17:21 |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if PROS service is stopped |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@37ad6335 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqz: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [96 empty] | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 |  | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [65 empty] | YES | YES | 2025-10-31 12:27 | 10060_*:*_1_*:*_642216_*¦*_3_*:*_1_*:*_13342467_*¦*_10041_*:*_1_*:*_2168098403_*¦*_13940_*:*_2_*:*_126381_*¦*_10024_*:*_1_*:*_2685816843 | [12 empty] | 31/Oct/25 2:26 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Post Migration: I have installed the SSM Agent for all the PROS prod instances. Configured CloudWatch Agent. Created Systems Manager Parameters for the CloudWatch Agent to fetch the config. Custom Metrics part completed. Monitoring done. Alerts generated for the metrics. | 31/Oct/25 5:20 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-10-31 17:21
AM20-1006 | Front End (SMS notification)- Business Level Improvements | To Do | 4 | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1885790 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-26 21:04 | 2026-01-26 21:53 | 2026-01-06 08:25 |  |  | 0 | As Product Owner I would like to take business input and configure the SMS accordingly so that informative SMS notification reached out to operation and support group. *Acceptance Criteria*: * SMS notification configured successfully as Business input |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@55581f2c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptv7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-08 09:34 | [13 empty] | 08/Jan/26 11:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reached out to Hoosen and Javier to enquire their availability for resuming the discussions, awaiting their response. | [29 empty] | To Do | 2025-12-30 08:45
AM20-1007 | POC for replacing IBM MQ with AWS MQ | To Do | 0 | None( Backlog) |  |  |  | Medium | 1795168 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 14:42 | 2026-01-25 15:38 |  |  |  | 0 | [57 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@63afd04c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02akq: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-09-30 17:36
AM20-1008 | Patch Management ¦¦ Dashboard Enhancement | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1746156 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 20:43 | 2026-01-15 22:07 |  |  |  | 0 | As Product manager compliance dashboard needs to be enhance and should covered details of patch file Acceptance Criteria: Compliance dashboard need to patch details and account details |  | Faisal Sayed | Yashwant Thakur |  |  |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 57600 |  | 0 | 28800 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4159e3f0 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0cz63: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-18 20:35 | [13 empty] | 18/Aug/25 10:34 PM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Update for Patch Manager Monitoring, in the compliance bucket there are 3 folders created after creating the resource data sync but not for the target acc we need. i have changed certain policies and also added some permissions both in security as well as dev acc. I am waiting for the data to pop up and also i can trigger data collection forcefully via aws cloudshell command but i do not have access i have intimated Aravind for permission addition. and the data that is being collected is basically json and that is the format that we need for it to be visualized in cloudwatch. | 25/Aug/25 8:52 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;spillover: the data sync which has been created in the management acc theoretically should be able to fetch the summaries from target account and sync that data in the s3 bucket in central account. the steps that were tried to force a sync were: {code:json}Check if the Instance is Managed by Systems Manager Check Current Associations Check Current Inventory Data Create the Inventory Association Verify Association Creation Check Association Status Monitor Association Execution Check for Updated Inventory Data{code} All of these were done and created an association manually for it to be populated into s3 bucket yet it did not work. the permission policies are provided yet the target account data is not being synced. the issue was that resource data sync must be created in each of the target account which was earlier thought as not needed. have created ressource data sync and waiting for the data to be populated. | 28/Aug/25 8:34 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Spillover Revised Comment: I was troubleshooting the resource data sync that i created since theoretically, resource data sync in the management account was enough. After rigorous attempts to fix the issue and trying to find out the workarounds they all failed. At the end of the week, close to sprint closure I found the solution and applied it and the solution worked. Hence, the delay and also for the data to populate into the intended bucket it sometime takes 10-12 hrs. | 03/Sep/25 8:35 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;# The Resource Data Sync has been troubleshoot correctly and is working as intended. # Lambda function has been created in backend-dev account so that it can brand all the instances as non-compliant initially. # EventBridge has been configured as such when any new instance is provisioned it shall be flagged as non-compliant using the lambda function mentioned in point no.2. # The data in S3 is being used to project it to CloudWatch and that is being do using a Lambda function which will create metrics from the data in S3. # CloudWatch Dashboard is created such that it will have visual data segregated acc to the Acc Ids. (which was requirement by Bhavish). | 08/Sep/25 6:35 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;need demo | 08/Sep/25 8:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: The story was completed sufficing all the acceptance criteria. Demo was not done due to unavailability, hence scheduling the demo for 9/9/2025 considering everyoneâ€™s availability. | 11/Sep/25 9:12 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;Demo was provided. The methodology and implementation was agreed upon and approved. There was an ask to involve another accounts, in order to check the workability. The accounts addition was done successfully and the data is presented on the custom dashboard as well. | 19/Sep/25 11:20 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [19 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-19 11:20
AM20-1009 | Informatica ¦¦ connectivity with Sales force, SAP Raise and EDW with test server | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | Medium | 1751445 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-01 20:22 | 2026-02-01 23:24 |  |  |  | 0 | As product Owner I would like to establish seamless connectivity between Informatica server and saleforce/Terradata so that the functinality does not break Acceptance Criteria: Informatica server connectivity established successfully with both Salesforce and Terradata TGW attachments, route tables and propogation allows reachability from Informatica to Salesforce and Terraform CIDR only Pripary path (DX or VPN) with secondary path tested, failover keeps sessions with degraded SLO Path MTU validated without fragmentation affection FTP data channels Passive FTP is enforced in AWS client Each FTP server exposes a fixed passive port range and publish it on the client Security groups: egress from AWS app to on-prem TCP21 the agreed passive range; return traffic allowed on-prem firewall allows the Aws static egress IP for TCP 21 and passive range FTP ALG/instapection behavour documented and validated Server authentication: username/password or TLS client auth are stored in secret manager no reliance on public IP, all traffic stays private via TGW Name resolution works both ways AWS can resolve slaesforce.corp and terradata.corp via resolver outbound rules, negative lookups dont hit public DNS TGW flow logs show accepted flows for TCP 21 and passive port Cloudwatch alarm on tunnel/BGP state, connection failures, repeated 4XX/%XX FTP responses, transfer timeouts Application log capture: server filename, size, checksum, duration, success/fail code, logs centralized Concurrency limited tuned so both servers can be hit in parallel without timeouts SLO defined (ex: sustainable throughput) and documented Checksum validated after transfer VPN/DX failover tested mid-transfer client resumes without manual intervention drift detection enabled |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@5cf8baca | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ddx3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | Sprint 14 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-12 06:25 | [13 empty] | 12/Aug/25 8:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Relevant flows has been added under application flows. Once implementation done i will work further. | 25/Aug/25 8:55 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Spill over Reason: Still comms under approval and implementation so this need to action after comms implementation. | 08/Sep/25 10:00 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;EDW side issue got fixed and working, right now SAP raise Sita compass side need to fix. I have scheduled troubleshooting call with relevant stake holder towards fixing. Still connectivity is not resolved, so i am not closed this story and it is moving to current sprint. | 12/Sep/25 8:10 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SAP Raise side SR has been logged, it will be implemented today. | 19/Sep/25 2:47 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SAP rise team has been configured NAC,SG and Routing but still connectivity issue persists, while checking traceroute, the request moving out to SAP Rise gateway but not troughing to shared VPC & vice versa. Further validation there is No routes advertised from DX side, engaged SAP team asking how SAP rise will be connected but they are not sure. Finally we have identified SAP rise is connecting via Direct connect, this was analyzed with the help of current working connection. | 19/Sep/25 2:49 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Notified network team to advertise complete shared VPC Prod and Dev vpc ranges to avoid future issues. 10.40.0.0/18 and 10.42.0.0/21. | 19/Sep/25 2:50 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Network team has bee advertise the range to SAP rise direct connect, after advertise the connectivity has been fixed. | 19/Sep/25 2:51 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;ticket information: Ticket ID 1163452562 & 1163792032 AWS Connectivity - FIREWALL RULES REQUIRED FOR CUSTOMER INFORMATICA & RISE COMMUNICATION | 19/Sep/25 2:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;I am resolving the story as connectivity has been fixed. | [21 empty] | Done | 2025-09-22 08:49
AM20-1010 | Security and compliance implementation on PROS account | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Aravind Raj | High | 1622524 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 16:08 | 2026-01-31 20:06 |  |  |  | 0 | As AWS expert I would be able to implement Security and compliance from NIST,CIS and AWSFSBP I would be implementing below security and Industrial implementation on PROS account to ensure that security compliance has been completed. * CIS,NIST and AWSFSBP policy implementation *Acceptance Criteria*: * CIS policy implementation successfully done in PROS DEV account * NIST policy implementation successfully done in PROS DEV account * AWSFSBP policy implementation successfully done in PROS DEV account |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Mar/25 2:18 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;14400 |  |  |  |  | 43200 | 0 | 43200 | 1 | 43200 | 0 | 43200 | [8 empty] | AM20-19 | AM20-17 |  |  | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20250317-060821.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1079558 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a53b25a | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxson: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-13 06:02 | [13 empty] | 13/Mar/25 8:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on the controls with the dependency services for the security frameworks. | 14/Mar/25 2:21 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;The controls were implemented in Pros DEV account, Pros Production account will be picked up in separate user story. | 17/Mar/25 8:08 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;!image-20250317-060821.png¦width=1277,height=642,alt="image-20250317-060821.png"! | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-03-14 14:22
AM20-1011 | Citrix ¦¦ LLD creation | Done | 6 | Sprint 4 | 2025-04-28 | 2025-05-09 | Sankalp Rai | High | 1619785 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 18:37 | 2026-01-13 20:45 |  |  |  | 0 | As AWS architect, I would create LLD for Citrix application migration *Acceptance Criteria*: * Low level design documentation including proposed architecture completed |  | Harsh Chandra | Sankalp Rai | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 28800 |  | 0 | 86400 | 28800 | [9 empty] | AM20-23 | [21 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b60bc29 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/4 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 4 | [60 empty] | 0 |  | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02775: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 4 | 0 |  | 1 |  | 1 | [70 empty] | YES | YES | 2025-05-20 08:23 | [13 empty] | 20/May/25 10:22 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;¦Needs discussion with customer on approach to be taken. We can either move with Greenfield Deployment or Migrate the exiting setup to AWS. The call was scheduled for 12th May, however that call did not as Nilesh and Team were not available. Follow-up mail for rescheduling the call has been sent. No Update from customer. We will be able to provide start date and end only after we finalize the approach.Â ¦ ¦ ¦ | 02/Jun/25 8:28 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Need to setup call with Nilesh on Citrix licences on cloud and on the approach for migration to AWS. | 02/Jun/25 8:29 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Moving to Blocked | 13/Jun/25 12:51 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;New business case needed, hence marking this as closed. | [23 empty] | 1582124 | FCBEM-122 | Application Assessments | Done | 2025-06-13 12:51
AM20-1012 | Create Fortinet Firewall Implementation SOW and client Proposal Document. | Done | 0 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1850377 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 19:07 | 2026-01-20 21:10 | 2025-11-21 10:34 | 2025-11-28 14:00 |  | 0 | As Product owner I would like to create SOW for Fortinet firewall implementation so that Stakeholders can review and take a call whether to implement it. Acceptance Criteria: The SOW document should consist of below topic. * Complete SOW Structure * Deployment Phases * Proposed Architecture * License and Billing * Key Deliverables * RACI * Assumptions and Risks |  | Harsh Chandra | Yashwant Thakur |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [29 empty] | 21/Nov/25 8:15 AM;20360e68-8649-477a-ba70-b71dd6b2aef5;SAA-FortiGateFirewall_Implementation.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1187538 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7e936038 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0nmmb: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_43219_*¦*_10041_*:*_1_*:*_63823497_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_43219_*¦*_10041_*:*_1_*:*_63823497_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_43219_*¦*_10041_*:*_1_*:*_63823497_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_43219_*¦*_10041_*:*_1_*:*_63823497_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-21 06:17 | 3_*:*_1_*:*_43219_*¦*_10041_*:*_1_*:*_63823497_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 21/Nov/25 8:16 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Attaching document on Sankalpâ€™s behalf because his Jira is not working. Moving this to review | 28/Nov/25 2:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2025-11-28 14:00
AM20-1013 | Servicenow Payload severity updates for Infra alarms | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Aravind Raj | Medium | 1835021 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-25 19:48 | 2026-01-25 20:00 | 2025-11-21 10:34 |  |  | 0 | Modify Lambda function to allow a parameter severity to the service now workload. |  | Aravind Raj | Harsh Chandra | Shreyash Talwekar |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 |  |  |  | ;19/Nov/25 2:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;57600 | [5 empty] | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [12 empty] | 19/Nov/25 1:50 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251119-115035.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186444 | 19/Nov/25 1:50 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251119-115039.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186445 | 19/Nov/25 1:51 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251119-115135.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186450 | 19/Nov/25 2:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251119-120126.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1186469 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@501b8627 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxab: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-19 11:51 | [13 empty] | 19/Nov/25 1:50 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have updated the lambda function to allow the severity parameter and have verified the payload getting via an email. | 19/Nov/25 1:50 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Production payload !image-20251119-115039.png¦width=423,alt="image-20251119-115039.png"! | 19/Nov/25 1:51 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Dev Payload !image-20251119-115135.png¦width=423,alt="image-20251119-115135.png"! | 19/Nov/25 2:01 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;QA payload !image-20251119-120126.png¦width=423,alt="image-20251119-120126.png"! | [23 empty] | 1832856 | AM20-264 | Update ServiceNow Payloads with severity | Done | 2025-11-19 14:02
AM20-1014 | TM1 ¦¦ Firewall Rule creation | Done | 2 | Sprint 3 | 2025-04-14 | 2025-04-25 | Sankalp Rai | Medium | 1644189 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 20:35 | 2026-01-31 22:04 |  |  |  | 0 | As AWS expert I will be creating firewall rules for TM1 application so that security compliance can be met Acceptance Criteria: * Firewall rules are created and sent to Vodacom implementation |  | Sankalp Rai | [5 empty] | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | [5 empty] | ;17/Apr/25 11:05 AM;f7717bb1-ea03-4bc4-a865-c48b056055a5;28800 | [5 empty] | 28800 | 0 | 28800 | 1 | 28800 | 0 | 28800 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2b493d0d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i014kb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-14 07:44 | [13 empty] | 14/Apr/25 9:44 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Call Pending on Firewall placement. Call scheduled for 15th April 2025 Vodacom: Leigh to manage the Firewall and create Rules on Firewall VOIS: Raise request for Firewall Rule in the provided Format | 17/Apr/25 11:06 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;AWS Network Firewall is for monitoring internet traffic coming into AWS and going out of AWS. TM1 does not require any connectivity over internet. Connectivity to TerraData is being done internally Some of the VMs under TerraData right now are being moved to Shared VPC. SAP Rise connectivity is not required. Since TM1 does not require internet connectivity, there is no need to create AWS Network Firewall rules for TM1 Moving to in review for closure | [25 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-04-21 09:03
AM20-1015 | Assessment on CMS Frontend SMS implementation | Done | 8 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Highest | 1842250 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-21 16:58 | 2026-01-21 19:11 | 2025-11-28 11:16 | 2025-11-28 14:00 |  | 0 | As a cloud platform application owner I want to perform a detailed assessment for enable SMS notification in the CMS frontend application hosted in AWS so that I can determine best approach, integration method, cost impact, security requirement and technical feasibility before implementation Acceptance Criteria: All use cases for SMS notification are documented SLA, frequency and criticality of SMS delivered and captured User flow diagrams for each SMS scenario prepared Assessment must identify How front will invoke API Required IAM permission documented for access for SMS publishing Consideration for rate limiting and Compliance requirements Risk, Assumption and dependencies |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Understanding alarm implementation and getting AWS frontend access from Leigh.;28/Nov/25 10:33 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | Worked on implementing SMS notification on frontend dev account;28/Nov/25 10:33 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | SMS implementation is working, worked on debugging minor issues and updating timeout of Lambda function to enable sending SMS to multiple numbers.;28/Nov/25 10:34 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 |  |  |  | 115200 | 28800 | 86400 | 0.75 | 115200 | 28800 | 86400 | [12 empty] | 28/Nov/25 1:49 PM;17cb9418-1850-4923-932b-7098ec51b6bb;SMS_frontend_alerts.docx;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190540 | 28/Nov/25 10:36 AM;17cb9418-1850-4923-932b-7098ec51b6bb;image-20251128-083619.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1190436 | [16 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@67436dd5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0n5jf: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-25 08:56 | 3_*:*_1_*:*_184559206_*¦*_10041_*:*_1_*:*_778611547_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 25/Nov/25 10:56 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Created a Whitepage access request to enable access for frontend AWS accounts, reached out to Leigh with ticket details. | 26/Nov/25 8:54 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Access request is approved, awaiting access enabling from Leigh. | 27/Nov/25 8:21 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Got the access from Leigh, worked on provisioning AWS resources (Lambda , eventbridge rule , dynamodb table) for alert implementation, need to get number from Hoosen for sending sms. | 28/Nov/25 10:36 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Hoosen confirmed he got SMS for sample alarm in frontend dev . !image-20251128-083619.png¦width=281,alt="image-20251128-083619.png"! | 28/Nov/25 1:49 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;[^SMS_frontend_alerts.docx] Please find attached document for SMS implementation. | 28/Nov/25 2:00 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [24 empty] | Done | 2025-11-28 14:00
AM20-1016 | Nexio AV ¦¦ establish internet connectivity via TGW | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650868 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-31 21:11 | 2026-01-31 21:23 |  |  |  | 0 | As Network expert I would establish internet connectivity by enabling connection via NAT Gateway and TGW *Acceptance Criteria*: Internet connectivity is established successfully via NAT Gateway and TGW |  | Harsh Chandra | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  | ;02/May/25 12:35 PM;f7717bb1-ea03-4bc4-a865-c48b056055a5;14400 | [5 empty] | 14400 | 0 | 14400 | 1 | 14400 | 0 | 14400 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1e57c316 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:x | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:43 | [13 empty] | 29/Apr/25 7:43 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;internet connectivity has ben setup, sending for review | 02/May/25 12:37 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Tested through SSM {quote}Ping to 8.8.8.8 working Tracert to 8.8.8.8 working{quote} Forwarding for PO Approval | 18/May/25 2:38 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [24 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-05-18 14:38
AM20-1017 | Budget management - AWS Cost Control on application | In Progress | 6 | Sprint 22 | 2026-01-05 | 2026-01-16 | Diksha Koul | Medium | 1885694 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 15:04 | 2026-02-02 17:45 | 2026-01-08 08:32 |  |  | 0 | As Product Owner, I would like to address frequent spikes on budget of AWS accounts so that we can manage cost within the forecasted cost. Acceptance Criteria: * Identify the root cost of cost spiked in EKS cluster, Audit account, SAA_Airnavx and CMS backend(Prod) * resolve the root cause to reduce the associated cost |  | Diksha Koul | [5 empty] | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | [5 empty] | ;08/Jan/26 7:38 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;28800 | [5 empty] | 86400 | 57600 | 28800 | 0.33 | 86400 | 57600 | 28800 | [12 empty] | 08/Jan/26 10:57 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-085716.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197716 | 08/Jan/26 11:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-093536.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197744 | 08/Jan/26 12:15 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-101131.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197769 | 08/Jan/26 12:15 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image-20260108-101412.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1197770 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3731daff | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptcb: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-06 11:56 | [13 empty] | 06/Jan/26 1:55 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have started working on the root cause and cost spike for AirnavX | 08/Jan/26 7:39 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have checked the costing spike for all accounts its showing that EC2 instances are consuming more cost. Now checking the cloud watch logs for them. | 08/Jan/26 10:57 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;I checked in the *AirnavX Account* there are snapshots which has been created for all EC2 instances including the DR instance and also the backup is enabled. Attaching the screenshot below: !image-20260108-085716.png¦width=641,alt="image-20260108-085716.png"! This is also one reason that the costing is spiking. For *Audit Account* also i checked that the SNS and Cloudwatch is consuming lot of cost spike due to which the budget costing is spiked. Attaching the screenshot: !image-20260108-093536.png¦width=613,alt="image-20260108-093536.png"! For *CMS_Backend_Prod* the t3.xlarge instances that is EKS nodes is cost consuming as you can see below Attached Screenshot below showing nodes spike for 4 months. !image-20260108-101131.png¦width=496,alt="image-20260108-101131.png"! Also, below screenshot showing instance type size for EC2 and EKS nodes and there costing for 4 months. !image-20260108-101412.png¦width=583,alt="image-20260108-101412.png"! | [27 empty] | In Progress | 2026-01-06 12:51
AM20-1018 | ServiceNow ¦¦ CloudWatch Rule for Error detection | Done | 2 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | High | 1650995 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 14:57 | 2026-01-11 16:37 |  |  |  | 0 | As a AWS engineer, I want to create CloudWatch alarms to send error-level logs to be notified of infrastructure issues Acceptance criteria: * CloudWatch metric filters to be configured to match specific error patterns or log levels |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7fabfe65 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0280b: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 06:03 | [13 empty] | 29/Apr/25 8:03 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Will review utkarsh terraform script and will assign this story to him. | 06/May/25 8:22 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Awaiting for utkarsh script to be reviewed. | 07/May/25 8:27 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;We can use utkarsh terraform script for cloud watch alarm creation, but sns topic cant be modified so we need manual update to SNS access policy. | 07/May/25 8:35 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;*As utkarsh conveyed*, SNS topic cannot be modified with terraform script, so we need to update manual access policy of SNS topic to use lambda function. *Only cloud watch alarm is created in terraform script, other resources like cloud event bridge, lambda function and SNS access policy needs to be created manually.* | 18/May/25 2:39 PM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Marking it done and approving on behalf of Yashwant as he has login issues in Jira | [22 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-05-18 14:39
AM20-1019 | Patch Solution cleanup | Done |  | Sprint 17 | 2025-10-27 | 2025-11-07 | Aravind Raj | Medium | 1818696 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-01-17 15:33 | 2026-01-17 17:19 |  |  |  | 0 |  |  | Aravind Raj | Faisal Sayed |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@698194ac | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0kzvv: | [167 empty] | Business | [12 empty] | Sprint 18 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-31 09:18 | [13 empty] | 31/Oct/25 11:17 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;The Patching instances are still needed, it shall be in stopped state when not in use and terminated once the patching demo is done which has been postponed. [~accountid:712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f] [~accountid:712020:54791a09-30fd-4ab7-8a1d-068b13e544d8] | [26 empty] | 1817985 | AM20-226 | Resources cleanup - Aws accounts | Done | 2025-11-14 20:26
AM20-1020 | Front End (SMS notification)- Business Level Improvements | To Do | 4 | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1885790 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 14:03 | 2026-01-25 14:12 | 2026-01-06 08:25 |  |  | 0 | As Product Owner I would like to take business input and configure the SMS accordingly so that informative SMS notification reached out to operation and support group. *Acceptance Criteria*: * SMS notification configured successfully as Business input |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [11 empty] | 57600 | 57600 |  | 0 | 57600 | 57600 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@55581f2c | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ptv7: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2026-01-08 09:34 | [13 empty] | 08/Jan/26 11:33 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Reached out to Hoosen and Javier to enquire their availability for resuming the discussions, awaiting their response. | [29 empty] | To Do | 2025-12-30 08:45
AM20-1021 | TM1 ¦¦ SSM provisioning and CloudWatch Agent with cutover instance | Done | 4 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1752616 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 14:36 | 2026-01-25 16:06 |  |  |  | 0 | As AWS expert, I would like to provision SSM and Cloudwatch on TM1 cutover instance Acceotance criteria: SSM instance and Cloudwatch instance is successfully provisioned |  | Aravind Raj | Yashwant Thakur |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;14/Aug/25 8:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;14/Aug/25 8:43 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 |  |  |  |  | 57600 | 0 | 57600 | 1 | 57600 | 0 | 57600 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@777f120 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0dnlf: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-13 06:17 | [13 empty] | 13/Aug/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Cloud watch agent setup is completed, will configure the config.json file to fetch relevant server metrics and application metrics. | 13/Aug/25 8:17 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;after cloud watch configuration will start working on setting up SSM agent. | 14/Aug/25 8:42 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;SSM agent installation is success upon stopping MacAfee and excluding from Trellix service. | 25/Aug/25 6:33 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-08-25 06:33
AM20-1022 | AirNavX ¦¦ Port opening, NACL and SG group Whitelisting | Done | 5 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772278 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 15:16 | 2026-01-28 18:15 |  |  |  | 0 | As a cloud infrastructure engineer I want to provision NACL, Security groups and port whitelisting with validated connectivity so that the new application can be securly deployed in AWS with controlled access, compliance to security standards and verified communication paths Acceptance Criteria: * Security groups are created per application tier * required inbound and outbound rules are defined for each tier ( HTTPS: 443 inbound from ALB to web, DB port 3306 from App SG) * no overly permissive rules (0.0.0.0/0) NACL config: * Network ACL applied at subnet level with stateless allow/deny rules for required application port * Both inbound and outbound NACL rules are explicitly documented * Default NACLs are not used Whitelisting: * External IP range for trusted users/ partners are whitelisted * Whitelisting rules are implemented at the SG/NACL level based on environment needs * Documentation include source IPs, purpose and without expiry date Connectivity validations: * E2E connectivity test performed APP--DBflow, External user ---Application endpoint (via ALB/API Gateway) * Connectivity validated using tools like telnet, nc and AWS connectivity tests * Validated evidence captured in the deployment checklist Security and compliance: * All configurations follow least privilege principle * Changes are auditable in CloudTrail with tagging (App, Env, Owner, ChangeID) Deliverable: * SG & NACL rule tables (port, protocol, source/destination) * Whitelist IP registry with owners and validity * Validation test results signed off by infra + security team |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4a97e1ad | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq8r: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-19 14:18 | [13 empty] | 19/Sep/25 4:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared and implemented. with the help of LIFT and CSOC. VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 19/Sep/25 4:19 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Bhavesh we have changed subnet from /27 to /28 and updated comms and shared Sita for implementation. | 19/Sep/25 4:21 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on Albert SITA has been implemented comms via subnet level. according to management i am closing this request and i will working on validation part with new request. | 19/Sep/25 4:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on Albert SITA has been implemented comms via subnet level. according to management i am closing this request and i will working on validation part with new request. | [26 empty] | Done | 2025-09-22 08:50
AM20-1023 | Adding Lambda for generating sonar scan reports | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Shreyash Talwekar | Medium | 1799079 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Shreyash Talwekar | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 2026-01-24 15:28 | 2026-01-24 16:06 |  |  |  | 0 | Adding terraform code to create Lambda and API Gateway for generating sonar scan reports. |  | Shreyash Talwekar | [5 empty] | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@62438a0e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ir8b: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 03/Oct/25 10:45 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Added lambda module and api gateway module and updated the api gateway url in sonar server webhook. | [26 empty] | 1786761 | AM20-182 | Push to FlySAA backend Alarm related code to the bitbucket in dev and preprod environment | Done | 2025-10-03 10:44
AM20-1024 | Miscellaneous Cluster discovery | Done | 6 | Sprint 18 | 2025-11-10 | 2025-11-21 | Yashwant Thakur | Medium | 1823345 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 18:29 | 2026-02-02 21:46 |  | 2025-11-14 11:13 |  | 0 | As Product and Application Architect I would like to analyse the Cabin crew application so that I can suggest the best possible way to modernize and migrate to AWS. Acceptance Criteria: * Application Overview and business context is captured ( Business criticality, use case, compliance and security needs, Pain point) * Current Architecture assessment ( Front end stack, Backend, integration, dabtabase, storage and compute requirements and assess modernize angles * Security and Governance - IAM and RBAC model, secret and configuration storage, certificate management, logging and audit requirements * Performance and Capacity utilization - CPU, memory and disk usage, scalability needs, Latency and throughput requirements are gathered * Dependency and integration landscape captured * Cost and Licensing requirements clarified (current cost of application, licenses etc.) * Modernization readiness documented * Modernization strategy proposed successfully * Operational readiness documented |  | Sumit Nikam | Yashwant Thakur |  |  |  |  | 712020:5d317226-2402-463f-bda5-c2cac5f43c13 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | Had workshop with Gayaz and Donald to understand the requirements.;14/Nov/25 8:14 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 | Analyzed requirements further.;14/Nov/25 8:15 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;21600 | Prepared SOW draft;14/Nov/25 8:15 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;28800 | Amended SOW as per inputs from internal review and shared with Gayaz.;14/Nov/25 8:16 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;14400 |  |  | 86400 | 7200 | 79200 | 0.91 | 86400 | 7200 | 79200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@27e6cfb4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ljt7: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-05 12:29 | 3_*:*_1_*:*_755271693_*¦*_10041_*:*_1_*:*_532796615_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Nov/25 2:29 PM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;# New version of Lounge Tracker application has been under development which consists of a Frontend and a backend microservice component. The backend component will be connecting with 3rd party interfaces like (Discovery Bank, DragonPass etc.) for validations. The ask is to deploy a 'Miscellaneous' cluster which would be capable of hosting diverse set of application microservices with ease. # Focus needs to be on reliability, scalability, and security along with ease of use for this new cluster. # Following two additional projects are in pipeline and business discussions are underway: ## Middleware (Java based microservice which will act as a layer between Amadeus. More clarity is expected by Dec-25) ## Cabin Crew (Project in pipeline) # Â Separate workshops and solutioning will be done for this once business alignment is completed and requirements are finalized. # *Action* â€“ VOIS to share the updated scope of work document for the miscellaneous cluster and related deployments for Gayazâ€™s sign off. | 10/Nov/25 8:16 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Draft SOW document has been prepared. To be reviewed internally. | 13/Nov/25 8:14 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;SOW document has been reviewed internally and shared with Gayaz and Vodacom both. | 14/Nov/25 8:12 AM;712020:5d317226-2402-463f-bda5-c2cac5f43c13;Followed up with Donald to confirm if there is any new update regarding requirements. There is none. We have already shared an SOW based on current understanding. Activity is completed for now. | 14/Nov/25 11:13 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-11-14 11:13
AM20-1025 | AirNavX ¦¦ CloudTrail and Guardrail implementation | Done | 2 | Sprint 6 | 2025-05-26 | 2025-06-06 | Aravind Raj | High | 1672697 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-30 13:04 | 2026-01-30 14:03 |  |  |  | 0 | As a Cloud Security analyst, I want AWS Cloudtrail to be enabled across AirNavX account so all User and API activities are captured for auditing and investigation. I want guardrails that block public access to S3 buckets and security group ports, so that we can prevent accidental exposure and network vulnerabilities Acceptance Criteria: * Cloudtrail and guardrails are successfully enabled * Cloudtrail S3 logging enabled * Public read/write prohibited |  | Aravind Raj | Harsh Chandra |  |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@cdd392e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i04fqr: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-20 06:27 | [13 empty] | 20/May/25 8:26 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Have started working on enabling the cloud config and guard duty along with macie. | 22/May/25 8:19 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;below mentioned service were enabled. | [25 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-05-22 08:19
AM20-1026 | Informatica Server ¦¦ NACL and Security group creation | Done | 2 | Sprint 5 | 2025-05-12 | 2025-05-23 | Yashwant Thakur | High | 1660593 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-21 21:12 | 2026-01-21 23:15 |  |  |  | 0 | As Network expert, I would be creating NACL and Security group along with inbound and outbound rules for Nexio AV Acceptance Criteria: NACL and Security group created successfully with all inbound and outbound rules |  | Aravind Raj | Harsh Chandra | Satya Varanasi | Shreyash Talwekar | Yashwant Thakur |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [7 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [13 empty] | 27/Jun/25 3:51 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-134901.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119369 | 27/Jun/25 3:51 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-134948.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119368 | 27/Jun/25 5:54 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155416.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119411 | 27/Jun/25 5:54 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250627-155445.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1119410 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4189bc9b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i03bbn: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 6 | Sprint 7 | Sprint 8 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-05-16 08:01 | [13 empty] | 16/May/25 10:01 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Waiting for terraform code towards build this. | 20/May/25 5:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Deepak and team, this need to be addressed with terraform code the same has been prepared by Utkarsh, until core not ready this story may not possible to address. | 10/Jun/25 2:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still â€œShreyashâ€ checking Utkarsh script, this story depending with script testing and execution. | 16/Jun/25 9:06 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Terraform script is under modification by â€œShreyashâ€, as per his update it will be ready this week. Hence this is the reason for spill over Sprint7 to Sprint8. | 18/Jun/25 11:11 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;The script is managing by â€œShreyashâ€ so i am assigning this task to him, once his work completes he will reassign to me. | 23/Jun/25 1:59 PM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;We were able to create AWS resources (mentioned in previous mail ) using terraform scripts on sharedvpc-dev account. To address some requirements like adding naming conventions and state file management, we will have to add some changes in terraform scripts. Due to current sprint activities I might not be able to work on the changes in this sprint. | 27/Jun/25 3:46 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Prod NACL/SG has been created, & tested internet access and same working fine. !image-20250627-134901.png¦width=1092,height=400,alt="image-20250627-134901.png"! !image-20250627-134948.png¦width=1308,height=579,alt="image-20250627-134948.png"! sh-5.2$ ping [http://google.com¦http://google.com¦smart-link] PING [http://google.com¦http://google.com¦smart-link] (142.251.47.238) 56(84) bytes of data. 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=1 ttl=108 time=20.5 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=2 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=3 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=4 ttl=108 time=19.7 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=5 ttl=108 time=19.8 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=6 ttl=108 time=19.6 ms 64 bytes from [jnb03s12-in-f14.1e100.net¦http://jnb03s12-in-f14.1e100.net] (142.251.47.238): icmp_seq=7 ttl=108 time=19.7 ms ^C --- [http://google.com¦http://google.com¦smart-link] ping statistics --- 7 packets transmitted, 7 received, 0% packet loss, time 6010ms rtt min/avg/max/mdev = 19.630/19.800/20.473/0.282 ms sh-5.2$ hostname [ip-10-40-0-213.awsflysaa.com¦http://ip-10-40-0-213.awsflysaa.com] sh-5.2$ ifconfig ens5: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 9001 inet 10.40.0.213 netmask 255.255.255.240 broadcast 10.40.0.223 inet6 fe80::4a7:ebff:fe03:c075 prefixlen 64 scopeid 0x20<link> ether 06:a7:eb:03:c0:75 txqueuelen 1000 (Ethernet) RX packets 1653 bytes 293385 (286.5 KiB) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 1809 bytes 265312 (259.0 KiB) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0 lo: flags=73<UP,LOOPBACK,RUNNING> mtu 65536 inet 127.0.0.1 netmask 255.0.0.0 inet6 ::1 prefixlen 128 scopeid 0x10<host> loop txqueuelen 1000 (Local Loopback) RX packets 12 bytes 1020 (1020.0 B) RX errors 0 dropped 0 overruns 0 frame 0 TX packets 12 bytes 1020 (1020.0 B) TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0. | 27/Jun/25 5:54 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dev: NACL/SG got created. !image-20250627-155416.png¦width=1246,height=457,alt="image-20250627-155416.png"! !image-20250627-155445.png¦width=1155,height=624,alt="image-20250627-155445.png"! | 27/Jun/25 6:13 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;NACL and Route table created for informatica environment, route entry and NACL rules to be created upon network requirement. | 29/Jun/25 8:13 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [17 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-06-29 20:13
AM20-1027 | Route53 cutover for FlySAA.com | Done | 2 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1865867 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-04 20:42 | 2026-02-05 00:24 | 2025-12-14 18:49 | 2025-12-12 11:18 |  | 0 | As product Ownwer I like to perform cutover for Route53 for [FlySAA.com¦http://FlySAA.com] Acceptance Criteria: The [flysaa.com¦http://flysaa.com] application must be highly available and resilient to single-region outages (e.g., 99.99% uptime). *Route 53 Implementation:* Configure *Failover Routing* policies. A primary record is associated with an active endpoint. A secondary, passive record is configured as a backup. Route 53 health checks automatically switch traffic to the secondary region if the primary endpoint is deemed unhealthy. |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;04/Dec/25 8:30 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;43200 | [5 empty] | 28800 | 0 | 43200 | 1.5 | 28800 | 0 | 43200 | [12 empty] | 04/Dec/25 8:30 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251204-063001.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1192161 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@769d9d3b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0o7mz: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-02 16:21 | 3_*:*_1_*:*_223764662_*¦*_10041_*:*_1_*:*_463376988_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Dec/25 6:20 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Latest zone file has been imported under public hosted zone route53 AWS.. Earlier 313 after upload 318 records has-been created. | 04/Dec/25 8:20 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;DNS pointer has been modified to route53. C:\Users\VaranasiS>nslookup -query=NS [flysaa.com¦http://flysaa.com] Server: [ECINDC307VW.internal.vodafone.com¦http://ECINDC307VW.internal.vodafone.com] Address: 10.74.250.24 Non-authoritative answer: [flysaa.com¦http://flysaa.com] nameserver = [ns-1419.awsdns-49.org¦http://ns-1419.awsdns-49.org] [flysaa.com¦http://flysaa.com] nameserver = [ns-308.awsdns-38.com¦http://ns-308.awsdns-38.com] [flysaa.com¦http://flysaa.com] nameserver = [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] [flysaa.com¦http://flysaa.com] nameserver = [ns-1777.awsdns-30.co.uk¦http://ns-1777.awsdns-30.co.uk] [ns-1419.awsdns-49.org¦http://ns-1419.awsdns-49.org] internet address = 205.251.197.139 [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] internet address = 205.251.194.93 [ns-605.awsdns-11.net¦http://ns-605.awsdns-11.net] AAAA IPv6 address = 2600:9000:5302:5d00::1 [ns-1777.awsdns-30.co.uk¦http://ns-1777.awsdns-30.co.uk] internet address = 205.251.198.241 C:\Users\VaranasiS> | 04/Dec/25 8:23 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Customer requested to add new alias zone for ALB. ¦[flysaa.com¦http://flysaa.com]¦A¦Simple¦-¦Yes¦[flysaa-cms-alb-402247724.af-south-1.elb.amazonaws.com¦http://flysaa-cms-alb-402247724.af-south-1.elb.amazonaws.com].¦ ¦ Zone has been created and validated after DNS cutover and same working fine. !image-20251204-063001.png¦width=591,alt="image-20251204-063001.png"! | 05/Dec/25 8:29 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;SAA SSL DNS has been modified according to request. the change requested under â€œCHG0068431/ CHR0031920â€ has been successfully implemented. Below you will find the latest and updated record for your reference. Â Â C:\Users\VaranasiS>nslookup [upwards.flysaa.com¦http://upwards.flysaa.com] Server:Â UnKnown Address:Â 2401:4900:50:9::7d5 Â Non-authoritative answer: Name:Â Â Â [upwards.flysaa.com¦http://upwards.flysaa.com] Address:Â [102.130.96.4¦https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2F102.130.96.4%2F&data=05%7C02%7Csatyasairam.varanasi%40vodafone.com%7C3d58714d9d324c04956d08de33430e8a%7C68283f3b84874c86adb3a5228f18b893%7C0%7C0%7C639004560572522291%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=w7K%2F%2Fjsk9kHTi00XQSJKC3mq2iHGjbBvw1316zlJjyk%3D&reserved=0] Â Â C:\Users\VaranasiS> Â | 12/Dec/25 11:18 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-12-12 11:18
AM20-1028 | AWS Centralized dashboard CloudWatch Dashboard for Nexio AV to monitor Performance, cost optimization and security Metrics | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | Medium | 1718753 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 21:01 | 2026-01-27 23:56 |  |  |  | 0 | As AWS expert, I would like to create centralized CloudWatch to capture Performance, Security and Cost metrics from across accounts. Acceptance Criteria: * CloudWatch dashboards can be created in one account (Payer9 account) anf pull metrics from other accounts * User cross account IAM roles to allow Payer9 account to read cloudwatch from other accounts * Add Widgets sourcing metrics from each account * Setup AWS config aggregator in the Payer9 account to collect configuration and compliance data across all members accounts * Performance metrics - Use below Cloudwatch metrics * EC2 : CPU, Network, Disk I/O * RDS: CPU, READ/Write IOPS * Lambda: Duration, Error Rate * and source these into widgets in the centralized dashboard * Security Metrics: Centralized Security Hub is already enabled, which can pull in findings from GuardDuty, Config, Macie, Cloudtrail, Inspector etc. |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@60b85e0b | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0aofj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-23 14:43 | [13 empty] | 23/Jul/25 4:43 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Created Trellix Dash board with CPU, Memory and Disk usage. | 25/Jul/25 7:59 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Dash board prepared for CPU, Disk, Network and memory for Trellix application. | 25/Jul/25 8:09 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sent for review | 27/Jul/25 10:02 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Could see the metrics for trellix server, moving to PO approval, | 28/Jul/25 9:57 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:57
AM20-1029 | Informatica ¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 12 | 2025-08-18 | 2025-08-29 | Yashwant Thakur | High | 1755978 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-25 18:14 | 2026-01-25 21:40 |  |  |  | 0 |  |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@3237a818 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0e0or: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 13 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-26 11:39 | [13 empty] | 26/Aug/25 1:39 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Firewall rules implemented. Identified as connectivity not working. Initiated network troubleshooting call towards fixing. Identified as routing not configured. Requested LIFT for approval LIFT approval took 3days Monday CSOC request raised and routing has ben implemented. Testing initiated but not working, initiated call for troubleshooting. This story can be addressed after network implementation successfully but still network not working hance this will be spill over to next sprint. | 28/Aug/25 8:18 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested connectivity from informatica Prod/Dev env. Initially Network team not configured Routing after new Lift and CSOC request issue got resolved. Reference Lift & CSOC details: Routing: # CSOC:CHR0026807 # LIFT:CHG0067489 App comms: # LiFT = CHG0067488 # CSOC = CHR0026691 AWS agent Comms: CSOC logged CHR0023951 LiFT logged CHG0066992 (RITM0051174) | 01/Sep/25 8:03 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Informatica Agent comms has been implemented and tested. Based on comms we have successfully completed agent installation for prod/Dev and setup test instance for the same. Hence sending request for closer. | 03/Sep/25 8:55 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-09-03 08:55
AM20-1030 | AirNavX ¦¦ Port opening, NACL and SG group Whitelisting | Done | 5 | Sprint 14 | 2025-09-15 | 2025-09-26 | Yashwant Thakur | Medium | 1772278 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-12 19:02 | 2026-01-12 21:44 |  |  |  | 0 | As a cloud infrastructure engineer I want to provision NACL, Security groups and port whitelisting with validated connectivity so that the new application can be securly deployed in AWS with controlled access, compliance to security standards and verified communication paths Acceptance Criteria: * Security groups are created per application tier * required inbound and outbound rules are defined for each tier ( HTTPS: 443 inbound from ALB to web, DB port 3306 from App SG) * no overly permissive rules (0.0.0.0/0) NACL config: * Network ACL applied at subnet level with stateless allow/deny rules for required application port * Both inbound and outbound NACL rules are explicitly documented * Default NACLs are not used Whitelisting: * External IP range for trusted users/ partners are whitelisted * Whitelisting rules are implemented at the SG/NACL level based on environment needs * Documentation include source IPs, purpose and without expiry date Connectivity validations: * E2E connectivity test performed APP--DBflow, External user ---Application endpoint (via ALB/API Gateway) * Connectivity validated using tools like telnet, nc and AWS connectivity tests * Validated evidence captured in the deployment checklist Security and compliance: * All configurations follow least privilege principle * Changes are auditable in CloudTrail with tagging (App, Env, Owner, ChangeID) Deliverable: * SG & NACL rule tables (port, protocol, source/destination) * Whitelist IP registry with owners and validity * Validation test results signed off by infra + security team |  | Satya Varanasi | Yashwant Thakur |  |  |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 72000 | 72000 |  | 0 | 72000 | 72000 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4a97e1ad | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fq8r: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-19 14:18 | [13 empty] | 19/Sep/25 4:18 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Comms has been prepared and implemented. with the help of LIFT and CSOC. VDC FW - CHR0027232Â Â Â Â Â Â Â SITA FW - REQ0056161 VDC routing addition - CHR0027231 | 19/Sep/25 4:19 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Bhavesh we have changed subnet from /27 to /28 and updated comms and shared Sita for implementation. | 19/Sep/25 4:21 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on Albert SITA has been implemented comms via subnet level. according to management i am closing this request and i will working on validation part with new request. | 19/Sep/25 4:22 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on Albert SITA has been implemented comms via subnet level. according to management i am closing this request and i will working on validation part with new request. | [26 empty] | Done | 2025-09-22 08:50
AM20-1031 | TM1 ¦¦ Monitoring Servers post migration | Done | 1 | Sprint 7 | 2025-06-09 | 2025-06-20 | Yashwant Thakur | High | 1651402 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 15:06 | 2026-01-20 17:04 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if TM1 server service is stopped |  | Aravind Raj | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 20/Aug/25 6:27 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250820-162717.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1142337 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2a36f4c8 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i05u4i:z | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | [107 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-06-13 15:59 | [13 empty] | 13/Jun/25 5:58 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This story is blocked with TM1 Agent Installation - [https://vodacom.atlassian.net/browse/FCBEM-593¦https://vodacom.atlassian.net/browse/FCBEM-593¦smart-link] | 13/Aug/25 12:42 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 cutover completed and monitoring enable but need to create TM1 dash board. | 18/Aug/25 4:26 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;TM1 dashboard has been created under 20Plus apps dashboard. | 19/Aug/25 5:46 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Alerts has been configured and currently in review stage. | 20/Aug/25 6:27 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;As per Service now team the alerts has been reaching to from cloud watch dash board. Attaching reference screen shot. !image-20250820-162717.png¦width=1910,height=508,alt="image-20250820-162717.png"! | 21/Aug/25 6:09 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Reviewed | 25/Aug/25 6:31 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620369 | AM20-5 | Rehosting & Replatforming of applications from on-Prem to AWS | Done | 2025-08-25 06:31
AM20-1032 | Nexio AV ¦¦ Subnet creation | Done | 1 | Sprint 4 | 2025-04-28 | 2025-05-09 | Yashwant Thakur | Medium | 1650863 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-06 12:41 | 2026-02-06 16:15 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for Nexio AV application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for Nexio AV and the configured based on the approved comms matrix |  | Sankalp Rai | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:8b1a5d94-1767-4111-80eb-b21856098c47 | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [13 empty] | 14/May/25 7:21 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-05-14 104729-20250514-051730.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100027 | 14/May/25 7:21 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;Screenshot 2025-05-14 105036-20250514-052037.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100026 | 14/May/25 7:24 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250514-052415.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1100028 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-072934.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103886 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-073009.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103885 | 22/May/25 9:31 AM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20250522-073047.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1103887 | [12 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@77400985 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i02776:t | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 5 | Sprint 6 | Sprint 7 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-04-29 05:40 | [13 empty] | 29/Apr/25 7:39 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Relevant subnet has been created, sending for review. | 02/May/25 12:22 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;IP Details ¦¦Nexio AV¦¦Production¦¦10.40.0.176/28¦¦10.40.0.176 - 10.40.0.191¦¦10.40.0.177 - 10.40.0.190¦¦14¦¦AZ1¦¦Â ¦¦ ¦¦Nexio AV (DR)¦Production¦10.40.0.192/28¦10.40.0.192 - 10.40.0.207¦10.40.0.193 - 10.40.0.206¦14¦Â ¦AZ2¦ ¦¦TG ATTACH-Subnet¦Production¦10.40.1.160/28¦10.40.1.160 - 10.40.1.175¦10.40.1.161 - 10.40.1.174¦14¦AZ1¦Â ¦ ¦¦TG ATTACH-Subnet¦Production¦10.40.1.176/28¦10.40.1.176 - 10.40.1.191¦10.40.1.177 - 10.40.1.190¦14¦Â ¦AZ2¦ Route table still need to cleaned up and updated properly. Assigning back the ticket to [~accountid:712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0] | 07/May/25 6:21 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Working on route table cleanup. | 14/May/25 7:21 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnets already created. IP CIDR Details for prod/DR ¦10.40.0.176/28¦10.40.0.176 - 10.40.0.191¦10.40.0.177 - 10.40.0.190¦14¦/28¦AZ1¦Â ¦ ¦10.40.0.192/28¦10.40.0.192 - 10.40.0.207¦10.40.0.193 - 10.40.0.206¦14¦/28¦Â ¦AZ2¦ Subnet info: !Screenshot 2025-05-14 104729-20250514-051730.png¦width=1117,height=580,alt="Screenshot 2025-05-14 104729-20250514-051730.png"! !Screenshot 2025-05-14 105036-20250514-052037.png¦width=1128,height=586,alt="Screenshot 2025-05-14 105036-20250514-052037.png"! Please review. | 14/May/25 7:24 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Attached route table screen shots. !image-20250514-052415.png¦width=1130,height=531,alt="image-20250514-052415.png"! | 19/May/25 11:08 AM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Action Item: Change the Name to Trellix AV from Nexio AV Correct the AZ for DR Route to be tested for correct routing Assigning back to Satya for correction | 19/May/25 6:02 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Sankalp updated me to change NexioAV to Trellix AV. I will update and assign it to Sankalp. | 20/May/25 5:16 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation done and assigned for review, and it has been reassigned for modification and routing validation. Find below reviewer comments. Action Item: Change the Name to Trellix AV from Nexio AV(New requirement according to app name) Correct the AZ for DR (resource name change) Route to be tested for correct routing | 22/May/25 9:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Based on inputs modification has been done. !image-20250522-072934.png¦width=1103,height=563,alt="image-20250522-072934.png"! !image-20250522-073009.png¦width=1107,height=575,alt="image-20250522-073009.png"! Route Table: !image-20250522-073047.png¦width=1107,height=526,alt="image-20250522-073047.png"! Please check and review the same. | 30/May/25 2:45 PM;712020:8b1a5d94-1767-4111-80eb-b21856098c47;Review done Transitioning to PO Approval | 02/Jun/25 11:36 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;approved | [16 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-06-02 11:36
AM20-1033 | CloudWatch Metrics configuration in all AWS account | To Do | 0 | None( Backlog) |  |  | Faisal Sayed | Medium | 1868810 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 20:38 | 2026-01-17 23:07 | 2026-01-06 08:22 |  |  | 0 | As Cloud Product Owner I wish to configure below metrices in Cloudwatch for all the AWS accounts so that we can monitor the memory and Disk availability for each applications residing over the AWS accounts. * Memory Available MBytes * LogicalDisk % Free Space * LogicalDisk Free Megabytes Acceptance Criteria * CloudWatch dashboard must consist of all the above mentioned metrics for all application so that we can view the memory and disk available space * Only specific IAM role must give permission to the CloudWatch agent to collect metrics from server * The above metrics view is restricted with relevant IAM role * The dashboard must be configured in centralized audit account ¦ ¦ | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@32f363c4 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v07g0002 | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2025-11-28 08:08
AM20-1034 | PROS¦¦ Migration Agent comms Metrics implementation | Done | 2 | Sprint 15 | 2025-09-29 | 2025-10-10 | Yashwant Thakur | Medium | 1773953 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 19:31 | 2026-01-27 20:01 |  |  |  | 0 | As Network expert I would create comms metrics based on routing rules suggested by business so that migration agent can use the same rules and routes to copy the application and data to target account in AWS Acceptance Criteria: Comms metrics is successfully deployed in Dev and Prod account for PROS Validations of the routing rules are completed successfully to ensure there is no error |  | Harsh Chandra | Satya Varanasi | Yashwant Thakur |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [9 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4ce03565 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0fwqr: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 16 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-24 06:04 | [13 empty] | 24/Sep/25 8:04 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;PROS migration agent comms has been implemented. SAA = REQ0056503 (CHG0067695) CSOC = CHR0027812 | 25/Sep/25 5:24 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Still CSOC under approval, also we have identified as some miss match in Agent Comms. I have updated and shared to Wanda for CSOC updation. | 06/Oct/25 8:40 AM;712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d;Spill over - Comms implementation delayed from SAA, hence will be spilled over and worked upon in subsequent sprint | 09/Oct/25 4:33 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Migration agent comms has been implemented and agent has been installed n all 3 PROS servers, Created test instance and handover to customer for testing. | 17/Oct/25 7:16 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [25 empty] | Done | 2025-10-17 07:16
AM20-1035 | Informatica Server ¦¦ Back up and DR | Done | 5 | Sprint 13 | 2025-09-01 | 2025-09-12 | Aravind Raj | Critical | 1751441 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 14:13 | 2026-01-20 16:33 |  |  |  | 0 | As AWS engineer, I want to configure automated backups and snapshots for databases and critical volumes so that we can recover data in case of failure Acceptance Criteria: * S3 replication and AMI copes configured * DNS failover configured * RTO and RPO are validated against validated requirements * DR - Invoke DR Execute DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM * Application - Sanity check * Joining [Informatica-application.awsflysaa.com¦http://tm1-application.awsflysaa.com/] Server to the AD * MAT Testing completed successfully * "DR - DR Rollback completed successfully by Executing DNS update to point to new IP address in AWS to Cutover traffic to the migrated AWS VM h2. Confluence content |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [5 empty] | ;30/Sep/25 6:38 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;28800 | ;13/Oct/25 6:32 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;43200 |  |  |  |  | 72000 | 0 | 72000 | 1 | 72000 | 0 | 72000 | [12 empty] | 13/Oct/25 6:32 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;image-20251013-163227.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1167346 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@76f244a1 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabl: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | Sprint 16 | [109 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-09-05 07:22 | [13 empty] | 05/Sep/25 9:21 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Informatica Test server is launched and trying to fix connectivity issue. Only after the cutover launch we will be able to configure DR and backup solution for this server, so this will be a spillover. | 22/Sep/25 8:44 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;This is a spillover due to the dependent userstory - [[AM20-140] Informatica Server ¦¦ Cutover - Jira¦https://vodacom.atlassian.net/browse/AM20-140], only after cutover we would be able to do backup and DR setup. | 30/Sep/25 6:37 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Since Cutover is completed have started working on setting UP DR, will be completing in sometime. | 03/Oct/25 9:23 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Backup is completed, DR is in progress, waiting for DR drill to complete. send a mail on asking for slot with app owner to perform DR drill, upon drill completion with complete this US. | 09/Oct/25 6:29 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;DR Drill is planned today with albert at 1:30PM, looking forward to complete the drill. | 13/Oct/25 6:32 PM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Drill is completed successfully. !image-20251013-163227.png¦width=1278,height=489,alt="image-20251013-163227.png"! | [24 empty] | Done | 2025-10-13 18:32
AM20-1036 | CMS Backend RDS instance (Pre-prod/Prod) analysis | Done | 6 | Sprint 19 | 2025-11-24 | 2025-12-05 | Yashwant Thakur | Medium | 1833687 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-17 19:55 | 2026-01-17 20:46 |  | 2025-11-27 09:21 |  | 0 | As Product owner I like to analyse RDS for rightsizing based on utlization to reduce cost |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;18/Nov/25 5:10 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;21600 | ;25/Nov/25 4:08 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;64800 |  |  |  |  | 86400 | 0 | 86400 | 1 | 86400 | 0 | 86400 | [12 empty] | 18/Nov/25 5:09 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251118-150648.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1185982 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@6460780 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mo2n: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-11-18 15:10 | 3_*:*_1_*:*_601595111_*¦*_10041_*:*_1_*:*_540987234_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 18/Nov/25 5:09 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;RDS cost analysis is started. Today, we have reduced backup retention period of preprod rds to 7 days from 35 days. Also, storage limit threshold for dev rds is updated to 200 GiB from 110GiB because it was generating alerts â€œ*_Storage size 100 GiB is approaching the maximum storage threshold 110 GiB. Increase the maximum storage threshold_*â€ !image-20251118-150648.png¦width=459,alt="image-20251118-150648.png"! Next we will monitor cpu, memory consumption across three environments | 25/Nov/25 4:15 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;h3. Next Steps for CMS Backend RDS Cost Optimization With discussion with Pankaj, we have identified the following points as next steps for CMS Backend RDS cost optimization: * Turn off non-prod RDS instances when not in use or during off-business hours and turn them back on when required. * Further reduce backup retention period for non-prod RDS instances (currently 7 days) to explore additional cost savings. These actions will be implemented post confirmation from FlySAA team. | 27/Nov/25 9:21 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [27 empty] | Done | 2025-11-27 09:21
AM20-1037 | Cynet ¦¦ Server Installation | To Do |  | Sprint 22 | 2026-01-05 | 2026-01-16 | Shreyash Talwekar | Medium | 1887432 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-15 17:36 | 2026-01-15 21:32 | 2026-01-07 08:19 |  |  | 0 | As Product owner I want to install Cynet agent on Linux/Windows EC2 instance so that threat detechtion and response coverage is enabled Acceptance Criteria. *Linux*: * Installation package hosted/accessible securely (S3 with KMS, repo, or Cynet direct download). * SSM document / automation executes successfully on a pilot group and then on all in-scope instances. * Agent registers to correct Cynet tenant and shows â€œonline/healthyâ€ in console within defined SLA (e.g., 15 minutes). * Installation is idempotent (re-run does not break existing installation). * Logging captured: instance ID, hostname, timestamp, status, version, and failure reason if any. *Windows*: * Silent install works (msi/exe unattended flags), including token/tenant configuration. * Service is running after installation and agent appears healthy in console. * Windows Event Logs / install logs are retained for troubleshooting. * | [56 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@19d1d99d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0q0i3: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | To Do | 2026-01-06 13:12
AM20-1038 | PROS ¦ Test-Over Instance | Done |  | Sprint 15 | 2025-09-29 | 2025-10-10 | Aravind Raj | Medium | 1801095 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | Aravind Raj | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | 2026-02-05 15:15 | 2026-02-05 17:12 |  |  |  | 0 |  |  | Aravind Raj | [5 empty] | 712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f | [48 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@32a969b9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0izhn: | [167 empty] | Business | [12 empty] | Sprint 16 | Sprint 17 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [14 empty] | 07/Oct/25 8:40 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Server replication is still on-going after completion of initial sync will start launching test instance. have updated the launch templet based on the LLD document. | 09/Oct/25 6:28 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;Test launch instance hand over is completed, awaiting for the response back from the application owner. | 17/Oct/25 11:07 AM;712020:cc0b2787-4f6f-4087-8da9-c6b5ba6c311f;connectivity issue is resolved, have received date to perform cutover. | [24 empty] | 1773952 | AM20-170 | PROS ¦¦ Cutover | Done | 2025-10-17 11:08
AM20-1039 | Code Pipeline creation using Terraform in Sandbox | Done | 8 | Sprint 17 | 2025-10-27 | 2025-11-07 | Yashwant Thakur | Medium | 1749627 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-22 21:31 | 2026-01-22 22:51 |  | 2025-10-31 17:19 |  | 0 | As Platform owner I want to create code pipeline POC in sandbox so that we can achieve a base module for centralizing CI/CD pipeline. *Acceptance Criteria*: * Code build and S3 and IAM role replica is created which is needed in code pipeline integration * Code pipeline base module is ready |  | Sanjot Fotedar | Yashwant Thakur |  |  |  |  | 712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;30/Oct/25 6:52 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;86400 | ;30/Oct/25 6:52 PM;2dfeb53c-1eba-4b39-a2f8-145806d16963;10800 | ;31/Oct/25 10:55 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;18120 |  |  |  | 115200 | 0 | 115320 | 1 | 115200 | 0 | 115320 | [12 empty] | 31/Oct/25 11:10 AM;2dfeb53c-1eba-4b39-a2f8-145806d16963;image-20251031-091042.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175916 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@648c36cb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnlj:09v05i | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-10-28 06:19 | 3_*:*_1_*:*_269631681_*¦*_10041_*:*_1_*:*_7076678660_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 28/Oct/25 8:19 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Started work on codepipeline module for Github base repository. Feature branch â€œfeat/codepipeline2â€ is created for this. | 30/Oct/25 6:51 PM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Modules have been created in feature branch of base and component repositories [https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa/tree/feat/codepipeline2¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-base-modules-vfsa/tree/feat/codepipeline2¦smart-link] [https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/tree/feat/codepipeline2¦https://github.com/VFGroup-ITInfraSWEngineering-VCollab/terraform-component-modules-vfsa/tree/feat/codepipeline2¦smart-link] These modules have been tested as well in sandbox aws account. Now in next sprint, we will focus on to have dependency of required modules like s3, iam roles, kms (if needed), codebuild to be integrated with codepipeline in Bitbucket repository alongwith modules creation in BB repo. | 31/Oct/25 11:10 AM;712020:a96ba44c-ac74-4d73-8f8c-5c9a2bd48c65;Following successful validation with â€œterraform planâ€, modules have now been pushed to remote feature branches of both base and component repositories. !image-20251031-091042.png¦width=459,alt="image-20251031-091042.png"! | 31/Oct/25 5:19 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [23 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-10-31 17:19
AM20-1040 | Terraform code to automate the Route 53 cutover | Done |  | Sprint 19 | 2025-11-24 | 2025-12-05 | Satya Varanasi | Medium | 1835056 | Sub-task | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 2026-01-28 19:19 | 2026-01-28 23:02 | 2025-11-25 08:21 |  |  | 0 | [airchefs.co.za¦http://airchefs.co.za] need to be setup on network account. |  | Harsh Chandra | Sanket Kale |  |  |  |  | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d | 712020:91948faf-1676-4820-bf6b-d50a7992943e | [47 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@279e63c7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0mxgj: | [167 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-11-20 07:08 | [13 empty] | 20/Nov/25 9:07 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Resources deployed on Network account. Today we have scheduled a call at 1 pm for validated and align with the team. | 25/Nov/25 8:17 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Validated with the internal team and assign it to Satyasairam for the review | [25 empty] | 1834911 | AM20-267 | Route53 cutover for Airchef | Done | 2025-11-25 09:23
AM20-1041 | Informatica ¦¦ Monitoring Servers post migration | Done | 2 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satya Varanasi | Medium | 1751442 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-27 16:36 | 2026-01-27 17:52 |  |  |  | 0 | As AWS expert, I want to setup infrastructure monitoring post migration so that we can detect any performance issues in the new AWS environment Acceptance criteria: * CloudWatch metrics are enabled for CPU, memory, disc, network I/O * Dashboards are created to monitor key services * SNS Alert should be generated if Informatica server service is stopped |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 28800 | 28800 |  | 0 | 28800 | 28800 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@a6a11cb | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabm: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:57 | [13 empty] | 25/Aug/25 8:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Spill over Reason: This need to action after migration. | 28/Aug/25 8:32 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 30/Sep/25 7:39 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Cutover change has been approved, once change completes we will close this ticket. | [26 empty] | Done | 2025-10-06 08:37
AM20-1042 | TM1 ¦¦ Subnet creation using terraform | Done |  | Sprint 1 | 2025-03-17 | 2025-03-28 | Satya Varanasi | Medium | 1620359 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-03 14:46 | 2026-02-03 16:19 |  |  |  | 0 | AS AWS expert, I would be creating shared subnets for TM1 application using Terraform *Acceptance Criteria*: Shared subnet successfully provisioned for TM1 and the configured based on the approved comms matrix |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [25 empty] | AM20-11 | [22 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1a96537d | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxnn3: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 2 | Sprint 3 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-03-12 15:53 | [13 empty] | 12/Mar/25 5:52 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation completed | 04/Apr/25 10:53 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Subnet creation got completed Manuel. As terraform not ready. While creating this TM1 subnets. | [25 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-04-07 10:11
AM20-1043 | Nexio AV ¦¦ E2E Integration testing of ServiceNow monitoring | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1732203 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-23 16:59 | 2026-01-23 17:49 |  |  |  | 0 | As Product Owner I would like to review e2e testing completed with servicenow team for all wave 1 application so that we can confirm to business that in case of any issue service ticket would be raised Acceptance Criteria: * Tickets/issues are getting raised successfully against the alerts raise via cloudwatch for all Wave1 applications * ServiceNow team signoff received * Showcase (demo) provided to all relevant stakeholders |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 19/Aug/25 10:36 AM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141324 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@1c3893f7 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0brrj: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-28 07:41 | [13 empty] | 28/Jul/25 9:41 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;[https://vodacom.atlassian.net/browse/AM20-116¦https://vodacom.atlassian.net/browse/AM20-116¦smart-link] Only after completing the above US will start working on this story. | 28/Jul/25 3:52 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;After completion of Faisal story i will be proceeding with this US. | 11/Aug/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: Since the story was blocked due to configuration of monitoring and alerting on NexioAV ec2 instances (application specific) which was completed on 8th Aug 2025 (evening), Diksha did not get any time to validate end to end solution. Hence, the spillover. | 19/Aug/25 10:17 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Have tried to triggered the alert to service now team. Now waiting for them to confirm from there side. | 19/Aug/25 10:33 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Got the confirmation for Priyanka and team the alerts are getting generated and tickets are being created in service now. Attaching the same screenshot for the reference. | 19/Aug/25 10:36 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image.png¦width=881,height=228,alt="image.png"! attaching the screenshot what service now team is getting the alerts for your reference from Priyanka and team. | 21/Aug/25 2:31 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [20 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:31
AM20-1044 | Disaster Recovery and Backup | In Progress |  | None( Epic) |  |  | Yashwant Thakur | Critical | 1717990 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-24 19:21 | 2026-01-24 22:41 |  |  |  | 0 | Automated Backup and Disaster Recovery Infrastructure via Terraform or manual |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [15 empty] | 432000 | 374400 | 86400 | [12 empty] | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133603.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175536 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133705.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175534 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133909.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175537 | 30/Oct/25 3:40 PM;ac0ffa06-607f-4f0d-9fec-35abc346d829;image-20251030-133947.png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1175535 | [14 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@2309b367 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-9 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | orange | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0anuj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-10-30 13:41 | [13 empty] | 30/Oct/25 3:40 PM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Validated PROS & Informatica backups, all are configure fine. Pros back up status: !image-20251030-133603.png¦width=612,alt="image-20251030-133603.png"! Policy: !image-20251030-133705.png¦width=597,alt="image-20251030-133705.png"! Informatica Prod Backup: !image-20251030-133909.png¦width=597,alt="image-20251030-133909.png"! Status: !image-20251030-133947.png¦width=597,alt="image-20251030-133947.png"! | 13/Nov/25 8:02 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Backup has been configured and working fine. DR step-up is done still sync in progress. Once sync completed we can initiate call for testing. | [28 empty] | In Progress | 2025-10-30 15:30
AM20-1045 | Convert Alarms description into simple user understandable format | Done | 4 | Sprint 21 | 2025-12-22 | 2026-01-02 | Yashwant Thakur | Medium | 1881266 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-29 13:04 | 2026-01-29 13:41 | 2026-01-04 09:12 | 2026-01-02 11:04 |  | 0 | As Product owner I like to convert alarm description into simple understandable language so that user or resolver group are able to understand what is causing the error for flysaa backend , Front end and airnavx. Acceptance Criteria: alarm description send to Service Now via SNS and Lamda function must be user understable and successfully cascaded to ServiceNow using API. |  | Shreyash Talwekar | Yashwant Thakur |  |  |  |  | 712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa |  |  |  |  | ;02/Jan/26 9:49 AM;17cb9418-1850-4923-932b-7098ec51b6bb;28800 | [5 empty] | 57600 | 28800 | 28800 | 0.5 | 72000 | 28800 | 43200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@18246054 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0pcib: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2026-01-02 07:49 | 3_*:*_1_*:*_1301386080_*¦*_10041_*:*_1_*:*_597437030_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 02/Jan/26 9:48 AM;712020:99b4cd17-5e8e-4d7f-9bfc-4da80b6a5da8;Description was added for infrastructure , Lambda function and Flysaa Frontend account alerts. Example payload of frontend account alert: {"Name": "FlySaaCms_ALB_HTTPCode_Target_4XX_Count","IP Address": "NA","Fully Qualified Domain Name": "[api.flysaa.com¦http://api.flysaa.com]","Company": "VFSA","Hostname": "app/FlySaaCmsWebALB/968b1f7492941705","Department": "App DevOps Team","Operating System": "Amazon Linux","DNS Domain": "[api-frontdev-flysaa.com¦http://api-frontdev-flysaa.com]","Disk Space (GB)": "NA","RAM (MB)": "NA","CPU Count": "2","CPU core count": "2","Alarm Time": "2026-01-01 19:42:30 UTC","Account ID": "261365109009","Environment": "prod","Cluster Name": "NA","MetricName": "HTTPCode_Target_4XX_Count","Current State": "ALARM","Reason": "Threshold Crossed: 3 out of the last 3 datapoints [6534.0 (01/01/26 19:35:00), 6206.0 (01/01/26 19:30:00), 3164.0 (01/01/26 19:25:00)] were greater than or equal to the threshold (3000.0) (minimum 3 datapoints for OK -> ALARM transition).","Severity": "Warning","Description": "Error Count for http request exceeded threshold for metric: HTTPCode_Target_4XX_Count ,Loadbalancer affected: app/FlySaaCmsWebALB/968b1f7492941705"} | 02/Jan/26 11:04 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [28 empty] | Done | 2026-01-02 11:04
AM20-1046 | AWS Infra Readiness for Migration | In Progress |  | None( Epic) |  |  |  | High | 1620340 | Epic | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  |  | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-13 12:54 | 2026-01-13 12:59 |  |  |  | 0 | AWS Platform for all 20+ application must be ready which includes provisioning of AWS workloads in respective application account, Security & Industry standard compliance implementation, connectivity, RBAC and resource tagging in place |  | Yashwant Thakur | [5 empty] | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [15 empty] | 1137600 | 950400 | 187200 | [30 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4545cda9 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [30 empty] | ghx-label-2 |  |  | To Do | [46 empty] | No | [72 empty] | Planned | [11 empty] | dark_yellow | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦hzxmzj: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | [44 empty] | In Progress | 2025-03-04 11:27
AM20-1047 | Trellix Integration with Informatica servers | Done | 1 | Sprint 13 | 2025-09-01 | 2025-09-12 | Satya Varanasi | High | 1751443 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-11 20:22 | 2026-01-11 22:53 |  |  |  | 0 | As Network experts I would like to integrate Trellix servers with Informatica account so that it is able to scan TM1 workloads for any vulnerabilities, malware reporting Acceptance Criteria: * Followup with Sinjun for Trellix agent reconfiguration in TM1 server * Trellix is able to access TM1 account successfully and perform scanning |  | Satya Varanasi | [5 empty] | 712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0 | [11 empty] | 14400 | 14400 |  | 0 | 14400 | 14400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@34aaf28e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0eabm:i | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 14 | Sprint 15 | [110 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-08-25 06:57 | [13 empty] | 25/Aug/25 8:57 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will required to action on after implementation. | 28/Aug/25 8:31 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This will required to action on after implementation. | 08/Sep/25 9:56 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;This need to action after migration. | 01/Oct/25 8:15 AM;712020:1b97384b-aa58-40dd-8a32-ae9eb667bfb0;Cutover and Trellix integration has been completed successful. | [23 empty] | 1717990 | AM20-99 | Disaster Recovery and Backup | Done | 2025-10-06 08:38
AM20-1048 | Cost Anomaly Detection | Done | 6 | Sprint 10 | 2025-07-21 | 2025-08-01 | Yashwant Thakur | High | 1719961 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-20 17:43 | 2026-01-20 18:18 |  |  |  | 0 | As AWS expert I would like to report any sudden spike in the cost against any of the application or accounts so that the concerned team can validate the reasoning and take appropriate action to ascertain reasons and take reactive measures Acceptance Criteria: < pre-req> : * Ensure all accounts are part of AWS Org. with consolidated billing enabled * Use the Payer9 account to see all account cost level Acceptance Criteria * Cost anomaly detection is enabled successfully * Anomaly monitor is is enabled * Anomaly subscription is successfully enabled using SNS * CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage * Use Amazon Athena or quicksight for stakeholder friendly dashboards * Graphical representation of the cost to be captured |  | Onkar Mirajkar | Yashwant Thakur |  |  |  |  | 712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74 | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@4d6b831e | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0attv: | [57 empty] | Online Dev | [109 empty] | Business | [124 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-18 06:07 | [13 empty] | 18/Jul/25 8:07 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;* CloudWatch alarm needs to customized to publish â€œ daily spend metricsâ€ to cloudWatch via AWS Cost Explorer API or CUR+ Athena and set Alarm *---Done* * Alarm trigger if cost >30% sudden spike in EC2 or Lamda usage *---Done* Cost anomaly detection is enabled successfully *---Done* * Anomaly monitor is is enabled *---Done* * Anomaly subscription is successfully enabled using SNS *---Done* | 23/Jul/25 8:08 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Working on Amazon Athena or quicksight for stakeholder friendly dashboards ---*Done* | 24/Jul/25 7:38 AM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;As discussed with Yashwant, we need to track cost anomalies for specific AWS services and implement it separately for each account. | 24/Jul/25 8:57 PM;712020:6804985c-54b3-4d9e-9b72-e0f4aa19fe74;Cost anomalies detction for specific AWS services and implement it separately for each account. *---Done* Updated for Only TM1 account.(As discussed with Yashwant) | 28/Jul/25 9:58 AM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [22 empty] | 1620340 | AM20-2 | AWS Infra Readiness for Migration | Done | 2025-07-28 09:58
AM20-1049 | Ingesting 500 of lines of inbound and outbound rules from excel to Terraform code for enablement | Done | 6 | Sprint 20 | 2025-12-08 | 2025-12-19 | Yashwant Thakur | Medium | 1869689 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  | Done | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-02-02 16:30 | 2026-02-02 20:02 | 2025-12-14 17:51 | 2025-12-12 14:51 |  | 0 |  |  | Sanket Kale | Yashwant Thakur |  |  |  |  | 712020:91948faf-1676-4820-bf6b-d50a7992943e | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [10 empty] | 86400 | 86400 |  | 0 | 86400 | 86400 | [31 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@7bae0685 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 | [120 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0ocbn: | [57 empty] | Online Dev | [109 empty] | Business | [110 empty] | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [10 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [65 empty] | YES | YES | 2025-12-05 06:26 | 3_*:*_1_*:*_602271434_*¦*_10041_*:*_1_*:*_329125612_*¦*_13940_*:*_1_*:*_0 | [12 empty] | 05/Dec/25 8:26 AM;712020:91948faf-1676-4820-bf6b-d50a7992943e;Done with the terraform script deployment. Currently we are adding the inbound and outbound rule with excel only. | 12/Dec/25 2:51 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approving provided we see workable solution during demo | [28 empty] | Done | 2025-12-12 14:51
AM20-1050 | TM1 ¦¦ E2E Integration testing of ServiceNow monitoring | Done | 0 | Sprint 11 | 2025-08-04 | 2025-08-15 | Yashwant Thakur | Highest | 1729976 | Story | AM20 | 20+ App Migration | software | Harsh Chandra | 712020:fdf96e9b-ccb7-4231-8189-a2bfcd943a7d |  |  | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | Yashwant Thakur | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | 2026-01-28 16:57 | 2026-01-28 19:23 |  |  |  | 0 | As Product Owner I would like to review e2e testing completed with servicenow team for all wave 1 application so that we can confirm to business that in case of any issue service ticket would be raised Acceptance Criteria: * Tickets/issues are getting raised successfully against the alerts raise via cloudwatch for all Wave1 applications * ServiceNow team signoff received * Showcase (demo) provided to all relevant stakeholders |  | Diksha Koul | Faisal Sayed | Yashwant Thakur |  |  |  | 712020:54791a09-30fd-4ab7-8a1d-068b13e544d8 | 712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb | 712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa | [28 empty] | 19/Aug/25 1:26 PM;fa9874c1-b6fa-45e2-90e5-5fd0aa859bd9;image (3).png;https://vodacom.atlassian.net/rest/api/3/attachment/content/1141522 | [17 empty] | NO | [42 empty] | com.atlassian.servicedesk.plugins.approvals.internal.customfield.ApprovalsCFValue@98c0df5 | [97 empty] | YES | [27 empty] | Moderate/Limited |  |  |  | Maintenance |  |  | Medium | [5 empty] | Checklist Progress: 0/0 |  | 0 | [118 empty] | {} | [32 empty] | TITAN Web UI | [80 empty] | No | [72 empty] | Planned | [12 empty] | 0 | 0 | 0 | [60 empty] | 0 | 0 | 0 | [122 empty] | minor | [71 empty] | To Do | [17 empty] | 1¦i0bmab: | [57 empty] | Online Dev | [109 empty] | Business | [12 empty] | Sprint 12 | [111 empty] | 0 | 0 |  | 0 |  | 0 | [70 empty] | YES | YES | 2025-07-28 07:32 | [13 empty] | 28/Jul/25 9:31 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Once after the TM1 cutover is completed we can proceed with this activity. | 11/Aug/25 7:33 AM;712020:689ee2a4-8190-40d7-be5c-6f5e6c9207cb;SpillOver: Since the story was blocked due to configuration of monitoring and alerting on TM1 ec2 instances (application specific) which was completed on 8th Aug 2025 (evening), Diksha did not get any time to validate end to end solution. Hence, the spillover. | 19/Aug/25 10:40 AM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;Will start working on this US from today. | 19/Aug/25 12:27 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;The Alerts are being generated and triggered now waiting for confirmation from Service now team to share the screenshot. | 19/Aug/25 1:26 PM;712020:54791a09-30fd-4ab7-8a1d-068b13e544d8;!image (3).png¦width=1146,height=305,alt="image (3).png"! Attaching the screenshot which I got from service now team that they are getting the alerts generated by our side. | 21/Aug/25 2:33 PM;712020:2ee01a6a-4661-4e3e-bfdd-28dde03accfa;Approved | [21 empty] | 1620376 | AM20-6 | AWS Infra Readiness for Migration | Done | 2025-08-21 14:33